## V1
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SARAT BARMAN | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 0
UPASANA CHAUDHARY | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
UPASANA CHAUDHARY | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
UPASANA CHAUDHARY | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
UPASANA CHAUDHARY | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
UPASANA CHAUDHARY | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
UPASANA CHAUDHARY | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
UPASANA CHAUDHARY | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 0
UPASANA CHAUDHARY | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SARAT BARMAN | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 15.63 | 0 | 100% | 2205.7056 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA SOIL CLEANING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
UPASANA CHAUDHARY | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0.003 | 100.1% | 5680 |  | 0 | SAVITA DEVI | 0
UPASANA CHAUDHARY | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0.002 | 100% | 4570 |  | 0 | SHOKAT | 0
UPASANA CHAUDHARY | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | -0.002 | 99.99% | 15110 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
UPASANA CHAUDHARY | FOOTING REINFORCEMENT | 23 | 7500 | 0.65 | MT | 0.65 | 0 | 100% | 4875 |  | 0 | SK ANSAR HOSSIAN | 0
UPASANA CHAUDHARY | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.75 | MT | 0.75 | 0 | 100% | 5625 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
UPASANA CHAUDHARY | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
UPASANA CHAUDHARY | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SUBHASMITA DAS | 0
UPASANA CHAUDHARY | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.8 | MT | 2.8 | 0 | 100% | 21000 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | V VENKATANARAYANA | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | YELLAPPA C | 0
UPASANA CHAUDHARY | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | TOTAL | 0
UPASANA CHAUDHARY | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0
UPASANA CHAUDHARY | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 18.25 | 0 | 100% | 5500.404 |  | 0
UPASANA CHAUDHARY | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
UPASANA CHAUDHARY | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
UPASANA CHAUDHARY | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | 0.004 | 100% | 6754.5 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100% | 1200 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.4 | 0 | 100% | 18000 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 20.55 | 0 | 100% | 6193.6056 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | -0.004 | 99.89% | 7180 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | -0.001 | 100% | 6099.75 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 1.28 | -0.004 | 99.69% | 1920 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
AAIDHUL MIAH | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.04 | MT | 0.04 | 0 | 100% | 280 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
SARAT BARMAN | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
AAIDHUL MIAH | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 3.81 | 0 | 100% | 1148.3035 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | -0.002 | 99.93% | 636.75 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
SARAT BARMAN | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 47.7 | 0 | 100% | 3129.12 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 64.23 | 0 | 100% | 4213.488 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 141 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 149 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 157 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 233.927 | SQM | 233.93 | 0.003 | 100% | 50360.4504 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 58.171 | SQM | 58.17 | -0.001 | 100% | 12522.8376 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 62.539 | SQM | 62.54 | 0.001 | 100% | 6731.8056 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 151.653 | SQM | 151.65 | -0.003 | 100% | 32647.212 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 62.539 | SQM | 62.54 | 0.001 | 100% | 6731.8056 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 312.43 | 0 | 100% | 15133.4843 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 160.99 | 0 | 100% | 7798.0336 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 190.72 | 0 | 100% | 9238.0954 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 758.48 | SQM | 758.48 | 0 | 100% | 36739.2542 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 758.48 | SQM | 758.48 | 0 | 100% | 12249.452 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 758.48 | SQM | 758.48 | 0 | 100% | 20410.6968 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 20.6 | SQM | 20.6 | 0 | 100% | 6208.6752 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 450 | 23 | NOS | 23 | 0 | 100% | 10350 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 44.743 | RMT | 44.74 | -0.003 | 99.99% | 3668.68 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 120 | RMT | 120 | 0 | 100% | 3936 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 24 | RMT | 24 | 0 | 100% | 3148.8 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 6 | NOS | 5 | -1 | 83.33% | 5000 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 94.02 | SQM | 94.02 | 0 | 100% | 17205.66 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 72.123 | RMT | 72.12 | -0.003 | 100% | 3548.304 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 101.36 | SQM | 101.36 | 0 | 100% | 18548.88 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 83.36 | RMT | 83.36 | 0 | 100% | 4101.312 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.698 | SQM | 3.7 | 0.002 | 100.1% | 677.1 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.86 | RMT | 5.86 | 0 | 100% | 288.312 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 5.13 | SQM | 5.13 | 0 | 100% | 938.79 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 9.83 | RMT | 9.83 | 0 | 100% | 483.636 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 28.012 | SQM | 28.01 | -0.002 | 99.99% | 5125.83 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 31.801 | RMT | 31.8 | -0.001 | 100% | 1564.56 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 29.24 | SQM | 29.24 | 0 | 100% | 5350.92 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 2180 | SFT | 2180 | 0 | 100% | 5450 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 6.26 | SQM | 6.26 | 0 | 100% | 1145.58 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 31.39 | SQM | 31.39 | 0 | 100% | 5744.37 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 14.87 | SQM | 14.87 | 0 | 100% | 2721.21 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 45.07 | SQM | 45.07 | 0 | 100% | 8247.81 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 247.018 | SQM | 247.02 | 0.002 | 100% | 15952.5516 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100% | 17500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 36.43 | RMT | 35.35 | -1.08 | 97.04% | 195662.25 |  | 0 |  |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100% | 1350 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 18938 | 1 | LUMP SUM | 1 | 0 | 100% | 18938 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100% | 5625 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100% | 1500 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 27 | 0 | 100% | 2079 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 89.3 | SFT | 89.3 | 0 | 100% | 2053.9 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 15 | 0 | 100% | 2265 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100% | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
UPASANA CHAUDHARY | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 295 | 290 | 193 | SQM | 193 | 0 | 100% | 55970 |  | 0
SARAT BARMAN | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 295 | 290 | 356.76 | SQM | 356.76 | 0 | 100% | 103460.4 |  | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 16800 | 1 | LUMP SUM | 1 | 0 | 100% | 16800 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | -3 | 0% | 0 |  | 0
RUPAK NAYAK | PAINT REWORK IN VILLAS AFTER WALL CRACK TREATMENT | 369 | 3060 | 1 | LUMP SUM | 1 | 0 | 100% | 3060 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 16378.8 | 1 | LUMP SUM | 1 | 0 | 100% | 16378.8 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
[9 empty] | 1802942.324 |  | 0

## V2
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SHEKAR T | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 350
DEEPA B | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0 | EBI ABRAHAM | 0
DEEPA B | TREE CUTTING | 3 | 500 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
DEEPA B | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 8000
DEEPA B | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
DEEPA B | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
SHEKAR T | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
SHEKAR T | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 21100
SHEKAR T | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 8999.886
SHEKAR T | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | 15.63 | 0% | 0 |  | 0 | RUPAK NAYAK | 39913.128
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 4511.8609
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 | 100% | 3000 | SARAT BARMAN | 0
DEEPA B | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | SAVITA DEVI | 1800
SHEKAR T | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | -0.002 | 100% | 4570 |  | 0 | SHOKAT | 0
SHEKAR T | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | 0.002 | 99.99% | 15110 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 195662.25
DEEPA B | FOOTING REINFORCEMENT | 23 | 7500 | 0.65 | MT | 0.65 | 0 | 100% | 4875 |  | 0 | SK ANSAR HOSSIAN | 4000
DEEPA B | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.75 | MT | 0 | 0.75 | 0% | 0 |  | 0 | SREE VINAYAKA ELECTRICALS | 18938
SHEKAR T | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
DEEPA B | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0 | 0.9 | 0% | 0 |  | 0 | SUBHASMITA DAS | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.8 | MT | 2.8 | 0 | 100% | 21000 |  | 0 | UDHABHAI R PARMAR | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0 | V VENKATANARAYANA | 3000
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | YELLAPPA C | 0
DEEPA B | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | TOTAL | 306275.1249
DEEPA B | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 0 | 31.67 | 0% | 0 |  | 0
SHEKAR T | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0
SHEKAR T | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 0 | 14.58 | 0% | 0 |  | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 18.25 | 0 | 100% | 5500.404 |  | 0
DEEPA B | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
DEEPA B | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 0 | 2.62 | 0% | 0 |  | 0
SHEKAR T | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
SHEKAR T | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | -0.004 | 100% | 6754.5 |  | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100% | 1200 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHEKAR T | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.4 | 0 | 100% | 18000 |  | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
SHEKAR T | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 0 | 14.58 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 20.55 | 0 | 100% | 6193.6056 |  | 0
SHEKAR T | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | 0.004 | 99.89% | 7180 |  | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | 0.001 | 100% | 6099.75 |  | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 0 | 1.773 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 1.28 | 0.004 | 99.69% | 1920 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.04 | MT | 0.04 | 0 | 100% | 300 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
SHEKAR T | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 3.81 | 0 | 100% | 1148.3035 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | 0.002 | 99.93% | 636.75 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
SHEKAR T | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHEKAR T | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
SHEKAR T | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
SHEKAR T | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
SHEKAR T | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 47.7 | 0 | 100% | 3129.12 |  | 0
SHEKAR T | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 64.23 | 0 | 100% | 4213.488 |  | 0
SHEKAR T | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
SHEKAR T | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
SHEKAR T | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
SHEKAR T | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 294.4 | 15.49 | 95% | 57040.5888 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 1 | 0 | 100% | 16500 |  | 0
SHEKAR T | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
SHEKAR T | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
SHEKAR T | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 198.65 | 10.46 | 95% | 38488.8348 |  | 0
SHEKAR T | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
SHEKAR T | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
SHEKAR T | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 171.53 | 9.03 | 95% | 33234.2806 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 238.03 | SQM | 238.03 | 0 | 100% | 51243.0984 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 27.34 | SQM | 27.34 | 0 | 100% | 5885.7552 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 68.047 | SQM | 68.05 | -0.003 | 100% | 7324.902 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 175.856 | SQM | 175.86 | -0.004 | 100% | 37859.1408 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 68.047 | SQM | 68.05 | -0.003 | 100% | 7324.902 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 16 | NOS | 16 | 0 | 100% | 3200 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 312.43 | 0 | 100% | 15133.4843 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 160.99 | 0 | 100% | 7798.0336 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 190.72 | 0 | 100% | 9238.0954 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 663.462 | SQM | 663.46 | 0.002 | 100% | 32136.6755 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 663.462 | SQM | 663.46 | 0.002 | 100% | 10714.879 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 663.462 | SQM | 0 | 663.462 | 0% | 0 | 100% | 17853.7624
SANTOSH KUMAR | STAIRCASE GRANITE | 215 | 301.392 | 2.7986 | SQM | 0 | 2.7986 | 0% | 0 |  | 0
SANTOSH KUMAR | LEDGE WALL GRANITE | 217 | 450 | 1 | NOS | 1 | 0 | 100% | 450 |  | 0
SANTOSH KUMAR | DOOR OPENING GRANITE | 218 | 350 | 28 | NOS | 28 | 0 | 100% | 9800 |  | 0
SANTOSH KUMAR | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 4.2 | RMT | 0 | 4.2 | 0% | 0 |  | 0
SANTOSH KUMAR | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 12.6 | RMT | 0 | 12.6 | 0% | 0 |  | 0
SANTOSH KUMAR | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 4.2 | RMT | 0 | 4.2 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 | 100% | 4000
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 204.516 | 103.887 | SQM | 98.69 | 5.197 | 95% | 20183.684 | 5% | 1062.3277
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 68.02 | RMT | 64.62 | 3.4 | 95% | 3179.304 | 5% | 167.3292
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 204.516 | 89.004 | SQM | 84.55 | 4.454 | 95% | 17291.8278 | 5% | 910.1371
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 76.302 | RMT | 72.49 | 3.812 | 95% | 3566.508 | 5% | 187.7029
SANTOSH KUMAR | TERRACE FLOOR TILING | 228 | 204.516 | 5.37 | SQM | 5.1 | 0.27 | 94.97% | 1043.0316 | 5% | 54.9125
SANTOSH KUMAR | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.069 | RMT | 4.82 | 0.249 | 95.09% | 237.144 | 5% | 12.4697
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 3.914 | SQM | 3.72 | 0.194 | 95.04% | 680.76 | 5% | 35.8131
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 7.44 | RMT | 7.07 | 0.37 | 95.03% | 347.844 | 5% | 18.3024
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 204.52 | 34.6 | SQM | 32.87 | 1.73 | 95% | 6722.5724 | 5% | 353.8196
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 43.82 | RMT | 41.63 | 2.19 | 95% | 2048.196 | 5% | 107.7972
SANTOSH KUMAR | CAR PARKING AREA TILING | 234 | 183 | 31.896 | SQM | 31.9 | -0.004 | 100% | 5837.7 |  | 0
SANTOSH KUMAR | FLOOR CHIPPING | 235 | 2.5 | 2234.585 | SFT | 2234.59 | -0.005 | 100% | 5586.475 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET FLOOR TILING | 237 | 204.516 | 4.078 | SQM | 3.87 | 0.208 | 94.9% | 791.4769 | 5% | 41.7008
SANTOSH KUMAR | GROUND FLOOR TOILET WALL TILING | 238 | 269.1 | 17.905 | SQM | 17.01 | 0.895 | 95% | 4577.391 | 5% | 240.9118
SANTOSH KUMAR | FIRST FLOOR TOILET FLOOR TILING | 239 | 204.516 | 10.795 | SQM | 10.26 | 0.535 | 95.04% | 2098.3342 | 5% | 110.3875
SANTOSH KUMAR | FIRST FLOOR TOILET WALL TILING | 240 | 269.1 | 41.906 | SQM | 39.81 | 2.096 | 95% | 10712.871 | 5% | 563.8452
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH (including toilet wall grouting and above 8ft dado grouting and terrace toilet) | 243 | 64.58 | 341.582 | SQM | 0 | 341.582 | 0% | 0 | 100% | 22059.3656
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 18500
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 0 | 1 | 0% | 0 | 100% | 600
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 8000
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 35.35 | RMT | 35.35 | 0 | 0% | 0 | 100% | 195662.25
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 0 | 4 | 0% | 0 | 100% | 1800
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 18938 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 18938
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 | 100% | 2601.986
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 0 | 27 | 0% | 0 | 100% | 2079
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 89.3 | SFT | 0 | 89.3 | 0% | 0 | 100% | 2053.9
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 0 | 15 | 0% | 0 | 100% | 2265
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
DEEPA B | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 80 | SFT | 80 | 0 | 100% | 24800 |  | 0
SHEKAR T | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 668.12 | SFT | 668.12 | 0 | 100% | 207117.2 |  | 0
SHEKAR T | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 76 | SFT | 76 | 0 | 100% | 23560 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTOMISATION JACUZZI POINT WORK | 409 | 1200 | 1 | NOS | 1 | 0 | 100% | 1200 |  | 0
SANTOSH KUMAR | CUSTOMISATION ADDITIONAL WALL TILING ABOVE 8FT IN ALL FLOOR TOILET | 410 | 269.1 | 26.889 | SQM | 25.54 | 1.349 | 94.98% | 6872.814 | 5% | 361.7915
SANTOSH KUMAR | CUSTOMISATION TERRACE FLOOR TOILET FLOOR TILE WORK | 411 | 204.516 | 4.078 | SQM | 3.87 | 0.208 | 94.9% | 791.4769 | 5% | 41.7008
SANTOSH KUMAR | CUSTOMISATION TERRACE FLOOR TOILET WALL TILE WORK | 412 | 269.1 | 17.905 | SQM | 17.01 | 0.895 | 95% | 4577.391 | 5% | 240.9118
SANTOSH KUMAR | BALCONY UPSTAND TOP COPING GRANITE | 547 | 78 | 30.21 | RFT | 30.21 | 0 | 100% | 2356.38 |  | 0
SANTOSH KUMAR | CUTOUT 40MM FRONT EDGE CUTTING, NOSING AT TOP & BOTTOM AND GLUING TOGETHER THE PIECES PRECISELY | 548 | 164 | 20.428 | RMT | 20.43 | -0.002 | 100% | 3350.52 |  | 0
[9 empty] | 1501765.8877 |  | 306275.1249

## V3
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
MORSELIM KHAN | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 0 | 151.12 | 0% | 0 |  | 0 | AAIDHUL MIAH | 350
MORSELIM KHAN | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MORSELIM KHAN | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MORSELIM KHAN | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
MORSELIM KHAN | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
MORSELIM KHAN | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
MORSELIM KHAN | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 19100
MORSELIM KHAN | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
MORSELIM KHAN | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | 15.63 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
MORSELIM KHAN | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | SARAT BARMAN | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | -0.002 | 100% | 4570 |  | 0 | SAVITA DEVI | 0
MORSELIM KHAN | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | 0.002 | 99.99% | 15110 |  | 0 | SHOKAT | 0
MORSELIM KHAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.65 | MT | 0.65 | 0 | 100% | 4875 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
MORSELIM KHAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.75 | MT | 0.75 | 0 | 100% | 5625 |  | 0 | SK ANSAR HOSSIAN | 0
MORSELIM KHAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 0 | 1 | 0% | 0 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
MORSELIM KHAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.8 | MT | 2.8 | 0 | 100% | 21000 |  | 0 | SUBHASMITA DAS | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | UDHABHAI R PARMAR | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | V VENKATANARAYANA | 0
MORSELIM KHAN | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | YELLAPPA C | 0
MORSELIM KHAN | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | TOTAL | 19450
MORSELIM KHAN | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 0 | 105.11 | 0% | 0 |  | 0
MORSELIM KHAN | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 18.25 | 0 | 100% | 5500.404 |  | 0
MORSELIM KHAN | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
MORSELIM KHAN | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
MORSELIM KHAN | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 0 | 7.41 | 0% | 0 |  | 0
MORSELIM KHAN | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | -0.004 | 100% | 6754.5 |  | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100% | 1200 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
MORSELIM KHAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.4 | 0 | 100% | 18000 |  | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
MORSELIM KHAN | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 20.55 | 0 | 100% | 6193.6056 |  | 0
MORSELIM KHAN | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | 0.004 | 99.89% | 7180 |  | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | 0.001 | 100% | 6099.75 |  | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 1.28 | 0.004 | 99.69% | 1920 |  | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.04 | MT | 0.04 | 0 | 100% | 300 |  | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
MORSELIM KHAN | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 3.81 | 0 | 100% | 1148.3035 |  | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | 0.002 | 99.93% | 636.75 |  | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
MORSELIM KHAN | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
MORSELIM KHAN | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
MORSELIM KHAN | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
MORSELIM KHAN | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
MORSELIM KHAN | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 47.7 | 0 | 100% | 3129.12 |  | 0
MORSELIM KHAN | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 64.23 | 0 | 100% | 4213.488 |  | 0
MORSELIM KHAN | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
MORSELIM KHAN | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
MORSELIM KHAN | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
MORSELIM KHAN | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 1 | 0 | 100% | 16500 |  | 0
MORSELIM KHAN | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
MORSELIM KHAN | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
MORSELIM KHAN | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
MORSELIM KHAN | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
MORSELIM KHAN | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
MORSELIM KHAN | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 290 | SQM | 0 | 290 | 0% | 0 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 267.48 | SQM | 267.48 | 0 | 100% | 57583.0944 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 36 | SQM | 0 | 36 | 0% | 0 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 84.3 | SQM | 84.3 | 0 | 100% | 18148.104 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 61 | SQM | 0 | 61 | 0% | 0 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 69.67 | SQM | 69.67 | 0 | 100% | 7499.2788 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 125 | SQM | 0 | 125 | 0% | 0 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 150.12 | SQM | 150.12 | 0 | 100% | 32317.8336 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 61 | SQM | 0 | 61 | 0% | 0 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 80.74 | SQM | 80.74 | 0 | 100% | 8690.8536 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 25 | NOS | 0 | 25 | 0% | 0 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 109.35 | 203.08 | 35% | 5296.6953 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 56.35 | 104.64 | 35% | 2729.4813 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 66.75 | 123.97 | 35% | 3233.2365 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 758.48 | SQM | 758.48 | 0 | 100% | 36739.2542 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 758.48 | SQM | 758.48 | 0 | 100% | 12249.452 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 758.48 | SQM | 0 | 758.48 | 0% | 0 |  | 0
SANTOSH KUMAR | STAIRCASE GRANITE | 215 | 301.392 | 26.866 | SQM | 24.18 | 2.686 | 90% | 7287.6586 |  | 0
SANTOSH KUMAR | LEDGE WALL GRANITE | 217 | 450 | 1 | NOS | 1 | 0 | 100% | 450 |  | 0
SANTOSH KUMAR | DOOR OPENING GRANITE | 218 | 350 | 22 | NOS | 22 | 0 | 100% | 7700 |  | 0
SANTOSH KUMAR | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 44.743 | RMT | 40.27 | 4.473 | 90% | 3302.14 |  | 0
SANTOSH KUMAR | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 134.23 | RMT | 120.81 | 13.42 | 90% | 3962.568 |  | 0
SANTOSH KUMAR | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 33.186 | RMT | 29.87 | 3.316 | 90.01% | 3918.944 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 183 | 94.092 | SQM | 89.39 | 4.702 | 95% | 16358.37 |  | 0
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 78.219 | RMT | 74.31 | 3.909 | 95% | 3656.052 |  | 0
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 183 | 99.654 | SQM | 94.67 | 4.984 | 95% | 17324.61 |  | 0
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 87.754 | RMT | 83.37 | 4.384 | 95% | 4101.804 |  | 0
SANTOSH KUMAR | TERRACE FLOOR TILING | 228 | 183 | 4.681 | SQM | 4.45 | 0.231 | 95.07% | 814.35 |  | 0
SANTOSH KUMAR | TERRACE FLOOR SKIRTING | 229 | 49.2 | 6.912 | RMT | 6.57 | 0.342 | 95.05% | 323.244 |  | 0
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 3.914 | SQM | 3.72 | 0.194 | 95.04% | 680.76 |  | 0
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 7.44 | RMT | 7.07 | 0.37 | 95.03% | 347.844 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 183 | 31.402 | SQM | 29.83 | 1.572 | 94.99% | 5458.89 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 33.824 | RMT | 32.13 | 1.694 | 94.99% | 1580.796 |  | 0
SANTOSH KUMAR | CAR PARKING AREA TILING | 234 | 183 | 31.896 | SQM | 0 | 31.896 | 0% | 0 |  | 0
SANTOSH KUMAR | FLOOR CHIPPING | 235 | 2.5 | 2221.894 | SFT | 2221.89 | 0.004 | 100% | 5554.725 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.078 | SQM | 3.87 | 0.208 | 94.9% | 708.21 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.905 | SQM | 17.01 | 0.895 | 95% | 3112.83 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 14.873 | SQM | 14.13 | 0.743 | 95% | 2585.79 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 59.811 | SQM | 56.82 | 2.991 | 95% | 10398.06 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 18500
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 0 | 1 | 0% | 0 | 100% | 600
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 1 | 0 | 100% | 7000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
MORSELIM KHAN | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 749.12 | SFT | 749.12 | 0 | 100% | 232227.2 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
[9 empty] | 1463515.4762 |  | 19450

## V4
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
MORSELIM KHAN | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MORSELIM KHAN | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
MORSELIM KHAN | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
MORSELIM KHAN | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
MORSELIM KHAN | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 7158.525
MORSELIM KHAN | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
MORSELIM KHAN | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | -15.63 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
MORSELIM KHAN | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0.003 | 100.1% | 5680 |  | 0 | SARAT BARMAN | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0.002 | 100% | 4570 |  | 0 | SAVITA DEVI | 0
MORSELIM KHAN | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | -0.002 | 99.99% | 15110 |  | 0 | SHOKAT | 0
MORSELIM KHAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.65 | MT | 0.65 | 0 | 100% | 4875 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
MORSELIM KHAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.75 | MT | 0.75 | 0 | 100% | 5625 |  | 0 | SK ANSAR HOSSIAN | 0
MORSELIM KHAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
MORSELIM KHAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.8 | MT | 2.8 | 0 | 100% | 21000 |  | 0 | SUBHASMITA DAS | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | UDHABHAI R PARMAR | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | V VENKATANARAYANA | 0
MORSELIM KHAN | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | YELLAPPA C | 0
MORSELIM KHAN | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | TOTAL | 7158.525
MORSELIM KHAN | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0
MORSELIM KHAN | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 18.25 | 0 | 100% | 5500.404 |  | 0
MORSELIM KHAN | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
MORSELIM KHAN | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
MORSELIM KHAN | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
MORSELIM KHAN | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | 0.004 | 100% | 6754.5 |  | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100% | 1200 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
MORSELIM KHAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.4 | 0 | 100% | 18000 |  | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
MORSELIM KHAN | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 20.55 | 0 | 100% | 6193.6056 |  | 0
MORSELIM KHAN | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | -0.004 | 99.89% | 7180 |  | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | -0.001 | 100% | 6099.75 |  | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 1.28 | -0.004 | 99.69% | 1920 |  | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.04 | MT | 0.04 | 0 | 100% | 300 |  | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
MORSELIM KHAN | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 3.81 | 0 | 100% | 1148.3035 |  | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | -0.002 | 99.93% | 636.75 |  | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
MORSELIM KHAN | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
MORSELIM KHAN | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
MORSELIM KHAN | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
MORSELIM KHAN | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
MORSELIM KHAN | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 47.7 | 0 | 100% | 3129.12 |  | 0
MORSELIM KHAN | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 64.23 | 0 | 100% | 4213.488 |  | 0
MORSELIM KHAN | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
MORSELIM KHAN | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
MORSELIM KHAN | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
MORSELIM KHAN | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 1 | 0 | 100% | 16500 |  | 0
MORSELIM KHAN | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
MORSELIM KHAN | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
MORSELIM KHAN | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
MORSELIM KHAN | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
MORSELIM KHAN | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
MORSELIM KHAN | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 328.76 | SQM | 328.76 | 0 | 100% | 70775.4528 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 177.78 | SQM | 177.78 | 0 | 100% | 38272.4784 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 103.01 | SQM | 103.01 | 0 | 100% | 11087.9964 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 153.3 | SQM | 153.3 | 0 | 100% | 33002.424 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 73.8 | SQM | 73.8 | 0 | 100% | 7943.832 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 24 | NOS | 24 | 0 | 100% | 4800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 93.73 | -218.7 | 30% | 4540.0937 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 48.3 | -112.69 | 30% | 2339.5554 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 57.22 | -133.5 | 30% | 2771.6224 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 758.48 | SQM | 758.48 | 0 | 100% | 36739.2542 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 758.48 | SQM | 758.48 | 0 | 100% | 12249.452 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 758.48 | SQM | 0 | -758.48 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 0.94 | -0.06 | 94% | 16450 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
MORSELIM KHAN | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 765.25 | SFT | 765.25 | 0 | 100% | 237227.5 |  | 0
MORSELIM KHAN | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 750 | SFT | 750 | 0 | 100% | 232500 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
SHEKAR T | LIFT REINFORCEMENT | 319 | 7500 | 0.767 | MT | 0.77 | 0.003 | 100.4% | 5775 |  | 0
SHEKAR T | LIFT EARTH WORK EXCAVATION | 320 | 424 | 12.337 | CUM | 12.34 | 0.003 | 100% | 5232.16 |  | 0
SHEKAR T | LIFT BOTTOM PCC | 321 | 1000 | 1 | CUM | 1 | 0 | 100% | 1000 |  | 0
SHEKAR T | LIFT RCC | 322 | 225 | 3.638 | CUM | 3.64 | 0.002 | 100.1% | 819 |  | 0
SHEKAR T | LIFT WALL BLOCK WORK | 323 | 258.34 | 40.99 | SQM | 40.99 | 0 | 100% | 10589.3566 |  | 0
SHEKAR T | LIFT WALL INTERNAL PLASTERING | 324 | 172.22 | 40.99 | SQM | 40.99 | 0 | 100% | 7059.2978 |  | 0
SHEKAR T | LIFT WALL EXTERNAL PLASTERING | 325 | 194 | 96.45 | SQM | 96.45 | 0 | 100% | 18711.3 |  | 0
SHEKAR T | LIFT SIDE REFILLING | 326 | 283 | 5.784 | CUM | 5.78 | -0.004 | 99.93% | 1635.74 |  | 0
SHEKAR T | LIFT RCC | 327 | 2000 | 4.764 | CUM | 4.76 | -0.004 | 99.92% | 9520 |  | 0
SHEKAR T | LIFT FOOTING WALL BEAM AND SLAB SHUTTERING | 328 | 302 | 106.234 | SQM | 106.23 | -0.004 | 100% | 32081.46 |  | 0
JMJ WATERPROOING ENTERPRISES | LIFT WATERPROOF COATING | 329 | 215.28 | 15.49 | SQM | 15.49 | 0 | 100% | 3334.6872 |  | 0
JMJ WATERPROOING ENTERPRISES | LIFT WATERPRROF PLASTERING | 330 | 215.28 | 15.49 | LUMP SUM | 15.49 | 0 | 100% | 3334.6872 |  | 0
JMJ WATERPROOING ENTERPRISES | LIFT 75MM THICK SCREED CONCRETE | 331 | 215.28 | 4.6 | SQM | 4.6 | 0 | 100% | 990.288 |  | 0
JMJ WATERPROOING ENTERPRISES | LIFT BORE PACKING | 332 | 200 | 1 | NOS | 1 | 0 | 100% | 200 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | -3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0.5 | -0.5 | 50% | 1500 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 14317.05 | 1 | LUMP SUM | 0 | -1 | 0% | 0 | 50% | 7158.525
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 2 | NOS | 2 | 0 | 100% | 2000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 193.0146 | SQM | 193.01 | -0.0046 | 100% | 9349.0184 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 193.0146 | SQM | 193.01 | -0.0046 | 100% | 3117.1115 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 193.0146 | SQM | 0 | -193.0146 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 63.2075 | SQM | 0 | -63.2075 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 63.2075 | SQM | 0 | -63.2075 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION AQUAGUARD TAP POINT WORK | 420 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
KRIUTTIBAS DAS | CUSTOMISATION TRAP POINT WORK | 422 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION TAP POINT WORK | 423 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
[9 empty] | 1826580.908 |  | 7158.525

## V5
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
KOUSHIK MANDAL | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 0 | -151.12 | 0% | 0 |  | 0 | AAIDHUL MIAH | 0
KOUSHIK MANDAL | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
KOUSHIK MANDAL | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
KOUSHIK MANDAL | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
KOUSHIK MANDAL | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
KOUSHIK MANDAL | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
KOUSHIK MANDAL | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
KOUSHIK MANDAL | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 0 | -62.8 | 0% | 0 |  | 0 | PRAKASH H N | 0
KOUSHIK MANDAL | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 0 | -151.12 | 0% | 0 |  | 0 | RAMAKRUSHNA PRADHAN | 0
KOUSHIK MANDAL | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | -15.63 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
KOUSHIK MANDAL | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0.003 | 100.1% | 5680 |  | 0 | SANTOSH KUMAR | 0
KOUSHIK MANDAL | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0.002 | 100% | 4570 |  | 0 | SARAT BARMAN | 0
KOUSHIK MANDAL | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 0 | -15.112 | 0% | 0 |  | 0 | SAVITA DEVI | 0
KOUSHIK MANDAL | FOOTING REINFORCEMENT | 23 | 7500 | 0.65 | MT | 0.65 | 0 | 100% | 4875 |  | 0 | SHOKAT | 0
KOUSHIK MANDAL | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.75 | MT | 0.75 | 0 | 100% | 5625 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
KOUSHIK MANDAL | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SK ANSAR HOSSIAN | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.8 | MT | 0 | -2.8 | 0% | 0 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0 | -0.18 | 0% | 0 |  | 0 | SUBHASMITA DAS | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0 | -0.18 | 0% | 0 |  | 0 | UDHABHAI R PARMAR | 0
KOUSHIK MANDAL | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | V VENKATANARAYANA | 0
KOUSHIK MANDAL | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | YELLAPPA C | 0
KOUSHIK MANDAL | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0 | TOTAL | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 56.91 | -3 | 94.99% | 17152.2187 |  | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 0 | -261.41 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 0 | -14.58 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 0 | -18.25 | 0% | 0 |  | 0
KOUSHIK MANDAL | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
KOUSHIK MANDAL | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
KOUSHIK MANDAL | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.33 | -0.18 | 94.87% | 6660 |  | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 0 | -30.016 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 0 | -1.773 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0 | -0.8 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 1 | MT | 0 | -1 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 0 | -2.4 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | -0.18 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0 | -0.2 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 0 | -61.4 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 0 | -243.08 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 0 | -14.58 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 0 | -20.55 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 0 | -3.594 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 0 | -27.111 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 0 | -1.773 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 0 | -1.284 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0 | -0.15 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0 | -0.25 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.04 | MT | 0 | -0.04 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | -8.1 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 0 | -29.38 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 0 | -3.81 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | -0.61 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 0 | -2.832 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | -0.22 | 0% | 0 |  | 0
KOUSHIK MANDAL | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 0 | -52 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 0 | -191.86 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 0 | -203.55 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 0 | -87.26 | 0% | 0 |  | 0
KOUSHIK MANDAL | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 0 | -47.7 | 0% | 0 |  | 0
KOUSHIK MANDAL | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | -64.23 | 0% | 0 |  | 0
KOUSHIK MANDAL | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 0 | -368.27 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 0 | -119.78 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 0 | -267.58 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 0 | -309.89 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 0 | -118.32 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 0 | -366.35 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 0 | -209.11 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 0 | -14.1 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 0 | -37.29 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 0 | -180.56 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KOUSHIK MANDAL | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 781.12 | SFT | 126 | -655.12 | 16.13% | 39060 |  | 0
KOUSHIK MANDAL | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 334 | SFT | 0 | -334 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | -3 | 0% | 0 |  | 0
[9 empty] | 232848.2391 |  | 0

## V6
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 151.12 | 0 | 100% | 6498.16 |  | 0 | RUPAK NAYAK | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0.003 | 100.1% | 5680 |  | 0 | SANTOSH KUMAR | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0.002 | 100% | 4570 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | -0.002 | 99.99% | 15110 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100% | 4550 |  | 0 | SHOKAT | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100% | 5250 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.8 | MT | 2.8 | 0 | 100% | 19600 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 36 | 7000 | 0.18 | MT | 0 | -0.18 | 0% | 0 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0 | YELLAPPA C | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0 | TOTAL | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 0 | -18.25 | 0% | 0 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | 0.004 | 100% | 6754.5 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0 | -0.8 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 72 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 76 | 7000 | 2.4 | MT | 2.4 | 0 | 100% | 16800 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 79 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 83 | 7000 | 0.2 | MT | 0 | -0.2 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 0 | -20.55 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 89 | 2000 | 3.594 | CUM | 3.59 | -0.004 | 99.89% | 7180 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | -0.001 | 100% | 6099.75 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 0 | -1.284 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 99 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 102 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 105 | 7000 | 0.04 | MT | 0 | -0.04 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 0 | -3.81 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 110 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | -0.002 | 99.93% | 636.75 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | -0.22 | 0% | 0 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 121 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 125 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 130 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 134 | 65.6 | 47.7 | RMT | 0 | -47.7 | 0% | 0 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | -64.23 | 0% | 0 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 0 | -368.27 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 119.78 | SQM | 0 | -119.78 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 267.58 | SQM | 0 | -267.58 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 149 | 193.752 | 309.89 | SQM | 0 | -309.89 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 1 | 0 | 100% | 16500 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 118.32 | SQM | 0 | -118.32 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 366.35 | SQM | 0 | -366.35 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 159 | 193.752 | 209.11 | SQM | 0 | -209.11 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 14.1 | SQM | 0 | -14.1 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 37.29 | SQM | 0 | -37.29 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 180.56 | SQM | 0 | -180.56 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 0.5 | -0.5 | 50% | 7500 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 1500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 1013 | 82.4 | SFT | 82.36 | -0.04 | 99.95% | 83430.68 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 1013 | 37.6 | SFT | 25 | -12.6 | 66.49% | 25325 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | -3 | 0% | 0 |  | 0
[9 empty] | 730262.4707 |  | 0

## V7
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 151.12 | 0 | 100% | 6498.16 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0.003 | 100.1% | 5680 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0.002 | 100% | 4570 |  | 0 | SHOKAT | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | -0.002 | 99.99% | 15110 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100% | 4550 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100% | 5250 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.9 | MT | 0.9 | 0 | 100% | 6300 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.8 | MT | 2.8 | 0 | 100% | 19600 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0 | YELLAPPA C | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | TOTAL | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 18.25 | 0 | 100% | 5500.404 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | 0.004 | 100% | 6754.5 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100% | 1200 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 2.4 | MT | 2.4 | 0 | 100% | 16800 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 20.55 | 0 | 100% | 6193.6056 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | -0.004 | 99.89% | 7180 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | -0.001 | 100% | 6099.75 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 1.28 | -0.004 | 99.69% | 1920 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.04 | MT | 0 | -0.04 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 0 | -3.81 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | -0.002 | 99.93% | 636.75 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | -0.22 | 0% | 0 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 48 | -4 | 92.31% | 2400 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 0 | -87.26 | 0% | 0 |  | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 0 | -47.7 | 0% | 0 |  | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | -64.23 | 0% | 0 |  | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 0 | -368.27 | 0% | 0 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 141 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 0 | -267.58 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 0 | -309.89 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 149 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 0 | -118.32 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 0 | -366.35 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 0 | -209.11 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 157 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 0 | -14.1 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 0 | -37.29 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 0 | -180.56 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 233.927 | SQM | 233.93 | 0.003 | 100% | 50360.4504 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 58.171 | SQM | 58.17 | -0.001 | 100% | 12522.8376 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 62.539 | SQM | 62.54 | 0.001 | 100% | 6731.8056 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 151.653 | SQM | 151.65 | -0.003 | 100% | 32647.212 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 62.539 | SQM | 62.54 | 0.001 | 100% | 6731.8056 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 312.43 | 0 | 100% | 15133.4843 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 160.99 | 0 | 100% | 7798.0336 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 190.72 | 0 | 100% | 9238.0954 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 758.48 | SQM | 758.48 | 0 | 100% | 36739.2542 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 758.48 | SQM | 758.48 | 0 | 100% | 12249.452 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 758.48 | SQM | 758.48 | 0 | 100% | 20410.6968 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 21.617 | SQM | 21.62 | 0.003 | 100% | 6516.095 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 23 | NOS | 23 | 0 | 100% | 8050 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.845 | RMT | 41.85 | 0.005 | 100% | 3431.7 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 125.535 | RMT | 125.54 | 0.005 | 100% | 4117.712 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 21.196 | RMT | 21.2 | 0.004 | 100% | 2781.44 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100% | 4000 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 94.67 | SQM | 94.67 | 0 | 100% | 17324.61 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 82.53 | RMT | 82.53 | 0 | 100% | 4060.476 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 109.49 | SQM | 109.49 | 0 | 100% | 20036.67 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 102.69 | RMT | 102.69 | 0 | 100% | 5052.348 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 4.42 | SQM | 4.42 | 0 | 100% | 808.86 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8.73 | RMT | 8.73 | 0 | 100% | 429.516 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 3.91 | SQM | 3.91 | 0 | 100% | 715.53 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 8.19 | RMT | 8.19 | 0 | 100% | 402.948 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 31.62 | SQM | 31.62 | 0 | 100% | 5786.46 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 41.35 | RMT | 41.35 | 0 | 100% | 2034.42 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 27.26 | SQM | 27.26 | 0 | 100% | 4988.58 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 2815 | SFT | 2815 | 0 | 100% | 7037.5 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 6.27 | SQM | 6.27 | 0 | 100% | 1147.41 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 30.43 | SQM | 30.43 | 0 | 100% | 5568.69 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 12.43 | SQM | 12.43 | 0 | 100% | 2274.69 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 59.784 | SQM | 59.78 | -0.004 | 99.99% | 10939.74 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 244.11 | SQM | 244.11 | 0 | 100% | 15764.6238 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100% | 17500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 1 | 0 | 100% | 7000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 3000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 35.76 | RMT | 32.8 | -2.96 | 91.72% | 181548 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 18938 | 1 | LUMP SUM | 1 | 0 | 100% | 18938 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100% | 5625 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100% | 1500 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
KRISHNAKUMAR SAHANI | SILL GRANITE | 289 | 75 | 49 | RFT | 49 | 0 | 100% | 3675 |  | 0
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 1013 | 80.5 | SFT | 80.48 | 0.02 | 99.97% | 81526.24 |  | 0
SARAT BARMAN | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 1013 | 39.5 | SFT | 39.5 | 0 | 100% | 40013.5 |  | 0
AAIDHUL MIAH | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 297 | 30 | 3663 | SFT | 3663 | 0 | 100% | 109890 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
RUPAK NAYAK | PAINT REWORK IN VILLAS AFTER WALL CRACK TREATMENT | 369 | 3060 | 1 | LUMP SUM | 1 | 0 | 100% | 3060 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100% | 800 |  | 0
[9 empty] | 1814781.9754 |  | 0

## V8
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 26300
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 0 | 62.8 | 0% | 0 |  | 0 | PRAKASH H N | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 0 | 151.12 | 0% | 0 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 0 | 151.12 | 0% | 0 |  | 0 | RUPAK NAYAK | 82199.4076
SHEKAR T | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | 15.63 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | -0.002 | 100% | 4570 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 0 | 15.112 | 0% | 0 |  | 0 | SHOKAT | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100% | 4550 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100% | 5250 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SHEKAR T | GROUND FLOOR COLUMN REINFORCEMENT | 28 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 31 | 7500 | 2.8 | MT | 2.8 | 0 | 100% | 21000 |  | 0 | SUBHASMITA DAS | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 34 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | UDHABHAI R PARMAR | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 36 | 7500 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | YELLAPPA C | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | TOTAL | 108499.4076
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0
SHEKAR T | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 0 | 18.25 | 0% | 0 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
SHEKAR T | GROUND FLOOR COLUMN RCC | 56 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB RCC | 60 | 225 | 30.016 | CUM | 30.02 | -0.004 | 100% | 6754.5 |  | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0 | 0.8 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHEKAR T | FIRST FLOOR COLUMN REINFORCEMENT | 72 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 76 | 7500 | 2.4 | MT | 2 | 0.4 | 83.33% | 15000 |  | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 79 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 83 | 7500 | 0.2 | MT | 0 | 0.2 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 0 | 20.55 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR COLUMN RCC | 89 | 2000 | 3.594 | CUM | 0 | 3.594 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | 0.001 | 100% | 6099.75 |  | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 0 | 1.284 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN REINFORCEMENT | 99 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 102 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 105 | 7500 | 0.04 | MT | 0 | 0.04 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
SHEKAR T | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 0 | 3.81 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN RCC | 110 | 2000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 0 | 2.832 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0% | 0 |  | 0
SHEKAR T | ALL LEVEL COLUMN STARTER | 117 | 50 | 52 | CUM | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHEKAR T | GROUND FLOOR BLOCK WORK | 121 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
SHEKAR T | FIRST FLOOR BLOCK WORK | 125 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
SHEKAR T | TERRACE FLOOR BLOCK WORK | 130 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
SHEKAR T | ELEVATION RCC BAND | 136 | 65.6 | 47.7 | RMT | 0 | 47.7 | 0% | 0 |  | 0
SHEKAR T | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | 64.23 | 0% | 0 |  | 0
SHEKAR T | RCC SURFACE HACKING | 141 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
SHEKAR T | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
SHEKAR T | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
SHEKAR T | GROUND FLOOR EXTERNAL WALL PLASTERING | 149 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 1 | 0 | 100% | 16500 |  | 0
SHEKAR T | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
SHEKAR T | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
SHEKAR T | FIRST FLOOR EXTERNAL WALL PLASTERING | 157 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
SHEKAR T | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
SHEKAR T | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
SHEKAR T | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 328.76 | SQM | 328.76 | 0 | 100% | 70775.4528 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 177.78 | SQM | 177.78 | 0 | 100% | 38272.4784 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 103.01 | SQM | 103.01 | 0 | 100% | 11087.9964 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 153.3 | SQM | 153.3 | 0 | 100% | 33002.424 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 73.8 | SQM | 73.8 | 0 | 100% | 7943.832 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 24 | NOS | 24 | 0 | 100% | 4800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 0 | 27.32 | 0% | 0 | 100% | 5881.4496
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 0 | 147.16 | 0% | 0 | 100% | 14256.8608
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 0 | 312.43 | 0% | 0 | 33.33% | 5044.495
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 0 | 160.99 | 0% | 0 | 33.03% | 2575.84
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 0 | 190.72 | 0% | 0 | 33.03% | 3051.52
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 0 | 148.64 | 0% | 0 | 100% | 2400.536
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 758.48 | SQM | 0 | 758.48 | 0% | 0 | 100% | 36739.2542
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 758.48 | SQM | 0 | 758.48 | 0% | 0 | 100% | 12249.452
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 758.48 | SQM | 0 | 758.48 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 7500 | 50% | 7500
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 10000
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 7000
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1800
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 1013 | 13.055 | SFT | 13.05 | 0.005 | 99.96% | 13219.65 |  | 0
SHEKAR T | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 1013 | 210.657 | SFT | 204.34 | 6.317 | 97% | 206996.42 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
108499.4076

## V9
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
RABIUL MOLLA | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 0
RABIUL MOLLA | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
RABIUL MOLLA | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
RABIUL MOLLA | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
RABIUL MOLLA | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
RABIUL MOLLA | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
RABIUL MOLLA | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 0
RABIUL MOLLA | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
RABIUL MOLLA | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | -15.63 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
RABIUL MOLLA | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0.003 | 100.1% | 5680 |  | 0 | SANTOSH KUMAR | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0.002 | 100% | 4570 |  | 0 | SARAT BARMAN | 0
RABIUL MOLLA | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | -0.002 | 99.99% | 15110 |  | 0 | SAVITA DEVI | 0
RABIUL MOLLA | FOOTING REINFORCEMENT | 23 | 7500 | 0.65 | MT | 0.65 | 0 | 100% | 4875 |  | 0 | SHOKAT | 0
RABIUL MOLLA | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.75 | MT | 0.75 | 0 | 100% | 5625 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
RABIUL MOLLA | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SK ANSAR HOSSIAN | 0
RABIUL MOLLA | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.8 | MT | 0 | -2.8 | 0% | 0 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0 | -0.18 | 0% | 0 |  | 0 | SUBHASMITA DAS | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.18 | MT | 0 | -0.18 | 0% | 0 |  | 0 | UDHABHAI R PARMAR | 0
RABIUL MOLLA | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | V VENKATANARAYANA | 0
RABIUL MOLLA | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | YELLAPPA C | 0
RABIUL MOLLA | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0 | TOTAL | 0
RABIUL MOLLA | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 0 | -59.91 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 0 | -261.41 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 0 | -14.58 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 0 | -18.25 | 0% | 0 |  | 0
RABIUL MOLLA | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
RABIUL MOLLA | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
RABIUL MOLLA | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
RABIUL MOLLA | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 0 | -3.51 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 0 | -30.016 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 0 | -1.773 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0 | -0.8 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 1 | MT | 0 | -1 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 0 | -2.4 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | -0.18 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.2 | MT | 0 | -0.2 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 0 | -61.4 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 0 | -243.08 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 0 | -14.58 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 0 | -20.55 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 0 | -3.594 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 0 | -27.111 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 0 | -1.773 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 0 | -1.284 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0 | -0.15 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0 | -0.25 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 10000 | 0.04 | MT | 0 | -0.04 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | -8.1 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 0 | -29.38 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 0 | -3.81 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | -0.61 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 0 | -2.832 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | -0.22 | 0% | 0 |  | 0
RABIUL MOLLA | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 0 | -52 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 0 | -191.86 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 0 | -203.55 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 0 | -87.26 | 0% | 0 |  | 0
RABIUL MOLLA | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 0 | -47.7 | 0% | 0 |  | 0
RABIUL MOLLA | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | -64.23 | 0% | 0 |  | 0
RABIUL MOLLA | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 0 | -368.27 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 0 | -119.78 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 0 | -267.58 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 0 | -309.89 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 0 | -118.32 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 0 | -366.35 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 0 | -209.11 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 0 | -14.1 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 0 | -37.29 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 0 | -180.56 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
RABIUL MOLLA | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 867.74 | SFT | 50 | -817.74 | 5.762% | 15500 |  | 0
RABIUL MOLLA | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 244 | SFT | 0 | -244 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | -3 | 0% | 0 |  | 0
[9 empty] | 220933.4764 |  | 0

## V10
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 147.3041 | SQM | 147.3 | -0.0041 | 100% | 3240.6 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 151.12 | 0 | 100% | 6498.16 |  | 0 | RUPAK NAYAK | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 15.63 | 0 | 100% | 2205.7056 |  | 0 | SANTOSH KUMAR | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0.003 | 100.1% | 5680 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0.002 | 100% | 4570 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | -0.002 | 99.99% | 15110 |  | 0 | SHOKAT | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100% | 4550 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100% | 5250 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.9 | MT | 0.9 | 0 | 100% | 6300 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.8 | MT | 2.8 | 0 | 100% | 19600 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.18 | MT | 0 | -0.18 | 0% | 0 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | YELLAPPA C | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | TOTAL | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | 0.004 | 100% | 6754.5 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100% | 1200 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 2.4 | MT | 2.4 | 0 | 100% | 16800 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0 | -0.2 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | -0.004 | 99.89% | 7180 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | -0.001 | 100% | 6099.75 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 0 | -1.284 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.04 | MT | 0 | -0.04 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | -0.002 | 99.93% | 636.75 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | -0.22 | 0% | 0 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 127 | 193.752 | 202.55 | SQM | 172.17 | -30.38 | 85% | 33358.2818 |  | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 132 | 193.752 | 87.26 | SQM | 74.17 | -13.09 | 85% | 14370.5858 |  | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 0 | -368.27 | 0% | 0 |  | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 0 | -309.89 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 0 | -118.32 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 0 | -366.35 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 0 | -209.11 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 0 | -14.1 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 0 | -37.29 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 0 | -180.56 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 658 | 233 | SFT | 101.26 | -131.74 | 43.46% | 66629.08 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | -3 | 0% | 0 |  | 0
[9 empty] | 682048.1844 |  | 0

## V11
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
KOUSHIK MANDAL | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 0 | -151.12 | 0% | 0 |  | 0 | AAIDHUL MIAH | 0
KOUSHIK MANDAL | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | EBI ABRAHAM | 0
KOUSHIK MANDAL | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
KOUSHIK MANDAL | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | KRIUTTIBAS DAS | 0
KOUSHIK MANDAL | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | LEGENDRY LANDSCAPE | 0
KOUSHIK MANDAL | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | MANJUNATHA P | 0
KOUSHIK MANDAL | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | NAGARAJ | 0
KOUSHIK MANDAL | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | -15.63 | 0% | 0 |  | 0 | PRAKASH H N | 0
KOUSHIK MANDAL | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0.003 | 100.1% | 5680 |  | 0 | RAMAKRUSHNA PRADHAN | 0
KOUSHIK MANDAL | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0.002 | 100% | 4570 |  | 0 | RUPAK NAYAK | 0
KOUSHIK MANDAL | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | -0.002 | 99.99% | 15110 |  | 0 | SANTOSH KUMAR | 0
KOUSHIK MANDAL | FOOTING REINFORCEMENT | 23 | 7500 | 0.65 | MT | 0.65 | 0 | 100% | 4875 |  | 0 | SARAT BARMAN | 0
KOUSHIK MANDAL | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.75 | MT | 0.75 | 0 | 100% | 5625 |  | 0 | SAVITA DEVI | 0
KOUSHIK MANDAL | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SHOKAT | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.8 | MT | 2.8 | 0 | 100% | 21000 |  | 0 | SK ANSAR HOSSIAN | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0 | -0.18 | 0% | 0 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
KOUSHIK MANDAL | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | SUBHASMITA DAS | 0
KOUSHIK MANDAL | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | UDHABHAI R PARMAR | 0
KOUSHIK MANDAL | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0 | V VENKATANARAYANA | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0 | YELLAPPA C | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0 | TOTAL | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 0 | -18.25 | 0% | 0 |  | 0
KOUSHIK MANDAL | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
KOUSHIK MANDAL | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
KOUSHIK MANDAL | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | 0.004 | 100% | 6754.5 |  | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0 | -0.8 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.4 | 0 | 100% | 18000 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0 | -0.2 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 0 | -20.55 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | -0.004 | 99.89% | 7180 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | -0.001 | 100% | 6099.75 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 0 | -1.284 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.04 | MT | 0 | -0.04 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 0 | -3.81 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | -0.002 | 99.93% | 636.75 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | -0.22 | 0% | 0 |  | 0
KOUSHIK MANDAL | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0.8 | -0.2 | 80% | 1600 |  | 0
KOUSHIK MANDAL | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 153.49 | -38.37 | 80% | 29738.9945 |  | 0
KOUSHIK MANDAL | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 101.78 | -101.77 | 50% | 19720.0786 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
KOUSHIK MANDAL | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 0 | -47.7 | 0% | 0 |  | 0
KOUSHIK MANDAL | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | -64.23 | 0% | 0 |  | 0
KOUSHIK MANDAL | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 349.86 | -18.41 | 95% | 3764.4936 |  | 0
KOUSHIK MANDAL | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 113.79 | -5.99 | 95% | 15922.8623 |  | 0
KOUSHIK MANDAL | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 254.2 | -13.38 | 95% | 35570.7144 |  | 0
KOUSHIK MANDAL | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 294.4 | -15.49 | 95% | 57040.5888 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 1 | 0 | 100% | 16500 |  | 0
KOUSHIK MANDAL | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 112.4 | -5.92 | 95% | 15728.3568 |  | 0
KOUSHIK MANDAL | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 348.03 | -18.32 | 95% | 48700.534 |  | 0
KOUSHIK MANDAL | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 198.65 | -10.46 | 95% | 38488.8348 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 13.4 | -0.7 | 95.04% | 1875.0888 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 35.43 | -1.86 | 95.01% | 4957.7908 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 171.53 | -9.03 | 95% | 33234.2806 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 0.5 | -0.5 | 50% | 7500 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 1500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KOUSHIK MANDAL | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 765.25 | SFT | 650.46 | -114.79 | 85% | 201642.6 |  | 0
KOUSHIK MANDAL | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 557 | SFT | 473.45 | -83.55 | 85% | 146769.5 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | -3 | 0% | 0 |  | 0
[9 empty] | 1193421.3902 |  | 0

## V12
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
KOUSHIK MANDAL | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
KOUSHIK MANDAL | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
KOUSHIK MANDAL | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
KOUSHIK MANDAL | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
KOUSHIK MANDAL | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
KOUSHIK MANDAL | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 0
KOUSHIK MANDAL | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
KOUSHIK MANDAL | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | -15.63 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
KOUSHIK MANDAL | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0.003 | 100.1% | 5680 |  | 0 | SANTOSH KUMAR | 0
KOUSHIK MANDAL | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0.002 | 100% | 4570 |  | 0 | SARAT BARMAN | 0
KOUSHIK MANDAL | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | -0.002 | 99.99% | 15110 |  | 0 | SAVITA DEVI | 0
KOUSHIK MANDAL | FOOTING REINFORCEMENT | 23 | 7500 | 0.65 | MT | 0.65 | 0 | 100% | 4875 |  | 0 | SHOKAT | 0
KOUSHIK MANDAL | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.75 | MT | 0.75 | 0 | 100% | 5625 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
KOUSHIK MANDAL | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SK ANSAR HOSSIAN | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.8 | MT | 2.8 | 0 | 100% | 21000 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SUBHASMITA DAS | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0 | -0.18 | 0% | 0 |  | 0 | UDHABHAI R PARMAR | 0
KOUSHIK MANDAL | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | V VENKATANARAYANA | 0
KOUSHIK MANDAL | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | YELLAPPA C | 0
KOUSHIK MANDAL | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0 | TOTAL | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 0 | -18.25 | 0% | 0 |  | 0
KOUSHIK MANDAL | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
KOUSHIK MANDAL | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
KOUSHIK MANDAL | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | 0.004 | 100% | 6754.5 |  | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0 | -0.8 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 1 | MT | 0.95 | -0.05 | 95% | 7125 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.28 | -0.12 | 95% | 17100 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.17 | -0.01 | 94.44% | 1275 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0 | -0.2 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 58.33 | -3.07 | 95% | 17580.1954 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 230.93 | -12.15 | 95% | 69600.4546 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 13.85 | -0.73 | 94.99% | 4174.2792 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 0 | -20.55 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.41 | -0.184 | 94.88% | 6820 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 25.76 | -1.351 | 95.02% | 5796 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.68 | -0.093 | 94.75% | 3360 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 0 | -1.284 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0 | -0.15 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0 | -0.25 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.04 | MT | 0 | -0.04 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | -8.1 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 0 | -29.38 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 0 | -3.81 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | -0.61 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 0 | -2.832 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | -0.22 | 0% | 0 |  | 0
KOUSHIK MANDAL | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 0 | -52 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0.5 | -0.5 | 50% | 1000 |  | 0
KOUSHIK MANDAL | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 0 | -191.86 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 0 | -203.55 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 0 | -87.26 | 0% | 0 |  | 0
KOUSHIK MANDAL | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 0 | -47.7 | 0% | 0 |  | 0
KOUSHIK MANDAL | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | -64.23 | 0% | 0 |  | 0
KOUSHIK MANDAL | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 0 | -368.27 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 0 | -119.78 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 0 | -267.58 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 0 | -309.89 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 0 | -118.32 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 0 | -366.35 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 0 | -209.11 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 0 | -14.1 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 0 | -37.29 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 0 | -180.56 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KOUSHIK MANDAL | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 765.25 | SFT | 288.66 | -476.59 | 37.72% | 89484.6 |  | 0
KOUSHIK MANDAL | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 557 | SFT | 295.21 | -261.79 | 53% | 91515.1 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | -3 | 0% | 0 |  | 0
[9 empty] | 663166.1783 |  | 0

## V13
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
KOUSHIK MANDAL | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 0
KOUSHIK MANDAL | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | EBI ABRAHAM | 0
KOUSHIK MANDAL | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
KOUSHIK MANDAL | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | KRIUTTIBAS DAS | 0
KOUSHIK MANDAL | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | LEGENDRY LANDSCAPE | 0
KOUSHIK MANDAL | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 0 | -62.8 | 0% | 0 |  | 0 | MANJUNATHA P | 0
KOUSHIK MANDAL | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 0 | -151.12 | 0% | 0 |  | 0 | NAGARAJ | 0
KOUSHIK MANDAL | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | -15.63 | 0% | 0 |  | 0 | PRAKASH H N | 0
KOUSHIK MANDAL | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0.003 | 100.1% | 5680 |  | 0 | RAMAKRUSHNA PRADHAN | 0
KOUSHIK MANDAL | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0.002 | 100% | 4570 |  | 0 | RUPAK NAYAK | 0
KOUSHIK MANDAL | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | -0.002 | 99.99% | 15110 |  | 0 | SANTOSH KUMAR | 0
KOUSHIK MANDAL | FOOTING REINFORCEMENT | 23 | 7500 | 0.65 | MT | 0.65 | 0 | 100% | 4875 |  | 0 | SARAT BARMAN | 0
KOUSHIK MANDAL | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.75 | MT | 0.75 | 0 | 100% | 5625 |  | 0 | SAVITA DEVI | 0
KOUSHIK MANDAL | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SHOKAT | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.8 | MT | 2.8 | 0 | 100% | 21000 |  | 0 | SK ANSAR HOSSIAN | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0 | -0.18 | 0% | 0 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
KOUSHIK MANDAL | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | SUBHASMITA DAS | 0
KOUSHIK MANDAL | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | UDHABHAI R PARMAR | 0
KOUSHIK MANDAL | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0 | V VENKATANARAYANA | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0 | YELLAPPA C | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0 | TOTAL | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 0 | -18.25 | 0% | 0 |  | 0
KOUSHIK MANDAL | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
KOUSHIK MANDAL | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
KOUSHIK MANDAL | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | 0.004 | 100% | 6754.5 |  | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0 | -0.8 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 1 | MT | 0.95 | -0.05 | 95% | 7125 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.28 | -0.12 | 95% | 17100 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.17 | -0.01 | 94.44% | 1275 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0 | -0.2 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 58.33 | -3.07 | 95% | 17580.1954 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 230.93 | -12.15 | 95% | 69600.4546 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 13.85 | -0.73 | 94.99% | 4174.2792 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 0 | -20.55 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.41 | -0.184 | 94.88% | 6820 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 25.76 | -1.351 | 95.02% | 5796 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.68 | -0.093 | 94.75% | 3360 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 0 | -1.284 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0 | -0.15 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0 | -0.25 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.04 | MT | 0 | -0.04 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | -8.1 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 0 | -29.38 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 0 | -3.81 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | -0.61 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 0 | -2.832 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | -0.22 | 0% | 0 |  | 0
KOUSHIK MANDAL | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 0 | -52 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0.5 | -0.5 | 50% | 1000 |  | 0
KOUSHIK MANDAL | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 0 | -191.86 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 0 | -203.55 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 0 | -87.26 | 0% | 0 |  | 0
KOUSHIK MANDAL | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 0 | -47.7 | 0% | 0 |  | 0
KOUSHIK MANDAL | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | -64.23 | 0% | 0 |  | 0
KOUSHIK MANDAL | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 0 | -368.27 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 0 | -119.78 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 0 | -267.58 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 0 | -309.89 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 0 | -118.32 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 0 | -366.35 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 0 | -209.11 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 0 | -14.1 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 0 | -37.29 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 0 | -180.56 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KOUSHIK MANDAL | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 765.25 | SFT | 290.8 | -474.45 | 38% | 90148 |  | 0
KOUSHIK MANDAL | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 557 | SFT | 295.21 | -261.79 | 53% | 91515.1 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | -3 | 0% | 0 |  | 0
[9 empty] | 646642.6023 |  | 0

## V14
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 152.08 | SQM | 0 | -152.08 | 0% | 0 |  | 0 | AAIDHUL MIAH | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 2242.27 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 0 | -2 | 0% | 0 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 166.4 | CUM | 81.67 | -84.73 | 49.08% | 17287.9056 |  | 0 | KRIUTTIBAS DAS | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 83.2 | SQM | 83.2 | 0 | 100% | 1830.4 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 148.93 | CUM | 148.93 | 0 | 100% | 21017.0016 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 8.53 | CUM | 8.53 | 0 | 100% | 1805.6304 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 71.9 | CUM | 71.9 | 0 | 100% | 10146.528 |  | 0 | PRAKASH H N | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 156.64 | SQM | 156.64 | 0 | 100% | 3446.08 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 152.08 | SQM | 0 | -152.08 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 11.44 | CUM | 0 | -11.44 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 5500 | SARAT BARMAN | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 5.95 | CUM | 5.95 | 0 | 100% | 5950 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.39 | CUM | 4.39 | 0 | 100% | 4390 |  | 0 | SHOKAT | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 15.66 | CUM | 15.66 | 0 | 100% | 15660 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 5600 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 5600 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.9 | MT | 0.9 | 0 | 100% | 6300 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.1 | MT | 0.1 | 0 | 100% | 700 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.9 | MT | 0.9 | 0 | 100% | 6300 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 3.2 | MT | 3.2 | 0 | 100% | 22400 |  | 0 | V VENKATANARAYANA | 5500
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | YELLAPPA C | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | TOTAL | 5500
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 57.94 | SQM | 57.94 | 0 | 100% | 17462.6525 |  | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 46.78 | SQM | 46.78 | 0 | 100% | 14099.1178 |  | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 106.9 | SQM | 106.9 | 0 | 100% | 32218.8048 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 62.72 | SQM | 62.72 | 0 | 100% | 18903.3062 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 273.15 | SQM | 273.15 | 0 | 100% | 82325.2248 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.79 | SQM | 12.79 | 0 | 100% | 3854.8037 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.53 | SQM | 18.53 | 0 | 100% | 5584.7938 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 22.26 | CUM | 22.26 | 0 | 100% | 5008.5 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.14 | CUM | 2.14 | 0 | 100% | 3210 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 8.15 | CUM | 8.15 | 0 | 100% | 7335 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.77 | CUM | 3.77 | 0 | 100% | 7540 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.04 | CUM | 30.04 | 0 | 100% | 6759 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.67 | CUM | 1.67 | 0 | 100% | 3340 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 1.14 | CUM | 1.14 | 0 | 100% | 1710 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.83 | MT | 0.83 | 0 | 100% | 5810 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 2.4 | MT | 2.4 | 0 | 100% | 16800 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 56.69 | SQM | 56.69 | 0 | 100% | 17085.9125 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 234.32 | SQM | 234.32 | 0 | 100% | 70622.1734 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.79 | SQM | 12.79 | 0 | 100% | 3854.8037 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 25.02 | SQM | 25.02 | 0 | 100% | 7540.8278 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.23 | CUM | 3.23 | 0 | 100% | 6460 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.63 | CUM | 27.63 | 0 | 100% | 6216.75 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.67 | CUM | 1.67 | 0 | 100% | 3340 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.41 | CUM | 1.41 | 0 | 100% | 2115 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.01 | MT | 0.01 | 0 | 100% | 70 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 26.85 | SQM | 26.85 | 0 | 100% | 8092.3752 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.815 | SQM | 1.82 | 0.005 | 100.3% | 548.5334 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.93 | CUM | 2.93 | 0 | 100% | 659.25 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.09 | CUM | 0.09 | 0 | 100% | 135 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 53 | NOS | 53 | 0 | 100% | 2650 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 201.77 | SQM | 201.77 | 0 | 100% | 39093.341 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 216.39 | SQM | 216.39 | 0 | 100% | 41925.9953 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.19 | SQM | 62.19 | 0 | 100% | 12049.4369 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 49.17 | RMT | 0 | -49.17 | 0% | 0 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 37.67 | RMT | 0 | -37.67 | 0% | 0 |  | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.26 | SQM | 0 | -1.26 | 0% | 0 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 338.17 | SQM | 0 | -338.17 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 117.33 | SQM | 0 | -117.33 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 307.83 | SQM | 0 | -307.83 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 347.17 | SQM | 0 | -347.17 | 0% | 0 |  | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14000 | 1 | LUMP SUM | 1 | 0 | 100% | 14000 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 129.31 | SQM | 0 | -129.31 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 431.24 | SQM | 0 | -431.24 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 198 | SQM | 0 | -198 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 13.49 | SQM | 0 | -13.49 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 47.73 | SQM | 0 | -47.73 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 204.32 | SQM | 0 | -204.32 | 0% | 0 |  | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 87.79 | SQM | 87.79 | 0 | 100% | 37798.8624 |  | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 160.35 | SQM | 160.35 | 0 | 100% | 69040.296 |  | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 38.15 | SQM | 38.15 | 0 | 100% | 8212.932 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 38.45 | SQM | 38.45 | 0 | 100% | 8277.516 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 28 | NOS | 19 | -9 | 67.86% | 3800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 312.43 | 0 | 100% | 15133.4843 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 160.99 | 0 | 100% | 7798.0336 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 190.72 | 0 | 100% | 9238.0954 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 215.481 | SQM | 215.48 | -0.001 | 100% | 19715.1271 |  | 0
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 93.864 | SQM | 93.86 | -0.004 | 100% | 8587.6268 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 301.868 | SQM | 301.87 | 0.002 | 100% | 27619.2938 |  | 0
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 103.448 | SQM | 103.45 | 0.002 | 100% | 9465.0543 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 33.411 | SQM | 33.41 | -0.001 | 100% | 3056.8145 |  | 0
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 10.792 | SQM | 10.79 | -0.002 | 99.98% | 987.2203 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 26.866 | SQM | 0 | -26.866 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 5 | NOS | 3 | -2 | 60% | 1350 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 23 | NOS | 18 | -5 | 78.26% | 6300 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 44.743 | RMT | 0 | -44.743 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 134.23 | RMT | 0 | -134.23 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 33.186 | RMT | 0 | -33.186 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 6 | NOS | 6 | 0 | 100% | 6000 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 106.54 | SQM | 106.54 | 0 | 100% | 19496.82 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 95.43 | RMT | 95.43 | 0 | 100% | 4695.156 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 110.61 | SQM | 110.61 | 0 | 100% | 20241.63 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 101.69 | RMT | 101.69 | 0 | 100% | 5003.148 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.698 | SQM | 3.7 | 0.002 | 100.1% | 677.1 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.86 | RMT | 5.86 | 0 | 100% | 288.312 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 5.13 | SQM | 5.13 | 0 | 100% | 938.79 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 9.83 | RMT | 9.83 | 0 | 100% | 483.636 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 28.012 | SQM | 28.01 | -0.002 | 99.99% | 5125.83 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 31.801 | RMT | 31.8 | -0.001 | 100% | 1564.56 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 38.52 | SQM | 38.52 | 0 | 100% | 7049.16 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 2836 | SFT | 2836 | 0 | 100% | 7090 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 8.66 | SQM | 8.66 | 0 | 100% | 1584.78 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 36.69 | SQM | 36.69 | 0 | 100% | 6714.27 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 15.007 | SQM | 15.01 | 0.003 | 100% | 2746.83 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 61.387 | SQM | 61.39 | 0.003 | 100% | 11234.37 |  | 0
PRAKASH JANA | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 398.25 | SQM | 398.25 | 0 | 100% | 10716.9075 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100% | 17500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 8000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 27.32 | RMT | 27.32 | 0 | 100% | 151216.2 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 18958 | 1 | LUMP SUM | 1 | 0 | 100% | 18958 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 100 | RFT | 100 | 0 | 100% | 3400 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 27 | 0 | 100% | 2079 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 249 | SFT | 249 | 0 | 100% | 5727 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 15 | 0 | 100% | 2265 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 555 | 207 | SFT | 56.79 | 150.21 | 27.43% | 31518.45 |  | 0
SAVITA DEVI | MS STAIRCASE HOLE DRILLING | 335 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | MS STAIRCASE STEPS RUBBER WOOD LAYING | 336 | 49000 | 1 | LUMP SUM | 1 | 0 | 100% | 49000 |  | 0
SAVITA DEVI | MS STAIRCASE WORK | 346 | 50000 | 1 | LUMP SUM | 1 | 0 | 100% | 50000 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION MS STAIRCASE PAINTING AND STEP WOOD POLISHING WORK | 424 | 30000 | 1 | LUMP SUM | 1 | 0 | 100% | 30000 |  | 0
[9 empty] | 1378993.3345 |  | 5500

## V15
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SHEKAR T | ATT IN PLINTH | 1 | 54 | 152.08 | SQM | 152.08 | 0 | 100% | 8212.32 |  | 0 | AAIDHUL MIAH | 350
SHEKAR T | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
SHEKAR T | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
SHEKAR T | FOOTING EXCAVATION | 4 | 211.68 | 166.4 | CUM | 166.4 | 0 | 100% | 35223.552 |  | 0 | KRIUTTIBAS DAS | 2000
SHEKAR T | FOOTING EARTH DRESSING | 5 | 22 | 83.2 | SQM | 83.2 | 0 | 100% | 1830.4 |  | 0 | LEGENDRY LANDSCAPE | 0
SHEKAR T | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 148.93 | CUM | 148.93 | 0 | 100% | 21017.0016 |  | 0 | MANJUNATHA P | 0
SHEKAR T | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 8.53 | CUM | 8.53 | 0 | 100% | 1805.6304 |  | 0 | NAGARAJ | 0
SHEKAR T | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 71.9 | CUM | 71.9 | 0 | 100% | 10146.528 |  | 0 | PRAKASH H N | 0
SHEKAR T | BASE FLOOR EARTH DRESSING | 14 | 22 | 156.64 | SQM | 156.64 | 0 | 100% | 3446.08 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SHEKAR T | SETBACK AREA SOIL FILLING | 16 | 141.12 | 11.44 | CUM | 0 | 11.44 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
SHEKAR T | FOOTING PCC WORK | 20 | 1000 | 5.95 | CUM | 5.95 | 0 | 100% | 5950 |  | 0 | SAVITA DEVI | 5625
SHEKAR T | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.39 | CUM | 4.39 | 0 | 100% | 4390 |  | 0 | SHOKAT | 0
SHEKAR T | BASE FLOOR PCC | 22 | 1000 | 15.66 | CUM | 15.66 | 0 | 100% | 15660 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SHEKAR T | FOOTING REINFORCEMENT | 23 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | SK ANSAR HOSSIAN | 0
SHEKAR T | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SHEKAR T | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SHEKAR T | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SUBHASMITA DAS | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 3.2 | MT | 3.2 | 0 | 100% | 24000 |  | 0 | UDHABHAI R PARMAR | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | V VENKATANARAYANA | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | YELLAPPA C | 0
SHEKAR T | FOOTING SHUTTERING | 41 | 301.392 | 57.94 | SQM | 57.94 | 0 | 100% | 17462.6525 |  | 0 | TOTAL | 7975
SHEKAR T | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 46.78 | SQM | 46.78 | 0 | 100% | 14099.1178 |  | 0
SHEKAR T | PLINTH BEAM SHUTTERING | 43 | 301.392 | 106.9 | SQM | 106.9 | 0 | 100% | 32218.8048 |  | 0
SHEKAR T | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 62.72 | SQM | 62.72 | 0 | 100% | 18903.3062 |  | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 273.15 | SQM | 273.15 | 0 | 100% | 82325.2248 |  | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.79 | SQM | 12.79 | 0 | 100% | 3854.8037 |  | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.53 | SQM | 18.53 | 0 | 100% | 5584.7938 |  | 0
SHEKAR T | FOOTING RCC | 50 | 225 | 22.26 | CUM | 22.26 | 0 | 100% | 5008.5 |  | 0
SHEKAR T | PEDESTAL COLUMN RCC | 51 | 1500 | 2.14 | CUM | 2.14 | 0 | 100% | 3210 |  | 0
SHEKAR T | PLINTH BEAM RCC | 53 | 900 | 8.15 | CUM | 8.15 | 0 | 100% | 7335 |  | 0
SHEKAR T | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.77 | CUM | 3.77 | 0 | 100% | 7540 |  | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.04 | CUM | 30.04 | 0 | 100% | 6759 |  | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.67 | CUM | 1.67 | 0 | 100% | 3340 |  | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 1.14 | CUM | 1.14 | 0 | 100% | 1710 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHEKAR T | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.83 | MT | 0.83 | 0 | 100% | 6225 |  | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.4 | 0 | 100% | 18000 |  | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
SHEKAR T | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 56.69 | SQM | 56.69 | 0 | 100% | 17085.9125 |  | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 234.32 | SQM | 234.32 | 0 | 100% | 70622.1734 |  | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.79 | SQM | 12.79 | 0 | 100% | 3854.8037 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 25.02 | SQM | 25.02 | 0 | 100% | 7540.8278 |  | 0
SHEKAR T | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.23 | CUM | 3.23 | 0 | 100% | 6460 |  | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.63 | CUM | 27.63 | 0 | 100% | 6216.75 |  | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.67 | CUM | 1.67 | 0 | 100% | 3340 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.41 | CUM | 1.41 | 0 | 100% | 2115 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
SHEKAR T | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 26.85 | SQM | 26.85 | 0 | 100% | 8092.3752 |  | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.815 | SQM | 1.82 | -0.005 | 100.3% | 548.5334 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.93 | CUM | 2.93 | 0 | 100% | 659.25 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.09 | CUM | 0.09 | 0 | 100% | 135 |  | 0
SHEKAR T | ALL LEVEL COLUMN STARTER | 116 | 50 | 53 | NOS | 53 | 0 | 100% | 2650 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHEKAR T | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 201.77 | SQM | 201.77 | 0 | 100% | 39093.341 |  | 0
SHEKAR T | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 216.39 | SQM | 216.39 | 0 | 100% | 41925.9953 |  | 0
SHEKAR T | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.19 | SQM | 62.19 | 0 | 100% | 12049.4369 |  | 0
SHEKAR T | ELEVATION RCC BAND | 133 | 65.6 | 49.17 | RMT | 49.17 | 0 | 100% | 3225.552 |  | 0
SHEKAR T | ELEVATION GROOVE | 137 | 65.6 | 37.67 | RMT | 37.67 | 0 | 100% | 2471.152 |  | 0
SHEKAR T | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.26 | SQM | 1.26 | 0 | 100% | 203.4396 |  | 0
SHEKAR T | RCC SURFACE HACKING | 140 | 10.76 | 338.17 | SQM | 338.17 | 0 | 100% | 3638.7092 |  | 0
SHEKAR T | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 117.33 | SQM | 117.33 | 0 | 100% | 16418.2216 |  | 0
SHEKAR T | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 307.83 | SQM | 307.83 | 0 | 100% | 43075.2676 |  | 0
SHEKAR T | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 347.17 | SQM | 347.17 | 0 | 100% | 67264.8818 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
SHEKAR T | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 129.31 | SQM | 129.31 | 0 | 100% | 18094.6069 |  | 0
SHEKAR T | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 431.24 | SQM | 431.24 | 0 | 100% | 60344.2757 |  | 0
SHEKAR T | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 198 | SQM | 198 | 0 | 100% | 38362.896 |  | 0
SHEKAR T | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 13.49 | SQM | 13.49 | 0 | 100% | 1887.6827 |  | 0
SHEKAR T | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 47.73 | SQM | 47.73 | 0 | 100% | 6678.9544 |  | 0
SHEKAR T | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 204.32 | SQM | 204.32 | 0 | 100% | 39587.4086 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 264.9569 | SQM | 264.96 | -0.0031 | 100% | 57040.5888 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 30.8256 | SQM | 30.83 | -0.0044 | 100% | 6637.0824 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 65.54 | SQM | 65.54 | 0 | 100% | 7054.7256 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 78.421 | SQM | 78.42 | 0.001 | 100% | 16882.2576 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 143.961 | SQM | 143.96 | 0.001 | 100% | 15495.8544 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 19 | NOS | 19 | 0 | 100% | 3800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 312.43 | 0 | 100% | 15133.4843 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 160.99 | 0 | 100% | 7798.0336 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 190.72 | 0 | 100% | 9238.0954 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 307.83 | SQM | 307.83 | 0 | 100% | 28164.598 |  | 0
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 117.33 | SQM | 117.33 | 0 | 100% | 10734.991 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 431.24 | SQM | 431.24 | 0 | 100% | 39455.8726 |  | 0
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 129.31 | SQM | 129.31 | 0 | 100% | 11831.0891 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 47.73 | SQM | 47.73 | 0 | 100% | 4367.0086 |  | 0
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 13.49 | SQM | 13.49 | 0 | 100% | 1234.2541 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 26.866 | SQM | 0 | 26.866 | 0% | 0 |  | 0
SANTOSH KUMAR | STAIRCASE GRANITE | 215 | 301.392 | 26.866 | SQM | 26.87 | -0.004 | 100% | 8098.403 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
SANTOSH KUMAR | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 1 | 2 | 33.33% | 450 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 0 | 16 | 0% | 0 |  | 0
SANTOSH KUMAR | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 15 | 1 | 93.75% | 5250 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 44.743 | RMT | 0 | 44.743 | 0% | 0 |  | 0
SANTOSH KUMAR | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 44.743 | RMT | 44.74 | 0.003 | 99.99% | 3668.68 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 134.23 | RMT | 0 | 134.23 | 0% | 0 |  | 0
SANTOSH KUMAR | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 134.23 | RMT | 134.23 | 0 | 100% | 4402.744 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 33.186 | RMT | 0 | 33.186 | 0% | 0 |  | 0
SANTOSH KUMAR | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 33.186 | RMT | 33.19 | -0.004 | 100% | 4354.528 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 6 | NOS | 0 | 6 | 0% | 0 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 6 | NOS | 0 | 6 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 172.224 | 102.693 | SQM | 0 | 102.693 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 172.224 | 102.693 | SQM | 102.69 | 0.003 | 100% | 17685.6826 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 58.4778 | RMT | 0 | 58.4778 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 58.4778 | RMT | 58.48 | -0.0022 | 100% | 2877.216 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 172.224 | 101.973 | SQM | 0 | 101.973 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 172.224 | 101.973 | SQM | 101.97 | 0.003 | 100% | 17561.6813 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 75.35 | RMT | 0 | 75.35 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 75.35 | RMT | 75.35 | 0 | 100% | 3707.22 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 172.224 | 3.657 | SQM | 0 | 3.657 | 0% | 0 |  | 0
SANTOSH KUMAR | TERRACE FLOOR TILING | 228 | 172.224 | 3.657 | SQM | 3.66 | -0.003 | 100.1% | 630.3398 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.94 | RMT | 0 | 4.94 | 0% | 0 |  | 0
SANTOSH KUMAR | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.94 | RMT | 4.94 | 0 | 100% | 243.048 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 172.224 | 5.868 | SQM | 0 | 5.868 | 0% | 0 |  | 0
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 5.868 | SQM | 5.87 | -0.002 | 100% | 1074.21 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 9.164 | RMT | 0 | 9.164 | 0% | 0 |  | 0
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 9.164 | RMT | 9.16 | 0.004 | 99.96% | 450.672 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 172.224 | 24.691 | SQM | 0 | 24.691 | 0% | 0 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 183 | 24.691 | SQM | 24.69 | 0.001 | 100% | 4518.27 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 28.31 | RMT | 0 | 28.31 | 0% | 0 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 28.31 | RMT | 28.31 | 0 | 100% | 1392.852 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 172.224 | 37.322 | SQM | 0 | 37.322 | 0% | 0 |  | 0
SANTOSH KUMAR | CAR PARKING AREA TILING | 234 | 183 | 21.806 | SQM | 21.81 | -0.004 | 100% | 3991.23 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 2531.574 | SFT | 0 | 2531.574 | 0% | 0 |  | 0
SANTOSH KUMAR | FLOOR CHIPPING | 235 | 2.5 | 2531.574 | SFT | 2531.57 | 0.004 | 100% | 6328.925 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 172.224 | 8.574 | SQM | 0 | 8.574 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET FLOOR TILING | 237 | 172.224 | 8.574 | SQM | 8.57 | 0.004 | 99.95% | 1475.9597 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 193.752 | 27.9805 | SQM | 0 | 27.9805 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET WALL TILING | 238 | 193.752 | 27.9805 | SQM | 27.98 | 0.00049 | 100% | 5421.181 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 172.224 | 19.678 | SQM | 0 | 19.678 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET FLOOR TILING | 239 | 172.224 | 19.678 | SQM | 19.68 | -0.002 | 100% | 3389.3683 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 193.752 | 58.9844 | SQM | 0 | 58.9844 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET WALL TILING | 240 | 193.752 | 58.9844 | SQM | 58.98 | 0.0044 | 99.99% | 11427.493 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 269.491 | SQM | 269.49 | 0.001 | 100% | 17403.6642 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 1 | 0 | 100% | 18500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 28.865 | RMT | 28.87 | -0.005 | 100% | 159795.45 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 18938 | 1 | LUMP SUM | 1 | 0 | 100% | 18938 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 0 | 12.5 | 0% | 0 | 100% | 5625
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 0 | 0 | 0% | 0 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 0 | 0% | 0 | 100% | 350
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100% | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SHEKAR T | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 295 | 290 | 399.21 | SQM | 399.21 | 0 | 100% | 115770.9 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 6826.35 | 1 | LUMP SUM | 1 | 0 | 100% | 6826.35 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 2 | NOS | 1 | 1 | 50% | 1000 |  | 0
SANTOSH KUMAR | CUSTOMISATION ADDITIONAL WALL TILING ABOVE 8FT IN ALL FLOOR TOILET | 410 | 193.752 | 23.28 | SQM | 22.12 | 1.16 | 95.02% | 4285.7942 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 0.5 | 0.5 | 50% | 750 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION TAP POINT WORK | 423 | 600 | 3 | NOS | 1.5 | 1.5 | 50% | 900 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION BATHTUB WORK | 425 | 3000 | 1 | NOS | 0.5 | 0.5 | 50% | 1500 |  | 0
SANTOSH KUMAR | UTILITY CUSTOMISATION WALL TILING WORK | 426 | 193.752 | 22.99 | SQM | 21.84 | 1.15 | 95% | 4231.5437 |  | 0
RUPAK NAYAK | CUSTOMISATION TERRACE EPOXY GROUTING AND SOAP WASH CLEANING WORK | 427 | 64.58 | 128.066 | SQM | 128.07 | -0.004 | 100% | 8270.7606 |  | 0
SANTOSH KUMAR | CUSTOMISATION FLOORING IN TERRACE/LAYING OF TILES IN TERRACE OF SIZE 2X2 (TILE PROVIDED BY CLIENT) | 428 | 215.28 | 135.739 | SQM | 135.74 | -0.001 | 100% | 29222.1072 |  | 0
SANTOSH KUMAR | CUSTOMISATION SKIRTING IN TERRACE/LAYING OF SKIRTING IN TERRACE (TILE PROVIDED BY CLIENT) | 429 | 49.2 | 68.434 | RMT | 68.43 | 0.004 | 99.99% | 3366.756 |  | 0
7975

## V16
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
RABIUL MOLLA | ATT IN PLINTH | 1 | 54 | 152.08 | SQM | 152.08 | 0 | 100% | 8212.32 |  | 0 | AAIDHUL MIAH | 0
RABIUL MOLLA | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
RABIUL MOLLA | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
RABIUL MOLLA | FOOTING EXCAVATION | 4 | 211.68 | 166.4 | CUM | 166.4 | 0 | 100% | 35223.552 |  | 0 | KRIUTTIBAS DAS | 9300
RABIUL MOLLA | FOOTING EARTH DRESSING | 5 | 22 | 83.2 | SQM | 83.2 | 0 | 100% | 1830.4 |  | 0 | LEGENDRY LANDSCAPE | 0
RABIUL MOLLA | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 148.93 | CUM | 148.93 | 0 | 100% | 21017.0016 |  | 0 | MANJUNATHA P | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 8.53 | CUM | 8.53 | 0 | 100% | 1805.6304 |  | 0 | NAGARAJ | 0
RABIUL MOLLA | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 71.9 | CUM | 71.9 | 0 | 100% | 10146.528 |  | 0 | PRAKASH H N | 10750
RABIUL MOLLA | BASE FLOOR EARTH DRESSING | 14 | 22 | 156.64 | SQM | 156.64 | 0 | 100% | 3446.08 |  | 0 | RAMAKRUSHNA PRADHAN | 0
RABIUL MOLLA | SETBACK AREA SOIL FILLING | 16 | 141.12 | 11.44 | CUM | 0 | 11.44 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
RABIUL MOLLA | FOOTING PCC WORK | 20 | 1000 | 5.95 | CUM | 5.95 | 0 | 100% | 5950 |  | 0 | SANTOSH KUMAR | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.39 | CUM | 4.39 | 0 | 100% | 4390 |  | 0 | SARAT BARMAN | 0
RABIUL MOLLA | BASE FLOOR PCC | 22 | 1000 | 15.66 | CUM | 15.66 | 0 | 100% | 15660 |  | 0 | SAVITA DEVI | 3000
RABIUL MOLLA | FOOTING REINFORCEMENT | 23 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | SHOKAT | 0
RABIUL MOLLA | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
RABIUL MOLLA | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SK ANSAR HOSSIAN | 0
RABIUL MOLLA | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 3.2 | MT | 3.2 | 0 | 100% | 24000 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SUBHASMITA DAS | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0 | UDHABHAI R PARMAR | 0
RABIUL MOLLA | FOOTING SHUTTERING | 41 | 301.392 | 57.94 | SQM | 57.94 | 0 | 100% | 17462.6525 |  | 0 | V VENKATANARAYANA | 0
RABIUL MOLLA | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 46.78 | SQM | 46.78 | 0 | 100% | 14099.1178 |  | 0 | YELLAPPA C | 0
RABIUL MOLLA | PLINTH BEAM SHUTTERING | 43 | 301.392 | 106.9 | SQM | 106.9 | 0 | 100% | 32218.8048 |  | 0 | RABIUL MOLLA | 163239.3269
RABIUL MOLLA | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 62.72 | SQM | 62.72 | 0 | 100% | 18903.3062 |  | 0 | TOTAL | 186289.3269
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 273.15 | SQM | 273.15 | 0 | 100% | 82325.2248 |  | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.79 | SQM | 12.79 | 0 | 100% | 3854.8037 |  | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.53 | SQM | 0 | 18.53 | 0% | 0 |  | 0
RABIUL MOLLA | FOOTING RCC | 50 | 225 | 22.26 | CUM | 22.26 | 0 | 100% | 5008.5 |  | 0
RABIUL MOLLA | PEDESTAL COLUMN RCC | 51 | 1500 | 2.14 | CUM | 2.14 | 0 | 100% | 3210 |  | 0
RABIUL MOLLA | PLINTH BEAM RCC | 53 | 900 | 8.15 | CUM | 8.15 | 0 | 100% | 7335 |  | 0
RABIUL MOLLA | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.77 | CUM | 3.77 | 0 | 100% | 7540 |  | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.04 | CUM | 30.04 | 0 | 100% | 6759 |  | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.67 | CUM | 1.67 | 0 | 100% | 3340 |  | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 1.14 | CUM | 0 | 1.14 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.83 | MT | 0.83 | 0 | 100% | 6225 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.4 | 0 | 100% | 18000 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0 | 0.2 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 56.69 | SQM | 56.69 | 0 | 100% | 17085.9125 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 234.32 | SQM | 234.32 | 0 | 100% | 70622.1734 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.79 | SQM | 12.79 | 0 | 100% | 3854.8037 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 25.02 | SQM | 0 | 25.02 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.23 | CUM | 3.23 | 0 | 100% | 6460 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.63 | CUM | 27.63 | 0 | 100% | 6216.75 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.67 | CUM | 1.67 | 0 | 100% | 3340 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.41 | CUM | 0 | 1.41 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0 | 0.25 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.01 | MT | 0 | 0.01 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 0 | 10.8 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 26.85 | SQM | 0 | 26.85 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.815 | SQM | 0 | 1.815 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.93 | CUM | 0 | 2.93 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.09 | CUM | 0 | 0.09 | 0% | 0 |  | 0
RABIUL MOLLA | ALL LEVEL COLUMN STARTER | 116 | 50 | 53 | NOS | 0 | 53 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
RABIUL MOLLA | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 201.77 | SQM | 191.68 | 10.09 | 95% | 37138.3834 |  | 0
RABIUL MOLLA | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 216.39 | SQM | 205.57 | 10.82 | 95% | 39829.5986 |  | 0
RABIUL MOLLA | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.19 | SQM | 59.08 | 3.11 | 95% | 11446.8682 |  | 0
RABIUL MOLLA | ELEVATION RCC BAND | 133 | 65.6 | 49.17 | RMT | 0 | 49.17 | 0% | 0 |  | 0
RABIUL MOLLA | ELEVATION GROOVE | 137 | 65.6 | 37.67 | RMT | 0 | 37.67 | 0% | 0 |  | 0
RABIUL MOLLA | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.26 | SQM | 0 | 1.26 | 0% | 0 |  | 0
RABIUL MOLLA | RCC SURFACE HACKING | 140 | 10.76 | 338.17 | SQM | 0 | 338.17 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 117.33 | SQM | 0 | 117.33 | 0% | 0 | 85% | 13955.4883
RABIUL MOLLA | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 307.83 | SQM | 0 | 307.83 | 0% | 0 | 85% | 36613.9774
RABIUL MOLLA | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 347.17 | SQM | 0 | 347.17 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 8250 | 50% | 8250
RABIUL MOLLA | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 129.31 | SQM | 0 | 129.31 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 431.24 | SQM | 0 | 431.24 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 198 | SQM | 0 | 198 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 13.49 | SQM | 0 | 13.49 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 47.73 | SQM | 0 | 47.73 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 204.32 | SQM | 0 | 204.32 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 50% | 6000
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1800
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RABIUL MOLLA | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 736.3 | SFT | 537.5 | 198.8 | 73% | 166625 |  | 0
RABIUL MOLLA | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 270 | 360.2173 | SFT | 0 | 360.2173 | 0% | 0 | 85% | 82669.8612
RABIUL MOLLA | CUSTOMIZATION WORK OF WALL DEMOLITION AND BLOCK WORK AS WELL AS TERRACE COLUMN AND SLAB CHIPPING FOR CUSTOMISATION ROOM COLUMN & SLAB STEEL LAPPING |  | 30000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 30000
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 50% | 1500
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2500
SAVITA DEVI | LABOUR FOR CUSTOMISATION ROOM PURPOSE STEEL EXTENSION WELDING WORKS | 414 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 3000
[9 empty] | 770782.4115 |  | 186289.3269

## V17
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
RABIUL MOLLA | ATT IN PLINTH | 1 | 54 | 152.08 | SQM | 152.08 | 0 | 100% | 8212.32 |  | 0 | AAIDHUL MIAH | 0
RABIUL MOLLA | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
RABIUL MOLLA | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
RABIUL MOLLA | FOOTING EXCAVATION | 4 | 211.68 | 166.4 | CUM | 166.4 | 0 | 100% | 35223.552 |  | 0 | KRIUTTIBAS DAS | 0
RABIUL MOLLA | FOOTING EARTH DRESSING | 5 | 22 | 83.2 | SQM | 83.2 | 0 | 100% | 1830.4 |  | 0 | LEGENDRY LANDSCAPE | 0
RABIUL MOLLA | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 148.93 | CUM | 148.93 | 0 | 100% | 21017.0016 |  | 0 | MANJUNATHA P | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 8.53 | CUM | 8.53 | 0 | 100% | 1805.6304 |  | 0 | NAGARAJ | 0
RABIUL MOLLA | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 71.9 | CUM | 71.9 | 0 | 100% | 10146.528 |  | 0 | PRAKASH H N | 0
RABIUL MOLLA | BASE FLOOR EARTH DRESSING | 14 | 22 | 156.64 | SQM | 156.64 | 0 | 100% | 3446.08 |  | 0 | RAMAKRUSHNA PRADHAN | 0
RABIUL MOLLA | SETBACK AREA SOIL FILLING | 16 | 141.12 | 11.44 | CUM | 0 | -11.44 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 5500 | SANTOSH KUMAR | 10055.2741
RABIUL MOLLA | FOOTING PCC WORK | 20 | 1000 | 5.95 | CUM | 5.95 | 0 | 100% | 5950 |  | 0 | SARAT BARMAN | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.39 | CUM | 4.39 | 0 | 100% | 4390 |  | 0 | SAVITA DEVI | 0
RABIUL MOLLA | BASE FLOOR PCC | 22 | 1000 | 15.66 | CUM | 15.66 | 0 | 100% | 15660 |  | 0 | SHOKAT | 0
RABIUL MOLLA | FOOTING REINFORCEMENT | 23 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
RABIUL MOLLA | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | SK ANSAR HOSSIAN | 0
RABIUL MOLLA | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
RABIUL MOLLA | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 3.2 | MT | 3.2 | 0 | 100% | 24000 |  | 0 | SUBHASMITA DAS | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | UDHABHAI R PARMAR | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | V VENKATANARAYANA | 5500
RABIUL MOLLA | FOOTING SHUTTERING | 41 | 301.392 | 57.94 | SQM | 57.94 | 0 | 100% | 17462.6525 |  | 0 | YELLAPPA C | 0
RABIUL MOLLA | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 46.78 | SQM | 46.78 | 0 | 100% | 14099.1178 |  | 0 | RABIUL MOLLA | 0
RABIUL MOLLA | PLINTH BEAM SHUTTERING | 43 | 301.392 | 106.9 | SQM | 106.9 | 0 | 100% | 32218.8048 |  | 0 | TOTAL | 15555.2741
RABIUL MOLLA | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 62.72 | SQM | 62.72 | 0 | 100% | 18903.3062 |  | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 273.15 | SQM | 273.15 | 0 | 100% | 82325.2248 |  | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.79 | SQM | 12.79 | 0 | 100% | 3854.8037 |  | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.53 | SQM | 18.53 | 0 | 100% | 5584.7938 |  | 0
RABIUL MOLLA | FOOTING RCC | 50 | 225 | 22.26 | CUM | 22.26 | 0 | 100% | 5008.5 |  | 0
RABIUL MOLLA | PEDESTAL COLUMN RCC | 51 | 1500 | 2.14 | CUM | 2.14 | 0 | 100% | 3210 |  | 0
RABIUL MOLLA | PLINTH BEAM RCC | 53 | 900 | 8.15 | CUM | 8.15 | 0 | 100% | 7335 |  | 0
RABIUL MOLLA | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.77 | CUM | 3.77 | 0 | 100% | 7540 |  | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.04 | CUM | 30.04 | 0 | 100% | 6759 |  | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.67 | CUM | 1.67 | 0 | 100% | 3340 |  | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 1.14 | CUM | 1.14 | 0 | 100% | 1710 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.83 | MT | 0.83 | 0 | 100% | 6225 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.4 | 0 | 100% | 18000 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 56.69 | SQM | 56.69 | 0 | 100% | 17085.9125 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 234.32 | SQM | 234.32 | 0 | 100% | 70622.1734 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.79 | SQM | 12.79 | 0 | 100% | 3854.8037 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 25.02 | SQM | 25.02 | 0 | 100% | 7540.8278 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.23 | CUM | 3.23 | 0 | 100% | 6460 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.63 | CUM | 27.63 | 0 | 100% | 6216.75 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.67 | CUM | 1.67 | 0 | 100% | 3340 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.41 | CUM | 1.41 | 0 | 100% | 2115 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.01 | MT | 0.01 | 0 | 100% | 75 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
RABIUL MOLLA | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 26.85 | SQM | 26.85 | 0 | 100% | 8092.3752 |  | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.815 | SQM | 1.82 | 0.005 | 100.3% | 550.0446 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.93 | CUM | 2.93 | 0 | 100% | 659.25 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.09 | CUM | 0.09 | 0 | 100% | 135 |  | 0
RABIUL MOLLA | ALL LEVEL COLUMN STARTER | 116 | 50 | 53 | NOS | 53 | 0 | 100% | 2650 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
RABIUL MOLLA | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 201.77 | SQM | 201.77 | 0 | 100% | 39093.341 |  | 0
RABIUL MOLLA | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 216.39 | SQM | 216.39 | 0 | 100% | 41925.9953 |  | 0
RABIUL MOLLA | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.19 | SQM | 62.19 | 0 | 100% | 12049.4369 |  | 0
RABIUL MOLLA | ELEVATION RCC BAND | 133 | 65.6 | 49.17 | RMT | 46.71 | -2.46 | 95% | 2910.8737 |  | 0
RABIUL MOLLA | ELEVATION GROOVE | 137 | 65.6 | 37.67 | RMT | 35.79 | -1.88 | 95.01% | 2230.6509 |  | 0
RABIUL MOLLA | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.26 | SQM | 1.26 | 0 | 100% | 203.4396 |  | 0
RABIUL MOLLA | RCC SURFACE HACKING | 140 | 10.76 | 338.17 | SQM | 0 | -338.17 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 117.33 | SQM | 111.46 | -5.87 | 95% | 14816.5144 |  | 0
RABIUL MOLLA | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 307.83 | SQM | 292.44 | -15.39 | 95% | 38875.8278 |  | 0
RABIUL MOLLA | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 347.17 | SQM | 347.17 | 0 | 100% | 67264.8818 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 1 | 0 | 100% | 16500 |  | 0
RABIUL MOLLA | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 129.31 | SQM | 122.84 | -6.47 | 95% | 16329.1863 |  | 0
RABIUL MOLLA | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 431.24 | SQM | 409.68 | -21.56 | 95% | 54461.2405 |  | 0
RABIUL MOLLA | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 198 | SQM | 198 | 0 | 100% | 38362.896 |  | 0
RABIUL MOLLA | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 13.49 | SQM | 12.82 | -0.67 | 95.03% | 1704.8302 |  | 0
RABIUL MOLLA | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 47.73 | SQM | 45.34 | -2.39 | 94.99% | 6026.8258 |  | 0
RABIUL MOLLA | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 204.32 | SQM | 204.32 | 0 | 100% | 39587.4086 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 324.61 | SQM | 324.61 | 0 | 100% | 69882.0408 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 129.1 | SQM | 129.1 | 0 | 100% | 27792.648 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 190.52 | 60.91 | SQM | 60.91 | 0 | 100% | 11604.5732 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 254.03 | 151.81 | SQM | 151.81 | 0 | 100% | 38564.2943 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 254.03 | 99.5 | SQM | 99.5 | 0 | 100% | 25275.985 |  | 0
JMJ WATERPROOING ENTERPRISES | PRESSURE GROUTING | 179 | 650 | 23 | NOS | 23 | 0 | 100% | 14950 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 21 | NOS | 21 | 0 | 100% | 4200 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 25.95 | -1.37 | 94.99% | 5306.3723 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 139.8 | -7.36 | 95% | 12866.4487 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 296.81 | -15.62 | 95% | 13658.1077 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 152.94 | -8.05 | 95% | 7037.6793 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 181.18 | -9.54 | 95% | 8337.0129 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 141.21 | -7.43 | 95% | 2166.5451 |  | 0
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 307.83 | SQM | 292.44 | -15.39 | 95% | 25418.8105 |  | 0
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 117.33 | SQM | 111.46 | -5.87 | 95% | 9687.721 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 431.24 | SQM | 409.68 | -21.56 | 95% | 35609.2727 |  | 0
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 129.31 | SQM | 122.84 | -6.47 | 95% | 10676.7757 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 47.73 | SQM | 45.34 | -2.39 | 94.99% | 3940.6169 |  | 0
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 13.49 | SQM | 12.82 | -0.67 | 95.03% | 1114.6967 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 1 | 0 | 100% | 7000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
SANTOSH KUMAR | WINDOW SILL & JAMBS COPING GRANITE WORK | 291 | 78 | 60.4885 | RFT | 0 | -60.4885 | 0% | 0 | 100% | 4718.1042
RABIUL MOLLA | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 736.3 | SFT | 714.21 | -22.09 | 97% | 214762.6463 |  | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 18200 | 1 | LUMP SUM | 1 | 0 | 100% | 18200 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
SHEKAR T | LIFT REINFORCEMENT | 319 | 8500 | 0.667 | MT | 0.08 | -0.587 | 11.99% | 81.5592 |  | 0
SHEKAR T | LIFT EARTH WORK EXCAVATION | 320 | 424 | 12.337 | CUM | 3.18 | -9.157 | 25.78% | 347.5446 |  | 0
SHEKAR T | LIFT BOTTOM PCC | 321 | 1000 | 1 | CUM | 0.53 | -0.47 | 53% | 280.9 |  | 0
SHEKAR T | LIFT RCC | 322 | 2000 | 1.6 | CUM | 1.59 | -0.01 | 99.38% | 3160.125 |  | 0
SHEKAR T | LIFT WALL BLOCK WORK | 323 | 258.34 | 40.99 | SQM | 40.99 | 0 | 100% | 10589.3566 |  | 0
SHEKAR T | LIFT WALL INTERNAL PLASTERING | 324 | 172.22 | 40.99 | SQM | 38.94 | -2.05 | 95% | 6370.8527 |  | 0
SHEKAR T | LIFT WALL EXTERNAL PLASTERING | 325 | 194 | 96.45 | SQM | 91.63 | -4.82 | 95% | 16887.8698 |  | 0
SHEKAR T | LIFT SIDE REFILLING | 326 | 283 | 5.784 | CUM | 5.78 | -0.004 | 99.93% | 1634.6088 |  | 0
SHEKAR T | LIFT RCC | 327 | 2000 | 4.764 | CUM | 4.76 | -0.004 | 99.92% | 9512.0067 |  | 0
SHEKAR T | LIFT FOOTING WALL BEAM AND SLAB SHUTTERING | 328 | 302 | 106.234 | SQM | 106.23 | -0.004 | 100% | 32080.252 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | -3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0.5 | -0.5 | 50% | 750 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 31248.3 | 1 | LUMP SUM | 0.5 | -0.5 | 50% | 7812.075 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
KRIUTTIBAS DAS | CUSTOMISATION TRAP POINT WORK | 422 | 500 | 5 | NOS | 5 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION TAP POINT WORK | 423 | 600 | 7 | NOS | 7 | 0 | 100% | 4200 |  | 0
KRIUTTIBAS DAS | CUSTOMISATION AC WASTE WATER LINE | 430 | 700 | 3 | NOS | 3 | 0 | 100% | 2100 |  | 0
KRIUTTIBAS DAS | CUSTOMISATION DRAINAGE PIPE | 431 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
SANTOSH KUMAR | BALCONY UPSTAND TOP COPING GRANITE | 547 | 78 | 68.4253 | RFT | 0 | -68.4253 | 0% | 0 | 100% | 5337.1699
15555.2741

## V18
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To date | Release % | Current Payment | Contractor | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 79.68 | SQM | 79.68 | 0 | 100% | 3426.24 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | NAGARAJ | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0 | PRAKASH H N | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | RAMAKRUSHNA PRADHAN | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 56.04 | SQM | 56.04 | 0 | 100% | 2409.72 |  | 0 | RUPAK NAYAK | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | SANTOSH KUMAR | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 151.12 | 0 | 100% | 6498.16 |  | 0 | SARAT BARMAN | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 15.63 | 0 | 100% | 2205.7056 |  | 0 | SAVITA DEVI | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0.003 | 100.1% | 5680 |  | 0 | SHOKAT | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0.002 | 100% | 4570 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | -0.002 | 99.99% | 15110 |  | 0 | SK ANSAR HOSSIAN | 0
BISWO RANJAN ROUT | FOOTING REINFORCEMENT | 23 | 6800 | 0.65 | MT | 0.65 | 0 | 100% | 4420 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
BISWO RANJAN ROUT | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.75 | MT | 0.75 | 0 | 100% | 5100 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
BISWO RANJAN ROUT | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 1 | MT | 1 | 0 | 100% | 6800 |  | 0 | SUBHASMITA DAS | 0
BISWO RANJAN ROUT | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.9 | MT | 0.9 | 0 | 100% | 6120 |  | 0 | UDHABHAI R PARMAR | 0
BISWO RANJAN ROUT | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 1.13 | MT | 1.13 | 0 | 100% | 7684 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.67 | MT | 1.67 | 0 | 100% | 12525 |  | 0 | YELLAPPA C | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | RABIUL MOLLA | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | TOTAL | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 9.05 | -9.2 | 49.59% | 2727.5976 |  | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
RUPAK NAYAK | PLINTH BEAM RCC | 54 | 2000 | 6.049 | CUM | 6.05 | 0.001 | 100% | 12100 |  | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | 0.004 | 100% | 6754.5 |  | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.8 | CUM | 0.8 | 0 | 100% | 2400 |  | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.4 | 0 | 100% | 18000 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 19.91 | -0.64 | 96.89% | 6000.7147 |  | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | -0.004 | 99.89% | 7180 |  | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | -0.001 | 100% | 6099.75 |  | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | -0.003 | 99.83% | 3540 |  | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.99 | CUM | 0.99 | 0 | 100% | 2970 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.04 | MT | 0.04 | 0 | 100% | 300 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 0 | -3.81 | 0% | 0 |  | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | -0.002 | 99.93% | 636.75 |  | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 47.7 | 0 | 100% | 3129.12 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 64.23 | 0 | 100% | 4213.488 |  | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 19.509 | SQM | 19.51 | 0.001 | 100% | 3780.1015 |  | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 419 | SQM | 419 | 0 | 100% | 14665 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 485 | SQM | 485 | 0 | 100% | 3915.405 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 233.927 | SQM | 233.93 | 0.003 | 100% | 50360.4504 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 58.171 | SQM | 58.17 | -0.001 | 100% | 12522.8376 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 62.539 | SQM | 62.54 | 0.001 | 100% | 6731.8056 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 151.653 | SQM | 151.65 | -0.003 | 100% | 32647.212 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 62.539 | SQM | 62.54 | 0.001 | 100% | 6731.8056 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 312.43 | 0 | 100% | 15133.4843 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 160.99 | 0 | 100% | 7798.0336 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 190.72 | 0 | 100% | 9238.0954 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 758.48 | SQM | 758.48 | 0 | 100% | 36739.2542 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 758.48 | SQM | 758.48 | 0 | 100% | 12249.452 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 758.48 | SQM | 758.48 | 0 | 100% | 20410.6968 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 20.6 | SQM | 20.6 | 0 | 100% | 6208.6752 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 5 | NOS | 5 | 0 | 100% | 2250 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 21 | NOS | 21 | 0 | 100% | 7350 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 49.35 | RMT | 49.35 | 0 | 100% | 4046.7 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 120 | RMT | 120 | 0 | 100% | 3936 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 24.6 | RMT | 24.6 | 0 | 100% | 3227.52 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 5 | NOS | 5 | 0 | 100% | 5000 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 94.02 | SQM | 94.02 | 0 | 100% | 17205.66 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 72.13 | RMT | 72.13 | 0 | 100% | 3548.796 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 101.36 | SQM | 101.36 | 0 | 100% | 18548.88 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 83.36 | RMT | 83.36 | 0 | 100% | 4101.312 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 4.42 | SQM | 4.42 | 0 | 100% | 808.86 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 6.3 | RMT | 6.3 | 0 | 100% | 309.96 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 3.91 | SQM | 3.91 | 0 | 100% | 715.53 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.45 | RMT | 7.45 | 0 | 100% | 366.54 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 31.61 | SQM | 31.61 | 0 | 100% | 5784.63 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 38.05 | RMT | 38.05 | 0 | 100% | 1872.06 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 25.24 | SQM | 25.24 | 0 | 100% | 4618.92 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 2180 | SFT | 2180 | 0 | 100% | 5450 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 6.26 | SQM | 6.26 | 0 | 100% | 1145.58 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 31.39 | SQM | 31.39 | 0 | 100% | 5744.37 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 14.87 | SQM | 14.87 | 0 | 100% | 2721.21 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 45.07 | SQM | 45.07 | 0 | 100% | 8247.81 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 244.11 | SQM | 244.11 | 0 | 100% | 15764.6238 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100% | 17500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 1 | 0 | 100% | 7000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 3000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 36.89 | RMT | 36.89 | 0 | 100% | 204186.15 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 176662 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 5 | NOS | 5 | 0 | 100% | 2250 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 18958 | 1 | LUMP SUM | 1 | 0 | 100% | 18958 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100% | 5625 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
AAIDHUL MIAH | RAIN WATER CHAMBER MAKING & COVER FIXING | 271 | 1500 | 36 | NOS | 30.6 | -5.4 | 85% | 45900 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
CHIRANJEEVI | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100% | 1500 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | -0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
Thingswork Design Attic Pvt. Ltd., | VILLA NUMBER SIGNAGES | 285 | 190 | 495 | NOS | 0 | -495 | 0% | 0 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
DEEPAK NAYAK | ADDITIONAL WORK/TERRACE FLOOR ROOF BEAM AND SLAB CONCRETE RATE HAS BEEN CHANGED, FOOTING EARTH DRESSING AND PLINTH BEAM BOTTOM EXCAVTION | 306 | 208525 | 1 | LUMP SUM | 1 | 0 | 100% | 208525 |  | 0
SHOKAT | ADDITIONAL WATERPROOFING WORK | 311 | 253321 | 1 | LUMP SUM | 1 | 0 | 100% | 253321 |  | 0
SUBRAMANI | MISCELENIOUS WORK INCLUDING ARCHITECT, CONCRETE, DRAWING, POWER SUPPLY, BACKFILLING EARTH SURVEYOR, AND NMR PAY | 314 | 1320585 | 1 | LUMP SUM | 1 | 0 | 100% | 1320585 |  | 0
KHALIL MIAH | LAYING FLOOR PROTECTOR SHEET & TILE CLEANING (VILLA NO. 38/39/43/63/124/131) | 342 | 36136 | 1 | LUMP SUM | 1 | 0 | 100% | 36136 |  | 0
SAVITA DEVI | MS STAIRCASE WORK | 346 | 50000 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | -3 | 0% | 0 |  | 0
RUPAK NAYAK | GROUND FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 376 | 16.146 | 216.8 | SQM | 216.8 | 0 | 100% | 3500.4528 |  | 0
RUPAK NAYAK | FIRST FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 377 | 16.146 | 84.356 | SQM | 84.36 | 0.004 | 100% | 1362.0766 |  | 0
RUPAK NAYAK | TERRACE FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 378 | 16.146 | 163.111 | SQM | 163.11 | -0.001 | 100% | 2633.5741 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 5831.4 | 1 | LUMP SUM | 1 | 0 | 100% | 5831.4 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 0.5 | -0.5 | 50% | 500 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION TAP POINT WORK | 423 | 600 | 1 | NOS | 0.5 | -0.5 | 50% | 300 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 432 | 750 | 1 | NOS | 0.5 | -0.5 | 50% | 375 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION TERRACE TAP POINT WORK | 433 | 700 | 1 | NOS | 0.5 | -0.5 | 50% | 350 |  | 0

## V19
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 1050
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 16000
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 600
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | 15.63 | 0% | 0 |  | 0 | RUPAK NAYAK | 25089.33
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | SAVITA DEVI | 8325
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | -0.002 | 100% | 4570 |  | 0 | SHOKAT | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | 0.002 | 99.99% | 15110 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7500 | 0.65 | MT | 0.65 | 0 | 100% | 4875 |  | 0 | SK ANSAR HOSSIAN | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.75 | MT | 0.75 | 0 | 100% | 5625 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.8 | MT | 2.8 | 0 | 100% | 21000 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | YELLAPPA C | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | TOTAL | 51064.33
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 18.25 | 0 | 100% | 5500.404 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | -0.004 | 100% | 6754.5 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100% | 1200 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.4 | 0 | 100% | 18000 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 20.55 | 0 | 100% | 6193.6056 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | 0.004 | 99.89% | 7180 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | 0.001 | 100% | 6099.75 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 1.28 | 0.004 | 99.69% | 1920 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.04 | MT | 0 | 0.04 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 3.81 | 0 | 100% | 1148.3035 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | 0.002 | 99.93% | 636.75 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 47.7 | 0 | 100% | 3129.12 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 64.23 | 0 | 100% | 4213.488 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 264.278 | SQM | 264.28 | -0.002 | 100% | 56894.1984 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 20.1552 | SQM | 20.16 | -0.0048 | 100% | 4340.0448 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 90.11 | SQM | 90.11 | 0 | 100% | 9699.4404 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 161.038 | SQM | 161.04 | -0.002 | 100% | 34668.6912 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 251.149 | SQM | 251.15 | -0.001 | 100% | 27033.786 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 312.43 | 0 | 100% | 15133.4843 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 160.99 | 0 | 100% | 7798.0336 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 190.72 | 0 | 100% | 9238.0954 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 758.48 | SQM | 758.48 | 0 | 100% | 36739.2542 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 758.48 | SQM | 758.48 | 0 | 100% | 12249.452 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 758.48 | SQM | 758.48 | 0 | 100% | 20410.6968 |  | 0
SANTOSH KUMAR | STAIRCASE GRANITE | 215 | 301.392 | 21.617 | SQM | 21.62 | -0.003 | 100% | 6516.095 |  | 0
SANTOSH KUMAR | LEDGE WALL GRANITE | 217 | 450 | 1 | NOS | 1 | 0 | 100% | 450 |  | 0
SANTOSH KUMAR | DOOR OPENING GRANITE | 218 | 350 | 23 | NOS | 13 | 10 | 56.52% | 4550 |  | 0
SANTOSH KUMAR | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.845 | RMT | 41.85 | -0.005 | 100% | 3431.7 |  | 0
SANTOSH KUMAR | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 125.535 | RMT | 0 | 125.535 | 0% | 0 |  | 0
SANTOSH KUMAR | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 21.196 | RMT | 21.2 | -0.004 | 100% | 2781.44 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 183 | 94.226 | SQM | 94.23 | -0.004 | 100% | 17244.09 |  | 0
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 77.397 | RMT | 77.4 | -0.003 | 100% | 3808.08 |  | 0
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 183 | 99.138 | SQM | 99.14 | -0.002 | 100% | 18142.62 |  | 0
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 85.543 | RMT | 85.54 | 0.003 | 100% | 4208.568 |  | 0
SANTOSH KUMAR | TERRACE FLOOR TILING | 228 | 183 | 7.332 | SQM | 7.33 | 0.002 | 99.97% | 1341.39 |  | 0
SANTOSH KUMAR | TERRACE FLOOR SKIRTING | 229 | 49.2 | 6.7 | RMT | 6.7 | 0 | 100% | 329.64 |  | 0
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 9.3 | SQM | 9.3 | 0 | 100% | 1701.9 |  | 0
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 17.534 | RMT | 17.53 | 0.004 | 99.98% | 862.476 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 183 | 33.571 | SQM | 33.57 | 0.001 | 100% | 6143.31 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 46.397 | RMT | 46.4 | -0.003 | 100% | 2282.88 |  | 0
SANTOSH KUMAR | CAR PARKING AREA TILING | 234 | 183 | 31.021 | SQM | 31.02 | 0.001 | 100% | 5676.66 |  | 0
SANTOSH KUMAR | FLOOR CHIPPING | 235 | 2.5 | 2493.082 | SFT | 2493.08 | 0.002 | 100% | 6232.7 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 6.264 | SQM | 6.26 | 0.004 | 99.94% | 1145.58 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 30.5248 | SQM | 30.52 | 0.0048 | 99.98% | 5585.16 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 14.873 | SQM | 14.87 | 0.003 | 99.98% | 2721.21 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 60.149 | SQM | 60.15 | -0.001 | 100% | 11007.45 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH (including toilet wall grouting) | 243 | 64.58 | 388.5 | SQM | 0 | 388.5 | 0% | 0 | 100% | 25089.33
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 1 | 0 | 100% | 18500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 0 | 1 | 0% | 0 | 100% | 600
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 6000 | 50% | 6000
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 8000
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 35.324 | RMT | 35.32 | 0.004 | 99.99% | 195496.2 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 6 | NOS | 0 | 6 | 0% | 0 | 100% | 2700
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 18938 | 1 | LUMP SUM | 1 | 0 | 100% | 18938 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 0 | 12.5 | 0% | 0 | 100% | 5625
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 3 | LUMP SUM | 0 | 3 | 0% | 0 | 100% | 1050
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 290 | 549.75 | SFT | 549.75 | 0 | 100% | 159427.5 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
SHEKAR T | LIFT REINFORCEMENT | 319 | 7500 | 0.752 | MT | 0.75 | 0.002 | 99.73% | 5625 |  | 0
SHEKAR T | LIFT EARTH WORK EXCAVATION | 320 | 424 | 11.81 | CUM | 11.81 | 0 | 100% | 5007.44 |  | 0
SHEKAR T | LIFT BOTTOM PCC | 321 | 1000 | 1 | CUM | 1 | 0 | 100% | 1000 |  | 0
SHEKAR T | LIFT RCC | 322 | 225 | 3.279 | CUM | 3.28 | -0.001 | 100% | 738 |  | 0
SHEKAR T | LIFT WALL BLOCK WORK | 323 | 194 | 21.813 | SQM | 21.81 | 0.003 | 99.99% | 4231.14 |  | 0
SHEKAR T | LIFT WALL INTERNAL PLASTERING | 324 | 162 | 44.957 | SQM | 38.21 | 6.747 | 84.99% | 6190.02 |  | 0
SHEKAR T | LIFT WALL EXTERNAL PLASTERING | 325 | 194 | 36.179 | SQM | 30.75 | 5.429 | 84.99% | 5965.5 |  | 0
SHEKAR T | LIFT SIDE REFILLING | 326 | 283 | 5.18 | CUM | 5.18 | 0 | 100% | 1465.94 |  | 0
SHEKAR T | LIFT RCC | 327 | 2000 | 3.08 | CUM | 3.08 | 0 | 100% | 6160 |  | 0
SHEKAR T | LIFT FOOTING WALL BEAM AND SLAB SHUTTERING | 328 | 302 | 67.208 | SQM | 67.21 | -0.002 | 100% | 20297.42 |  | 0
SHOKAT | LIFT WATERPROOF COATING | 329 | 215.28 | 12.623 | SQM | 12.62 | 0.003 | 99.98% | 2716.8336 |  | 0
SHOKAT | LIFT WATERPRROF PLASTERING | 330 | 215.28 | 1.594 | LUMP SUM | 1.59 | 0.004 | 99.75% | 342.2952 |  | 0
SHOKAT | LIFT 75MM THICK SCREED CONCRETE | 331 | 215.28 | 1.709 | SQM | 1.71 | -0.001 | 100.1% | 368.1288 |  | 0
SHOKAT | LIFT BORE PACKING | 332 | 200 | 2 | NOS | 2 | 0 | 100% | 400 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 9132 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 4566 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 0.5 | 0.5 | 50% | 500 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION AQUA GUARD POINT WORK | 434 | 600 | 1 | NOS | 0.5 | 0.5 | 50% | 300 |  | 0
SANTOSH KUMAR | CAR PARKING BOUNDARY WALL TOP COPING GRANITE | 550 | 78 | 21.94 | RFT | 21.94 | 0 | 100% | 1711.32 |  | 0
51064.33

## V20
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 350
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 2600
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 15.63 | 0 | 100% | 2205.7056 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | -0.002 | 100% | 4570 |  | 0 | SHOKAT | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | 0.002 | 99.99% | 15110 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100% | 4550 |  | 0 | SK ANSAR HOSSIAN | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100% | 5250 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.9 | MT | 0.9 | 0 | 100% | 6300 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.8 | MT | 2.8 | 0 | 100% | 19600 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | YELLAPPA C | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | TOTAL | 2950
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 18.25 | 0 | 100% | 5500.404 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | -0.004 | 100% | 6754.5 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100% | 1200 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 2.4 | MT | 2.4 | 0 | 100% | 16800 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 20.55 | 0 | 100% | 6193.6056 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | 0.004 | 99.89% | 7180 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | 0.001 | 100% | 6099.75 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 1.28 | 0.004 | 99.69% | 1920 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.04 | MT | 0.04 | 0 | 100% | 280 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 3.81 | 0 | 100% | 1148.3035 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | 0.002 | 99.93% | 636.75 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 47.7 | 0 | 100% | 3129.12 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 64.23 | 0 | 100% | 4213.488 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 233.927 | SQM | 233.93 | -0.003 | 100% | 50360.4504 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 58.171 | SQM | 58.17 | 0.001 | 100% | 12522.8376 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 62.539 | SQM | 62.54 | -0.001 | 100% | 6731.8056 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 151.653 | SQM | 151.65 | 0.003 | 100% | 32647.212 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 62.539 | SQM | 62.54 | -0.001 | 100% | 6731.8056 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 312.43 | 0 | 100% | 15133.4843 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 160.99 | 0 | 100% | 7798.0336 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 190.72 | 0 | 100% | 9238.0954 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 758.48 | SQM | 758.48 | 0 | 100% | 36739.2542 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 758.48 | SQM | 758.48 | 0 | 100% | 12249.452 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 758.48 | SQM | 758.48 | 0 | 100% | 20410.6968 |  | 0
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 20.6 | SQM | 20.6 | 0 | 100% | 6208.6752 |  | 0
ANSAR HOSSAIAN SK | LEDGE WALL GRANITE | 217 | 450 | 5 | NOS | 2 | 3 | 40% | 900 |  | 0
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 21 | NOS | 21 | 0 | 100% | 7350 |  | 0
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 49.35 | RMT | 49.35 | 0 | 100% | 4046.7 |  | 0
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 120 | RMT | 120 | 0 | 100% | 3936 |  | 0
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 24.6 | RMT | 24.6 | 0 | 100% | 3227.52 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100% | 4000 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 94.02 | SQM | 94.02 | 0 | 100% | 17205.66 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 72.13 | RMT | 72.13 | 0 | 100% | 3548.796 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 101.36 | SQM | 101.36 | 0 | 100% | 18548.88 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 83.36 | RMT | 83.36 | 0 | 100% | 4101.312 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 4.42 | SQM | 4.42 | 0 | 100% | 808.86 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 6.3 | RMT | 6.3 | 0 | 100% | 309.96 |  | 0
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 3.91 | SQM | 3.91 | 0 | 100% | 715.53 |  | 0
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 7.45 | RMT | 7.45 | 0 | 100% | 366.54 |  | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 31.61 | SQM | 31.61 | 0 | 100% | 5784.63 |  | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 38.05 | RMT | 38.05 | 0 | 100% | 1872.06 |  | 0
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 31.896 | SQM | 31.9 | -0.004 | 100% | 5837.7 |  | 0
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 2180 | SFT | 2180 | 0 | 100% | 5450 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 6.26 | SQM | 6.26 | 0 | 100% | 1145.58 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 31.39 | SQM | 31.39 | 0 | 100% | 5744.37 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 14.87 | SQM | 14.87 | 0 | 100% | 2721.21 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 45.07 | SQM | 45.07 | 0 | 100% | 8247.81 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 250.519 | SQM | 250.52 | -0.001 | 100% | 16178.5816 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100% | 17500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 0 | 1 | 0% | 0 | 100% | 600
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 56 | RMT | 56 | 0 | 100% | 309960 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 18938 | 1 | LUMP SUM | 1 | 0 | 100% | 18938 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100% | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 304 | 290 | 568.17 | SQM | 568.17 | 0 | 100% | 164769.3 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
YELLAPPA C | CHAIN LINK STAIRCASE WORK | 334 | 20000 | 1 | LUMP SUM | 1 | 0 | 100% | 20000 |  | 0
YELLAPPA C | FIRST FLOOR CHAINLINK STAIRCASE WORK | 338 | 20000 | 1 | NOS | 1 | 0 | 100% | 20000 |  | 0
PRAKASH H N | LIFT ELECTRICAL WORK | 347 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100% | 800 |  | 0
SANTOSH KUMAR | CAR PARKING BOUNDARY WALL TOP COPING GRANITE | 550 | 78 | 29.17 | RFT | 29.17 | 0 | 100% | 2275.26 |  | 0
2950

## V21
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 1400
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 4000
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 18000
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 9255.35
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 151.12 | 0 | 100% | 6498.16 |  | 0 | RUPAK NAYAK | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | 15.63 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SARAT BARMAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SAVITA DEVI | 450
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | SHOKAT | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | -0.002 | 100% | 4570 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 117950.85
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | 0.002 | 99.99% | 15110 |  | 0 | SK ANSAR HOSSIAN | 1000
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100% | 4550 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100% | 5250 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.9 | MT | 0.9 | 0 | 100% | 6300 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.8 | MT | 2.8 | 0 | 100% | 19600 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | YELLAPPA C | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | TOTAL | 152056.2
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 18.25 | 0 | 100% | 5500.404 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | -0.004 | 100% | 6754.5 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100% | 1200 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 2.4 | MT | 2.4 | 0 | 100% | 16800 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 20.55 | 0 | 100% | 6193.6056 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | 0.004 | 99.89% | 7180 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | 0.001 | 100% | 6099.75 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 1.28 | 0.004 | 99.69% | 1920 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.04 | MT | 0.04 | 0 | 100% | 280 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 3.81 | 0 | 100% | 1148.3035 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | 0.002 | 99.93% | 636.75 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 47.7 | 0 | 100% | 3129.12 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 64.23 | 0 | 100% | 4213.488 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14000 | 1 | LUMP SUM | 1 | 0 | 100% | 14000 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 247.987 | SQM | 247.99 | -0.003 | 100% | 53387.2872 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 75.89 | SQM | 75.89 | 0 | 100% | 16337.5992 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 35.028 | SQM | 35.03 | -0.002 | 100% | 3770.6292 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 79.534 | SQM | 79.53 | 0.004 | 99.99% | 17121.2184 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 35.028 | SQM | 35.03 | -0.002 | 100% | 3770.6292 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 24 | NOS | 24 | 0 | 100% | 4800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 27.312 | SQM | 27.31 | 0.002 | 99.99% | 5879.2968 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 97.73 | SQM | 97.73 | 0 | 100% | 9468.0824 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 620.15 | SQM | 620.15 | 0 | 100% | 10015.4225 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 620.15 | SQM | 620.15 | 0 | 100% | 20025.8838 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.8 | SQM | 148.8 | 0 | 100% | 2403.12 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 1046.93 | SQM | 1046.93 | 0 | 100% | 50711.1953 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 1046.93 | SQM | 1046.93 | 0 | 100% | 16907.9195 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 1046.93 | SQM | 1046.93 | 0 | 100% | 28172.8863 |  | 0
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 21.617 | SQM | 21.62 | -0.003 | 100% | 6516.095 |  | 0
ANSAR HOSSAIAN SK | LEDGE WALL GRANITE | 217 | 350 | 1 | NOS | 1 | 0 | 100% | 350 |  | 0
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 25 | NOS | 23 | 2 | 92% | 8050 |  | 0
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.845 | RMT | 41.85 | -0.005 | 100% | 3431.7 |  | 0
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 125.535 | RMT | 125.54 | -0.005 | 100% | 4117.712 |  | 0
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 21.196 | RMT | 21.2 | -0.004 | 100% | 2781.44 |  | 0
SK ANSAR HOSSIAN | WASH BASIN GRANITE FIXING | 222 | 1000 | 1 | NOS | 0 | -1 | 0% | 0 | 100% | 1000
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 269 | 109.67 | SQM | 109.67 | 0 | 100% | 29501.23 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 82.53 | RMT | 82.53 | 0 | 100% | 4060.476 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 269 | 97.489 | SQM | 97.49 | -0.001 | 100% | 26224.81 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 102.69 | RMT | 102.69 | 0 | 100% | 5052.348 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 269 | 38.27 | SQM | 38.27 | 0 | 100% | 10294.63 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8.73 | RMT | 8.73 | 0 | 100% | 429.516 |  | 0
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 3.607 | SQM | 3.61 | -0.003 | 100.1% | 660.63 |  | 0
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 8.19 | RMT | 8.19 | 0 | 100% | 402.948 |  | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 18.998 | SQM | 19 | -0.002 | 100% | 3477 |  | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 25.32 | RMT | 25.32 | 0 | 100% | 1245.744 |  | 0
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 23.866 | SQM | 23.87 | -0.004 | 100% | 4368.21 |  | 0
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 2815 | SFT | 2815 | 0 | 100% | 7037.5 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 5.501 | SQM | 5.5 | 0.001 | 99.98% | 1006.5 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 33.958 | SQM | 33.96 | -0.002 | 100% | 6214.68 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 16.86 | SQM | 13.77 | 3.09 | 81.67% | 2519.91 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 89.955 | SQM | 64.41 | 25.545 | 71.6% | 11787.03 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 244.11 | SQM | 244.11 | 0 | 100% | 15764.6238 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100% | 17500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 3 | NOS | 1 | 2 | 33.33% | 600 | 66.67% | 1200
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 5000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 10000
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 5000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 5000
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 56.08 | RMT | 34.77 | 21.31 | 62% | 192451.95 | 38% | 117950.85
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 18938 | 1 | LUMP SUM | 1 | 0 | 100% | 18938 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 1 | NOS | 0 | 1 | 0% | 0 | 100% | 450
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 3 | LUMP SUM | 0 | 3 | 0% | 0 | 100% | 1050
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 100 | RFT | 100 | 0 | 100% | 3400 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 27 | 0 | 100% | 2079 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 249 | SFT | 249 | 0 | 100% | 5727 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 15 | 0 | 100% | 2265 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
ANSAR HOSSAIAN SK | SILL GRANITE | 289 | 75 | 186 | RFT | 186 | 0 | 100% | 13950 |  | 0
ANSAR HOSSAIAN SK | WINDOW SILL & JAMBS COPING GRANITE | 291 | 78 | 120 | RFT | 120 | 0 | 100% | 9360 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 421 | 627 | SFT | 627 | 0 | 100% | 263967 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 4000
SHEKAR T | LIFT REINFORCEMENT | 319 | 7500 | 0.985 | MT | 0.99 | -0.005 | 100.5% | 7425 |  | 0
SHEKAR T | LIFT EARTH WORK EXCAVATION | 320 | 424 | 11.81 | CUM | 11.81 | 0 | 100% | 5007.44 |  | 0
SHEKAR T | LIFT BOTTOM PCC | 321 | 1000 | 1 | CUM | 1 | 0 | 100% | 1000 |  | 0
SHEKAR T | LIFT RCC | 322 | 225 | 3.279 | CUM | 3.27 | 0.009 | 99.73% | 735.75 |  | 0
SHEKAR T | LIFT WALL BLOCK WORK | 323 | 194 | 43.319 | SQM | 43.32 | -0.001 | 100% | 8404.08 |  | 0
SHEKAR T | LIFT WALL INTERNAL PLASTERING | 324 | 162 | 76 | SQM | 76 | 0 | 100% | 12312 |  | 0
SHEKAR T | LIFT WALL EXTERNAL PLASTERING | 325 | 194 | 84.182 | SQM | 84.18 | 0.002 | 100% | 16330.92 |  | 0
SHEKAR T | LIFT SIDE REFILLING | 326 | 283 | 5.18 | CUM | 5.18 | 0 | 100% | 1465.94 |  | 0
SHEKAR T | LIFT RCC | 327 | 2000 | 4.688 | CUM | 4.69 | -0.002 | 100% | 9380 |  | 0
SHEKAR T | LIFT FOOTING WALL BEAM AND SLAB SHUTTERING | 328 | 302 | 98 | SQM | 98 | 0 | 100% | 29596 |  | 0
SHEKAR T | CHAIN LINK STAIRCASE WORK | 334 | 20000 | 1 | LUMP SUM | 1 | 0 | 100% | 20000 |  | 0
SHEKAR T | FIRST FLOOR CHAINLINK STAIRCASE WORK | 338 | 20000 | 1 | NOS | 1 | 0 | 100% | 20000 |  | 0
PRAKASH H N | LIFT ELECTRICAL WORK | 348 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
ANSAR HOSSAIAN SK | ADDITIONAL UTILITY WALL TILING WORK | 356 | 183 | 9.94 | SQM | 9.94 | 0 | 100% | 1819.02 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1000
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 12110.7 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 6055.35 | 50% | 6055.35
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 2 | LUMP SUM | 2 | 0 | 100% | 5000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 2 | LUMP SUM | 2 | 0 | 100% | 5000 |  | 0
PRAKASH H N | CUSTOMIZATION LIFT ELECTRICAL WORK | 435 | 6500 | 1 | LUMP SUM | 1 | 0 | 100% | 6500 |  | 0
ANSAR HOSSAIAN SK | CUSTOMIZATION TOILET TILE WORK | 436 | 1212.415 | 4.56 | SQM | 4.56 | 0 | 100% | 5528.6124 |  | 0
ANSAR HOSSAIAN SK | CUSTOMISATION BALCONY ENTRANCE STAIRCASE GRANITE WORK WITH NOSING | 437 | 334.841 | 2.511 | SQM | 2.51 | 0.001 | 99.96% | 840.4509 |  | 0
SHOKAT | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 4.535 | SQM | 4.54 | -0.005 | 100.1% | 977.3712 |  | 0
SHOKAT | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 25.651 | SQM | 25.65 | 0.001 | 100% | 11043.864 |  | 0
SHOKAT | CUSTOMIZATION LIFT WALL WATERPROOFING WORK | 440 | 215.28 | 88.134 | SQM | 88.13 | 0.004 | 100% | 18972.6264 |  | 0
152056.2

## V22
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 350
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 151.12 | 0 | 100% | 6498.16 |  | 0 | RUPAK NAYAK | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | 15.63 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | SARAT BARMAN | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | -0.002 | 100% | 4570 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | 0.002 | 99.99% | 15110 |  | 0 | SHOKAT | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100% | 4550 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100% | 5250 |  | 0 | SK ANSAR HOSSIAN | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.9 | MT | 0.9 | 0 | 100% | 6300 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.8 | MT | 2.8 | 0 | 100% | 19600 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | YELLAPPA C | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0 | TOTAL | 350
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 18.25 | 0 | 100% | 5500.404 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | -0.004 | 100% | 6754.5 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100% | 1200 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 2.4 | MT | 2.4 | 0 | 100% | 16800 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 20.55 | 0 | 100% | 6193.6056 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | 0.004 | 99.89% | 7180 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | 0.001 | 100% | 6099.75 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 1.28 | 0.004 | 99.69% | 1920 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.04 | MT | 0.04 | 0 | 100% | 280 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 3.81 | 0 | 100% | 1148.3035 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | 0.002 | 99.93% | 636.75 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 47.7 | 0 | 100% | 3129.12 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 64.23 | 0 | 100% | 4213.488 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 254.03 | 196 | SQM | 196 | 0 | 100% | 49789.88 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 254.03 | 15.794 | SQM | 15.79 | 0.004 | 99.97% | 4011.1337 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 190.52 | 13.32 | SQM | 13.32 | 0 | 100% | 2537.7264 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 254.03 | 168.75 | SQM | 168.75 | 0 | 100% | 42867.5625 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 254.03 | 68.47 | SQM | 68.47 | 0 | 100% | 17393.4341 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 19 | NOS | 19 | 0 | 100% | 3800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 27.312 | SQM | 27.31 | 0.002 | 99.99% | 5879.2968 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 97.73 | SQM | 97.73 | 0 | 100% | 9468.0824 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 620.15 | SQM | 620.15 | 0 | 100% | 10015.4225 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 620.15 | SQM | 620.15 | 0 | 100% | 20025.8838 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.8 | SQM | 148.8 | 0 | 100% | 2403.12 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 1046.93 | SQM | 1046.93 | 0 | 100% | 50711.1953 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 1046.93 | SQM | 1046.93 | 0 | 100% | 16907.9195 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 1046.93 | SQM | 1046.93 | 0 | 100% | 28172.8863 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 21.617 | SQM | 21.62 | -0.003 | 100% | 6516.095 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 350 | 1 | NOS | 1 | 0 | 100% | 350 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 23 | NOS | 20 | 3 | 86.96% | 7000 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.845 | RMT | 41.85 | -0.005 | 100% | 3431.7 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 125.535 | RMT | 125.54 | -0.005 | 100% | 4117.712 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 21.196 | RMT | 21.2 | -0.004 | 100% | 2781.44 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 7 | NOS | 7 | 0 | 100% | 7000 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 109.67 | SQM | 109.67 | 0 | 100% | 20069.61 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 82.53 | RMT | 82.53 | 0 | 100% | 4060.476 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 97.489 | SQM | 97.49 | -0.001 | 100% | 17840.67 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 102.69 | RMT | 102.69 | 0 | 100% | 5052.348 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 13.096 | SQM | 13.1 | -0.004 | 100% | 2397.3 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8.73 | RMT | 8.73 | 0 | 100% | 429.516 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 3.607 | SQM | 3.61 | -0.003 | 100.1% | 660.63 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.43 | RMT | 7.43 | 0 | 100% | 365.556 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 18.998 | SQM | 19 | -0.002 | 100% | 3477 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 25.32 | RMT | 25.32 | 0 | 100% | 1245.744 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 23.866 | SQM | 23.87 | -0.004 | 100% | 4368.21 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 2815 | SFT | 2815 | 0 | 100% | 7037.5 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 5.501 | SQM | 5.5 | 0.001 | 99.98% | 1006.5 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 32.71 | SQM | 32.71 | 0 | 100% | 5985.93 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 13.766 | SQM | 13.77 | -0.004 | 100% | 2519.91 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 64.411 | SQM | 64.41 | 0.001 | 100% | 11787.03 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 244.11 | SQM | 244.11 | 0 | 100% | 15764.6238 |  | 0
PRAKASH JANA | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 375 | SQM | 375 | 0 | 100% | 10091.25 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100% | 17500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 3 | NOS | 3 | 0 | 100% | 1800 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 2 | LUMP SUM | 2 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 1 | 0 | 100% | 7000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 1355 | 19.69 | RMT | 19.69 | 0 | 100% | 26679.95 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 18958 | 1 | LUMP SUM | 1 | 0 | 100% | 18958 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY SS RAILING | 266 | 5535 | 15.74 | RMT | 15.74 | 0 | 100% | 87120.9 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | STAIRCASE SS RAILING | 267 | 2438 | 19.69 | RMT | 19.69 | 0 | 100% | 48004.22 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 1008 | 121 | SFT | 121 | 0 | 100% | 121968 |  | 0
SHREE INTERIORS | MAID ROOM FALSE CEILING | 305 | 14000 | 1 | LUMP SUM | 1 | 0 | 100% | 14000 |  | 0
SHEKAR T | LIFT SCAFFOLDING | 318 | 193.75 | 36.81 | SQM | 36.81 | 0 | 100% | 7131.9375 |  | 0
SHEKAR T | LIFT REINFORCEMENT | 319 | 8500 | 0.0815 | MT | 0.08 | 0.0015 | 98.16% | 680 |  | 0
SHEKAR T | LIFT EARTH WORK EXCAVATION | 320 | 424 | 3.182 | CUM | 3.18 | 0.002 | 99.94% | 1348.32 |  | 0
SHEKAR T | LIFT BOTTOM PCC | 321 | 1000 | 0.534 | CUM | 0.53 | 0.004 | 99.25% | 530 |  | 0
SHEKAR T | LIFT RCC | 322 | 2000 | 1.591 | CUM | 1.59 | 0.001 | 99.94% | 3180 |  | 0
SHEKAR T | LIFT WALL BLOCK WORK | 323 | 258.34 | 40.99 | SQM | 40.99 | 0 | 100% | 10589.3566 |  | 0
SHEKAR T | LIFT WALL INTERNAL PLASTERING | 324 | 172.22 | 40.99 | SQM | 40.99 | 0 | 100% | 7059.2978 |  | 0
SHEKAR T | LIFT WALL EXTERNAL PLASTERING | 325 | 269.1 | 49.833 | SQM | 49.83 | 0.003 | 99.99% | 13409.253 |  | 0
SHEKAR T | CHAIN LINK STAIRCASE WORK | 334 | 20000 | 2 | LUMP SUM | 2 | 0 | 100% | 40000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMISATION TERRACE EPOXY GROUTING AND SOAP WASH CLEANING WORK | 427 | 64.58 | 11.523 | SQM | 11.52 | 0.003 | 99.97% | 743.9616 |  | 0
PRAKASH H N | CUSTOMIZATION LIFT ELECTRICAL WORK | 435 | 5000 | 1 | LUMP SUM | 1 | 0 | 100% | 5000 |  | 0
KRISHNAKUMAR SAHANI | CUSTOMIZATION TOILET TILE WORK | 436 | 1185.21 | 2.91 | SQM | 0 | 2.91 | 0% | 0 |  | 0
SAVITA DEVI | CUSTAMIZATION LIFT MS WORK | 441 | 46500 | 1 | LUMP SUM | 1 | 0 | 100% | 46500 |  | 0
KRISHNAKUMAR SAHANI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 251.26 | 13.096 | SQM | 0 | 13.096 | 0% | 0 |  | 0
IRSAD | CUSTOMIZATION TERRACE ROOM PUF PANEL ROOF WORK/THE RATE IS INCLUSIVE OF 60X40 MM MS BOX SECTION AND 30MM THICK PUF PANEL | 443 | 270 | 175 | SFT | 175 | 0 | 100% | 47250 |  | 0
SHEKAR T | TERRACE CUSTOMIZATION CIVIL WORK | 444 | 290 | 49 | SFT | 49 | 0 | 100% | 14210 |  | 0
SHEKAR T | TERRACE EXCLUDING RCC ROOF CUSTOMIZATION CIVIL WORK | 445 | 190 | 96 | SFT | 96 | 0 | 100% | 18240 |  | 0
SAVITA DEVI | CUSTOMIZATION MAID ROOM ROOF CEILING AND GATE WORK | 446 | 22000 | 1 | LUMP SUM | 1 | 0 | 100% | 22000 |  | 0
350

## V23
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 350
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 151.12 | 0 | 100% | 6498.16 |  | 0 | RUPAK NAYAK | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 15.63 | 0 | 100% | 2205.7056 |  | 0 | SANTOSH KUMAR | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | SARAT BARMAN | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | -0.002 | 100% | 4570 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | 0.002 | 99.99% | 15110 |  | 0 | SHOKAT | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100% | 4550 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100% | 5250 |  | 0 | SK ANSAR HOSSIAN | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.9 | MT | 0.9 | 0 | 100% | 6300 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.8 | MT | 2.8 | 0 | 100% | 19600 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | YELLAPPA C | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0 | TOTAL | 350
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 18.25 | 0 | 100% | 5500.404 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | -0.004 | 100% | 6754.5 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100% | 1200 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 2.4 | MT | 2.4 | 0 | 100% | 16800 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 20.55 | 0 | 100% | 6193.6056 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | 0.004 | 99.89% | 7180 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | 0.001 | 100% | 6099.75 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 1.28 | 0.004 | 99.69% | 1920 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.04 | MT | 0.04 | 0 | 100% | 280 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 3.81 | 0 | 100% | 1148.3035 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | 0.002 | 99.93% | 636.75 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 47.7 | 0 | 100% | 3129.12 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 64.23 | 0 | 100% | 4213.488 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 250.753 | SQM | 250.75 | 0.003 | 100% | 53981.46 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 74.695 | SQM | 74.7 | -0.005 | 100% | 16081.416 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 48.652 | SQM | 48.65 | 0.002 | 100% | 5236.686 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 162.772 | SQM | 162.77 | 0.002 | 100% | 35041.1256 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 48.652 | SQM | 48.65 | 0.002 | 100% | 5236.686 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 21 | NOS | 21 | 0 | 100% | 4200 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 312.43 | 0 | 100% | 15133.4843 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 160.99 | 0 | 100% | 7798.0336 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 190.72 | 0 | 100% | 9238.0954 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 758.48 | SQM | 758.48 | 0 | 100% | 36739.2542 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 758.48 | SQM | 758.48 | 0 | 100% | 12249.452 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 758.48 | SQM | 758.48 | 0 | 100% | 20410.6968 |  | 0
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 6 | NOS | 6 | 0 | 100% | 6000 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 94.67 | SQM | 94.67 | 0 | 100% | 17324.61 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 82.53 | RMT | 82.53 | 0 | 100% | 4060.476 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 109.49 | SQM | 109.48 | 0.01 | 99.99% | 20034.84 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 102.69 | RMT | 102.69 | 0 | 100% | 5052.348 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 4.42 | SQM | 4.42 | 0 | 100% | 808.86 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8.73 | RMT | 8.73 | 0 | 100% | 429.516 |  | 0
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 3.91 | SQM | 3.91 | 0 | 100% | 715.53 |  | 0
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 8.19 | RMT | 8.19 | 0 | 100% | 402.948 |  | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 31.62 | SQM | 31.62 | 0 | 100% | 5786.46 |  | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 41.35 | RMT | 41.35 | 0 | 100% | 2034.42 |  | 0
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 27.26 | SQM | 27.26 | 0 | 100% | 4988.58 |  | 0
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 2815 | SFT | 2815 | 0 | 100% | 7037.5 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 7.705 | SQM | 7.71 | -0.005 | 100.1% | 1410.93 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 45.638 | SQM | 45.64 | -0.002 | 100% | 8352.12 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 14.25 | SQM | 14.25 | 0 | 100% | 2607.75 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 80.518 | SQM | 80.52 | -0.002 | 100% | 14735.16 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 244.11 | SQM | 244.11 | 0 | 100% | 15764.6238 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100% | 17500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 36.97 | RMT | 35.97 | 1 | 97.3% | 199093.95 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 5 | NOS | 5 | 0 | 100% | 2250 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 18958 | 1 | LUMP SUM | 1 | 0 | 100% | 18958 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100% | 225 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 831 | CFT | 831 | 0 | 100% | 7334.406 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 554 | SFT | 554 | 0 | 100% | 13157.5 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 498 | 404 | SFT | 404 | 0 | 100% | 201192 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | MS STAIRCASE STEPS RUBBER WOOD LAYING | 336 | 49000 | 1 | LUMP SUM | 1 | 0 | 100% | 49000 |  | 0
SAVITA DEVI | MS STAIRCASE WORK | 337 | 35000 | 1.42 | MT | 0 | 1.42 | 0% | 0 |  | 0
SAVITA DEVI | MS STAIRCASE WORK | 346 | 52500 | 1 | LUMP SUM | 1 | 0 | 100% | 52500 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 2 | NOS | 2 | 0 | 100% | 2000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 73.544 | SQM | 0 | 73.544 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 73.544 | SQM | 0 | 73.544 | 0% | 0 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 73.544 | SQM | 0 | 73.544 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 39.277 | SQM | 0 | 39.277 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 39.277 | SQM | 0 | 39.277 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION MS STAIRCASE PAINTING AND STEP WOOD POLISHING WORK | 424 | 30000 | 1 | LUMP SUM | 1 | 0 | 100% | 30000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 432 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
ANSAR HOSSAIAN SK | CUSTOMIZATION TOILET TILE WORK | 436 | 1276.511 | 4.24 | SQM | 0 | 4.24 | 0% | 0 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 7500 | 1 | LUMP SUM | 1 | 0 | 100% | 7500 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY TAP POINT WORK | 448 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
350

## V24
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 350
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 4500
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 1800
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | 15.63 | 0% | 0 |  | 0 | RUPAK NAYAK | 52260.1273
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | SAVITA DEVI | 3750
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | -0.002 | 100% | 4570 |  | 0 | SHOKAT | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | 0.002 | 99.99% | 15110 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100% | 4550 |  | 0 | SK ANSAR HOSSIAN | 32203.2213
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100% | 5250 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.9 | MT | 0.9 | 0 | 100% | 6300 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.8 | MT | 2.8 | 0 | 100% | 19600 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | YELLAPPA C | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | TOTAL | 94863.3486
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 18.25 | 0 | 100% | 5500.404 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | -0.004 | 100% | 6754.5 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100% | 1200 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 2.4 | MT | 2.4 | 0 | 100% | 16800 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 20.55 | 0 | 100% | 6193.6056 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | 0.004 | 99.89% | 7180 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | 0.001 | 100% | 6099.75 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 1.28 | 0.004 | 99.69% | 1920 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.04 | MT | 0.04 | 0 | 100% | 280 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 3.81 | 0 | 100% | 1148.3035 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | 0.002 | 99.93% | 636.75 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 47.7 | 0 | 100% | 3129.12 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 64.23 | 0 | 100% | 4213.488 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 245.81 | SQM | 245.81 | 0 | 100% | 52917.9768 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 77.8 | SQM | 77.8 | 0 | 100% | 16748.784 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 63.63 | SQM | 63.63 | 0 | 100% | 6849.1332 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 153.88 | SQM | 153.88 | 0 | 100% | 33127.2864 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 63.63 | SQM | 63.63 | 0 | 100% | 6849.1332 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 20 | NOS | 20 | 0 | 100% | 4000 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 312.43 | SQM | 156.22 | 156.21 | 50% | 7566.9844 | 50% | 7566.7422
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 160.99 | SQM | 80.5 | 80.49 | 50% | 3899.259 | 50% | 3899.0168
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 190.72 | SQM | 95.36 | 95.36 | 50% | 4619.0477 | 50% | 4619.0477
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 758.48 | SQM | 758.48 | 0 | 100% | 36739.2542 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 758.48 | SQM | 758.48 | 0 | 100% | 12249.452 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 758.48 | SQM | 0 | 758.48 | 0% | 0 | 100% | 20410.6968
SK ANSAR HOSSIAN | STAIRCASE GRANITE | 215 | 301.392 | 26.866 | SQM | 24.18 | 2.686 | 90% | 7287.6586 | 9.998% | 809.5389
SK ANSAR HOSSIAN | LEDGE WALL GRANITE | 216 | 350 | 2 | NOS | 2 | 0 | 100% | 700 |  | 0
SK ANSAR HOSSIAN | DOOR OPENING GRANITE | 218 | 350 | 23 | NOS | 19 | 4 | 82.61% | 6650 |  | 0
SK ANSAR HOSSIAN | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 44.743 | RMT | 40.27 | 4.473 | 90% | 3302.14 | 9.997% | 366.786
SK ANSAR HOSSIAN | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 134.23 | RMT | 120.81 | 13.42 | 90% | 3962.568 | 9.998% | 440.176
SK ANSAR HOSSIAN | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 33.186 | RMT | 29.87 | 3.316 | 90.01% | 3918.944 | 9.992% | 435.0592
SK ANSAR HOSSIAN | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 | 100% | 4000
SK ANSAR HOSSIAN | GROUND FLOOR TILING | 224 | 183 | 106.54 | SQM | 74.58 | 31.96 | 70% | 13648.14 | 30% | 5848.68
SK ANSAR HOSSIAN | GROUND FLOOR SKIRTING | 225 | 49.2 | 95.43 | RMT | 66.8 | 28.63 | 70% | 3286.56 | 30% | 1408.596
SK ANSAR HOSSIAN | FIRST FLOOR TILING | 226 | 183 | 110.61 | SQM | 77.43 | 33.18 | 70% | 14169.69 | 30% | 6071.94
SK ANSAR HOSSIAN | FIRST FLOOR SKIRTING | 227 | 49.2 | 101.69 | RMT | 71.18 | 30.51 | 70% | 3502.056 | 30% | 1501.092
SK ANSAR HOSSIAN | TERRACE FLOOR TILING | 228 | 183 | 3.698 | SQM | 2.96 | 0.738 | 80.04% | 541.68 | 19.96% | 135.054
SK ANSAR HOSSIAN | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.86 | RMT | 4.69 | 1.17 | 80.03% | 230.748 | 19.97% | 57.564
SK ANSAR HOSSIAN | UTILITY FLOOR TILING | 230 | 183 | 5.13 | SQM | 4.87 | 0.26 | 94.93% | 891.21 | 5.068% | 47.58
SK ANSAR HOSSIAN | UTILITY SKIRTING | 231 | 49.2 | 9.83 | RMT | 9.34 | 0.49 | 95.02% | 459.528 | 4.985% | 24.108
SK ANSAR HOSSIAN | BALCONY & SITOUT TILING | 232 | 183 | 28.012 | SQM | 14.01 | 14.002 | 50.01% | 2563.83 | 49.99% | 2562.366
SK ANSAR HOSSIAN | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 31.801 | RMT | 15.9 | 15.901 | 50% | 782.28 | 50% | 782.3292
SK ANSAR HOSSIAN | CAR PARKING AREA TILING | 234 | 183 | 38.52 | SQM | 36.59 | 1.93 | 94.99% | 6695.97 | 5.01% | 353.19
SK ANSAR HOSSIAN | FLOOR CHIPPING | 235 | 2.5 | 2836 | SFT | 2836 | 0 | 100% | 7090 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 8.66 | SQM | 3.9 | 4.76 | 45.03% | 713.7 | 54.97% | 871.08
SK ANSAR HOSSIAN | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 36.69 | SQM | 16.51 | 20.18 | 45% | 3021.33 | 55% | 3692.94
SK ANSAR HOSSIAN | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 15.007 | SQM | 12.01 | 2.997 | 80.03% | 2197.83 | 19.97% | 548.451
SK ANSAR HOSSIAN | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 61.387 | SQM | 49.11 | 12.277 | 80% | 8987.13 | 20% | 2246.691
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 244.11 | SQM | 0 | 244.11 | 0% | 0 | 100% | 15764.6238
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 1 | 0 | 100% | 18500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 3 | NOS | 0 | 3 | 0% | 0 | 100% | 1800
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 8500 | 1 | LUMP SUM | 1 | 0 | 100% | 8500 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 4500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 4500
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 30.7071 | RMT | 30.71 | -0.0029 | 100% | 169979.85 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 5 | NOS | 0 | 5 | 0% | 0 | 100% | 2250
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1500
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100% | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 304 | 290 | 568.17 | SQM | 466.71 | 101.46 | 82.14% | 135345.9 |  | 0
SHEKAR T | LIFT REINFORCEMENT | 319 | 7500 | 0.767 | MT | 0.77 | -0.003 | 100.4% | 5775 |  | 0
SHEKAR T | LIFT EARTH WORK EXCAVATION | 320 | 424 | 12.337 | CUM | 12.34 | -0.003 | 100% | 5232.16 |  | 0
SHEKAR T | LIFT BOTTOM PCC | 321 | 1000 | 1 | CUM | 1 | 0 | 100% | 1000 |  | 0
SHEKAR T | LIFT RCC | 322 | 225 | 3.638 | CUM | 3.64 | -0.002 | 100.1% | 819 |  | 0
SHEKAR T | LIFT WALL BLOCK WORK | 323 | 194 | 48.679 | SQM | 48.68 | -0.001 | 100% | 9443.92 |  | 0
SHEKAR T | LIFT WALL INTERNAL PLASTERING | 324 | 162 | 95.252 | SQM | 95.25 | 0.002 | 100% | 15430.5 |  | 0
SHEKAR T | LIFT WALL EXTERNAL PLASTERING | 325 | 194 | 96.45 | SQM | 96.45 | 0 | 100% | 18711.3 |  | 0
SHEKAR T | LIFT SIDE REFILLING | 326 | 283 | 5.784 | CUM | 5.78 | 0.004 | 99.93% | 1635.74 |  | 0
SHEKAR T | LIFT RCC | 327 | 2000 | 4.764 | CUM | 4.76 | 0.004 | 99.92% | 9520 |  | 0
SHEKAR T | LIFT FOOTING WALL BEAM AND SLAB SHUTTERING | 328 | 302 | 106.234 | SQM | 106.23 | 0.004 | 100% | 32081.46 |  | 0
JMJ WATERPROOING ENTERPRISES | LIFT WATERPROOF COATING | 329 | 215.28 | 15.49 | SQM | 15.49 | 0 | 100% | 3334.6872 |  | 0
JMJ WATERPROOING ENTERPRISES | LIFT WATERPRROF PLASTERING | 330 | 215.28 | 15.49 | LUMP SUM | 15.49 | 0 | 100% | 3334.6872 |  | 0
JMJ WATERPROOING ENTERPRISES | LIFT 75MM THICK SCREED CONCRETE | 331 | 215.28 | 4.6 | SQM | 4.6 | 0 | 100% | 990.288 |  | 0
JMJ WATERPROOING ENTERPRISES | LIFT BORE PACKING | 332 | 200 | 1 | NOS | 1 | 0 | 100% | 200 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 0.5 | 0.5 | 50% | 500 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 2 | NOS | 1 | 1 | 50% | 1000 |  | 0
PRAKASH H N | CUSTOMIZATION LIFT ELECTRICAL WORK | 435 | 5000 | 1 | LUMP SUM | 1 | 0 | 100% | 5000 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 4500 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 2250 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION GYSER POINT | 449 | 750 | 1 | NOS | 0.5 | 0.5 | 50% | 375 |  | 0
94863.3486

## V25
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
KOUSHIK MANDAL | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 0 | 151.12 | 0% | 0 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 7000
KOUSHIK MANDAL | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
KOUSHIK MANDAL | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
KOUSHIK MANDAL | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 0
KOUSHIK MANDAL | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
KOUSHIK MANDAL | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | 15.63 | 0% | 0 |  | 0 | RUPAK NAYAK | 80164.8662
KOUSHIK MANDAL | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | SANTOSH KUMAR | 0
KOUSHIK MANDAL | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | -0.002 | 100% | 4570 |  | 0 | SARAT BARMAN | 0
KOUSHIK MANDAL | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | 0.002 | 99.99% | 15110 |  | 0 | SAVITA DEVI | 0
KOUSHIK MANDAL | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100% | 4550 |  | 0 | SHOKAT | 0
KOUSHIK MANDAL | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100% | 5250 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
KOUSHIK MANDAL | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0 | SK ANSAR HOSSIAN | 84924.5852
KOUSHIK MANDAL | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.9 | MT | 0.9 | 0 | 100% | 6300 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.8 | MT | 2.8 | 0 | 100% | 19600 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | SUBHASMITA DAS | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0 | UDHABHAI R PARMAR | 0
KOUSHIK MANDAL | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | V VENKATANARAYANA | 0
KOUSHIK MANDAL | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | YELLAPPA C | 0
KOUSHIK MANDAL | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0 | RABIUL MOLLA | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0 | KOUSHIK MANDAL | 233374.646
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0 | TOTAL | 405464.0973
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 0 | 18.25 | 0% | 0 |  | 0
KOUSHIK MANDAL | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
KOUSHIK MANDAL | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
KOUSHIK MANDAL | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | -0.004 | 100% | 6754.5 |  | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0 | 0.8 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 2.4 | MT | 2.4 | 0 | 100% | 16800 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0 | 0.2 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 0 | 20.55 | 0% | 0 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | 0.004 | 99.89% | 7180 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | 0.001 | 100% | 6099.75 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 0 | 1.284 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.04 | MT | 0 | 0.04 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 0 | 3.81 | 0% | 0 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | 0.002 | 99.93% | 636.75 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0% | 0 |  | 0
KOUSHIK MANDAL | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KOUSHIK MANDAL | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
KOUSHIK MANDAL | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 142.49 | 61.06 | 70% | 27607.7225 | 30% | 11830.4971
KOUSHIK MANDAL | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 43.63 | 43.63 | 50% | 8453.3998 | 50% | 8453.3998
KOUSHIK MANDAL | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 0 | 47.7 | 0% | 0 |  | 0
KOUSHIK MANDAL | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | 64.23 | 0% | 0 |  | 0
KOUSHIK MANDAL | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 0 | 368.27 | 0% | 0 |  | 0
KOUSHIK MANDAL | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100% | 16761.055 |  | 0
KOUSHIK MANDAL | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
KOUSHIK MANDAL | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 0 | 309.89 | 0% | 0 | 100% | 60041.8073
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 1 | 0 | 100% | 16500 |  | 0
KOUSHIK MANDAL | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
KOUSHIK MANDAL | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
KOUSHIK MANDAL | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 0 | 209.11 | 0% | 0 | 100% | 40515.4807
KOUSHIK MANDAL | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 0 | 180.56 | 0% | 0 | 100% | 34983.8611
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 313.24 | SQM | 313.24 | 0 | 100% | 67434.3072 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 156.24 | SQM | 156.24 | 0 | 100% | 33635.3472 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 73.8 | SQM | 73.8 | 0 | 100% | 7943.832 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 103.01 | SQM | 103.01 | 0 | 100% | 22175.9928 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 148.7 | SQM | 148.7 | 0 | 100% | 16006.068 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 24 | NOS | 24 | 0 | 100% | 4800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 0 | 27.32 | 0% | 0 | 100% | 5881.4496
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 0 | 147.16 | 0% | 0 | 100% | 14256.8608
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 181.66 | SQM | 0 | 181.66 | 0% | 0 | 33% | 2903.7515
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 167.3 | SQM | 0 | 167.3 | 0% | 0 | 33% | 2674.2135
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 188.59 | SQM | 0 | 188.59 | 0% | 0 | 33% | 3014.5244
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 0 | 148.64 | 100% | 0 | 100% | 2400.536
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 759.174 | SQM | 0 | 759.174 | 0% | 0 | 100% | 36772.8702
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 759.174 | SQM | 0 | 759.174 | 0% | 0 | 100% | 12260.6601
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 759.174 | SQM | 0 | 759.174 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | STAIRCASE GRANITE | 215 | 301.392 | 26.866 | SQM | 0 | 26.866 | 0% | 0 | 85% | 6882.6179
SK ANSAR HOSSIAN | LEDGE WALL GRANITE | 216 | 350 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | DOOR OPENING GRANITE | 218 | 350 | 23 | NOS | 0 | 23 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 44.743 | RMT | 0 | 44.743 | 0% | 0 | 85% | 3118.5871
SK ANSAR HOSSIAN | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 134.23 | RMT | 0 | 134.23 | 0% | 0 | 85% | 3742.3324
SK ANSAR HOSSIAN | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 33.186 | RMT | 0 | 33.186 | 0% | 0 | 85% | 3700.9027
SK ANSAR HOSSIAN | WASH BASIN GRANITE FIXING | 222 | 1000 | 5 | NOS | 0 | 5 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TILING | 224 | 183 | 91.876 | SQM | 0 | 91.876 | 0% | 0 | 90% | 15131.9772
SK ANSAR HOSSIAN | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.4 | RMT | 0 | 59.4 | 0% | 0 | 90% | 2630.232
SK ANSAR HOSSIAN | FIRST FLOOR TILING | 226 | 183 | 82.8 | SQM | 0 | 82.8 | 0% | 0 | 90% | 13637.16
SK ANSAR HOSSIAN | FIRST FLOOR SKIRTING | 227 | 49.2 | 59.428 | RMT | 0 | 59.428 | 0% | 0 | 90% | 2631.4718
SK ANSAR HOSSIAN | TERRACE FLOOR TILING | 228 | 183 | 39.341 | SQM | 0 | 39.341 | 0% | 0 | 90% | 6479.4627
SK ANSAR HOSSIAN | TERRACE FLOOR SKIRTING | 229 | 49.2 | 35.108 | RMT | 0 | 35.108 | 0% | 0 | 90% | 1554.5822
SK ANSAR HOSSIAN | UTILITY FLOOR TILING | 230 | 183 | 4.854 | SQM | 0 | 4.854 | 0% | 0 | 0% | 0
SK ANSAR HOSSIAN | UTILITY SKIRTING | 231 | 49.2 | 8.242 | RMT | 0 | 8.242 | 0% | 0 | 0% | 0
SK ANSAR HOSSIAN | BALCONY & SITOUT TILING | 232 | 183 | 37.586 | SQM | 0 | 37.586 | 0% | 0 | 0% | 0
SK ANSAR HOSSIAN | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 47.496 | RMT | 0 | 47.496 | 0% | 0 | 0% | 0
SK ANSAR HOSSIAN | CAR PARKING AREA TILING | 234 | 183 | 24.735 | SQM | 0 | 24.735 | 0% | 0 | 0% | 0
SK ANSAR HOSSIAN | FLOOR CHIPPING | 235 | 2.5 | 2708.29 | SFT | 0 | 2708.29 | 0% | 0 | 100% | 6770.725
SK ANSAR HOSSIAN | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 2.717 | SQM | 0 | 2.717 | 0% | 0 | 90% | 447.4899
SK ANSAR HOSSIAN | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 14.324 | SQM | 0 | 14.324 | 0% | 0 | 90% | 2359.1628
SK ANSAR HOSSIAN | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 9.22 | SQM | 0 | 9.22 | 0% | 0 | 90% | 1518.534
SK ANSAR HOSSIAN | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.3 | SQM | 0 | 38.3 | 0% | 0 | 90% | 6308.01
SK ANSAR HOSSIAN | TERRACE FLOOR TOILET FLOOR TILING | 239 | 183 | 9.592 | SQM | 0 | 9.592 | 0% | 0 | 90% | 1579.8024
SK ANSAR HOSSIAN | TERRACE FLOOR TOILET WALL TILING | 240 | 183 | 39.05 | SQM | 0 | 39.05 | 0% | 0 | 90% | 6431.535
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 21500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 6000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 6000
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KOUSHIK MANDAL | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 916.85 | SFT | 666.69 | 250.16 | 72.72% | 206673.9 | 27.28% | 77549.6
KOUSHIK MANDAL | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 35 | SFT | 0 | 35 | 0% | 0 |  | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 18300 | 1 | LUMP SUM | 1 | 0 | 100% | 18300 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1000
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 1500 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 12279.74 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 6139.87 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
405464.0973

## V26
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
KOUSHIK MANDAL | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100% | 4255.2 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
KOUSHIK MANDAL | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0.004 | 100% | 24110.352 |  | 0 | KRIUTTIBAS DAS | 14300
KOUSHIK MANDAL | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0.002 | 100% | 1252.9 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | FOOTING EARTH DRESSING | 6 | 22 | 56.952 | SQM | 56.95 | 0.002 | 100% | 1252.9 |  | 0 | MANJUNATHA P | 0
KOUSHIK MANDAL | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0.004 | 100% | 13692.8736 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 9 | 141.12 | 97.034 | CUM | 97.03 | 0.004 | 100% | 13692.8736 |  | 0 | PRAKASH H N | 2500
KOUSHIK MANDAL | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0.002 | 99.97% | 1318.7664 |  | 0 | RAMAKRUSHNA PRADHAN | 0
KOUSHIK MANDAL | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0.002 | 99.99% | 5560.128 |  | 0 | RUPAK NAYAK | 0
KOUSHIK MANDAL | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100% | 1733.6 |  | 0 | SANTOSH KUMAR | 0
KOUSHIK MANDAL | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0% | 0 |  | 0 | SARAT BARMAN | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 5500 | SAVITA DEVI | 0
KOUSHIK MANDAL | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0.001 | 99.98% | 4130 |  | 0 | SHOKAT | 75994.148
KOUSHIK MANDAL | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | -0.004 | 100.1% | 3120 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
KOUSHIK MANDAL | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100% | 7880 |  | 0 | SK ANSAR HOSSIAN | 0
KOUSHIK MANDAL | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100% | 2800 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
KOUSHIK MANDAL | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100% | 3150 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
KOUSHIK MANDAL | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100% | 4200 |  | 0 | SUBHASMITA DAS | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100% | 3500 |  | 0 | UDHABHAI R PARMAR | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 1.45 | 0 | 100% | 10875 |  | 0 | V VENKATANARAYANA | 5500
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0 | YELLAPPA C | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0 | 0.1 | 0% | 0 | 100% | 700 | RABIUL MOLLA | 0
KOUSHIK MANDAL | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | -0.005 | 100% | 10627.0819 |  | 0 | KOUSHIK MANDAL | 242301.2564
KOUSHIK MANDAL | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100% | 8336.5027 |  | 0 | TOTAL | 340595.4044
KOUSHIK MANDAL | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | -0.001 | 100% | 20145.0413 |  | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | -0.005 | 100% | 14328.1757 |  | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0.004 | 100% | 46381.2149 |  | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0.0044 | 99.97% | 3851.7898 |  | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0% | 0 | 100% | 3779.4557
KOUSHIK MANDAL | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0.001 | 99.99% | 2493 |  | 0
KOUSHIK MANDAL | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100% | 2400 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 52 | 1500 | 1.6 | CUM | 1.6 | 0 | 100% | 2400 |  | 0
KOUSHIK MANDAL | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0.004 | 99.91% | 4203 |  | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0.001 | 99.97% | 6760 |  | 0
KOUSHIK MANDAL | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | -0.001 | 100% | 3858.75 |  | 0
KOUSHIK MANDAL | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | -0.002 | 100.1% | 3620 |  | 0
KOUSHIK MANDAL | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0 | 0.626 | 0% | 0 | 100% | 939
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KOUSHIK MANDAL | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 | 100% | 1050
KOUSHIK MANDAL | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | -0.005 | 100% | 11886.9005 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0.002 | 100% | 38777.0947 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0.004 | 99.97% | 3851.7898 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.495 | 0% | 0 | 100% | 4670.069
KOUSHIK MANDAL | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0.004 | 99.83% | 4580 |  | 0
KOUSHIK MANDAL | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | -0.003 | 100% | 3141 |  | 0
KOUSHIK MANDAL | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | -0.002 | 100.1% | 3620 |  | 0
KOUSHIK MANDAL | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0 | 0.699 | 0% | 0 | 100% | 1048.5
KOUSHIK MANDAL | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.14 | 0.01 | 93.33% | 980 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0.19 | 0.01 | 95% | 1330 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0 | 0.02 | 0% | 0 | 100% | 140
KOUSHIK MANDAL | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 7.7 | 0.4 | 95.06% | 2320.7184 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 26.72 | 1.409 | 94.99% | 8053.1942 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.455 | 0% | 0 | 100% | 739.9174
KOUSHIK MANDAL | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.67 | 0.039 | 94.5% | 1340 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.53 | 0.138 | 94.83% | 569.25 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0 | 0.196 | 0% | 0 | 100% | 294
KOUSHIK MANDAL | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100% | 2050 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KOUSHIK MANDAL | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100% | 21742.8494 |  | 0
KOUSHIK MANDAL | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100% | 25858.1419 |  | 0
KOUSHIK MANDAL | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100% | 13808.705 |  | 0
KOUSHIK MANDAL | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 0 | 32.74 | 0% | 0 | 100% | 2147.744
KOUSHIK MANDAL | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0% | 0 | 100% | 4736.976
KOUSHIK MANDAL | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0 | 0.66 | 0% | 0 | 100% | 106.5636
KOUSHIK MANDAL | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 0 | 201.86 | 0% | 0 | 100% | 2172.0136
KOUSHIK MANDAL | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 0 | 72.04 | 0% | 0 | 100% | 10080.7013
KOUSHIK MANDAL | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 0 | 187.02 | 0% | 0 | 100% | 26170.0826
KOUSHIK MANDAL | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 0 | 201.853 | 0% | 0 | 100% | 39109.4225
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
KOUSHIK MANDAL | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 0 | 64.644 | 0% | 0 | 100% | 9045.7642
KOUSHIK MANDAL | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 0 | 206.23 | 0% | 0 | 100% | 28858.1764
KOUSHIK MANDAL | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 0 | 132.03 | 0% | 0 | 100% | 25581.0766
KOUSHIK MANDAL | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 0 | 12.3 | 0% | 0 | 100% | 1721.1636
KOUSHIK MANDAL | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 0 | 39.21 | 0% | 0 | 100% | 5486.7337
KOUSHIK MANDAL | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 0 | 138.781 | 0% | 0 | 100% | 26889.0963
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 170.21 | SQM | 0 | 0 | 0% | 0 | 100% | 36642.8088
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 33.57 | SQM | 0 | 0 | 0% | 0 | 100% | 7226.9496
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 41.03 | SQM | 0 | 0 | 0% | 0 | 100% | 4416.4692
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 90.54 | SQM | 0 | 0 | 0% | 0 | 100% | 19491.4512
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 41.03 | SQM | 0 | 0 | 0% | 0 | 100% | 4416.4692
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 19 | NOS | 0 | 0 | 0% | 0 | 100% | 3800
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 9000
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 500
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1800
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KOUSHIK MANDAL | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 559.57 | SFT | 408.49 | 151.08 | 73% | 126631.9 | 27% | 46834.8
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 15900 | 1 | LUMP SUM | 1 | 0 | 100% | 15900 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
YELLAPPA C | FOOTING RCC REWORK | 363 | 225 | 11.081 | CUM | 11.08 | 0.001 | 99.99% | 2493 |  | 0
YELLAPPA C | FOOTING SHUTTERING REWORK | 364 | 301.392 | 35.255 | SQM | 35.26 | -0.005 | 100% | 10627.0819 |  | 0
KOUSHIK MANDAL | FOOTING REINFORCEMENT REWORK | 365 | 7500 | 0.4 | MT | 0 | 0.4 | 0% | 0 |  | 0
YELLAPPA C | FOOTING REINFORCEMENT REWORK | 365 | 7000 | 0.4 | MT | 0.4 | 0 | 100% | 2800 |  | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING REWORK | 366 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100% | 8336.5027 |  | 0
KOUSHIK MANDAL | PEDESTAL COLUMN REINFORCEMENT REWORK | 367 | 7500 | 0.45 | MT | 0 | 0.45 | 0% | 0 |  | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT REWORK | 367 | 7000 | 0.45 | MT | 0.45 | 0 | 100% | 3150 |  | 0
KOUSHIK MANDAL | GROUND FLOOR COLUMN REINFORCEMENT REWORK | 368 | 7500 | 0.5 | MT | 0 | 0.5 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT REWORK | 368 | 7000 | 0.5 | MT | 0.5 | 0 | 100% | 3500 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 3000
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2500
340595.4044

## V27
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
RABIUL MOLLA | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 0 | 78.8 | 0 | 0 | 0 | 0
RABIUL MOLLA | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
RABIUL MOLLA | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
RABIUL MOLLA | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
RABIUL MOLLA | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
RABIUL MOLLA | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
RABIUL MOLLA | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
RABIUL MOLLA | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
RABIUL MOLLA | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0 | 0 | 0 | 0
RABIUL MOLLA | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
RABIUL MOLLA | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
RABIUL MOLLA | FOOTING REINFORCEMENT | 23 | 7500 | 0.4 | MT | 0.4 | 0 | 100 | 3000 | 0 | 0
RABIUL MOLLA | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
RABIUL MOLLA | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.6 | MT | 0.6 | 0 | 100 | 4500 | 0 | 0
RABIUL MOLLA | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 1.45 | 0 | 100 | 10875 | 0 | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
RABIUL MOLLA | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
RABIUL MOLLA | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
RABIUL MOLLA | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
RABIUL MOLLA | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0 | 0 | 0 | 0
RABIUL MOLLA | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
RABIUL MOLLA | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
RABIUL MOLLA | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
RABIUL MOLLA | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0 | 0.63 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
RABIUL MOLLA | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.5 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0 | 0.7 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.46 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0 | 0.2 | 0 | 0 | 0 | 0
RABIUL MOLLA | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
RABIUL MOLLA | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 106.61 | 5.61 | 95 | 20655.9007 | 0 | 0
RABIUL MOLLA | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 126.79 | 6.67 | 95 | 24565.8161 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 67.71 | 3.56 | 95 | 13118.9479 | 0 | 0
RABIUL MOLLA | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 0 | 32.74 | 0 | 0 | 0 | 0
RABIUL MOLLA | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0 | 0 | 0 | 0
RABIUL MOLLA | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0 | 0.66 | 0 | 0 | 0 | 0
RABIUL MOLLA | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 0 | 201.86 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 0 | 72.04 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 0 | 187.02 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 0 | 201.85 | 0 | 0 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 0 | 64.64 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 0 | 206.23 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 0 | 132.03 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 0 | 12.3 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 0 | 39.21 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 0 | 138.78 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RABIUL MOLLA | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 255 | SFT | 255 | 0 | 100 | 79050 | 0 | 0
RABIUL MOLLA | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 326 | SFT | 237.98 | 88.02 | 73 | 73773.8 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0

## V28
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
RABIUL MOLLA | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
RABIUL MOLLA | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
RABIUL MOLLA | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
RABIUL MOLLA | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
RABIUL MOLLA | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
RABIUL MOLLA | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
RABIUL MOLLA | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 0 | 39.4 | 0 | 0 | 0 | 0
RABIUL MOLLA | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 0 | 78.8 | 0 | 0 | 0 | 0
RABIUL MOLLA | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0 | 0 | 0 | 0
RABIUL MOLLA | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
RABIUL MOLLA | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
RABIUL MOLLA | FOOTING REINFORCEMENT | 23 | 7500 | 0.4 | MT | 0.4 | 0 | 100 | 3000 | 0 | 0
RABIUL MOLLA | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
RABIUL MOLLA | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.6 | MT | 0.6 | 0 | 100 | 4500 | 0 | 0
RABIUL MOLLA | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 1.45 | 0 | 100 | 10875 | 0 | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
RABIUL MOLLA | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
RABIUL MOLLA | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
RABIUL MOLLA | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
RABIUL MOLLA | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0 | 0 | 0 | 0
RABIUL MOLLA | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
RABIUL MOLLA | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
RABIUL MOLLA | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
RABIUL MOLLA | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0 | 0.63 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
RABIUL MOLLA | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0.52 | 0.03 | 95 | 3900 | 0 | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 1.14 | 0.06 | 95 | 8550 | 0 | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.16 | 0.01 | 95 | 1200 | 0 | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 37.46 | 1.97 | 95 | 11290.1443 | 0 | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 122.23 | 6.43 | 95 | 36839.1442 | 0 | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.14 | 0.64 | 95 | 3658.8989 | 0 | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.5 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.18 | 0.11 | 95 | 4360 | 0 | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 0 | 13.96 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.72 | 0.09 | 95 | 3440 | 0 | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0 | 0.7 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0 | 0.2 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 0 | 28.13 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.46 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0 | 0.71 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 0 | 2.67 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0 | 0.2 | 0 | 0 | 0 | 0
RABIUL MOLLA | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 0 | 41 | 0 | 0 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 0 | 112.22 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 0 | 133.46 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 0 | 71.27 | 0 | 0 | 0 | 0
RABIUL MOLLA | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 0 | 32.74 | 0 | 0 | 0 | 0
RABIUL MOLLA | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0 | 0 | 0 | 0
RABIUL MOLLA | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0 | 0.66 | 0 | 0 | 0 | 0
RABIUL MOLLA | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 0 | 201.86 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 0 | 72.04 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 0 | 187.02 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 0 | 201.85 | 0 | 0 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 0 | 64.64 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 0 | 206.23 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 0 | 132.03 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 0 | 12.3 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 0 | 39.21 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 0 | 138.78 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 16000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RABIUL MOLLA | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 255 | SFT | 135.15 | 119.85 | 53 | 41896.5 | 0 | 0
RABIUL MOLLA | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 290 | SFT | 153.7 | 136.3 | 53 | 47647 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V29
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
RABIUL MOLLA | ATT IN PLINTH | 1 | 54 | 137.52 | SQM | 0 | 137.52 | 0% | 0 |  | 0 | AAIDHUL MIAH | 0
RABIUL MOLLA | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
RABIUL MOLLA | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
RABIUL MOLLA | FOOTING EXCAVATION | 4 | 211.68 | 135.57 | CUM | 135.57 | 0 | 100% | 28697.4576 |  | 0 | KRIUTTIBAS DAS | 17000
RABIUL MOLLA | FOOTING EARTH DRESSING | 5 | 22 | 67.79 | SQM | 67.79 | 0 | 100% | 1491.38 |  | 0 | LEGENDRY LANDSCAPE | 0
RABIUL MOLLA | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 114.59 | CUM | 114.59 | 0 | 100% | 16170.9408 |  | 0 | MANJUNATHA P | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.845 | CUM | 5.85 | -0.005 | 100.1% | 1238.328 |  | 0 | NAGARAJ | 0
RABIUL MOLLA | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 65.48 | CUM | 65.48 | 0 | 100% | 9240.5376 |  | 0 | PRAKASH H N | 0
RABIUL MOLLA | BASE FLOOR EARTH DRESSING | 14 | 22 | 137.52 | SQM | 137.52 | 0 | 100% | 3025.44 |  | 0 | RAMAKRUSHNA PRADHAN | 0
RABIUL MOLLA | SETBACK AREA SOIL FILLING | 16 | 141.12 | 13.18 | CUM | 0 | 13.18 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 5500 | SANTOSH KUMAR | 0
RABIUL MOLLA | FOOTING PCC WORK | 20 | 1000 | 4.566 | CUM | 4.57 | -0.004 | 100.1% | 4570 |  | 0 | SARAT BARMAN | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.923 | CUM | 2.92 | 0.003 | 99.9% | 2920 |  | 0 | SAVITA DEVI | 0
RABIUL MOLLA | BASE FLOOR PCC | 22 | 1000 | 13.752 | CUM | 13.75 | 0.002 | 99.99% | 13750 |  | 0 | SHOKAT | 0
RABIUL MOLLA | FOOTING REINFORCEMENT | 23 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
RABIUL MOLLA | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100% | 5250 |  | 0 | SK ANSAR HOSSIAN | 0
RABIUL MOLLA | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
RABIUL MOLLA | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2 | MT | 2 | 0 | 100% | 15000 |  | 0 | SUBHASMITA DAS | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0 | UDHABHAI R PARMAR | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0 | V VENKATANARAYANA | 5500
RABIUL MOLLA | FOOTING SHUTTERING | 41 | 301.392 | 43.26 | SQM | 43.26 | 0 | 100% | 13038.2179 |  | 0 | YELLAPPA C | 0
RABIUL MOLLA | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 28.8 | SQM | 28.8 | 0 | 100% | 8680.0896 |  | 0 | RABIUL MOLLA | 0
RABIUL MOLLA | PLINTH BEAM SHUTTERING | 43 | 301.392 | 64.28 | SQM | 64.28 | 0 | 100% | 19373.4778 |  | 0 | KOUSHIK MANDAL | 0
RABIUL MOLLA | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.51 | SQM | 51.51 | 0 | 100% | 15524.7019 |  | 0 | TOTAL | 22500
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 187.91 | SQM | 187.91 | 0 | 100% | 56634.5707 |  | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 13.1328 | SQM | 13.13 | 0.0028 | 99.98% | 3957.277 |  | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.61 | SQM | 15.61 | 0 | 100% | 4704.7291 |  | 0
RABIUL MOLLA | FOOTING RCC | 50 | 225 | 15.37 | CUM | 15.37 | 0 | 100% | 3458.25 |  | 0
RABIUL MOLLA | PEDESTAL COLUMN RCC | 51 | 1500 | 2.56 | CUM | 2.56 | 0 | 100% | 3840 |  | 0
RABIUL MOLLA | PLINTH BEAM RCC | 53 | 900 | 4.38 | CUM | 4.38 | 0 | 100% | 3942 |  | 0
RABIUL MOLLA | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.05 | CUM | 3.05 | 0 | 100% | 6100 |  | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 21.874 | CUM | 21.87 | 0.004 | 99.98% | 4920.75 |  | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 2.233 | CUM | 2.23 | 0.003 | 99.87% | 4460 |  | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 1.1 | CUM | 1.1 | 0 | 100% | 1650 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.75 | MT | 0.75 | 0 | 100% | 5625 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.3 | MT | 1.3 | 0 | 100% | 9750 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 47.03 | SQM | 47.03 | 0 | 100% | 14174.4658 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 165.84 | SQM | 165.84 | 0 | 100% | 49982.8493 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 13.1328 | SQM | 13.13 | 0.0028 | 99.98% | 3957.277 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 18.21 | SQM | 18.21 | 0 | 100% | 5488.3483 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.784 | CUM | 2.78 | 0.004 | 99.86% | 5560 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 18.898 | CUM | 18.9 | -0.002 | 100% | 4252.5 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 2.233 | CUM | 2.23 | 0.003 | 99.87% | 4460 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.153 | CUM | 1.15 | 0.003 | 99.74% | 1725 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.05 | MT | 0.05 | 0 | 100% | 375 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
RABIUL MOLLA | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.47 | SQM | 29.47 | 0 | 100% | 8882.0222 |  | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.88 | SQM | 3.88 | 0 | 100% | 1169.401 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.81 | CUM | 0.81 | 0 | 100% | 1620 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 3.352 | CUM | 3.35 | 0.002 | 99.94% | 753.75 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.26 | CUM | 0.26 | 0 | 100% | 390 |  | 0
RABIUL MOLLA | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100% | 2150 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
RABIUL MOLLA | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 139.91 | SQM | 139.91 | 0 | 100% | 27107.8423 |  | 0
RABIUL MOLLA | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 178.84 | SQM | 178.84 | 0 | 100% | 34650.6077 |  | 0
RABIUL MOLLA | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 75.48 | SQM | 75.48 | 0 | 100% | 14624.401 |  | 0
RABIUL MOLLA | ELEVATION RCC BAND | 133 | 65.6 | 38.284 | RMT | 38.28 | 0.004 | 99.99% | 2511.168 |  | 0
RABIUL MOLLA | ELEVATION GROOVE | 137 | 65.6 | 49.952 | RMT | 49.95 | 0.002 | 100% | 3276.72 |  | 0
RABIUL MOLLA | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.38 | SQM | 1.38 | 0 | 100% | 222.8148 |  | 0
RABIUL MOLLA | RCC SURFACE HACKING | 140 | 10.76 | 258.02 | SQM | 258.02 | 0 | 100% | 2776.2952 |  | 0
RABIUL MOLLA | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 81.36 | SQM | 81.36 | 0 | 100% | 11384.8675 |  | 0
RABIUL MOLLA | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.704 | SQM | 187.7 | 0.004 | 100% | 26265.2364 |  | 0
RABIUL MOLLA | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 228.17 | SQM | 228.17 | 0 | 100% | 44208.3938 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 1 | 0 | 100% | 16500 |  | 0
RABIUL MOLLA | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
RABIUL MOLLA | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 304.83 | SQM | 304.83 | 0 | 100% | 42655.4716 |  | 0
RABIUL MOLLA | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 160.44 | SQM | 160.44 | 0 | 100% | 31085.5709 |  | 0
RABIUL MOLLA | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.87 | SQM | 14.87 | 0 | 100% | 2080.7888 |  | 0
RABIUL MOLLA | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 38.01 | SQM | 38.01 | 0 | 100% | 5318.8153 |  | 0
RABIUL MOLLA | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 158.39 | SQM | 158.39 | 0 | 100% | 30688.3793 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 200.752 | SQM | 200.75 | 0.002 | 100% | 43217.46 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 27.748 | SQM | 27.75 | -0.002 | 100% | 5974.02 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 70.11 | SQM | 70.11 | 0 | 100% | 7546.6404 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 216.28 | 98.256 | SQM | 98.26 | -0.004 | 100% | 21251.6728 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 70.11 | SQM | 70.11 | 0 | 100% | 7546.6404 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 76.68 | SQM | 76.68 | 0 | 100% | 7428.7584 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 192.54 | SQM | 77.02 | 115.52 | 40% | 3730.6948 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 131.38 | SQM | 52.55 | 78.83 | 40% | 2545.4169 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 145.63 | SQM | 58.25 | 87.38 | 40% | 2821.5135 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 198.11 | SQM | 118.87 | 79.24 | 60% | 10875.8918 |  | 0
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 76.48 | SQM | 45.89 | 30.59 | 60% | 4198.6597 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 316.673 | SQM | 190 | 126.673 | 60% | 17383.86 |  | 0
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 92.25 | SQM | 55.35 | 36.9 | 60% | 5064.1929 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 38.01 | SQM | 22.81 | 15.2 | 60.01% | 2086.9781 |  | 0
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 13.36 | SQM | 8.02 | 5.34 | 60.03% | 733.7819 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 1 | 0 | 100% | 18500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 10000
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 7000
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RABIUL MOLLA | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 938.82 | SFT | 910.66 | 28.16 | 97% | 282304.6 |  | 0
RABIUL MOLLA | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 100 | SFT | 97 | 3 | 97% | 30070 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 5344.34 | 1 | LUMP SUM | 1 | 0 | 100% | 5344.34 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 54.6232 | SQM | 54.62 | 0.00317 | 99.99% | 2645.6836 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 54.6232 | SQM | 54.62 | 0.00317 | 99.99% | 882.113 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 54.6232 | SQM | 0 | 54.6232 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 33.135 | SQM | 33.14 | -0.005 | 100% | 535.211 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 33.135 | SQM | 0 | 33.135 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION AQUAGUARD TAP POINT WORK | 420 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
22500

## V30
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 103.17 | SQM | 103.17 | 0 | 100% | 5571.18 |  | 0 | AAIDHUL MIAH | 350
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 150.56 | CUM | 150.56 | 0 | 100% | 31870.5408 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 46.12 | SQM | 46.12 | 0 | 100% | 1014.64 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 116.13 | CUM | 116.13 | 0 | 100% | 16388.2656 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 56.74 | CUM | 56.74 | 0 | 100% | 8007.1488 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 103.17 | SQM | 103.17 | 0 | 100% | 2269.74 |  | 0 | PRAKASH H N | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | RAMAKRUSHNA PRADHAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 7.53 | CUM | 7.53 | 0 | 100% | 7530 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.994 | CUM | 3.99 | 0.004 | 99.9% | 3990 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 10.32 | CUM | 10.32 | 0 | 100% | 10320 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | SHOKAT | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100% | 5250 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.95 | MT | 0.95 | 0 | 100% | 7125 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.6 | MT | 2.6 | 0 | 100% | 19500 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.16 | MT | 0.16 | 0 | 100% | 1200 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | -0.004 | 106.1% | 525 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 65.78 | SQM | 65.78 | 0 | 100% | 19825.5658 |  | 0 | YELLAPPA C | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 37.11 | SQM | 37.11 | 0 | 100% | 11184.6571 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 79.884 | SQM | 79.88 | 0.004 | 99.99% | 24075.193 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 67.86 | SQM | 67.86 | 0 | 100% | 20452.4611 |  | 0 | TOTAL | 350
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 218.06 | SQM | 218.06 | 0 | 100% | 65721.5395 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.793 | SQM | 0 | 12.793 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 11.65 | SQM | 0 | 11.65 | 0% | 0 |  | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 77 | SFT | 77 | 0 | 100% | 2156 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 17.19 | CUM | 17.19 | 0 | 100% | 3867.75 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.18 | CUM | 2.18 | 0 | 100% | 3270 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 5.991 | CUM | 5.99 | 0.001 | 99.98% | 5391 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.98 | CUM | 3.98 | 0 | 100% | 7960 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 23.5 | CUM | 23.5 | 0 | 100% | 5287.5 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.673 | CUM | 1.67 | 0.003 | 99.82% | 3340 |  | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100% | 1440 |  | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.85 | MT | 1.85 | 0 | 100% | 13875 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 56.55 | SQM | 56.55 | 0 | 100% | 17043.7176 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 188.59 | SQM | 188.59 | 0 | 100% | 56839.5173 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.793 | SQM | 0 | 12.793 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 14.11 | SQM | 0 | 14.11 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.33 | CUM | 3.33 | 0 | 100% | 6660 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 19.19 | CUM | 19.19 | 0 | 100% | 4317.75 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.673 | CUM | 1.67 | 0.003 | 99.82% | 3340 |  | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.57 | CUM | 1.57 | 0 | 100% | 2355 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.3 | MT | 0.3 | 0 | 100% | 2250 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100% | 150 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 26.6 | SQM | 26.6 | 0 | 100% | 8017.0272 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.815 | SQM | 0 | 1.815 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 3.07 | CUM | 3.07 | 0 | 100% | 690.75 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.17 | CUM | 0.17 | 0 | 100% | 255 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 53 | NOS | 53 | 0 | 100% | 2650 |  | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 146.37 | SQM | 146.37 | 0 | 100% | 28359.4802 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 185.55 | SQM | 185.55 | 0 | 100% | 35950.6836 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 72.29 | SQM | 72.29 | 0 | 100% | 14006.3321 |  | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 49.17 | RMT | 49.17 | 0 | 100% | 3225.552 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 33.82 | RMT | 33.82 | 0 | 100% | 2218.592 |  | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 19.045 | SQM | 19.05 | -0.005 | 100% | 3690.9756 |  | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 406 | SQM | 0 | 406 | 0% | 0 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 483 | SQM | 0 | 483 | 0% | 0 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 94.21 | SQM | 94.21 | 0 | 100% | 13182.9937 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 266.24 | SQM | 266.24 | 0 | 100% | 37255.4957 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 261.11 | SQM | 30 | 231.11 | 11.49% | 5812.56 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 92.25 | SQM | 92.25 | 0 | 100% | 12908.727 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 364.2 | SQM | 364.2 | 0 | 100% | 50963.2344 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 163.72 | SQM | 0 | 163.72 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 13.2 | SQM | 13.2 | 0 | 100% | 1847.1024 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.271 | SQM | 32.5 | 4.771 | 87.2% | 4547.79 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 163.58 | SQM | 0 | 163.58 | 0% | 0 |  | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 62.44 | SQM | 62.44 | 0 | 100% | 26884.1664 |  | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 131.809 | SQM | 131.81 | -0.001 | 100% | 56752.1136 |  | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 23.61 | SQM | 23.61 | 0 | 100% | 5082.7608 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 30.573 | SQM | 30.57 | 0.003 | 99.99% | 6581.1096 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 21 | SQM | 21 | 0 | 100% | 4200 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 27.313 | SQM | 27.31 | 0.003 | 99.99% | 5879.2968 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 531.773 | SQM | 531.77 | 0.003 | 100% | 8588.0855 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 531.77 | SQM | 531.77 | 0 | 100% | 17171.9168 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 609.07 | SQM | 609.07 | 0 | 100% | 29502.1327 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 609.07 | SQM | 609.07 | 0 | 100% | 9836.4805 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 609.07 | SQM | 609.07 | 0 | 100% | 16390.0737 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 19.869 | SQM | 19.87 | -0.001 | 100% | 5988.659 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 1 | NOS | 1 | 0 | 100% | 450 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 18 | NOS | 8 | 10 | 44.44% | 2800 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 49.76 | RMT | 49.76 | 0 | 100% | 4080.32 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 115.23 | RMT | 115.23 | 0 | 100% | 3779.544 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.906 | RMT | 23.91 | -0.004 | 100% | 3136.992 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 6 | NOS | 1 | 5 | 16.67% | 1000 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 77.202 | SQM | 50.93 | 26.272 | 65.97% | 9320.19 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 52.156 | RMT | 40 | 12.156 | 76.69% | 1968 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 76.443 | SQM | 76.44 | 0.003 | 100% | 13988.52 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 75.032 | RMT | 75.03 | 0.002 | 100% | 3691.476 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 4.028 | SQM | 4.03 | -0.002 | 100% | 737.49 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.86 | RMT | 5.86 | 0 | 100% | 288.312 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 3.238 | SQM | 3.24 | -0.002 | 100.1% | 592.92 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 8.85 | RMT | 8.85 | 0 | 100% | 435.42 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 23.216 | SQM | 23.22 | -0.004 | 100% | 4249.26 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 43.349 | RMT | 43.35 | -0.001 | 100% | 2132.82 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 33.637 | SQM | 33.64 | -0.003 | 100% | 6156.12 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1719.747 | SFT | 1719.74 | 0.007 | 100% | 4299.35 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 8.229 | SQM | 8.23 | -0.001 | 100% | 1506.09 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 45.526 | SQM | 45.53 | -0.004 | 100% | 8331.99 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.376 | SQM | 7.38 | -0.004 | 100.1% | 1350.54 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 44.673 | SQM | 44.67 | 0.003 | 99.99% | 8174.61 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100% | 17500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 3000 | 1 | LUMP SUM | 0.67 | 0.33 | 67% | 2010 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 48.79 | RMT | 48.79 | 0 | 100% | 270052.65 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100% | 5625 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100% | 225 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
CHIRANJEEVI | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100% | 1500 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
CHIRANJEEVI | CHAIN LINK STAIRCASE PLASTERING | 333 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
YELLAPPA C | ADDITIONAL SHUTTERING WORK/CUSTOMIZATION - 41340 (S/C - 25000/-, ADDITIONAL BALCONY - 7687/-, TERRACE ROOF - 8652/- | 357 | 301.392 | 88.8248 | SFT | 88.82 | 0.0048 | 99.99% | 26769.6374 |  | 0
SHOKAT | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 8.811 | SQM | 8.81 | 0.001 | 99.99% | 1896.6168 |  | 0
SHOKAT | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 12.529 | SQM | 12.53 | -0.001 | 100% | 5394.9168 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
KRISHNAKUMAR SAHANI | CUSTOMIZATION TOILET TILE WORK | 450 | 183 | 38.966 | SQM | 38.97 | -0.004 | 100% | 7131.51 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT | 451 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT | 452 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION SHOWER POINT WORK | 453 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
350

## V31
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 | AAIDHUL MIAH | 350
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 2450 | 1 | LUMP SUM | 1 | 0 | 100% | 2450 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100% | 13191.8976 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0.002 | 99.97% | 1221.3936 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100% | 4925.088 |  | 0 | PRAKASH H N | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100% | 3949.98 |  | 0 | RUPAK NAYAK | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 10.81 | 0 | 100% | 1525.5072 |  | 0 | SANTOSH KUMAR | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | -0.004 | 100.1% | 3470 |  | 0 | SARAT BARMAN | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | -0.004 | 100.1% | 2890 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | -0.004 | 100% | 9190 |  | 0 | SHOKAT | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100% | 2100 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0 | SK ANSAR HOSSIAN | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100% | 3850 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 5600 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100% | 10500 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0 | YELLAPPA C | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0.0047 | 99.99% | 19144.4198 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100% | 15578.9525 |  | 0 | TOTAL | 350
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100% | 46305.8669 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100% | 4813.2302 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0.002 | 99.98% | 2225.25 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0.002 | 99.92% | 3660 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100% | 1485 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100% | 7700 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100% | 15033.433 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100% | 39985.6766 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100% | 5087.497 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0.003 | 99.9% | 5880 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100% | 3082.5 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | -0.003 | 100.3% | 1410 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100% | 700 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0.03 | 0 | 100% | 210 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100% | 8176.765 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100% | 828.828 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0.002 | 99.92% | 542.25 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100% | 22453.9193 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100% | 25809.7039 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100% | 2101.824 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100% | 2102.48 |  | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100% | 184.0644 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0.002 | 100% | 2224.4148 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100% | 27220.972 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100% | 40362.4166 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0.002 | 100% | 10409.5415 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | -0.003 | 100% | 30850.808 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100% | 27543.7843 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100% | 4677.9268 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100% | 29719.6193 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 52.132 | SQM | 52.13 | 0.002 | 100% | 22445.0928 |  | 0
JMJ WATERPROOING ENTERPRISES | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 82.955 | SQM | 82.96 | -0.005 | 100% | 35719.2576 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 22.29 | SQM | 22.29 | 0 | 100% | 4798.5912 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 35.405 | SQM | 35.41 | -0.005 | 100% | 7623.0648 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 19 | SQM | 19 | 0 | 100% | 3800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0.003 | 99.99% | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100% | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100% | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100% | 13137.0314 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0.004 | 99.99% | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0.004 | 100% | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0.003 | 100% | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0.001 | 100% | 15634.9791 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100% | 6413.6218 |  | 0
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 11 | 4 | 73.33% | 3850 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0.002 | 99.99% | 3040.56 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100% | 3649 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | -0.002 | 100% | 3581.76 |  | 0
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100% | 3000 |  | 0
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 58.71 | SQM | 45 | 13.71 | 76.65% | 8235 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.43 | RMT | 50 | 9.43 | 84.13% | 2460 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 50 | 9.742 | 83.69% | 9150 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 60 | 9.16 | 86.76% | 2952 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100% | 675.27 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.6 | 0 | 100% | 275.52 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 0 | 2.512 | 0% | 0 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 0 | 7.61 | 0% | 0 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 7.41 | SQM | 0 | 7.41 | 0% | 0 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 11.15 | RMT | 0 | 11.15 | 0% | 0 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100% | 4973.94 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100% | 2955 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 4.06 | 0.002 | 99.95% | 742.98 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.11 | SQM | 18.11 | 0 | 100% | 3314.13 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 5 | 3.15 | 61.35% | 915 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 36.28 | SQM | 25 | 11.28 | 68.91% | 4575 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 3000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR PARKING AREA CHIPPING AND EXCAVATION | 259 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.67 | RMT | 25.67 | 0 | 100% | 142083.45 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100% | 1350 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100% | 225 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 99 | CFT | 99 | 0 | 100% | 873.774 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 99 | SFT | 99 | 0 | 100% | 2351.25 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
INDAL SAHNI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 40.3 | RMT | 40.3 | 0 | 100% | 1321.84 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 177 | 290 | LUMP SUM | 45.75 | 244.25 | 15.78% | 8097.75 |  | 0
YELLAPPA C | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 174 | 290 | SFT | 290 | 0 | 100% | 50460 |  | 0
INDAL SAHNI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 3.953 | SQM | 3.95 | 0.003 | 99.92% | 1190.4984 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 65.584 | SQM | 65.58 | 0.004 | 99.99% | 1059.117 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 65.584 | SQM | 65.58 | 0.004 | 99.99% | 2117.7094 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 432 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 3.45 | SQM | 3.45 | 0 | 100% | 742.716 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 5.835 | SQM | 5.84 | -0.005 | 100.1% | 2514.4704 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 11600 | 1 | LUMP SUM | 1 | 0 | 100% | 11600 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TERRACE WATERPROOFING WORK | 454 | 215.28 | 49.25 | SQM | 49.25 | 0 | 100% | 10602.54 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TERRACE SCREED CONCRETE WORK | 455 | 215.28 | 49.25 | SQM | 49.25 | 0 | 100% | 10602.54 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WATER PURIFIER POINT WORK | 456 | 500 | 1 | NOS | 1 | 0 | 100% | 500 |  | 0
PRAKASH H N | CUSTAMIZATION FLOOR ROOF CONDUIT WORK | 457 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
350

## V32
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 | AAIDHUL MIAH | 350
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100% | 13191.8976 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100% | 4925.088 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | -0.004 | 100.1% | 3470 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | -0.004 | 100.1% | 2890 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | -0.004 | 100% | 9190 |  | 0 | SANTOSH KUMAR | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100% | 2250 |  | 0 | SARAT BARMAN | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100% | 5250 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0 | SHOKAT | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100% | 11250 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | -0.004 | 106.1% | 525 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0.0047 | 99.99% | 19144.4198 |  | 0 | YELLAPPA C | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 41 | 10.69 | 79.32% | 12357.072 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 145 | 8.64 | 94.38% | 43701.84 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 10 | 2.33 | 81.1% | 3013.92 |  | 0 | TOTAL | 350
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0% | 0 |  | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 40.26 | SFT | 40.26 | 0 | 100% | 1127.28 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0.002 | 99.98% | 2225.25 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0.002 | 99.92% | 3660 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100% | 1485 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100% | 5250 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100% | 8250 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100% | 15033.433 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100% | 39985.6766 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0.003 | 99.9% | 5880 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100% | 3082.5 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | -0.003 | 100.3% | 1410 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100% | 750 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0.03 | 0 | 100% | 225 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 23.44 | 3.69 | 86.4% | 7064.6285 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0.002 | 99.92% | 542.25 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100% | 22453.9193 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100% | 25809.7039 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100% | 2101.824 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100% | 2102.48 |  | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 5.258 | SQM | 5.26 | -0.002 | 100% | 1019.1355 |  | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 307 | SQM | 307 | 0 | 100% | 10745 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 450 | SQM | 450 | 0 | 100% | 3632.85 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100% | 27220.972 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100% | 40362.4166 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0.002 | 100% | 10409.5415 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | -0.003 | 100% | 30850.808 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100% | 27543.7843 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100% | 4677.9268 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100% | 29719.6193 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 142.926 | SQM | 142.93 | -0.004 | 100% | 30769.9704 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 46.895 | SQM | 46.9 | -0.005 | 100% | 10096.632 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 22.98 | SQM | 22.98 | 0 | 100% | 2473.5672 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 96.031 | SQM | 96.03 | 0.001 | 100% | 20673.3384 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 22.98 | SQM | 22.98 | 0 | 100% | 2473.5672 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 14 | 0 | 100% | 2800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0.003 | 99.99% | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100% | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100% | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100% | 13137.0314 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0.004 | 99.99% | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0.004 | 100% | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0.003 | 100% | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0.001 | 100% | 15634.9791 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.048 | SQM | 19.05 | -0.002 | 100% | 5741.5176 |  | 0
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 14 | 0 | 100% | 4900 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100% | 3375.94 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 102.54 | RMT | 102.54 | 0 | 100% | 3363.312 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 25.568 | RMT | 25.57 | -0.002 | 100% | 3354.784 |  | 0
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100% | 4000 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 55.989 | SQM | 55.99 | -0.001 | 100% | 10246.17 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.761 | RMT | 48.76 | 0.001 | 100% | 2398.992 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 53.821 | SQM | 53.82 | 0.001 | 100% | 9849.06 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 52.607 | RMT | 52.61 | -0.003 | 100% | 2588.412 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100% | 675.27 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8 | RMT | 8 | 0 | 100% | 393.6 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0.002 | 99.92% | 459.33 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100% | 374.412 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 11.397 | SQM | 11.4 | -0.003 | 100% | 2086.2 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 25.3 | RMT | 25.3 | 0 | 100% | 1244.76 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100% | 4973.94 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100% | 2955 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.763 | SQM | 3.76 | 0.003 | 99.92% | 688.08 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.197 | SQM | 18.2 | -0.003 | 100% | 3330.6 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.565 | SQM | 7.57 | -0.005 | 100.1% | 1385.31 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 36.602 | SQM | 36.6 | 0.002 | 99.99% | 6697.8 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 26.7 | RMT | 26.7 | 0 | 100% | 147784.5 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100% | 225 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
CHIRANJEEVI | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 3 | NOS | 3 | 0 | 100% | 2250 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 261 | CFT | 261 | 0 | 100% | 2303.586 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 261 | SFT | 261 | 0 | 100% | 6198.75 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
INDAL SAHNI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 35.36 | RMT | 35.36 | 0 | 100% | 1159.808 |  | 0
INDAL SAHNI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 3.672 | SQM | 3.67 | 0.002 | 99.95% | 1106.1086 |  | 0
PRAKASH JANA | LAYING FLOOR PROTECTOR SHEET & TILE CLEANING | 341 | 1.5 | 1182 | SFT | 0 | 1182 | 0% | 0 |  | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 95.756 | SQM | 95.76 | -0.004 | 100% | 4638.4229 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 95.756 | SQM | 95.76 | -0.004 | 100% | 1546.524 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 95.756 | SQM | 95.76 | -0.004 | 100% | 2576.9016 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 15.263 | SQM | 15.26 | 0.003 | 99.98% | 246.449 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 15.263 | SQM | 15.26 | 0.003 | 99.98% | 492.7759 |  | 0
INDAL SAHNI | CUSTOMIZATION TOILET TILE WORK | 436 | 1091 | 3.474 | SQM | 3.47 | 0.004 | 99.88% | 3785.77 |  | 0
INDAL SAHNI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 233.916 | 18.839 | SQM | 18.84 | -0.001 | 100% | 4406.9774 |  | 0
YELLAPPA C | CUSTOMIZATION SHUTTERING OF TERRACE COLUMN, BEAM AND SLAB, LINTEL AND CHAJJA | 458 | 301.392 | 52.1182 | SQM | 52.12 | -0.0018 | 100% | 15708.551 |  | 0
CHIRANJEEVI | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 33.5 | SQM | 0 | 33.5 | 0% | 0 |  | 0
CHIRANJEEVI | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 64.05 | SQM | 0 | 64.05 | 0% | 0 |  | 0
CHIRANJEEVI | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 39.24 | SQM | 39.24 | 0 | 100% | 7602.8285 |  | 0
350

## V33
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 | AAIDHUL MIAH | 350
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100% | 13191.8976 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0.002 | 99.97% | 1221.3936 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100% | 4925.088 |  | 0 | PRAKASH H N | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100% | 3949.98 |  | 0 | RUPAK NAYAK | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | -0.004 | 100.1% | 3470 |  | 0 | SARAT BARMAN | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | -0.004 | 100.1% | 2890 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | -0.004 | 100% | 9190 |  | 0 | SHOKAT | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100% | 2100 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0 | SK ANSAR HOSSIAN | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100% | 3850 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 5600 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100% | 10500 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0 | YELLAPPA C | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0.0047 | 99.99% | 19144.4198 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100% | 15578.9525 |  | 0 | TOTAL | 350
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100% | 46305.8669 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100% | 4813.2302 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0.002 | 99.98% | 2225.25 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0.002 | 99.92% | 3660 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100% | 1485 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100% | 7700 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100% | 15033.433 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100% | 39985.6766 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100% | 5087.497 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0.003 | 99.9% | 5880 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100% | 3082.5 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | -0.003 | 100.3% | 1410 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100% | 700 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0.03 | 0 | 100% | 210 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100% | 8176.765 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100% | 828.828 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0.002 | 99.92% | 542.25 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100% | 22453.9193 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100% | 25809.7039 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0% | 0 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0% | 0 |  | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0% | 0 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0.002 | 100% | 2224.4148 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100% | 27220.972 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100% | 40362.4166 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0.002 | 100% | 10409.5415 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | -0.003 | 100% | 30850.808 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100% | 27543.7843 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100% | 4677.9268 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 110 | 43.39 | 71.71% | 21312.72 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 136.228 | SQM | 136.23 | -0.002 | 100% | 29327.5944 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 45.157 | SQM | 45.16 | -0.003 | 100% | 9722.0448 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 31.548 | SQM | 31.55 | -0.002 | 100% | 3396.042 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 86.017 | SQM | 86.02 | -0.003 | 100% | 18518.3856 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 31.548 | SQM | 31.55 | -0.002 | 100% | 3396.042 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 18 | NOS | 18 | 0 | 100% | 3600 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 13.885 | SQM | 13.89 | -0.005 | 100% | 2990.2392 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 19.932 | SQM | 19.93 | 0.002 | 99.99% | 1930.8184 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 407.375 | SQM | 407.38 | -0.005 | 100% | 6579.187 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 407.375 | SQM | 407.38 | -0.005 | 100% | 13155.115 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0.004 | 100% | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0.003 | 100% | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0.001 | 100% | 15634.9791 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.407 | SQM | 19.41 | -0.003 | 100% | 5850.0187 |  | 0
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100% | 1350 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100% | 5250 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 44.402 | RMT | 44.4 | 0.002 | 100% | 3640.8 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 102.456 | RMT | 102.46 | -0.004 | 100% | 3360.688 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 25.18 | RMT | 25.18 | 0 | 100% | 3303.616 |  | 0
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 54.039 | SQM | 54.04 | -0.001 | 100% | 9889.32 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 50.02 | RMT | 50.02 | 0 | 100% | 2460.984 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 45.132 | SQM | 45.13 | 0.002 | 100% | 8258.79 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 39.23 | RMT | 39.23 | 0 | 100% | 1930.116 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100% | 675.27 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8 | RMT | 8 | 0 | 100% | 393.6 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0.002 | 99.92% | 459.33 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100% | 374.412 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 9.872 | SQM | 9.87 | 0.002 | 99.98% | 1806.21 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 20.402 | RMT | 20.4 | 0.002 | 99.99% | 1003.68 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100% | 4973.94 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1368 | SFT | 1368 | 0 | 100% | 3420 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.451 | SQM | 3.45 | 0.001 | 99.97% | 631.35 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.528 | SQM | 17.53 | -0.002 | 100% | 3207.99 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 11.13 | SQM | 11.13 | 0 | 100% | 2036.79 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 42.789 | SQM | 42.79 | -0.001 | 100% | 7830.57 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 144.33 | SQM | 144.33 | 0 | 100% | 9320.8314 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100% | 17500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 34.29 | RMT | 27.04 | 7.25 | 78.86% | 149666.4 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100% | 225 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 195 | CFT | 195 | 0 | 100% | 1721.07 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 195 | SFT | 195 | 0 | 100% | 4631.25 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
INDAL SAHNI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 42.25 | RMT | 42.25 | 0 | 100% | 1385.8 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 157 | 410 | SFT | 410 | 0 | 100% | 64370 |  | 0
INDAL SAHNI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 4.563 | SQM | 4.56 | 0.003 | 99.93% | 1374.3475 |  | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
INDAL SAHNI | CUSTOMIZATION TOILET TILE WORK | 436 | 1101 | 3.541 | SQM | 3.54 | 0.001 | 99.97% | 3897.54 |  | 0
INDAL SAHNI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 228.35 | 22.387 | SQM | 22.39 | -0.003 | 100% | 5112.7565 |  | 0
350

## V34
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22.1959 | 91.86 | SQM | 91.86 | 0 | 100 | 2038.9154 | 0 | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100 | 3949.98 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100 | 2100 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100 | 5600 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100 | 10500 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100 | 4813.2302 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100 | 5087.497 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100 | 1750 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0.03 | 0 | 100 | 210 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100 | 828.828 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100 | 22453.9193 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100 | 2101.824 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100 | 2102.48 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0 | 100 | 2224.4148 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100 | 29719.6193 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 122.867 | SQM | 122.87 | 0 | 100 | 26451.4536 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 35.516 | SQM | 35.52 | 0 | 100 | 7646.7456 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 26.031 | SQM | 26.03 | 0 | 100 | 2801.8692 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 87.351 | SQM | 87.35 | 0 | 100 | 18804.708 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 26.031 | SQM | 26.03 | 0 | 100 | 2801.8692 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 15 | NOS | 15 | 0 | 100 | 3000 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100 | 4299.1416 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100 | 6003.6536 | 0 | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0 | 100 | 5579.825 | 0 | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 20.21 | SQM | 20.21 | 0 | 100
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 12 | NOS | 12 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 49.757 | RMT | 49.76 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 113.757 | RMT | 113.76 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.259 | RMT | 23.26 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 49.627 | SQM | 40.63 | 9 | 81.865
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 45.016 | RMT | 38.02 | 7 | 84.45
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 48.346 | SQM | 40.35 | 8 | 83.453
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 47.32 | RMT | 40.32 | 7 | 85.207
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 4.49 | SQM | 3.49 | 1 | 77.728
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 6.1 | RMT | 0 | 6.1 | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 0 | 2.51 | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 0 | 7.61 | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 10.585 | SQM | 10.59 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 22.792 | RMT | 22.79 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 17.623 | SQM | 17.62 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1122.3 | SFT | 1122.3 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.027 | SQM | 3.03 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 15.292 | SQM | 12.29 | 3 | 80.382
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 15.37 | SQM | 12.37 | 3 | 80.481
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 57.343 | SQM | 48.34 | 9 | 84.305
TANMAY | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 115.56 | SQM | 115.56 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.165 | RMT | 25.17 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 290 | 33.5 | LUMP SUM | 33.5 | 0 | 100
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0

## V35
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 60 | SQM | 60 | 0 | 100 | 2580 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100 | 2500 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 23.31 | SQM | 23.31 | 0 | 100 | 1002.33 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 78.8 | SQM | 78.8 | 0 | 100 | 3388.4 | 0 | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
NARESH PURTY | FOOTING REINFORCEMENT | 23 | 6800 | 0.4 | MT | 0.4 | 0 | 100 | 2720 | 0 | 0
NARESH PURTY | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.45 | MT | 0.45 | 0 | 100 | 3060 | 0 | 0
NARESH PURTY | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.6 | MT | 0.6 | 0 | 100 | 4080 | 0 | 0
NARESH PURTY | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.5 | MT | 0.5 | 0 | 100 | 3400 | 0 | 0
NARESH PURTY | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 1.45 | MT | 1.45 | 0 | 100 | 9860 | 0 | 0
NARESH PURTY | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 6800 | 0.17 | MT | 0.17 | 0 | 100 | 1156 | 0 | 0
NARESH PURTY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 6800 | 0.1 | MT | 0.1 | 0 | 100 | 680 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0 | 0 | 0 | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0.63 | 0 | 100 | 945 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
NARESH PURTY | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 6800 | 0.55 | MT | 0.55 | 0 | 100 | 3740 | 0 | 0
NARESH PURTY | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 6800 | 1.2 | MT | 1.2 | 0 | 100 | 8160 | 0 | 0
NARESH PURTY | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 6800 | 0.17 | MT | 0.17 | 0 | 100 | 1156 | 0 | 0
NARESH PURTY | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 6800 | 0.15 | MT | 0.15 | 0 | 100 | 1020 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.5 | 0 | 0 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0.7 | 0 | 100 | 1050 | 0 | 0
NARESH PURTY | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 6800 | 0.15 | MT | 0.15 | 0 | 100 | 1020 | 0 | 0
NARESH PURTY | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 6800 | 0.2 | MT | 0.2 | 0 | 100 | 1360 | 0 | 0
NARESH PURTY | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 6800 | 0.02 | MT | 0.02 | 0 | 100 | 136 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 21.68 | 6.45 | 77.067 | 6534.1786 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.46 | 0 | 0 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0 | 0 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 13.842 | SQM | 0.66 | 13.18 | 4.768 | 106.5636 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 287.2 | SQM | 287.2 | 0 | 100 | 10052 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 371.61 | SQM | 371.61 | 0 | 100 | 3000.0075 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
SALLAUDDIN ANSARI | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 0.792 | LUMP SUM | 0.79 | 0 | 100 | 9480 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 0.208 | LUMP SUM | 0.21 | 0 | 100 | 2520 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 91.89 | 46.89 | 66.211 | 17803.8713 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 19.97 | SQM | 19.97 | 0 | 100 | 4299.1416 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 61.97 | SQM | 61.97 | 0 | 100 | 6003.6536 | 0 | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 183.89 | SQM | 183.89 | 0 | 100 | 8907.2638 | 0 | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 110.81 | SQM | 110.81 | 0 | 100 | 5367.4148 | 0 | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 128.79 | SQM | 105.43 | 23.36 | 81.862
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.5 | 202.03 | SQM | 202.03 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.5 | 72.04 | SQM | 72.04 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.5 | 221.75 | SQM | 221.75 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.5 | 64.644 | SQM | 64.64 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.5 | 39.21 | SQM | 39.21 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.5 | 12.3 | SQM | 12.3 | 0 | 100
SANTHOSH KUMAR K | STAIRCASE GRANITE | 215 | 301.392 | 9.989 | SQM | 9.99 | 0 | 100
SANTHOSH KUMAR K | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100
SANTHOSH KUMAR K | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 24.085 | RMT | 24.09 | 0 | 100
SANTHOSH KUMAR K | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 56.71 | RMT | 56.71 | 0 | 100
SANTHOSH KUMAR K | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 10.8232 | RMT | 10.82 | 0 | 100
SANTHOSH KUMAR K | GROUND FLOOR TILING | 224 | 172.224 | 13.03 | SQM | 13.03 | 0 | 100
SANTHOSH KUMAR K | GROUND FLOOR SKIRTING | 225 | 49.2 | 13.51 | RMT | 13.51 | 0 | 100
SANTHOSH KUMAR K | FIRST FLOOR TILING | 226 | 172.224 | 38.113 | SQM | 38.11 | 0 | 100
SANTHOSH KUMAR K | FIRST FLOOR SKIRTING | 227 | 49.2 | 30.49 | RMT | 30.49 | 0 | 100
SANTHOSH KUMAR K | TERRACE FLOOR TILING | 228 | 172.224 | 4.18 | SQM | 4.18 | 0 | 100
SANTHOSH KUMAR K | TERRACE FLOOR SKIRTING | 229 | 49.2 | 7.06 | RMT | 7.06 | 0 | 100
SANTHOSH KUMAR K | GROUND FLOOR TOILET FLOOR TILING | 237 | 172.224 | 3.74 | SQM | 3.74 | 0 | 100
SANTHOSH KUMAR K | GROUND FLOOR TOILET WALL TILING | 238 | 430.56 | 10.43 | SQM | 10.43 | 0 | 100
SANTHOSH KUMAR K | FIRST FLOOR TOILET FLOOR TILING | 239 | 172.224 | 8.16 | SQM | 8.16 | 0 | 100
SANTHOSH KUMAR K | FIRST FLOOR TOILET WALL TILING | 240 | 430.56 | 57.4 | SQM | 57.4 | 0 | 100
SALLAUDDIN ANSARI | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 0.45 | LUMP SUM | 0.45 | 0 | 100
H R ENGINEERS | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 0.55 | LUMP SUM | 0.55 | 0 | 100
H R ENGINEERS | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
ANU P | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
ANU P | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 1 | 0 | 100
ANU P | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 0.24167 | LUMP SUM | 0 | 0.24 | 0
ANU P | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 0.75833 | LUMP SUM | 0.76 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 60 | RFT | 60 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 10 | RFT | 10 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 106 | SFT | 106 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 10 | RFT | 10 | 0 | 100
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 171 | CFT | 171 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 171 | SFT | 171 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
RUPAK NAYAK | GROUND FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 379 | 16.146 | 183.89 | SQM | 183.89 | 0 | 100
RUPAK NAYAK | FIRST FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 380 | 16.146 | 110.81 | SQM | 110.81 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 381 | 16.146 | 128.79 | SQM | 128.79 | 0 | 100

## V36
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 30.86 | SQM | 30.86 | 0 | 100 | 6643.5408 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 30.86 | SQM | 30.86 | 0 | 100 | 6643.5408 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 14.313 | SQM | 14.31 | 0 | 100 | 1540.3284 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 14.313 | SQM | 14.31 | 0 | 100 | 1540.3284 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 2 | NOS | 2 | 0 | 100 | 400 | 0 | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 138.88 | SQM | 138.88 | 0 | 100 | 8968.8704 | 0 | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100 | 600 | 0 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 31.36 | RMT | 31.36 | 0 | 100 | 173577.6 | 0 | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100 | 1350 | 0 | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100 | 1500 | 0 | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100 | 250 | 0 | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100 | 1500 | 0 | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100 | 350 | 0 | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100 | 350 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 48 | 62.37 | RFT | 62.37 | 0 | 100 | 2993.76 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 89 | 18.67 | RFT | 18.67 | 0 | 100 | 1661.63 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 42 | 58 | SFT | 58 | 0 | 100 | 2436 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 250 | 11 | RFT | 11 | 0 | 100 | 2750 | 0 | 0
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 207 | CFT | 207 | 0 | 100 | 1826.982 | 0 | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100 | 350 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100 | 400 | 0 | 0
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 207 | SFT | 207 | 0 | 100 | 4916.25 | 0 | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100 | 800 | 0 | 0
RUPAK NAYAK | EXTERNAL WALL & CHEJJA ONE COAT PRIMER, TWO COATS EXTERNAL EMULSION PAINT REWORK | 382 | 48.438 | 606.58 | SQM | 606.58 | 0 | 100 | 29381.522 | 0 | 0
RUPAK NAYAK | ALL FLOOR INTERNAL WALL TWO COATS PUTTY, ONE COAT PRIMER, TWO COAT EMULSION PAINT REWORK | 383 | 75.325 | 611.94 | SQM | 611.94 | 0 | 100 | 46094.3805 | 0 | 0
SHOKAT | TERRACE & SHR WATERPROOF COATING REWORK | 385 | 215.28 | 95.461 | SQM | 95.46 | 0 | 100 | 20550.6288 | 0 | 0
SHOKAT | TERRACE & SHR SCREED CONCRTE CHIPPING AND DEBRISH REMOVAL REWORK | 386 | 107.64 | 75.481 | SQM | 75.48 | 0 | 100 | 8124.6672 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V37
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 118.09 | SQM | 118.09 | 0 | 100 | 7626.2522 | 0 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 8000 | 1 | LUMP SUM | 1 | 0 | 100 | 8000 | 0 | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 1 | 0 | 100 | 10000 | 0 | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100 | 14832 | 0 | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100 | 1500 | 0 | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100 | 250 | 0 | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100 | 1500 | 0 | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100 | 350 | 0 | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100 | 350 | 0 | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100 | 350 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100 | 400 | 0 | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100 | 800 | 0 | 0
SUBHASMITA DAS | TERRACE CONCRETE CHIPPING | 339 | 107.64 | 118.54 | SQM | 118.54 | 0 | 100 | 12759.6456 | 0 | 0
RUPAK NAYAK | EXTERNAL WALL & CHEJJA ONE COAT PRIMER, TWO COATS EXTERNAL EMULSION PAINT REWORK | 382 | 48.438 | 686.99 | SQM | 686.99 | 0 | 100 | 33276.4216 | 0 | 0
RUPAK NAYAK | ALL FLOOR INTERNAL WALL TWO COATS PUTTY, ONE COAT PRIMER, TWO COAT EMULSION PAINT REWORK | 383 | 75.325 | 666.46 | SQM | 666.46 | 0 | 100 | 50201.0995 | 0 | 0
RUPAK NAYAK | CUSTOMIZATION MS STAIRCASE PAINTING AND STEP WOOD POLISHING REWORK | 387 | 23000 | 1 | LUMP SUM | 1 | 0 | 100 | 23000 | 0 | 0
ANSAR HOSSAIAN SK | TERRACE TERRACOTTA TILE REWORK | 388 | 21 | 1200 | SFT | 1200 | 0 | 100 | 25200 | 0 | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING WORK REWORK | 389 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V38
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 103.17 | SQM | 103.17 | 0 | 100 | 5571.18 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 150.56 | CUM | 150.56 | 0 | 100 | 31870.5408 | 0 | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 46.12 | SQM | 46.12 | 0 | 100 | 1014.64 | 0 | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 86.12 | SQM | 86.12 | 0 | 100 | 3703.16 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 116.13 | CUM | 116.13 | 0 | 100 | 16388.2656 | 0 | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100 | 2500 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 45.09 | SQM | 45.09 | 0 | 100 | 1938.87 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 56.74 | CUM | 56.74 | 0 | 100 | 8007.1488 | 0 | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 103.17 | SQM | 103.17 | 0 | 100 | 2269.74 | 0 | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 130.85 | SQM | 130.85 | 0 | 100 | 5626.55 | 0 | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 7.53 | CUM | 7.53 | 0 | 100 | 7530 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.994 | CUM | 3.99 | 0 | 100 | 3990 | 0 | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 10.32 | CUM | 10.32 | 0 | 100 | 10320 | 0 | 0
BISWO RANJAN ROUT | FOOTING REINFORCEMENT | 23 | 6800 | 0.8 | MT | 0.8 | 0 | 100 | 5440 | 0 | 0
BISWO RANJAN ROUT | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.7 | MT | 0.7 | 0 | 100 | 4760 | 0 | 0
BISWO RANJAN ROUT | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.95 | MT | 0.95 | 0 | 100 | 6460 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.8 | MT | 0.8 | 0 | 100 | 5440 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 1.01 | MT | 1.01 | 0 | 100 | 6868 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.59 | MT | 1.59 | 0 | 100 | 11925 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.16 | MT | 0.16 | 0 | 100 | 1200 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 65.78 | SQM | 65.78 | 0 | 100 | 19825.5658 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 37.11 | SQM | 37.11 | 0 | 100 | 11184.6571 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 79.884 | SQM | 79.88 | 0 | 100 | 24075.193 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 67.86 | SQM | 67.86 | 0 | 100 | 20452.4611 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 218.06 | SQM | 218.06 | 0 | 100 | 65721.5395 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.793 | SQM | 0 | 12.79 | 0 | 0 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 11.65 | SQM | 0 | 11.65 | 0 | 0 | 0 | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 17.19 | CUM | 17.19 | 0 | 100 | 3867.75 | 0 | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 2.18 | CUM | 2.18 | 0 | 100 | 3270 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 5.991 | CUM | 5.99 | 0 | 100 | 5391 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.98 | CUM | 3.98 | 0 | 100 | 7960 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 23.5 | CUM | 23.5 | 0 | 100 | 5287.5 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.673 | CUM | 1.67 | 0 | 100 | 3340 | 0 | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100 | 1440 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.8 | MT | 0.8 | 0 | 100 | 6000 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.85 | MT | 1.85 | 0 | 100 | 13875 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 56.55 | SQM | 56.55 | 0 | 100 | 17043.7176 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 188.59 | SQM | 174.5 | 14.09 | 92.527 | 52592.904 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.793 | SQM | 0 | 12.79 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 14.11 | SQM | 0 | 14.11 | 0 | 0 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.33 | CUM | 3.33 | 0 | 100 | 6660 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 19.19 | CUM | 19.19 | 0 | 100 | 4317.75 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.673 | CUM | 1.67 | 0 | 100 | 3340 | 0 | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.57 | CUM | 1.57 | 0 | 100 | 2355 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.3 | MT | 0.3 | 0 | 100 | 2250 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100 | 150 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 26.6 | SQM | 0 | 26.6 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.815 | SQM | 0 | 1.82 | 0 | 0 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 3.07 | CUM | 3.07 | 0 | 100 | 690.75 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.17 | CUM | 0.17 | 0 | 100 | 255 | 0 | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 53 | NOS | 53 | 0 | 100 | 2650 | 0 | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 146.37 | SQM | 146.37 | 0 | 100 | 28359.4802 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 185.55 | SQM | 185.55 | 0 | 100 | 35950.6836 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 72.29 | SQM | 72.29 | 0 | 100 | 14006.3321 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 49.17 | RMT | 0 | 49.17 | 0 | 0 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 33.82 | RMT | 0 | 33.82 | 0 | 0 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 19.045 | SQM | 19.05 | 0 | 100 | 3690.9756 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 406 | SQM | 406 | 0 | 100 | 14210 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 483.1 | SQM | 483.1 | 0 | 100 | 3900.0663 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 94.21 | SQM | 94.21 | 0 | 100 | 13182.9937 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 266.24 | SQM | 266.24 | 0 | 100 | 37255.4957 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 261.11 | SQM | 261.11 | 0 | 100 | 50590.5847 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14000 | 1 | LUMP SUM | 1 | 0 | 100 | 14000 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 92.25 | SQM | 92.25 | 0 | 100 | 12908.727 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 364.2 | SQM | 210.72 | 153.48 | 57.858 | 29486.471 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 163.72 | SQM | 163.72 | 0 | 100 | 31721.0774 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 13.2 | SQM | 13.2 | 0 | 100 | 1847.1024 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.271 | SQM | 0 | 37.27 | 0 | 0 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 163.58 | SQM | 106.94 | 56.64 | 65.376 | 20719.8389 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 254.03 | 246.05 | SQM | 246.05 | 0 | 100 | 62504.0815 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 254.03 | 25.443 | SQM | 25.44 | 0 | 100 | 6462.5232 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 190.52 | 19.11 | SQM | 19.11 | 0 | 100 | 3640.8372 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 254.03 | 106.643 | SQM | 106.64 | 0 | 100 | 27089.7592 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 254.03 | 149.94 | SQM | 149.94 | 0 | 100
SHOKAT | BORE PACKING ALL FLOOR | 180 | 295 | 10 | NOS | 10 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 237.55 | SQM | 237.55 | 0 | 100
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 143.3 | SQM | 143.3 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 150.93 | SQM | 150.93 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.5 | 266.24 | SQM | 266.24 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.5 | 94.21 | SQM | 94.21 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.5 | 364.2 | SQM | 364.2 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.5 | 92.25 | SQM | 92.25 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.5 | 37.27 | SQM | 37.27 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.5 | 13.2 | SQM | 13.2 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 19.98 | SQM | 0 | 19.98 | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 5 | NOS | 0 | 5 | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 24 | NOS | 24 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.2 | RMT | 0 | 41.2 | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.8 | RMT | 0 | 98.8 | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 32.22 | RMT | 0 | 32.22 | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 5 | NOS | 5 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 172.224 | 84.56 | SQM | 84.1 | 0.46 | 99.456
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 62.78 | RMT | 62.28 | 0.5 | 99.204
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 172.224 | 84.38 | SQM | 84.38 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 96.78 | RMT | 96.78 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 172.22 | 3.698 | SQM | 3.7 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.86 | RMT | 5.86 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 7.325 | SQM | 7.33 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 12.804 | RMT | 12.8 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 25.719 | SQM | 25.72 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 41.463 | RMT | 41.46 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 172.224 | 33.637 | SQM | 33.64 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 236 | 2.5 | 1843 | SFT | 1843 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 172.224 | 7.48 | SQM | 7.48 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 193.752 | 34.903 | SQM | 34.9 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 172.224 | 11.93 | SQM | 11.93 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 193.752 | 52.68 | SQM | 52.68 | 0 | 100
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 327.466 | SQM | 327.47 | 0 | 100
H R ENGINEERS | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 16000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 0.5 | LUMP SUM | 0 | 0.5 | 0
BICHITRA CHOUDHURI | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 0.5 | LUMP SUM | 0.5 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 8000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 18.87 | RMT | 0 | 18.87 | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 137 | RFT | 137 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 20 | RFT | 20 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 228 | SFT | 228 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 363 | 16.5 | RFT | 16.5 | 0 | 100
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 258 | CFT | 258 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 216 | SFT | 216 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | MS STAIRCASE STEPS RUBBER WOOD LAYING | 336 | 45500 | 1 | LUMP SUM | 0 | 1 | 0
KHALIL MIAH | LAYING FLOOR PROTECTOR SHEET & TILE CLEANING | 341 | 1.5 | 1843 | SFT | 1843 | 0 | 100
SAVITA DEVI | MS STAIRCASE WORK | 346 | 50000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION MS STAIRCASE PAINTING AND STEP WOOD POLISHING WORK | 424 | 30000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 15700 | 1 | LUMP SUM | 1 | 0 | 100
CHIRANJEEVI | CUSTOMIZATION WORK/THE RATE IS INCLUSIVE OF MASONRY WORK/PLASTERING WORK/ELEVATION WORK | 462 | 83784 | 1 | LUMP SUM | 1 | 0 | 100
KRISHNAKUMAR SAHANI | CUSTOMIZATION GRANITE WORK | 463 | 246 | 28.1 | RMT | 28.1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION CAR PARKING TAP POINT WORK | 465 | 750 | 1 | NOS | 1 | 0 | 100

## V39
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 53.8 | SQM | 53.8 | 0 | 100 | 2313.4 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100 | 2500 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 35.66 | SQM | 35.66 | 0 | 100 | 1533.38 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100 | 3949.98 | 0 | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
RAKESHA PALAI | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100 | 2100 | 0 | 0
RAKESHA PALAI | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
RAKESHA PALAI | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.35 | MT | 0.35 | 0 | 100 | 2380 | 0 | 0
RAKESHA PALAI | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 1.5 | MT | 1.5 | 0 | 100 | 10200 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 6800 | 0.2 | MT | 0.2 | 0 | 100 | 1360 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 6800 | 0.15 | MT | 0.15 | 0 | 100 | 1020 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100 | 4813.2302 | 0 | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
BISWO RANJAN ROUT | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 6.18 | 10.7 | 36.631 | 1862.6026 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100 | 1875 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0 | 0 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 113.07 | 2.82 | 97.57 | 21907.5386 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 63.82 | 3.49 | 94.821 | 12365.2526 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32 | 0.04 | 99.875 | 2099.2 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32 | 0.05 | 99.844 | 2099.2 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 5.258 | SQM | 1.14 | 4.12 | 21.681 | 184.0644 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 307 | SQM | 307 | 0 | 100 | 10745 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 450 | SQM | 450 | 0 | 100 | 3632.85 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 56.37 | 97.02 | 36.749 | 10921.8002 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 254.03 | 183.48 | SQM | 183.48 | 0 | 100 | 46609.4244 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 254.03 | 17.242 | SQM | 17.24 | 0 | 100 | 4379.4772 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 190.52 | 15.75 | SQM | 15.75 | 0 | 100 | 3000.69 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 254.03 | 78.44 | SQM | 78.44 | 0 | 100
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 254.03 | 123.624 | SQM | 123.62 | 0 | 100
SHOKAT | BORE PACKING ALL FLOOR | 180 | 295 | 8 | NOS | 8 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.29 | 25.09 | SQM | 25.09 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 167.69 | SQM | 167.69 | 0 | 100
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 101.64 | SQM | 101.64 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 137.5 | SQM | 137.5 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.5 | 180.53 | SQM | 180.53 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 82.42 | SQM | 82.42 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.5 | 206.47 | SQM | 206.47 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.5 | 70.572 | SQM | 70.57 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.5 | 28.43 | SQM | 28.43 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.5 | 8.61 | SQM | 8.61 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 0 | 21.28 | 0
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 6 | 10 | 37.5
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 0 | 41.17 | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 0 | 111.25 | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 0 | 27.3 | 0
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 236.81 | 58.71 | SQM | 0 | 58.71 | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 74 | RMT | 0 | 74 | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 236.81 | 59.742 | SQM | 0 | 59.74 | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 81.73 | RMT | 0 | 81.73 | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 236.81 | 3.69 | SQM | 0 | 3.69 | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8 | RMT | 0 | 8 | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.98 | SQM | 2.98 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 11.16 | SQM | 11.16 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 25.3 | RMT | 25.3 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.1 | SQM | 0 | 4.1 | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 376.75 | 22.84 | SQM | 0 | 22.84 | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.17 | SQM | 0 | 8.17 | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 376.75 | 46.15 | SQM | 0 | 46.15 | 0
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 225.15 | SQM | 225.15 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
BICHITRA CHOUDHURI | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 31.1 | RMT | 31.1 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 48 | 77.33 | RFT | 77.33 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 89 | 12 | RFT | 12 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 42 | 48.75 | SFT | 48.75 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 250 | 14.917 | RFT | 14.92 | 0 | 100
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 250 | CFT | 250 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 250 | SFT | 250 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
INDAL SAHNI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 35.19 | RMT | 0 | 35.19 | 0
INDAL SAHNI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 3.902 | SQM | 0 | 3.9 | 0
KHALIL MIAH | LAYING FLOOR PROTECTOR SHEET & TILE CLEANING | 341 | 1.5 | 1182 | SFT | 1182 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION TAP POINT WORK | 423 | 750 | 2 | NOS | 2 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 15650 | 1 | LUMP SUM | 1 | 0 | 100
CHIRANJEEVI | CUSTOMIZATION WORK/THE RATE IS INCLUSIVE OF MASONRY WORK/PLASTERING WORK/ELEVATION WORK | 462 | 32005 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION INTERNAL WALL THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERIOR EMULSION PAINTING WORK | 466 | 91.494 | 60.944 | SQM | 60.94 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION EXTERNAL WALL ONE COAT PRIMER, TWO COATS EXTERIOR EMULSION PAINTING WORK | 467 | 48.438 | 36.511 | SQM | 36.51 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 468 | 750 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION BATHTUB CONNECTION POINT WORK | 469 | 750 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WATER SOFTENER POINT WORK | 470 | 750 | 1 | NOS | 1 | 0 | 100

## V40
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100 | 2250 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100 | 6000 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100 | 11250 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | 0 | 100 | 525 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100 | 4813.2302 | 0 | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 63 | SFT | 63 | 0 | 100 | 1764 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 8.35 | 3.98 | 67.745 | 2516.6232 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100 | 5087.497 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100 | 1875 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 0 | 27.13 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100 | 828.828 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 94.61 | 21.28 | 81.64 | 18330.8767 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 119.38 | 13.83 | 89.617 | 23130.1138 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 63.82 | 3.49 | 94.821 | 12365.2526 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0 | 0 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0 | 0 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 5.258 | SQM | 0 | 5.26 | 0 | 0 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 307 | SQM | 0 | 307 | 0 | 0 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 450 | SQM | 0 | 450 | 0 | 0 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 0 | 71.63 | 0 | 0 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 0 | 194.53 | 0 | 0 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 20 | 188.32 | 9.601 | 3875.04 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 0 | 74.39 | 0 | 0 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 0 | 220.47 | 0 | 0 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 0 | 142.16 | 0 | 0 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 0 | 11.61 | 0 | 0 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 0 | 33.43 | 0 | 0 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 0 | 153.39 | 0 | 0 | 0 | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 54.705 | SQM | 46.22 | 8.49 | 84.49 | 19900.4832 | 0 | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 85.145 | SQM | 85.15 | 0 | 100 | 36662.184 | 0 | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 11.334 | SQM | 7.9 | 3.43 | 69.702 | 1700.712 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 37.142 | SQM | 21.93 | 15.22 | 59.03 | 4721.0904 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 21 | SQM | 19 | 2 | 90.476 | 3800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100 | 5399.2224 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100 | 2628.3544 | 0 | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100 | 6570.143 | 0 | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100 | 13137.0314 | 0 | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100 | 937.669 | 0 | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100 | 27233.7811 | 0 | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 15.705 | SQM | 15.71 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 20.15 | RMT | 20.15 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 56.939 | SQM | 56.94 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.43 | RMT | 59.43 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 51.289 | SQM | 51.29 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 69.16 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.801 | SQM | 2.8 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.6 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 7.41 | SQM | 7.41 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 11.15 | RMT | 11.15 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 5.573 | SQM | 5.57 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 25.4 | SQM | 25.4 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 9.711 | SQM | 9.71 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 46.79 | SQM | 46.79 | 0 | 100
PRAKASH JANA | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 208.534 | SQM | 208.53 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 31.25 | RMT | 31.25 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
CHIRANJEEVI | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 1 | NOS | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 395 | CFT | 395 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 395 | SFT | 395 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
INDAL SAHNI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 31.68 | RMT | 31.68 | 0 | 100
INDAL SAHNI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 3.34 | SQM | 3.34 | 0 | 100
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0

## V41
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 10.81 | 0 | 100 | 1525.5072 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100 | 2250 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100 | 6000 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100 | 11250 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100 | 4813.2302 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100 | 5087.497 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100 | 1875 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100 | 828.828 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100 | 22453.9193 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100 | 2101.824 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100 | 2102.48 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0 | 100 | 2224.4148 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12500 | 1 | LUMP SUM | 1 | 0 | 100 | 12500 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100 | 29719.6193 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 50.865 | SQM | 50.87 | 0 | 100 | 21902.5872 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 85.145 | SQM | 85.15 | 0 | 100 | 36662.184 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 22.29 | SQM | 22.29 | 0 | 100 | 4798.5912 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 35.405 | SQM | 35.41 | 0 | 100 | 7623.0648 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 19 | SQM | 19 | 0 | 100 | 3800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100 | 5399.2224 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100 | 2628.3544 | 0 | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 19.048 | SQM | 19.05 | 0 | 100
ANSAR HOSSAIAN SK | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 14 | 0 | 100
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0 | 100
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 25.568 | RMT | 25.57 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 55.989 | SQM | 55.99 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.761 | RMT | 48.76 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 53.82 | SQM | 53.82 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 52.61 | RMT | 52.61 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8 | RMT | 8 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 11.397 | SQM | 11.4 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 25.3 | RMT | 25.3 | 0 | 100
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.763 | SQM | 3.76 | 0 | 99.92
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.11 | SQM | 18.11 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.565 | SQM | 7.57 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 36.28 | SQM | 36.28 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 132.064 | SQM | 132.06 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.61 | RMT | 25.61 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 0 | 3 | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | ENTRANCE STEPS SS RAILING | 268 | 5535 | 1.0057 | RMT | 1.01 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 390 | CFT | 390 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 312 | SFT | 312 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
ANSAR HOSSAIAN SK | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 33.5 | RMT | 33.5 | 0 | 100
YELLAPPA C | ADDITIONAL SHUTTERING WORK CHAIN LINK STAIRCASE | 302 | 301.392 | 4.7489 | SFT | 4.75 | 0 | 100
YELLAPPA C | ADDITIONAL SHUTTERING WORK OF LINTEL AND CHEJJA | 308 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
ANSAR HOSSAIAN SK | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 3.484 | SQM | 3.48 | 0 | 100
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100

## V43
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 58 | SQM | 58 | 0 | 100 | 2494 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100 | 2500 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 31.45 | SQM | 31.45 | 0 | 100 | 1352.35 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100 | 3949.98 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
BISWO RANJAN ROUT | FOOTING REINFORCEMENT | 23 | 6800 | 0.3 | MT | 0.3 | 0 | 100 | 2040 | 0 | 0
BISWO RANJAN ROUT | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.7 | MT | 0.7 | 0 | 100 | 4760 | 0 | 0
BISWO RANJAN ROUT | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.55 | MT | 0.55 | 0 | 100 | 3740 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.45 | MT | 0.45 | 0 | 100 | 3060 | 0 | 0
NARESH PURTY | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 1.5 | MT | 1.5 | 0 | 100 | 10200 | 0 | 0
NARESH PURTY | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 6800 | 0.2 | MT | 0.2 | 0 | 100 | 1360 | 0 | 0
NARESH PURTY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 6800 | 0.15 | MT | 0.15 | 0 | 100 | 1020 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100 | 4813.2302 | 0 | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
NARESH PURTY | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 6800 | 0.7 | MT | 0.7 | 0 | 100 | 4760 | 0 | 0
NARESH PURTY | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 6800 | 1.1 | MT | 1.1 | 0 | 100 | 7480 | 0 | 0
NARESH PURTY | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 6800 | 0.2 | MT | 0.2 | 0 | 100 | 1360 | 0 | 0
NARESH PURTY | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 6800 | 0.15 | MT | 0.15 | 0 | 100 | 1020 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100 | 5087.497 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
NARESH PURTY | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 6800 | 0.1 | MT | 0.1 | 0 | 100 | 680 | 0 | 0
NARESH PURTY | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 6800 | 0.25 | MT | 0.25 | 0 | 100 | 1700 | 0 | 0
NARESH PURTY | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 6800 | 0.03 | MT | 0.03 | 0 | 100 | 204 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100 | 828.828 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 113.07 | 2.82 | 97.57 | 21907.5386 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 63.82 | 3.49 | 94.821 | 12365.2526 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32 | 0.04 | 99.875 | 2099.2 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32 | 0.05 | 99.844 | 2099.2 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 5.258 | SQM | 5.26 | 0 | 100 | 1019.1355 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 307 | SQM | 307 | 0 | 100 | 10745 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 450 | SQM | 450 | 0 | 100 | 3632.85 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 56.34 | 97.05 | 36.729 | 10915.9877 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100 | 5399.2224 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 27.13 | SQM | 27.13 | 0 | 100 | 2628.2459 | 0 | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 174.8873 | SQM | 154.3 | 20.59 | 88.228 | 7473.9834 | 0 | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 108.8273 | SQM | 108.83 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 123.1045 | SQM | 123.1 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 182.0044 | SQM | 182 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 197 | 44.6 | 182.0044 | SQM | 182 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 71.63 | SQM | 71.63 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 201 | 44.6 | 71.63 | SQM | 71.63 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 207.9444 | SQM | 207.94 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 204 | 44.6 | 207.9444 | SQM | 207.94 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 74.392 | SQM | 74.39 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 208 | 44.6 | 74.392 | SQM | 74.39 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 33.43 | SQM | 33.43 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 211 | 44.6 | 33.43 | SQM | 33.43 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 11.61 | SQM | 11.61 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 213 | 44.6 | 11.61 | SQM | 11.61 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 19.97 | 1.31 | 93.844
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 1 | 2 | 33.333
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 0 | 111.25 | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 8.38 | 18.92 | 30.698
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | HALF ROUND AND EDGE POLISHING IN VILLA MAIN ENTRANCE GRANITE | 223 | 82 | 8.36 | RMT | 8.36 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 236.81 | 58.71 | SQM | 58.71 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.43 | RMT | 59.43 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 236.81 | 59.742 | SQM | 59.74 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 69.16 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 236.81 | 3.69 | SQM | 3.69 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.6 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 7.41 | SQM | 7.41 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 11.15 | RMT | 11.15 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 4.06 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 376.75 | 23.02 | SQM | 23.02 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 8.15 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 376.75 | 46.11 | SQM | 46.11 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 132.064 | SQM | 132.06 | 0 | 100
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 225.15 | SQM | 0 | 225.15 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 0.5 | LUMP SUM | 0 | 0.5 | 0
BICHITRA CHOUDHURI | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 0.5 | LUMP SUM | 0.5 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 28.41 | RMT | 28.41 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 12850 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | ENTRANCE STEPS SS RAILING | 268 | 5535 | 1.4934 | RMT | 1.49 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 341 | CFT | 341 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 306 | SFT | 306 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
INDAL SAHNI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 30.45 | RMT | 30.45 | 0 | 100
INDAL SAHNI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 3.992 | SQM | 3.99 | 0 | 100
CHIRANJEEVI | CHAIN LINK STAIRCASE PLASTERING | 333 | 15000 | 1 | LUMP SUM | 1 | 0 | 100
KHALIL MIAH | LAYING FLOOR PROTECTOR SHEET & TILE CLEANING | 341 | 1.5 | 1182 | SFT | 1182 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 11400 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION FLOOR ROOF CONDUIT WORK | 457 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION INTERNAL WALL THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERIOR EMULSION PAINTING WORK | 466 | 91.494 | 32.516 | SQM | 32.52 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION EXTERNAL WALL AND CHEJJA ONE COAT PRIMER, TWO COAT EXTERIOR EMULSION PAINTING WORK | 476 | 48.438 | 40.877 | SQM | 40.88 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION INTERNAL WALL THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERNAL EMULSION PAINTING WORK | 477 | 43 | 32.516 | SQM | 32.52 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | CUSTOMISATION SS RALING FOR BALCONY (INCLUDING MATERIAL) | 478 | 4954 | 5.61 | RMT | 5.61 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | CUSTOMISATION SS RALING FOR BALCONY & STAIRCASE(INCLUDING MATERIAL) | 479 | 2786.8 | 34.02 | RMT | 15.25 | 18.77 | 44.827

## V42
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100 | 3949.98 | 0 | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0 | 0 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100 | 2100 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100 | 5600 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100 | 10500 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100 | 4813.2302 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100 | 5087.497 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100 | 1750 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0.03 | 0 | 100 | 210 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100 | 828.828 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100 | 22453.9193 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100 | 2101.824 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100 | 2102.48 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0 | 100 | 2224.4148 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12500 | 1 | LUMP SUM | 1 | 0 | 100 | 12500 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100 | 29719.6193 | 0 | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 52.132 | SQM | 52.13 | 0 | 100 | 22445.0928 | 0 | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 82.955 | SQM | 82.96 | 0 | 100 | 35719.2576 | 0 | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 22.29 | SQM | 22.29 | 0 | 100 | 4798.5912 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 35.405 | SQM | 35.41 | 0 | 100 | 7623.0648 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 19 | SQM | 19 | 0 | 100 | 3800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100 | 5399.2224 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100 | 2628.3544 | 0 | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 19.048 | SQM | 0 | 19.05 | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 14 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 0 | 41.17 | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 102.54 | RMT | 0 | 102.54 | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 25.568 | RMT | 0 | 25.57 | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 5 | NOS | 4 | 1 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 53.821 | SQM | 53.82 | 0 | 99.998
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 52.607 | RMT | 52.6 | 0.01 | 99.987
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8 | RMT | 8 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 11.397 | SQM | 11.4 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 25.3 | RMT | 25.3 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.763 | SQM | 3.76 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.197 | SQM | 18.2 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.565 | SQM | 7.57 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 36.602 | SQM | 36.6 | 0 | 100
TANMAY | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 130.13 | SQM | 130.13 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 23.28 | RMT | 21.98 | 1.3 | 94.416
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 8.08 | RMT | 8.08 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | ENTRANCE STEPS SS RAILING | 268 | 5535 | 1.0057 | RMT | 1.01 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 303 | CFT | 303 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 303 | SFT | 303 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
KRISHNAKUMAR SAHANI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 35.19 | RMT | 35.19 | 0 | 100
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 146 | 277 | SFT | 277 | 0 | 100
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 290 | 29 | LUMP SUM | 29 | 0 | 100
KRISHNAKUMAR SAHANI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 3.902 | SQM | 3.9 | 0 | 100
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 73.298 | SQM | 73.3 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 73.298 | SQM | 73.3 | 0 | 100
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 73.298 | SQM | 73.3 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 24.45 | SQM | 24.45 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 24.45 | SQM | 24.45 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 432 | 750 | 1 | NOS | 1 | 0 | 100
KRISHNAKUMAR SAHANI | CUSTOMIZATION TOILET TILE WORK | 436 | 1146.52 | 3.385 | SQM | 3.39 | 0 | 100
SHOKAT | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 3.45 | SQM | 3.45 | 0 | 100
SHOKAT | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 5.835 | SQM | 5.84 | 0 | 100
KRISHNAKUMAR SAHANI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 244.5 | 18.479 | SQM | 18.47 | 0.01 | 99.951
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 5300 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100
CHIRANJEEVI | CUSTOMISATION LABOUR SUPPLY FOR BASE FLOOR EARTH DRESSING AND CONSOLIDATED WORK | 471 | 22 | 31.976 | SQM | 31.98 | 0 | 100
CHIRANJEEVI | CUSTOMISATION LABOUR FOR BLOCK WORK | 472 | 193.752 | 3.594 | SQM | 3.59 | 0 | 100
CHIRANJEEVI | CUSTOMISATION LABOUR FOR BASE FLOOR PCC WORK | 473 | 1000 | 3.1976 | CUM | 3.2 | 0 | 100
CHIRANJEEVI | CUSTOMISATION LABOUR FOR BASE FLOOR SOLING WORK | 474 | 43 | 31.976 | SQM | 31.98 | 0 | 100
CHIRANJEEVI | CUSTOMISATION LABOUR FOR EXTERNAL WALL PLASTERING WORK | 475 | 193.752 | 8.985 | SQM | 8.99 | 0 | 100
ANSAR HOSSAIAN SK | CAR PARKING BOUNDARY WALL TOP COPING GRANITE | 550 | 78 | 32.81 | RFT | 32.81 | 0 | 100

## V44
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100 | 2250 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100 | 6000 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100 | 11250 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 0 | 12.33 | 0 | 0 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 130 | 2.67 | 97.99 | 39180.96 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 0 | 12.33 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100 | 1875 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100 | 828.828 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100 | 22453.9193 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100 | 2101.824 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100 | 2102.48 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0 | 100 | 2224.4148 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100 | 29719.6193 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 50.865 | SQM | 50.87 | 0 | 100 | 21902.5872 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 85.145 | SQM | 85.15 | 0 | 100 | 36662.184 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 22.29 | SQM | 22.29 | 0 | 100 | 4798.5912 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 35.405 | SQM | 35.41 | 0 | 100 | 7623.0648 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 19 | SQM | 19 | 0 | 100 | 3800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100 | 5399.2224 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100 | 2628.3544 | 0 | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 0 | 406.82 | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 393.57 | 168.67 | 70
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 402.23 | 172.38 | 70
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 406.71 | 174.3 | 70
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 10 | 6 | 62.5
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.159 | RMT | 41.16 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 107 | RMT | 107 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | 0 | 100
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 55.826 | SQM | 50 | 5.83 | 89.564
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.148 | RMT | 45 | 3.15 | 93.462
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 52.927 | SQM | 45 | 7.93 | 85.023
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 53.838 | RMT | 50 | 3.84 | 92.871
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.6 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.973 | SQM | 0 | 2.97 | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 0 | 7.61 | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 11.148 | SQM | 11.15 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.1 | RMT | 16.1 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 0 | 27.18 | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1223 | SFT | 1223 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.75 | SQM | 3.75 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.08 | SQM | 18.08 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.44 | SQM | 7.44 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 40.646 | SQM | 40.64 | 0.01 | 99.985
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.61 | RMT | 25.61 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 0 | 1 | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0

## V45
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 2405 | 1 | LUMP SUM | 1 | 0 | 100 | 2405 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 90.98 | 0.88 | 99.04 | 3912.14 | 0 | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0 | 0 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100 | 2100 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100 | 5600 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100 | 10500 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0 | 0 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0 | 0.99 | 0 | 0 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.3 | 0.03 | 99.757 | 3707.1216 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0 | 0.94 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100 | 1750 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0 | 0 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100 | 22453.9193 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0 | 0 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0 | 0 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 0 | 206.73 | 0 | 0 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 0 | 71.63 | 0 | 0 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 0 | 194.53 | 0 | 0 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 0 | 208.32 | 0 | 0 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 0 | 74.39 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 0 | 220.47 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 0 | 142.16 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 0 | 11.61 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 0 | 33.43 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 0 | 153.39 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
MORSELIM KHAN | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 290 | SFT | 203 | 87 | 70 | 62930 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V46
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 | AAIDHUL MIAH | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 2405 | 1 | LUMP SUM | 1 | 0 | 100% | 2405 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100% | 13191.8976 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0.002 | 99.97% | 1221.3936 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100% | 4925.088 |  | 0 | PRAKASH H N | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100% | 3949.98 |  | 0 | RUPAK NAYAK | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | -0.004 | 100.1% | 3470 |  | 0 | SARAT BARMAN | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | -0.004 | 100.1% | 2890 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | -0.004 | 100% | 9190 |  | 0 | SHOKAT | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100% | 2100 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0 | SK ANSAR HOSSIAN | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100% | 3850 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 5600 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100% | 10500 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0 | YELLAPPA C | 11737.3024
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0.0047 | 99.99% | 19144.4198 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100% | 15578.9525 |  | 0 | TOTAL | 11737.3024
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100% | 46305.8669 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0% | 0 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0.002 | 99.98% | 2225.25 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0.002 | 99.92% | 3660 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0 | 0.99 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100% | 7700 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0 | 0.2 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100% | 15033.433 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100% | 39985.6766 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0.003 | 99.9% | 5880 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100% | 3082.5 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0 | 0.937 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0 | 0.1 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0 | 0.25 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0 | 0.03 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 0 | 27.13 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0 | 0.41 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 0 | 2.412 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0% | 0 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 110.1 | 5.79 | 95% | 21332.0952 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 126.55 | 6.66 | 95% | 24519.3156 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 0 | 67.31 | 0% | 0 | 90% | 11737.3024
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0% | 0 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0% | 0 |  | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0% | 0 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 0 | 206.732 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 0 | 71.63 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 0 | 194.53 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 0 | 208.32 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 0 | 74.392 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 0 | 220.467 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 0 | 142.16 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 0 | 11.61 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 0 | 33.43 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 0 | 153.39 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
MORSELIM KHAN | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 290 | SFT | 159.5 | 130.5 | 55% | 49445 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
11737.3024

## V47
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SHEKAR T | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
SHEKAR T | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
SHEKAR T | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
SHEKAR T | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
SHEKAR T | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
SHEKAR T | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
SHEKAR T | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
SHEKAR T | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
SHEKAR T | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
SHEKAR T | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0 | 0 | 0 | 0
SHEKAR T | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
SHEKAR T | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
SHEKAR T | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
SHEKAR T | FOOTING REINFORCEMENT | 23 | 7500 | 0.4 | MT | 0.4 | 0 | 100 | 3000 | 0 | 0
SHEKAR T | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SHEKAR T | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.6 | MT | 0.6 | 0 | 100 | 4500 | 0 | 0
SHEKAR T | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 0 | 1.45 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0 | 0.17 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
SHEKAR T | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
SHEKAR T | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
SHEKAR T | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
SHEKAR T | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 45.16 | 2.38 | 95 | 13610.8627 | 0 | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 146.2 | 7.69 | 95 | 44063.5104 | 0 | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.15 | 0.64 | 95 | 3661.9128 | 0 | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0 | 0 | 0 | 0
SHEKAR T | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
SHEKAR T | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
SHEKAR T | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
SHEKAR T | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.21 | 0.17 | 95 | 6420 | 0 | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 0 | 17.15 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 0 | 1.81 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0 | 0.63 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0 | 0.55 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 0 | 1.2 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0 | 0.17 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 0 | 39.44 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 0 | 128.66 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 0 | 12.78 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.5 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 0 | 2.29 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 0 | 13.96 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 0 | 1.81 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0 | 0.7 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0 | 0.2 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 0 | 28.13 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.46 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0 | 0.71 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 0 | 2.67 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0 | 0.2 | 0 | 0 | 0 | 0
SHEKAR T | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 0 | 52 | 0 | 0 | 0 | 0
SHEKAR T | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 0 | 41 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 0 | 112.22 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 0 | 133.46 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 0 | 71.27 | 0 | 0 | 0 | 0
SHEKAR T | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 0 | 32.74 | 0 | 0 | 0 | 0
SHEKAR T | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0 | 0 | 0 | 0
SHEKAR T | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0 | 0.66 | 0 | 0 | 0 | 0
SHEKAR T | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 0 | 201.86 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 0 | 72.04 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 0 | 187.02 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 0 | 201.85 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 0 | 64.64 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 0 | 206.23 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 0 | 132.03 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 0 | 12.3 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 0 | 39.21 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 0 | 138.78 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
SHEKAR T | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 163.65 | SFT | 0 | 163.65 | 0 | 0 | 0 | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 10400 | 1 | LUMP SUM | 1 | 0 | 100 | 10400 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V48
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0 | 0 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100 | 2250 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100 | 6000 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100 | 11250 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100 | 4813.2302 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100 | 5087.497 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100 | 1875 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100 | 828.828 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100 | 22453.9193 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0 | 0 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0 | 0 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0 | 100 | 2224.4148 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100 | 29719.6193 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 170.03 | SQM | 170.03 | 0 | 100 | 36604.0584 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 61.69 | SQM | 61.69 | 0 | 100 | 13280.6232 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 33.16 | SQM | 33.16 | 0 | 100 | 3569.3424 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 84.71 | SQM | 84.71 | 0 | 100 | 18236.3688 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 33.16 | SQM | 33.16 | 0 | 100 | 3569.3424 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 25 | NOS | 25 | 0 | 100 | 5000 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 18.85 | SQM | 18.85 | 0 | 100
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 1 | 2 | 33.333
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 13 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.08 | RMT | 46.08 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111 | RMT | 111 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.93 | RMT | 23.93 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 56.93 | SQM | 42.7 | 14.23 | 75
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.49 | RMT | 35.62 | 11.87 | 75
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 52.2 | SQM | 39.15 | 13.05 | 75
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.84 | RMT | 38.13 | 12.71 | 75
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 4.484 | SQM | 4.48 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 6.994 | RMT | 6.99 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1232 | SFT | 1232 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 2.99 | 0.75 | 80
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 14.5 | 3.62 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.57 | SQM | 6.86 | 1.71 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.43 | SQM | 30.74 | 7.69 | 80
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 136.904 | SQM | 136.9 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 30.1432 | RMT | 30.14 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 290 | 254 | SFT | 181 | 73 | 71.26
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 52.276 | SQM | 52.28 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 52.276 | SQM | 52.28 | 0 | 100
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 52.276 | SQM | 52.28 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 34.446 | SQM | 34.45 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 34.446 | 39.277 | SQM | 39.28 | 0 | 100
KRISHNAKUMAR SAHANI | CUSTOMIZATION TOILET TILE WORK | 436 | 1185.21 | 4.1037 | SQM | 3.28 | 0.82 | 80
KRISHNAKUMAR SAHANI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 251.26 | 17.8149 | SQM | 14.25 | 3.56 | 80
RUPAK NAYAK | CUSTOMISATION EPOXY GROUTING & SOAP WASH | 480 | 64.58 | 29.256 | SQM | 29.26 | 0 | 100

## V49
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 |  | 0 | AAIDHUL MIAH | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 |  | 0 | KRIUTTIBAS DAS | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 |  | 0 | PRAKASH H N | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 78.8 | SQM | 78.8 | 0 | 100 | 3388.4 |  | 0 | RUPAK NAYAK | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0 | 0 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 |  | 0 | SARAT BARMAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 |  | 0 | SAVITA DEVI | 1350
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 |  | 0 | SHOKAT | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 |  | 0 | SK ANSAR HOSSIAN | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100 | 2800 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100 | 4200 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 1.45 | 0 | 100 | 10150 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 |  | 0 | YELLAPPA C | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 |  | 0 | TOTAL | 1350
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100 | 3779.4557 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0.63 | 0 | 100 | 945 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 15.5 | 0 | 100 | 4671.576 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0.7 | 0 | 100 | 1050 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 2.46 | 0 | 100 | 741.4243 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100 | 4736.976 |  | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100 | 106.5636 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0 | 100 | 26888.9026 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 157.34 | SQM | 157.34 | 0 | 100 | 33872.1552 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 46.43 | SQM | 46.43 | 0 | 100 | 9995.4504 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 39.34 | SQM | 39.34 | 0 | 100 | 4234.5576 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 52.81 | SQM | 52.81 | 0 | 100 | 11368.9368 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 30 | SQM | 30 | 0 | 100 | 3229.2 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 24 | NOS | 24 | 0 | 100 | 4800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100 | 4299.1416 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100 | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100 | 6462.0995 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100 | 12920.998 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100 | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100 | 29641.1497 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100 | 9882.831 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100 | 16467.3054 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 18.85 | SQM | 18.85 | 0 | 100 | 5681.2392 |  | 0
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0 | 0 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 13 | 0 | 100 | 4550 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.08 | RMT | 46.08 | 0 | 100 | 3778.56 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111 | RMT | 111 | 0 | 100 | 3640.8 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.93 | RMT | 23.93 | 0 | 100 | 3139.616 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 56.93 | SQM | 0 | 56.93 | 0 | 0 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.49 | RMT | 0 | 47.49 | 0 | 0 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 52.2 | SQM | 0 | 52.2 | 0 | 0 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.84 | RMT | 0 | 50.84 | 0 | 0 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 3.63 | SQM | 3.63 | 0 | 100 | 664.29 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.64 | RMT | 5.64 | 0 | 100 | 277.488 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.96 | SQM | 0 | 2.96 | 0 | 0 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 6.75 | RMT | 0 | 6.75 | 0 | 0 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 10.85 | SQM | 10.85 | 0 | 100 | 1985.55 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 18.3 | 0 | 100 | 900.36 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 20.12 | SQM | 20.12 | 0 | 100 | 3681.96 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1232 | SFT | 1232 | 0 | 100 | 3080 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.37 | 0.37 | 90 | 616.71 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 16.31 | 1.81 | 90 | 2984.73 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.57 | SQM | 7.71 | 0.86 | 90 | 1410.93 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.43 | SQM | 34.59 | 3.84 | 90 | 6329.97 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 138.88 | SQM | 138.88 | 0 | 100 | 8968.8704 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 0.5 | 0.5 | #VALUE! | 7250 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100 | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100 | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100 | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100 | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100 | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 32.84 | RMT | 32.84 | 0 | 100 | 181769.4 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 0 | 3 | 0% | 0 | 100% | 1350
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100 | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100 | 1500 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100 | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100 | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100 | 350 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100 | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100 | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100 | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0 | 0 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100 | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 215 | 168 | SFT | 168 | 0 | 100 | 36120 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0 | 0 |  | 0
1350

## V50
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 78.8 | SQM | 78.8 | 0 | 100 | 3388.4 | 0 | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 10.28 | 0 | 100 | 1450.7136 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100 | 2800 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100 | 4200 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 1.45 | 0 | 100 | 10150 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100 | 3779.4557 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0.63 | 0 | 100 | 945 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 15.5 | 0 | 100 | 4671.576 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0.7 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 2.46 | 0 | 100 | 741.4243 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100 | 4736.976 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100 | 106.5636 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 0 | 206.23 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 0 | 12.3 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0 | 100 | 26888.9026 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 157.34 | SQM | 157.34 | 0 | 100 | 33872.1552 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 46.43 | SQM | 46.43 | 0 | 100 | 9995.4504 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 39.34 | SQM | 39.34 | 0 | 100 | 4234.5576 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 52.81 | SQM | 52.81 | 0 | 100 | 11368.9368 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 30 | SQM | 30 | 0 | 100 | 3229.2 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 24 | NOS | 24 | 0 | 100 | 4800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 18.85 | SQM | 18.85 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 2 | 1 | 66.667
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 11 | 2 | 84.615
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.08 | RMT | 46.08 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111 | RMT | 111 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.93 | RMT | 23.93 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 56.93 | SQM | 56.93 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.49 | RMT | 47.49 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 52.2 | SQM | 52.2 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.84 | RMT | 50.84 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 3.63 | SQM | 3.63 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.64 | RMT | 5.64 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.96 | SQM | 2.96 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 6.75 | RMT | 6.75 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 10.85 | SQM | 10.85 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 18.3 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 20.12 | SQM | 20.12 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1232 | SFT | 1232 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.74 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 18.12 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.57 | SQM | 8.57 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.43 | SQM | 38.43 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 136.904 | SQM | 136.9 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 31.22 | RMT | 31.22 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 1014 | CFT | 1014 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 338 | SFT | 338 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 215 | 168 | SFT | 168 | 0 | 100
YELLAPPA C | UTILITY SLAB EXTENSION WORK | 312 | 250 | 20 | SFT | 0 | 20 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 4200 | 1 | LUMP SUM | 1 | 0 | 100

## V51
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 78.8 | SQM | 78.8 | 0 | 100 | 3388.4 | 0 | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 10.28 | 0 | 100 | 1450.7136 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100 | 2800 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100 | 4200 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 1.45 | 0 | 100 | 10150 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100 | 3779.4557 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0.63 | 0 | 100 | 945 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 15.5 | 0 | 100 | 4671.576 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0.7 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 2.46 | 0 | 100 | 741.4243 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100 | 4736.976 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100 | 106.5636 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0 | 100 | 26888.9026 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 140.071 | SQM | 140.07 | 0 | 100 | 30154.2696 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 42.976 | SQM | 42.98 | 0 | 100 | 9252.7344 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 28.191 | SQM | 28.19 | 0 | 100 | 3034.3716 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 103.187 | SQM | 103.19 | 0 | 100 | 22214.7432 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 28.191 | SQM | 28.19 | 0 | 100 | 3034.3716 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 16 | NOS | 16 | 0 | 100 | 3200 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100 | 4299.1416 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 21.82 | SQM | 21.82 | 0 | 100
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 18 | NOS | 18 | 0 | 100
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.62 | RMT | 41.62 | 0 | 100
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 78 | RMT | 78 | 0 | 100
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 20.82 | RMT | 20.82 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 52.85 | SQM | 52.85 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 37.54 | RMT | 37.54 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 52.624 | SQM | 52.62 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 52.572 | RMT | 52.57 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 4.18 | SQM | 4.18 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8.16 | RMT | 8.16 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 7.37 | SQM | 7.37 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 17.1 | RMT | 17.1 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 19.88 | SQM | 19.88 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 34.45 | RMT | 34.45 | 0 | 100
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 20.32 | SQM | 20.32 | 0 | 100
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 1700 | SFT | 1700 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.74 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 16.839 | SQM | 16.84 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.208 | SQM | 8.21 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.943 | SQM | 35.94 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 136.904 | SQM | 136.9 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 2 | LUMP SUM | 2 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 30.78 | RMT | 30.78 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 1014 | CFT | 1014 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 338 | SFT | 338 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 215 | 168 | SFT | 168 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 96.574 | SQM | 0 | 96.57 | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 96.574 | SQM | 0 | 96.57 | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 96.574 | SQM | 0 | 96.57 | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 432 | 750 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 15000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100

## V52
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 78.8 | SQM | 78.8 | 0 | 100 | 3388.4 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100 | 2800 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100 | 4200 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 1.45 | 0 | 100 | 10150 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100 | 3779.4557 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0.63 | 0 | 100 | 945 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 15.5 | 0 | 100 | 4671.576 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0.7 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 2.46 | 0 | 100 | 741.4243 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100 | 4736.976 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100 | 106.5636 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100 | 15000 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0 | 100 | 26888.9026 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 151.38 | SQM | 151.38 | 0 | 100 | 32589.0864 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 53.98 | SQM | 53.98 | 0 | 100 | 11620.8144 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 36.9 | SQM | 36.9 | 0 | 100 | 3971.916 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 77.33 | SQM | 77.33 | 0 | 100 | 16647.6024 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 36.9 | SQM | 36.9 | 0 | 100 | 3971.916 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 22 | NOS | 22 | 0 | 100 | 4400 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 18.93 | SQM | 18.93 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 4 | NOS | 4 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.81 | RMT | 46.81 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 118.97 | RMT | 118.97 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.2 | RMT | 23.2 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 59.45 | SQM | 59.45 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.69 | RMT | 47.69 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 54.39 | SQM | 54.39 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 51.62 | RMT | 51.62 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 7.1 | SQM | 7.1 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 6.62 | RMT | 6.62 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 3.24 | SQM | 3.24 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 8.85 | RMT | 8.85 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 16.27 | SQM | 16.27 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 29.73 | RMT | 29.73 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 19.19 | SQM | 19.19 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1321.58 | SFT | 1321.58 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.74 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 18.12 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.19 | SQM | 8.19 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 37.23 | SQM | 37.23 | 0 | 100
TANMAY | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 136.904 | SQM | 109.52 | 27.38 | 80
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 31.22 | RMT | 31.22 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 265 | 505 | SFT | 505 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 86.595 | SQM | 86.6 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 86.595 | SQM | 86.6 | 0 | 100
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 86.595 | SQM | 86.6 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 18.848 | SQM | 18.85 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 18.848 | SQM | 18.85 | 0 | 100
INDAL SAHNI | CUSTOMIZATION TOILET TILE WORK | 436 | 1018.78 | 4.05 | SQM | 4.05 | 0 | 100
INDAL SAHNI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 266.42 | 17.7 | SQM | 17.7 | 0 | 100

## V53
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0 | 0 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100 | 2800 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100 | 4200 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 1.45 | 0 | 100 | 10150 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0 | 0 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0 | 0.63 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.5 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0 | 0.7 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.46 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0 | 0.71 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 0 | 32.74 | 0 | 0 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0 | 0 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0 | 0.66 | 0 | 0 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 0 | 138.78 | 0 | 0 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 157.82 | SQM | 157.82 | 0 | 100 | 33975.4896 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 46.99 | SQM | 46.99 | 0 | 100 | 10116.0072 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 38.68 | SQM | 38.68 | 0 | 100 | 4163.5152 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 52.79 | SQM | 52.79 | 0 | 100 | 11364.6312 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 29.45 | SQM | 29.45 | 0 | 100 | 3169.998 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 24 | NOS | 24 | 0 | 100 | 4800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100 | 4299.1416 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 18.85 | SQM | 18.85 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 1.43 | 11.57 | 11
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.08 | RMT | 46.08 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111 | RMT | 111 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.93 | RMT | 23.93 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 56.93 | SQM | 56.93 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.49 | RMT | 47.49 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 52.2 | SQM | 52.2 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.84 | RMT | 50.84 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 3.63 | SQM | 3.63 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.64 | RMT | 5.64 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.96 | SQM | 2.96 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 6.75 | RMT | 6.75 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 10.85 | SQM | 10.85 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 18.3 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 20.12 | SQM | 20.12 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1232 | SFT | 1232 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.74 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 18.12 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.57 | SQM | 8.57 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.43 | SQM | 38.43 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 136.904 | SQM | 136.9 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 31.22 | RMT | 31.22 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 304 | 290 | 136.06 | SQM | 38 | 98.06 | 27.929
YELLAPPA C | UTILITY SLAB EXTENSION WORK | 312 | 250 | 20 | SFT | 0 | 20 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | CUSTOMISATION BOUNDARY WALL AROUND VILLA | 481 | 7500 | 1 | LUMP SUM | 1 | 0 | 100

## V54
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SHEKAR T | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
SHEKAR T | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
SHEKAR T | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
SHEKAR T | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 99.996 | 24110.352 | 0 | 0
SHEKAR T | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
SHEKAR T | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
SHEKAR T | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
SHEKAR T | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
SHEKAR T | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
SHEKAR T | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0 | 0 | 0 | 0
SHEKAR T | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
SHEKAR T | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
SHEKAR T | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
SHEKAR T | FOOTING REINFORCEMENT | 23 | 7500 | 0.4 | MT | 0.4 | 0 | 100 | 3000 | 0 | 0
SHEKAR T | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SHEKAR T | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.6 | MT | 0.6 | 0 | 100 | 4500 | 0 | 0
SHEKAR T | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 1.45 | 0 | 100 | 10875 | 0 | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
SHEKAR T | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.25 | 0.01 | 99.986 | 10624.068 | 0 | 0
SHEKAR T | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
SHEKAR T | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
SHEKAR T | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0 | 0 | 0 | 0
SHEKAR T | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
SHEKAR T | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
SHEKAR T | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
SHEKAR T | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0 | 0.63 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SHEKAR T | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.5 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0 | 0.7 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
SHEKAR T | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.46 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0 | 0.2 | 0 | 0 | 0 | 0
SHEKAR T | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SHEKAR T | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 0 | 112.22 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 0 | 133.46 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 0 | 71.27 | 0 | 0 | 0 | 0
SHEKAR T | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 0 | 32.74 | 0 | 0 | 0 | 0
SHEKAR T | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0 | 0 | 0 | 0
SHEKAR T | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0 | 0.66 | 0 | 0 | 0 | 0
SHEKAR T | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 0 | 201.86 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 0 | 72.04 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 0 | 187.02 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 0 | 201.85 | 0 | 0 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 0 | 64.64 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 0 | 206.23 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 0 | 132.03 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 0 | 12.3 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 0 | 39.21 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 0 | 138.78 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
SHEKAR T | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 255 | SFT | 161.12 | 93.88 | 63.184 | 49947.2 | 0 | 0
SHEKAR T | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 290 | SFT | 159.5 | 130.5 | 55 | 49445 | 0 | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V55
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SHEKAR T | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
SHEKAR T | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
SHEKAR T | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
SHEKAR T | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
SHEKAR T | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
SHEKAR T | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
SHEKAR T | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
SHEKAR T | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
SHEKAR T | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
SHEKAR T | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0 | 0 | 0 | 0
SHEKAR T | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
SHEKAR T | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
SHEKAR T | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
SHEKAR T | FOOTING REINFORCEMENT | 23 | 7500 | 0.4 | MT | 0.4 | 0 | 100 | 3000 | 0 | 0
SHEKAR T | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SHEKAR T | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.6 | MT | 0.6 | 0 | 100 | 4500 | 0 | 0
SHEKAR T | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 1.45 | 0 | 100 | 10875 | 0 | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
SHEKAR T | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
SHEKAR T | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
SHEKAR T | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
SHEKAR T | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0 | 0 | 0 | 0
SHEKAR T | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
SHEKAR T | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
SHEKAR T | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
SHEKAR T | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0 | 0.63 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SHEKAR T | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.5 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0 | 0.7 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
SHEKAR T | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.46 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0 | 0.2 | 0 | 0 | 0 | 0
SHEKAR T | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SHEKAR T | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 0 | 112.22 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 0 | 133.46 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 0 | 71.27 | 0 | 0 | 0 | 0
SHEKAR T | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 0 | 32.74 | 0 | 0 | 0 | 0
SHEKAR T | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0 | 0 | 0 | 0
SHEKAR T | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0 | 0.66 | 0 | 0 | 0 | 0
SHEKAR T | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 0 | 201.86 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 0 | 72.04 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 0 | 187.02 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 0 | 201.85 | 0 | 0 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 0 | 64.64 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 0 | 206.23 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 0 | 132.03 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 0 | 12.3 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 0 | 39.21 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 0 | 138.78 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
SHEKAR T | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 255 | SFT | 100 | 155 | 39.216 | 31000 | 0 | 0
SHEKAR T | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 290 | SFT | 159.5 | 130.5 | 55 | 49445 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V56
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SHEKAR T | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100% | 4255.2 |  | 0 | AAIDHUL MIAH | 0
SHEKAR T | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
SHEKAR T | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
SHEKAR T | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0.004 | 100% | 24110.352 |  | 0 | KRIUTTIBAS DAS | 7500
SHEKAR T | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0.002 | 100% | 1252.9 |  | 0 | LEGENDRY LANDSCAPE | 0
SHEKAR T | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0.004 | 100% | 13692.8736 |  | 0 | MANJUNATHA P | 0
SHEKAR T | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0.002 | 99.97% | 1318.7664 |  | 0 | NAGARAJ | 0
SHEKAR T | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0.002 | 99.99% | 5560.128 |  | 0 | PRAKASH H N | 17000
SHEKAR T | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100% | 1733.6 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SHEKAR T | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
SHEKAR T | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0.001 | 99.98% | 4130 |  | 0 | SANTOSH KUMAR | 0
SHEKAR T | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | -0.004 | 100.1% | 3120 |  | 0 | SARAT BARMAN | 0
SHEKAR T | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100% | 7880 |  | 0 | SAVITA DEVI | 0
SHEKAR T | FOOTING REINFORCEMENT | 23 | 7500 | 0.4 | MT | 0.4 | 0 | 100% | 3000 |  | 0 | SHOKAT | 0
SHEKAR T | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100% | 3375 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SHEKAR T | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.6 | MT | 0.6 | 0 | 100% | 4500 |  | 0 | SK ANSAR HOSSIAN | 0
SHEKAR T | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 1.45 | 0 | 100% | 10875 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0 | SUBHASMITA DAS | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.1 | MT | 0 | 0.1 | 0% | 0 |  | 0 | UDHABHAI R PARMAR | 0
SHEKAR T | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | -0.005 | 100% | 10627.0819 |  | 0 | V VENKATANARAYANA | 0
SHEKAR T | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100% | 8336.5027 |  | 0 | YELLAPPA C | 0
SHEKAR T | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | -0.001 | 100% | 20145.0413 |  | 0 | RABIUL MOLLA | 0
SHEKAR T | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | -0.005 | 100% | 14328.1757 |  | 0 | KOUSHIK MANDAL | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0.004 | 100% | 46381.2149 |  | 0 | TOTAL | 24500
SHEKAR T | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0.0044 | 99.97% | 3851.7898 |  | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0% | 0 |  | 0
SHEKAR T | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0.001 | 99.99% | 2493 |  | 0
SHEKAR T | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100% | 2400 |  | 0
SHEKAR T | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0.004 | 99.91% | 4203 |  | 0
SHEKAR T | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0.001 | 99.97% | 6760 |  | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | -0.001 | 100% | 3858.75 |  | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | -0.002 | 100.1% | 3620 |  | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0 | 0.626 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHEKAR T | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | -0.005 | 100% | 11886.9005 |  | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0.002 | 100% | 38777.0947 |  | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0.004 | 99.97% | 3851.7898 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.495 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0.004 | 99.83% | 4580 |  | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | -0.003 | 100% | 3141 |  | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | -0.002 | 100.1% | 3620 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0 | 0.699 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0 | 0.2 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0 | 0.02 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 0 | 28.129 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.455 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0 | 0.709 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 0 | 2.668 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0 | 0.196 | 0% | 0 |  | 0
SHEKAR T | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 0 | 41 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHEKAR T | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100% | 21742.8494 |  | 0
SHEKAR T | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100% | 25858.1419 |  | 0
SHEKAR T | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100% | 13808.705 |  | 0
SHEKAR T | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 0 | 32.74 | 0% | 0 |  | 0
SHEKAR T | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0% | 0 |  | 0
SHEKAR T | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0 | 0.66 | 0% | 0 |  | 0
SHEKAR T | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 0 | 201.86 | 0% | 0 |  | 0
SHEKAR T | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 0 | 72.04 | 0% | 0 |  | 0
SHEKAR T | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 0 | 187.02 | 0% | 0 |  | 0
SHEKAR T | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 0 | 201.853 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 14500
SHEKAR T | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 0 | 64.644 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 0 | 206.23 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 0 | 132.03 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 0 | 12.3 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 0 | 39.21 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 0 | 138.781 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 50% | 6000
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHEKAR T | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 255 | SFT | 186.15 | 68.85 | 73% | 57706.5 |  | 0
SHEKAR T | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 290 | SFT | 211.7 | 78.3 | 73% | 65627 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 50% | 1500
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2500
24500

## V57
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SHEKAR T | ATT IN PLINTH | 1 | 54 | 137.52 | SQM | 137.52 | 0 | 100 | 7426.08 | 0 | 0
SHEKAR T | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
SHEKAR T | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
SHEKAR T | FOOTING EXCAVATION | 4 | 211.68 | 135.57 | CUM | 135.57 | 0 | 100 | 28697.4576 | 0 | 0
SHEKAR T | FOOTING EARTH DRESSING | 5 | 22 | 67.79 | SQM | 67.79 | 0 | 100 | 1491.38 | 0 | 0
SHEKAR T | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 114.59 | CUM | 114.59 | 0 | 100 | 16170.9408 | 0 | 0
SHEKAR T | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.845 | CUM | 5.85 | 0 | 100 | 1238.328 | 0 | 0
SHEKAR T | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 65.48 | CUM | 65.48 | 0 | 100 | 9240.5376 | 0 | 0
SHEKAR T | BASE FLOOR EARTH DRESSING | 14 | 22 | 137.52 | SQM | 137.52 | 0 | 100 | 3025.44 | 0 | 0
SHEKAR T | SETBACK AREA SOIL FILLING | 16 | 141.12 | 13.18 | CUM | 0 | 13.18 | 0 | 0 | 0 | 0
SHEKAR T | FOOTING PCC WORK | 20 | 1000 | 4.566 | CUM | 4.57 | 0 | 100 | 4570 | 0 | 0
SHEKAR T | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.923 | CUM | 2.92 | 0 | 100 | 2920 | 0 | 0
SHEKAR T | BASE FLOOR PCC | 22 | 1000 | 13.752 | CUM | 13.75 | 0 | 100 | 13750 | 0 | 0
SHEKAR T | FOOTING REINFORCEMENT | 23 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SHEKAR T | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
SHEKAR T | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SHEKAR T | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100 | 6750 | 0 | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2 | MT | 2 | 0 | 100 | 15000 | 0 | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
SHEKAR T | FOOTING SHUTTERING | 41 | 301.392 | 43.26 | SQM | 43.26 | 0 | 100 | 13038.2179 | 0 | 0
SHEKAR T | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 28.8 | SQM | 28.8 | 0 | 100 | 8680.0896 | 0 | 0
SHEKAR T | PLINTH BEAM SHUTTERING | 43 | 301.392 | 64.28 | SQM | 64.28 | 0 | 100 | 19373.4778 | 0 | 0
SHEKAR T | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.51 | SQM | 51.51 | 0 | 100 | 15524.7019 | 0 | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 187.91 | SQM | 187.91 | 0 | 100 | 56634.5707 | 0 | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 13.1328 | SQM | 13.13 | 0 | 100 | 3957.277 | 0 | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.61 | SQM | 0 | 15.61 | 0 | 0 | 0 | 0
SHEKAR T | FOOTING RCC | 50 | 225 | 15.37 | CUM | 15.37 | 0 | 100 | 3458.25 | 0 | 0
SHEKAR T | PEDESTAL COLUMN RCC | 51 | 1500 | 2.56 | CUM | 2.56 | 0 | 100 | 3840 | 0 | 0
SHEKAR T | PLINTH BEAM RCC | 53 | 900 | 4.38 | CUM | 4.38 | 0 | 100 | 3942 | 0 | 0
SHEKAR T | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.05 | CUM | 3.05 | 0 | 100 | 6100 | 0 | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 21.874 | CUM | 21.87 | 0 | 100 | 4920.75 | 0 | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 2.233 | CUM | 2.23 | 0 | 100 | 4460 | 0 | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 1.1 | CUM | 0 | 1.1 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SHEKAR T | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.75 | MT | 0.75 | 0 | 100 | 5625 | 0 | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.3 | MT | 1.3 | 0 | 100 | 9750 | 0 | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.17 | MT | 0 | 0.17 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 47.03 | SQM | 47.03 | 0 | 100 | 14174.4658 | 0 | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 165.84 | SQM | 165.84 | 0 | 100 | 49982.8493 | 0 | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 13.1328 | SQM | 13.13 | 0 | 100 | 3957.277 | 0 | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 18.21 | SQM | 0 | 18.21 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.784 | CUM | 2.78 | 0 | 100 | 5560 | 0 | 0
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 18.898 | CUM | 18.9 | 0 | 100 | 4252.5 | 0 | 0
SHEKAR T | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 2.233 | CUM | 2.23 | 0 | 100 | 4460 | 0 | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.153 | CUM | 0 | 1.15 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.05 | MT | 0 | 0.05 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
SHEKAR T | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.47 | SQM | 29.47 | 0 | 100 | 8882.0222 | 0 | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.88 | SQM | 0 | 3.88 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.81 | CUM | 0.81 | 0 | 100 | 1620 | 0 | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 3.352 | CUM | 3.35 | 0 | 100 | 753.75 | 0 | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.26 | CUM | 0 | 0.26 | 0 | 0 | 0 | 0
SHEKAR T | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SHEKAR T | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 139.91 | SQM | 139.91 | 0 | 100 | 27107.8423 | 0 | 0
SHEKAR T | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 178.84 | SQM | 178.84 | 0 | 100 | 34650.6077 | 0 | 0
SHEKAR T | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 75.48 | SQM | 75.48 | 0 | 100 | 14624.401 | 0 | 0
SHEKAR T | ELEVATION RCC BAND | 133 | 65.6 | 38.284 | RMT | 0 | 38.28 | 0 | 0 | 0 | 0
SHEKAR T | ELEVATION GROOVE | 137 | 65.6 | 49.952 | RMT | 0 | 49.95 | 0 | 0 | 0 | 0
SHEKAR T | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.38 | SQM | 0 | 1.38 | 0 | 0 | 0 | 0
SHEKAR T | RCC SURFACE HACKING | 140 | 10.76 | 258.02 | SQM | 0 | 258.02 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 81.36 | SQM | 0 | 81.36 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.704 | SQM | 0 | 187.7 | 0 | 0 | 0 | 0
SHEKAR T | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 228.17 | SQM | 0 | 228.17 | 0 | 0 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 304.83 | SQM | 0 | 304.83 | 0 | 0 | 0 | 0
SHEKAR T | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 160.44 | SQM | 0 | 160.44 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.87 | SQM | 0 | 14.87 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 38.01 | SQM | 0 | 38.01 | 0 | 0 | 0 | 0
SHEKAR T | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 158.39 | SQM | 0 | 158.39 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
SHEKAR T | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 938.82 | SFT | 685.34 | 253.48 | #VALUE! | 212455.4 | 0 | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0

## V58
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 103.17 | SQM | 103.17 | 0 | 100% | 103.17 |  | 0 | AAIDHUL MIAH | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 2 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 6 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 150.56 | CUM | 150.56 | 0 | 100% | 602.24 |  | 0 | KRIUTTIBAS DAS | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 46.12 | SQM | 46.12 | 0 | 100% | 230.6 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 116.13 | CUM | 116.13 | 0 | 100% | 929.04 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 7.99 | CUM | 7.99 | 0 | 100% | 87.89 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 56.74 | CUM | 56.74 | 0 | 100% | 737.62 |  | 0 | PRAKASH H N | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 103.17 | SQM | 103.17 | 0 | 100% | 1444.38 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 130.85 | SQM | 130.85 | 0 | 100% | 1962.75 |  | 0 | RUPAK NAYAK | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.3 | CUM | 0 | 10.3 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 17 |  | 0 | SARAT BARMAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 19 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 7.53 | CUM | 7.53 | 0 | 100% | 150.6 |  | 0 | SHOKAT | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.994 | CUM | 3.99 | 0.004 | 99.9% | 83.79 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 89667
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 10.32 | CUM | 10.32 | 0 | 100% | 227.04 |  | 0 | SK ANSAR HOSSIAN | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 18.4 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 16.8 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.95 | MT | 0.95 | 0 | 100% | 23.75 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 20.8 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.6 | MT | 2.6 | 0 | 100% | 75.4 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 5.76 |  | 0 | YELLAPPA C | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.16 | MT | 0.16 | 0 | 100% | 5.6 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 65.78 | SQM | 65.78 | 0 | 100% | 2696.98 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 37.11 | SQM | 37.11 | 0 | 100% | 1558.62 |  | 0 | TOTAL | 89667
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 79.884 | SQM | 79.88 | 0.004 | 99.99% | 3434.84 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 67.86 | SQM | 67.86 | 0 | 100% | 2985.84 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 218.06 | SQM | 218.06 | 0 | 100% | 9812.7 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.793 | SQM | 12.79 | 0.003 | 99.98% | 588.34 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 11.65 | SQM | 11.65 | 0 | 100% | 547.55 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 17.19 | CUM | 17.19 | 0 | 100% | 859.5 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.18 | CUM | 2.18 | 0 | 100% | 111.18 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 5.991 | CUM | 5.99 | 0.001 | 99.98% | 317.47 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.98 | CUM | 3.98 | 0 | 100% | 218.9 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 23.5 | CUM | 23.5 | 0 | 100% | 1363 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.673 | CUM | 1.67 | 0.003 | 99.82% | 101.87 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100% | 60.48 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 68 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 55.2 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.85 | MT | 1.85 | 0 | 100% | 135.05 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 13.86 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 16 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 56.55 | SQM | 56.55 | 0 | 100% | 4750.2 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 188.59 | SQM | 188.59 | 0 | 100% | 16030.15 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.793 | SQM | 12.79 | 0.003 | 99.98% | 1099.94 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 14.11 | SQM | 14.11 | 0 | 100% | 1227.57 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.33 | CUM | 3.33 | 0 | 100% | 293.04 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 19.19 | CUM | 19.19 | 0 | 100% | 1746.29 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.673 | CUM | 1.67 | 0.003 | 99.82% | 153.64 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.57 | CUM | 1.57 | 0 | 100% | 146.01 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 14.55 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.3 | MT | 0.3 | 0 | 100% | 30 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100% | 2.06 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 1144.8 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 26.6 | SQM | 26.6 | 0 | 100% | 2846.2 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.815 | SQM | 1.82 | -0.005 | 100.3% | 196.56 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 66.49 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 3.07 | CUM | 3.07 | 0 | 100% | 343.84 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.17 | CUM | 0.17 | 0 | 100% | 19.21 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 53 | NOS | 53 | 0 | 100% | 6148 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 118 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 146.37 | SQM | 146.37 | 0 | 100% | 17564.4 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 185.55 | SQM | 185.55 | 0 | 100% | 23008.2 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 72.29 | SQM | 72.29 | 0 | 100% | 9325.41 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 49.17 | RMT | 49.17 | 0 | 100% | 6539.61 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 33.82 | RMT | 33.82 | 0 | 100% | 4633.34 |  | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.38 | SQM | 1.38 | 0 | 100% | 190.44 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 259.56 | SQM | 259.56 | 0 | 100% | 36338.4 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 94.21 | SQM | 94.21 | 0 | 100% | 13377.82 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 266.24 | SQM | 266.24 | 0 | 100% | 38072.32 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 261.11 | SQM | 261.11 | 0 | 100% | 38383.17 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 150 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 92.25 | SQM | 92.25 | 0 | 100% | 13929.75 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 364.2 | SQM | 364.2 | 0 | 100% | 55358.4 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 163.72 | SQM | 163.72 | 0 | 100% | 25540.32 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 13.2 | SQM | 13.2 | 0 | 100% | 2112 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.271 | SQM | 37.27 | 0.001 | 100% | 6000.47 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 163.58 | SQM | 163.58 | 0 | 100% | 26990.7 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 179.69 | SQM | 179.69 | 0 | 100% | 30187.92 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 53.879 | SQM | 53.88 | -0.001 | 100% | 9159.6 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 50.898 | SQM | 50.9 | -0.002 | 100% | 8805.7 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 107.553 | SQM | 107.55 | 0.003 | 100% | 18713.7 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 50.989 | SQM | 50.99 | -0.001 | 100% | 9076.22 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 16.2 | RMT | 0 | 16.2 | 0% | 0 | 100% | 89667

## V59
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) |  | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 91.86 | 4960.44 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 | AAIDHUL MIAH | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 2405 | 1 | 2405 | LUMP SUM | 1 | 0 | 100% | 2405 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | 1000 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | 22766.184 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | 1183.16 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | 13191.8976 | CUM | 93.48 | 0 | 100% | 13191.8976 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | 1221.817 | CUM | 5.77 | 0.002 | 99.97% | 1221.3936 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | 4925.088 | CUM | 34.9 | 0 | 100% | 4925.088 |  | 0 | PRAKASH H N | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | 2020.92 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | 3949.98 | SQM | 91.86 | 0 | 100% | 3949.98 |  | 0 | RUPAK NAYAK | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | 1525.5072 | CUM | 0 | 10.81 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | 5500 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SARAT BARMAN | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 3.466 | 3466 | CUM | 3.47 | -0.004 | 100.1% | 3470 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | 2886 | CUM | 2.89 | -0.004 | 100.1% | 2890 |  | 0 | SHOKAT | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 9.186 | 9186 | CUM | 9.19 | -0.004 | 100% | 9190 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | 2100 | MT | 0.3 | 0 | 100% | 2100 |  | 0 | SK ANSAR HOSSIAN | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | 4900 | MT | 0.7 | 0 | 100% | 4900 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | 3850 | MT | 0.55 | 0 | 100% | 3850 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | 5600 | MT | 0.8 | 0 | 100% | 5600 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | 10500 | MT | 1.5 | 0 | 100% | 10500 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | 1400 | MT | 0.2 | 0 | 100% | 1400 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | 1050 | MT | 0 | 0.15 | 0% | 0 |  | 0 | YELLAPPA C | 61305.0703
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | 8342.5306 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | 8984.4955 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | 19145.8364 | SQM | 63.52 | 0.0047 | 99.99% | 19144.4198 |  | 0 | TOTAL | 61305.0703
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | 15578.9525 | SQM | 51.69 | 0 | 100% | 15578.9525 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | 46305.8669 | SQM | 153.64 | 0 | 100% | 46305.8669 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | 3716.1634 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | 4813.2302 | SQM | 0 | 15.97 | 0% | 0 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 9.892 | 2225.7 | CUM | 9.89 | 0.002 | 99.98% | 2225.25 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | 3663 | CUM | 2.44 | 0.002 | 99.92% | 3660 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.33 | 3897 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | 6082 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | 3795.075 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | 3540 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | 1485 | CUM | 0 | 0.99 | 0% | 0 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | 2000 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | 4900 | MT | 0.7 | 0 | 100% | 4900 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | 7700 | MT | 1.1 | 0 | 100% | 7700 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | 1400 | MT | 0.2 | 0 | 100% | 1400 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | 1050 | MT | 0 | 0.15 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | 15033.433 | SQM | 49.88 | 0 | 100% | 15033.433 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | 39985.6766 | SQM | 132.67 | 0 | 100% | 39985.6766 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | 3716.1634 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | 5087.497 | SQM | 0 | 16.88 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | 5886 | CUM | 2.94 | 0.003 | 99.9% | 5880 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | 3082.5 | CUM | 13.7 | 0 | 100% | 3082.5 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | 3980 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | 1405.5 | CUM | 0 | 0.937 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | 700 | MT | 0.1 | 0 | 100% | 700 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | 1750 | MT | 0.25 | 0 | 100% | 1750 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | 210 | MT | 0 | 0.03 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | 2441.2752 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | 8176.765 | SQM | 27.13 | 0 | 100% | 8176.765 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | 828.828 | SQM | 0 | 2.75 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | 820 | CUM | 0.41 | 0 | 100% | 820 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | 542.7 | CUM | 2.41 | 0.002 | 99.92% | 542.25 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | 330 | CUM | 0 | 0.22 | 0% | 0 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | 2200 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | 2000 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | 22453.9193 | SQM | 0 | 115.89 | 0% | 0 | 100% | 22453.9193
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | 25809.7039 | SQM | 0 | 133.21 | 0% | 0 | 100% | 25809.7039
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | 13041.4471 | SQM | 0 | 67.31 | 0% | 0 | 100% | 13041.4471
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | 2101.824 | RMT | 0 | 32.04 | 0% | 0 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 32.05 | 2102.48 | RMT | 0 | 32.05 | 0% | 0 |  | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | 184.0644 | SQM | 0 | 1.14 | 0% | 0 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | 2224.4363 | SQM | 0 | 206.732 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | 10023.3292 | SQM | 0 | 71.63 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | 27220.972 | SQM | 0 | 194.53 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | 40362.4166 | SQM | 0 | 208.32 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | 13000 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | 10409.8213 | SQM | 0 | 74.392 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | 30850.3882 | SQM | 0 | 220.467 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | 27543.7843 | SQM | 0 | 142.16 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | 1624.6105 | SQM | 0 | 11.61 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | 4677.9268 | SQM | 0 | 33.43 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | 29719.6193 | SQM | 0 | 153.39 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 1 | 14000 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | 2000 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | 400 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | 800 | NOS | 1 | 0 | 100% | 800 |  | 0
MORSELIM KHAN | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 290 | 89900 | SFT | 159.5 | 130.5 | 55% | 49445 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
61305.0703

## V60
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 | AAIDHUL MIAH | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 2405 | 1 | LUMP SUM | 1 | 0 | 100% | 2405 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100% | 13191.8976 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0.002 | 99.97% | 1221.3936 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100% | 4925.088 |  | 0 | PRAKASH H N | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100% | 3949.98 |  | 0 | RUPAK NAYAK | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | -0.004 | 100.1% | 3470 |  | 0 | SARAT BARMAN | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | -0.004 | 100.1% | 2890 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | -0.004 | 100% | 9190 |  | 0 | SHOKAT | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100% | 2100 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0 | SK ANSAR HOSSIAN | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100% | 3850 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 5600 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100% | 10500 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0 | YELLAPPA C | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0.0047 | 99.99% | 19144.4198 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100% | 15578.9525 |  | 0 | TOTAL | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100% | 46305.8669 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100% | 4813.2302 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0.002 | 99.98% | 2225.25 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0.002 | 99.92% | 3660 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100% | 1485 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100% | 7700 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100% | 15033.433 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100% | 39985.6766 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100% | 5087.497 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0.003 | 99.9% | 5880 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100% | 3082.5 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | -0.003 | 100.3% | 1410 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100% | 700 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0.03 | 0 | 100% | 210 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100% | 8176.765 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100% | 828.828 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0.002 | 99.92% | 542.25 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100% | 22453.9193 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100% | 25809.7039 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100% | 2101.824 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100% | 2102.48 |  | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100% | 184.0644 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0.002 | 100% | 2224.4148 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100% | 27220.972 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100% | 40362.4166 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0.002 | 100% | 10409.5415 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | -0.003 | 100% | 30850.808 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100% | 27543.7843 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100% | 4677.9268 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100% | 29719.6193 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 142.03 | SQM | 142.03 | 0 | 100% | 30576.2184 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 47.97 | SQM | 47.97 | 0 | 100% | 10326.9816 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 39.24 | SQM | 39.24 | 0 | 100% | 4223.7936 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 77.15 | SQM | 77.15 | 0 | 100% | 16608.852 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 39.24 | SQM | 39.24 | 0 | 100% | 4223.7936 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 15 | NOS | 15 | 0 | 100% | 3000 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0.003 | 99.99% | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100% | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100% | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 0 | 406.82 | 0% | 0 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0.004 | 99.99% | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0.004 | 100% | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 0 | 574.613 | 0% | 0 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 0 | 581.011 | 0% | 0 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100% | 6413.6218 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 0 | 14 | 0% | 0 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0.002 | 99.99% | 3040.56 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100% | 3649 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | -0.002 | 100% | 3581.76 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 58.71 | SQM | 55.77 | 2.94 | 94.99% | 10205.91 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 59 | RMT | 53.1 | 5.9 | 90% | 2612.52 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 53.77 | 5.972 | 90% | 9839.91 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 65.7 | 3.46 | 95% | 3232.44 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 5.448 | SQM | 4.9 | 0.548 | 89.94% | 896.7 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 7.129 | RMT | 6.77 | 0.359 | 94.96% | 333.084 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 0 | 2.512 | 0% | 0 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 0 | 7.61 | 0% | 0 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 7.41 | SQM | 0 | 7.41 | 0% | 0 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 11.15 | RMT | 0 | 11.15 | 0% | 0 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 0 | 27.18 | 0% | 0 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1122.9 | 59.1 | 95% | 2807.25 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 3.86 | 0.202 | 95.03% | 706.38 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 16.19 | SQM | 12.95 | 3.24 | 79.99% | 2369.85 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 4.08 | 4.07 | 50.06% | 746.64 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 30.83 | SQM | 18.5 | 12.33 | 60.01% | 3385.5 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 132.064 | SQM | 0 | 132.064 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100% | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 290 | 91 | SFT | 91 | 0 | 100% | 26390 |  | 0
MORSELIM KHAN | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 290 | SFT | 290 | 0 | 100% | 89900 |  | 0
YELLAPPA C | PARKING COLUMN SHIFTING | 343 | 10000 | 2 | LUMP SUM | 2 | 0 | 100% | 20000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 77.385 | SQM | 77.39 | -0.005 | 100% | 3748.6168 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 77.385 | SQM | 77.39 | -0.005 | 100% | 1249.8485 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 77.385 | SQM | 0 | 77.385 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 56.212 | SQM | 56.21 | 0.002 | 100% | 907.7915 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 56.212 | SQM | 0 | 56.212 | 0% | 0 |  | 0
INDAL SAHNI | CUSTOMIZATION TOILET TILE WORK | 436 | 1185.21 | 5.177 | SQM | 0 | 5.177 | 0% | 0 |  | 0
INDAL SAHNI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 251.26 | 15.293 | SQM | 14.53 | 0.763 | 95.01% | 3650.8078 |  | 0
RUPAK NAYAK | CUSTOMISATION EPOXY GROUTING & SOAP WASH | 480 | 64.58 | 27.119 | SQM | 0 | 27.119 | 0% | 0 |  | 0

## V61
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 2405 | 1 | LUMP SUM | 1 | 0 | 100 | 2405 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100 | 3949.98 | 0 | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0 | 0 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100 | 2100 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100 | 5600 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100 | 10500 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0 | 0 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0 | 0.99 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0 | 0.94 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100 | 1750 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0 | 0 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 0 | 115.89 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 0 | 133.21 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 0 | 67.31 | 0 | 0 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0 | 0 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0 | 0 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 0 | 206.73 | 0 | 0 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 0 | 71.63 | 0 | 0 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 0 | 194.53 | 0 | 0 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 0 | 208.32 | 0 | 0 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 0 | 74.39 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 0 | 220.47 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 0 | 142.16 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 0 | 11.61 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 0 | 33.43 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 0 | 153.39 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100 | 2500 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
MORSELIM KHAN | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 290 | SFT | 159.5 | 130.5 | 55 | 49445 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V62
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 | AAIDHUL MIAH | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100% | 13191.8976 |  | 0 | MANJUNATHA P | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | -0.002 | 99.97% | 1221.3936 |  | 0 | NAGARAJ | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100% | 4925.088 |  | 0 | PRAKASH H N | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 | RAMAKRUSHNA PRADHAN | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 10.81 | 0 | 100% | 1525.5072 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0.004 | 100.1% | 3470 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0.004 | 100.1% | 2890 |  | 0 | SHOKAT | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0.004 | 100% | 9190 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100% | 2250 |  | 0 | SK ANSAR HOSSIAN | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100% | 5250 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100% | 11250 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0 | YELLAPPA C | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | -0.0047 | 99.99% | 19144.4198 |  | 0 | TOTAL | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100% | 15578.9525 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100% | 46305.8669 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100% | 4813.2302 |  | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | -0.002 | 99.98% | 2225.25 |  | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | -0.002 | 99.92% | 3660 |  | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | -0.001 | 99.97% | 6080 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0.003 | 100% | 3795.75 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100% | 1485 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100% | 5250 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100% | 8250 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100% | 15033.433 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100% | 39985.6766 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100% | 5087.497 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | -0.003 | 99.9% | 5880 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100% | 3082.5 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0.003 | 100.3% | 1410 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100% | 750 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0.03 | 0 | 100% | 225 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100% | 8176.765 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100% | 828.828 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | -0.002 | 99.92% | 542.25 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100% | 22453.9193 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100% | 25809.7039 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100% | 2101.824 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100% | 2102.48 |  | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100% | 184.0644 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | -0.002 | 100% | 2224.4148 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100% | 27220.972 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100% | 40362.4166 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13500 | 1 | LUMP SUM | 1 | 0 | 100% | 13500 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | -0.002 | 100% | 10409.5415 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0.003 | 100% | 30850.808 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100% | 27543.7843 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100% | 4677.9268 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100% | 29719.6193 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 132.486 | SQM | 132.49 | 0.004 | 100% | 28522.4472 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 36.3 | SQM | 36.3 | 0 | 100% | 7814.664 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 35.028 | SQM | 35.03 | 0.002 | 100% | 3770.6292 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 79.534 | SQM | 79.53 | -0.004 | 99.99% | 17121.2184 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 35.028 | SQM | 35.03 | 0.002 | 100% | 3770.6292 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 14 | 0 | 100% | 2800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | -0.003 | 99.99% | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100% | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100% | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100% | 13137.0314 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | -0.004 | 99.99% | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | -0.004 | 100% | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | -0.003 | 100% | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | -0.001 | 100% | 15634.9791 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100% | 6413.6218 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 12 | NOS | 0 | -12 | 0% | 0 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | -0.002 | 99.99% | 3040.56 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100% | 3649 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | 0.002 | 100% | 3581.76 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 58.71 | SQM | 58.71 | 0 | 100% | 10743.93 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 59 | RMT | 59 | 0 | 100% | 2902.8 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 59.74 | -0.002 | 100% | 10932.42 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 69.16 | 0 | 100% | 3402.672 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100% | 675.27 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.6 | 0 | 100% | 275.52 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | -0.002 | 99.92% | 459.33 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100% | 374.412 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 7.41 | SQM | 7.41 | 0 | 100% | 1356.03 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 11.15 | RMT | 11.15 | 0 | 100% | 548.58 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100% | 4973.94 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100% | 2955 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 4.06 | -0.002 | 99.95% | 742.98 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 16.19 | SQM | 16.19 | 0 | 100% | 2962.77 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 8.15 | 0 | 100% | 1491.45 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 30.83 | SQM | 30.83 | 0 | 100% | 5641.89 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 138.88 | SQM | 138.88 | 0 | 100% | 8968.8704 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100% | 15500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 31.819 | RMT | 31.82 | 0.001 | 100% | 176123.7 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 26.72 | RFT | 26.72 | 0 | 100% | 4034.72 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | -1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 290 | 70.07 | SFT | 70.07 | 0 | 100% | 20320.3 |  | 0
YELLAPPA C | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 310 | 16 | SFT | 16 | 0 | 100% | 4960 |  | 0
SANTOSH KUMAR | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 4.13 | SQM | 4.13 | 0 | 100% | 1244.749 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | -3 | 0% | 0 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 450 | 1 | LUMP SUM | 1 | 0 | 100% | 450 |  | 0

## V63
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 54.2 | SQM | 54.2 | 0 | 100% | 2330.6 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100% | 13191.8976 |  | 0 | NAGARAJ | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0 | PRAKASH H N | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 35.66 | SQM | 35.66 | 0 | 100% | 1533.38 |  | 0 | RAMAKRUSHNA PRADHAN | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100% | 4925.088 |  | 0 | RUPAK NAYAK | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 | SANTOSH KUMAR | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100% | 3949.98 |  | 0 | SARAT BARMAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SAVITA DEVI | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SHOKAT | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | -0.004 | 100.1% | 3470 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | -0.004 | 100.1% | 2890 |  | 0 | SK ANSAR HOSSIAN | 1583.8066
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | -0.004 | 100% | 9190 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
BISWO RANJAN ROUT | FOOTING REINFORCEMENT | 23 | 6800 | 0.3 | MT | 0.3 | 0 | 100% | 2040 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
BISWO RANJAN ROUT | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.7 | MT | 0.7 | 0 | 100% | 4760 |  | 0 | SUBHASMITA DAS | 0
BISWO RANJAN ROUT | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.55 | MT | 0.55 | 0 | 100% | 3740 |  | 0 | UDHABHAI R PARMAR | 0
BISWO RANJAN ROUT | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.45 | MT | 0.45 | 0 | 100% | 3060 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.35 | MT | 0.35 | 0 | 100% | 2625 |  | 0 | YELLAPPA C | 0
NARESH PURTY | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 1.5 | MT | 1.5 | 0 | 100% | 10200 |  | 0 | RABIUL MOLLA | 0
NARESH PURTY | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 6800 | 0.2 | MT | 0.2 | 0 | 100% | 1360 |  | 0 | KOUSHIK MANDAL | 0
NARESH PURTY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 6800 | 0.15 | MT | 0.15 | 0 | 100% | 1020 |  | 0 | TOTAL | 1583.8066
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0.0047 | 99.99% | 19144.4198 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100% | 15578.9525 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100% | 46305.8669 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 0 | 12.33 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0% | 0 |  | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0.002 | 99.98% | 2225.25 |  | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0.002 | 99.92% | 3660 |  | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100% | 1485 |  | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
NARESH PURTY | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 6800 | 0.05 | MT | 0.05 | 0 | 100% | 340 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.65 | MT | 0.65 | 0 | 100% | 4875 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100% | 8250 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100% | 15033.433 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100% | 39985.6766 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 0 | 12.33 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0% | 0 |  | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0.003 | 99.9% | 5880 |  | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100% | 3082.5 |  | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | -0.003 | 100.3% | 1410 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100% | 750 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0.03 | 0 | 100% | 225 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 22.75 | 4.38 | 83.86% | 6856.668 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0% | 0 |  | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0.002 | 99.92% | 542.25 |  | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100% | 22453.9193 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100% | 25809.7039 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32 | 0.04 | 99.88% | 2099.2 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32 | 0.05 | 99.84% | 2099.2 |  | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 5.258 | SQM | 5.26 | -0.002 | 100% | 1019.1355 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 450 | SQM | 450 | 0 | 100% | 3632.85 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100% | 27220.972 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100% | 40362.4166 |  | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0.002 | 100% | 10409.5415 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | -0.003 | 100% | 30850.808 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100% | 27543.7843 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100% | 4677.9268 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 76.34 | 77.05 | 49.77% | 14791.0277 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 254.03 | 183.48 | SQM | 183.48 | 0 | 100% | 46609.4244 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 254.03 | 17.242 | SQM | 17.24 | 0.002 | 99.99% | 4379.4772 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 190.52 | 15.75 | SQM | 15.75 | 0 | 100% | 3000.69 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 254.03 | 78.44 | SQM | 78.44 | 0 | 100% | 19926.1132 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 254.03 | 123.624 | SQM | 123.62 | 0.004 | 100% | 31403.1886 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 295 | 8 | NOS | 8 | 0 | 100% | 2360 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.29 | 25.09 | SQM | 25.09 | 0 | 100% | 5401.6261 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100% | 2628.3544 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 167.69 | SQM | 167.69 | 0 | 100% | 8122.5682 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 101.64 | SQM | 101.64 | 0 | 100% | 4923.2383 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 137.5 | SQM | 137.5 | 0 | 100% | 6660.225 |  | 0
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.5 | 180.53 | SQM | 180.53 | 0 | 100% | 16518.495 |  | 0
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 82.41 | SQM | 82.41 | 0 | 100% | 7540.0205 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.5 | 206.47 | SQM | 206.47 | 0 | 100% | 18892.005 |  | 0
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.5 | 70.572 | SQM | 70.57 | 0.002 | 100% | 6457.155 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.5 | 28.43 | SQM | 28.43 | 0 | 100% | 2601.345 |  | 0
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.5 | 8.61 | SQM | 8.61 | 0 | 100% | 787.815 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100% | 6413.6218 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 0 | 15 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0.002 | 99.99% | 3040.56 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100% | 3649 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | -0.002 | 100% | 3581.76 |  | 0
SK ANSAR HOSSIAN | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0% | 0 | 25% | 750
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 182.88 | 58.71 | SQM | 58.71 | 0 | 100% | 10736.8848 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.43 | RMT | 59.43 | 0 | 100% | 2923.956 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 182.88 | 59.742 | SQM | 59.74 | 0.002 | 100% | 10925.2512 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 69.16 | 0 | 100% | 3402.672 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 182.88 | 3.69 | SQM | 3.69 | 0 | 100% | 674.8272 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.6 | 0 | 100% | 275.52 |  | 0
SK ANSAR HOSSIAN | UTILITY FLOOR TILING | 230 | 182.88 | 2.512 | SQM | 0 | 2.512 | 0% | 0 | 100% | 459.3946
SK ANSAR HOSSIAN | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 0 | 7.61 | 0% | 0 | 100% | 374.412
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 182.88 | 7.41 | SQM | 7.41 | 0 | 100% | 1355.1408 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 22.3 | RMT | 22.3 | 0 | 100% | 1097.16 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 182.88 | 27.18 | SQM | 27.18 | 0 | 100% | 4970.6784 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100% | 2955 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 172.224 | 4.062 | SQM | 4.06 | 0.002 | 99.95% | 699.2294 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 193.752 | 18.11 | SQM | 18.11 | 0 | 100% | 3508.8487 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 172.224 | 8.15 | SQM | 8.15 | 0 | 100% | 1403.6256 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 193.752 | 36.28 | SQM | 36.28 | 0 | 100% | 7029.3226 |  | 0
PRAKASH JANA | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 208.534 | SQM | 0 | 208.534 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 0.5 | LUMP SUM | 0 | 0.5 | 0% | 0 |  | 0
BICHITRA CHOUDHURI | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 0.5 | LUMP SUM | 0.5 | 0 | 100% | 4500 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 28.41 | RMT | 28.41 | 0 | 100% | 140743.14 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100% | 1350 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100% | 5625 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
CHIRANJEEVI | ADDITIONAL SCAFFOLDING WORK OF EXTERNAL PLASTERING | 300 | 35 | 307 | SQM | 307 | 0 | 100% | 10745 |  | 0
KHALIL MIAH | LAYING FLOOR PROTECTOR SHEET & TILE CLEANING | 341 | 1.5 | 1182 | SFT | 1182 | 0 | 100% | 1773 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | GROUND FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 379 | 13.455 | 183.89 | SQM | 183.89 | 0 | 100% | 2474.2399 |  | 0
RUPAK NAYAK | FIRST FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 380 | 13.455 | 110.81 | SQM | 110.81 | 0 | 100% | 1490.9486 |  | 0
RUPAK NAYAK | TERRACE FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 381 | 13.455 | 128.79 | SQM | 128.79 | 0 | 100% | 1732.8694 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 2900 | 1 | LUMP SUM | 1 | 0 | 100% | 2900 |  | 0
CHIRANJEEVI | CUSTOMIZATION WORK/THE RATE IS INCLUSIVE OF MASONRY WORK/PLASTERING WORK/ELEVATION WORK | 462 | 8521 | 1 | LUMP SUM | 1 | 0 | 100% | 8521 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | CUSTOMISATION SS RALING FOR BALCONY (INCLUDING MATERIAL) | 478 | 4954 | 6.2 | RMT | 6.2 | 0 | 100% | 30714.8 |  | 0
1583.8066

## V64
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100% | 13191.8976 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0.002 | 99.97% | 1221.3936 |  | 0 | NAGARAJ | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100% | 4925.088 |  | 0 | PRAKASH H N | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100% | 3949.98 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | -0.004 | 100.1% | 3470 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | -0.004 | 100.1% | 2890 |  | 0 | SHOKAT | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | -0.004 | 100% | 9190 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100% | 2100 |  | 0 | SK ANSAR HOSSIAN | 3236.676
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100% | 3850 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 5600 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100% | 10500 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0 | YELLAPPA C | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0 | RABIUL MOLLA | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0 | KOUSHIK MANDAL | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0.0047 | 99.99% | 19144.4198 |  | 0 | TOTAL | 3236.676
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100% | 15578.9525 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100% | 46305.8669 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0% | 0 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0.002 | 99.98% | 2225.25 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0.002 | 99.92% | 3660 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100% | 1485 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100% | 7700 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100% | 15033.433 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100% | 39985.6766 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0.003 | 99.9% | 5880 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100% | 3082.5 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0 | 0.937 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100% | 700 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0 | 0.03 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100% | 8176.765 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0.002 | 99.92% | 542.25 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0% | 0 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100% | 22453.9193 |  | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100% | 25809.7039 |  | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0% | 0 |  | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0% | 0 |  | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0% | 0 |  | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 0 | 206.732 | 0% | 0 |  | 0
MD GIYAS | RCC SURFACE HACKING | 141 | 10.76 | 206.732 | SQM | 206.73 | 0.002 | 100% | 2224.4148 |  | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 0 | 71.63 | 0% | 0 |  | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 0 | 194.53 | 0% | 0 |  | 0
MD GIYAS | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
MD GIYAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100% | 27220.972 |  | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 0 | 208.32 | 0% | 0 |  | 0
MD GIYAS | GROUND FLOOR EXTERNAL WALL PLASTERING | 149 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100% | 40362.4166 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 0 | 74.392 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 0 | 220.467 | 0% | 0 |  | 0
MD GIYAS | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 74.392 | SQM | 74.39 | 0.002 | 100% | 10409.5415 |  | 0
MD GIYAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 220.467 | SQM | 220.47 | -0.003 | 100% | 30850.808 |  | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 0 | 142.16 | 0% | 0 |  | 0
MD GIYAS | FIRST FLOOR EXTERNAL WALL PLASTERING | 157 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100% | 27543.7843 |  | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 0 | 11.61 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 0 | 33.43 | 0% | 0 |  | 0
MD GIYAS | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
MD GIYAS | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100% | 4677.9268 |  | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 0 | 153.39 | 0% | 0 |  | 0
MD GIYAS | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100% | 29719.6193 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 146.17 | SQM | 146.17 | 0 | 100% | 31467.4776 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 46.657 | SQM | 46.66 | -0.003 | 100% | 10044.9648 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 32.679 | SQM | 32.68 | -0.001 | 100% | 3517.6752 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 79.939 | SQM | 79.94 | -0.001 | 100% | 17209.4832 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 123.624 | SQM | 123.62 | 0.004 | 100% | 13306.4568 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0.003 | 99.99% | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100% | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100% | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100% | 13137.0314 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0.004 | 99.99% | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0.004 | 100% | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0.003 | 100% | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0.001 | 100% | 15634.9791 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 18.85 | SQM | 18.85 | 0 | 100% | 5681.2392 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 10 | 3 | 76.92% | 3500 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.08 | RMT | 46.08 | 0 | 100% | 3778.56 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111 | RMT | 111 | 0 | 100% | 3640.8 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.93 | RMT | 23.93 | 0 | 100% | 3139.616 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100% | 4000 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 56.93 | SQM | 56.93 | 0 | 100% | 10418.19 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.49 | RMT | 47.49 | 0 | 100% | 2336.508 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 52.2 | SQM | 52.2 | 0 | 100% | 9552.6 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.84 | RMT | 50.84 | 0 | 100% | 2501.328 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.63 | SQM | 3.63 | 0 | 100% | 664.29 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.64 | RMT | 5.64 | 0 | 100% | 277.488 |  | 0
SK ANSAR HOSSIAN | UTILITY FLOOR TILING | 230 | 183 | 2.96 | SQM | 0 | 2.96 | 0% | 0 | 100% | 541.68
SK ANSAR HOSSIAN | UTILITY SKIRTING | 231 | 49.2 | 6.75 | RMT | 0 | 6.75 | 0% | 0 | 100% | 332.1
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 10.85 | SQM | 9.77 | 1.08 | 90.05% | 1787.91 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 16.47 | 1.83 | 90% | 810.324 |  | 0
SK ANSAR HOSSIAN | BALCONY & SITOUT TILING | 232 | 183 | 10.85 | SQM | 9.77 | 1.08 | 90.05% | 1787.91 | 10% | 198.555
SK ANSAR HOSSIAN | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 16.47 | 1.83 | 90% | 810.324 | 10% | 90.036
SK ANSAR HOSSIAN | CAR PARKING AREA TILING | 234 | 183 | 20.12 | SQM | 19.11 | 1.01 | 94.98% | 3497.13 | 5% | 184.098
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1232 | SFT | 1232 | 0 | 100% | 3080 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.18 | 0.56 | 85.03% | 581.94 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 15.4 | 2.72 | 84.99% | 2818.2 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.57 | SQM | 7.28 | 1.29 | 84.95% | 1332.24 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.43 | SQM | 32.67 | 5.76 | 85.01% | 5978.61 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.18 | 0.56 | 85.03% | 581.94 | 15% | 102.663
SK ANSAR HOSSIAN | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 15.4 | 2.72 | 84.99% | 2818.2 | 15% | 497.394
SK ANSAR HOSSIAN | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.57 | SQM | 7.28 | 1.29 | 84.95% | 1332.24 | 15% | 235.2465
SK ANSAR HOSSIAN | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.43 | SQM | 32.67 | 5.76 | 85.01% | 5978.61 | 15% | 1054.9035
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 138.88 | SQM | 138.88 | 0 | 100% | 8968.8704 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 30.7 | RMT | 30.7 | 0 | 100% | 169924.5 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
KRISHNAKUMAR SAHANI | FRONT OF THE HOUSE RAMP GRANITE | 286 | 301.392 | 4.8959 | SQM | 4.9 | -0.0041 | 100.1% | 1476.8208 |  | 0
KRISHNAKUMAR SAHANI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 39.52 | RMT | 0 | 39.52 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | SILL GRANITE | 289 | 75 | 116 | RFT | 116 | 0 | 100% | 8700 |  | 0
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 178 | 366 | SFT | 366 | 0 | 100% | 65148 |  | 0
KRISHNAKUMAR SAHANI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 4.317 | SQM | 0 | 4.317 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 89.526 | SQM | 89.53 | -0.004 | 100% | 4336.6541 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 89.526 | SQM | 89.53 | -0.004 | 100% | 1445.9095 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 89.526 | SQM | 89.53 | -0.004 | 100% | 2409.2523 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 14.102 | SQM | 14.1 | 0.002 | 99.99% | 227.715 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 14.102 | SQM | 14.1 | 0.002 | 99.99% | 455.3172 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION AQUAGUARD TAP POINT WORK | 420 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 432 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
KRISHNAKUMAR SAHANI | CUSTOMIZATION TOILET TILE WORK | 436 | 1018.78 | 4.05 | SQM | 4.05 | 0 | 100% | 4126.059 |  | 0
KRISHNAKUMAR SAHANI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 266.42 | 17.7 | SQM | 17.7 | 0 | 100% | 4715.634 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 7250 | 1 | LUMP SUM | 1 | 0 | 100% | 7250 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
RUPAK NAYAK | CUSTOMISATION EPOXY GROUTING & SOAP WASH | 480 | 64.58 | 21.75 | SQM | 21.75 | 0 | 100% | 1404.615 |  | 0
SANTOSH KUMAR | CAR PARKING BOUNDARY WALL TOP COPING GRANITE | 550 | 78 | 24.11 | RFT | 0 | 24.11 | 0% | 0 |  | 0
3236.676

## V65
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 13000
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100% | 13191.8976 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0.002 | 99.97% | 1221.3936 |  | 0 | NAGARAJ | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100% | 4925.088 |  | 0 | PRAKASH H N | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 10.81 | 0 | 100% | 1525.5072 |  | 0 | RUPAK NAYAK | 60809.2823
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 5500 | SANTOSH KUMAR | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | -0.004 | 100.1% | 3470 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | -0.004 | 100.1% | 2890 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | -0.004 | 100% | 9190 |  | 0 | SHOKAT | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100% | 2100 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0 | SK ANSAR HOSSIAN | 69165.3187
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100% | 3850 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 5600 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100% | 10500 |  | 0 | SUBHASMITA DAS | 12000
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0 | V VENKATANARAYANA | 5500
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0 | YELLAPPA C | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0 | RABIUL MOLLA | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0 | KOUSHIK MANDAL | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0.0047 | 99.99% | 19144.4198 |  | 0 | TOTAL | 160474.6009
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100% | 15578.9525 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100% | 46305.8669 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0% | 0 |  | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100% | 4813.2302 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0.002 | 99.98% | 2225.25 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0.002 | 99.92% | 3660 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0 | 0.99 | 0% | 0 |  | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100% | 1485 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100% | 7700 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100% | 15033.433 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100% | 39985.6766 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100% | 5087.497 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0.003 | 99.9% | 5880 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100% | 3082.5 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0 | 0.937 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | -0.003 | 100.3% | 1410 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100% | 700 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0 | 0.03 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0.03 | 0 | 100% | 210 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100% | 8176.765 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100% | 828.828 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0.002 | 99.92% | 542.25 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 41 | 3 | 93.18% | 2050 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100% | 22453.9193 |  | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100% | 25809.7039 |  | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0% | 0 |  | 0
SHEKAR T | ELEVATION RCC BAND | 135 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100% | 2101.824 |  | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0% | 0 |  | 0
SHEKAR T | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100% | 2102.48 |  | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0% | 0 |  | 0
MD GIYAS | RCC SURFACE HACKING | 141 | 10.76 | 206.732 | SQM | 206.73 | 0.002 | 100% | 2224.4148 |  | 0
MD GIYAS | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
SHEKAR T | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 97.265 | SQM | 97.27 | -0.005 | 100% | 13611.1856 |  | 0
MD GIYAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 194.53 | SQM | 97.27 | 97.26 | 50% | 13611.1856 |  | 0
SHEKAR T | GROUND FLOOR EXTERNAL WALL PLASTERING | 149 | 193.752 | 23.32 | SQM | 23.32 | 0 | 100% | 4518.2966 |  | 0
MD GIYAS | GROUND FLOOR EXTERNAL WALL PLASTERING | 149 | 193.752 | 208.32 | SQM | 185 | 23.32 | 88.81% | 35844.12 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
MD GIYAS | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 74.392 | SQM | 74.39 | 0.002 | 100% | 10409.5415 |  | 0
SHEKAR T | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 110.2335 | SQM | 110.23 | 0.0035 | 100% | 15424.7044 |  | 0
MD GIYAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 220.467 | SQM | 110.23 | 110.237 | 50% | 15424.7044 |  | 0
MD GIYAS | FIRST FLOOR EXTERNAL WALL PLASTERING | 157 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100% | 27543.7843 |  | 0
MD GIYAS | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
SHEKAR T | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 16.715 | SQM | 16.72 | -0.005 | 100% | 2339.663 |  | 0
MD GIYAS | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 33.43 | SQM | 16.72 | 16.71 | 50.01% | 2339.663 |  | 0
MD GIYAS | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100% | 29719.6193 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 135.83 | SQM | 135.83 | 0 | 100% | 29241.4824 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 21.683 | SQM | 21.68 | 0.003 | 99.99% | 4667.2704 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 32.765 | SQM | 32.77 | -0.005 | 100% | 3527.3628 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 91.645 | SQM | 91.65 | -0.005 | 100% | 19730.412 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 124.41 | SQM | 124.41 | 0 | 100% | 13391.4924 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 14 | 0 | 100% | 2800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 0 | 25.083 | 0% | 0 | 100% | 5399.8682
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 0 | 27.13 | 0% | 0 | 100% | 2628.3544
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 0 | 406.82 | 0% | 0 | 100% | 6570.143
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 0 | 406.82 | 0% | 0 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 0 | 58.064 | 0% | 0 | 100% | 937.7336
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 0 | 562.244 | 0% | 0 | 100% | 27233.9749
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 0 | 574.613 | 0% | 0 | 100% | 9279.9999
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 0 | 581.011 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 0 | 21.28 | 0% | 0 | 90% | 5772.2596
SK ANSAR HOSSIAN | DOOR OPENING GRANITE | 218 | 350 | 19 | NOS | 0 | 19 | 0% | 0 | 100% | 6650
SK ANSAR HOSSIAN | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 0 | 37.082 | 0% | 0 | 90% | 2736.6516
SK ANSAR HOSSIAN | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 0 | 111.25 | 0% | 0 | 90% | 3284.1
SK ANSAR HOSSIAN | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 0 | 27.298 | 0% | 0 | 90% | 3223.3478
SK ANSAR HOSSIAN | GROUND FLOOR TILING | 224 | 183 | 58.71 | SQM | 0 | 58.71 | 0% | 0 | 95% | 10206.7335
SK ANSAR HOSSIAN | GROUND FLOOR SKIRTING | 225 | 49.2 | 59 | RMT | 0 | 59 | 0% | 0 | 90% | 2612.52
SK ANSAR HOSSIAN | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 0 | 59.742 | 0% | 0 | 95% | 10386.1467
SK ANSAR HOSSIAN | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 0 | 69.16 | 0% | 0 | 90% | 3062.4048
SK ANSAR HOSSIAN | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 0 | 3.69 | 0% | 0 | 95% | 641.5065
SK ANSAR HOSSIAN | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 0 | 5.6 | 0% | 0 | 90% | 247.968
SK ANSAR HOSSIAN | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 0 | 2.512 | 0% | 0 | 0% | 0
SK ANSAR HOSSIAN | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 0 | 7.61 | 0% | 0 | 0% | 0
SK ANSAR HOSSIAN | BALCONY & SITOUT TILING | 232 | 183 | 7.41 | SQM | 0 | 7.41 | 0% | 0 | 95% | 1288.2285
SK ANSAR HOSSIAN | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 11.15 | RMT | 0 | 11.15 | 0% | 0 | 90% | 493.722
SK ANSAR HOSSIAN | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 0 | 27.18 | 0% | 0 | 0% | 0
SK ANSAR HOSSIAN | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 0 | 1182 | 0% | 0 | 100% | 2955
SK ANSAR HOSSIAN | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 0 | 4.062 | 0% | 0 | 95% | 706.1787
SK ANSAR HOSSIAN | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 16.19 | SQM | 0 | 16.19 | 0% | 0 | 90% | 2666.493
SK ANSAR HOSSIAN | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 0 | 8.15 | 0% | 0 | 95% | 1416.8775
SK ANSAR HOSSIAN | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 30.83 | SQM | 0 | 30.83 | 0% | 0 | 90% | 5077.701
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 6000
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 4000
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 12000
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 295 | 290 | 371.67 | SFT | 371.67 | 0 | 100% | 107784.3 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1000
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 1500 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 8086.35 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 4043.175 |  | 0
SK ANSAR HOSSIAN | ...LABOUR FOR CUSTOMISATION TERRACE FLOOR TOILET FLOOR TILE WORK/LAYING OF CERAMIC FLOOR TILES OF 300X300MM SIZE OF APPROVED MAKE IN FLOORING LAID IN PAT | 411 | 183 | 4.016 | SQM | 0 | 4.016 | 0% | 0 | 95% | 698.1816
SK ANSAR HOSSIAN | ...LABOUR FOR CUSTOMISATION TERRACE FLOOR TOILET WALL TILE WORK/LAYING OF CERAMIC WALL TILES OF 300X600MM SIZE OF APPROVED MAKE IN PLASTERING LAID IN PAT | 412 | 49.2 | 18.4189 | RMT | 0 | 18.4189 | 0% | 0 | 90% | 815.5889
SK ANSAR HOSSIAN | LABOR FOR CUSTOMIZATION MAIN FLOORING WORK/THE RATE IS INCLUSIVE OF FLOOR CHIPPING/MAIN FLOORING AND SKIRTING WORK |  | 232.9217 | 19.088 | SQM | 0 | 19.088 | 0% | 0 | 95% | 4223.7089
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 0.5 | 0.5 | 50% | 750 |  | 0
MD GIYAS | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 33.5 | SQM | 33.5 | 0 | 100% | 6490.625 |  | 0
MD GIYAS | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 64.05 | SQM | 64.05 | 0 | 100% | 8962.6446 |  | 0
MD GIYAS | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 39.24 | SQM | 39.24 | 0 | 100% | 7602.8285 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL PAINTING WORK (3 COAT PUTTY, 1 COAT PRIMER, 2 COAT PAINT) | 466 | 193.752 | 62.404 | SQM | 0 | 62.404 | 0% | 0 | 33% | 3989.9969
RUPAK NAYAK | CUSTOMIZATION ROOM EXTERNAL PAINTING WORK (1 COAT PRIMER, 2 COAT PAINT) | 467 | 193.752 | 74.591 | SQM | 0 | 74.591 | 0% | 0 | 33% | 4769.2113
160474.6009

## V66
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 42.12 | 49.74 | 45.852 | 2274.48 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 3405.06 | 1 | LUMP SUM | 1 | 0 | 100 | 3405.06 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 0 | 34.9 | 0 | 0 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 0 | 91.86 | 0 | 0 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 0 | 91.86 | 0 | 0 | 0 | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0 | 0 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 0 | 9.19 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100 | 2100 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100 | 5600 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100 | 10500 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0 | 0 | 0 | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 63 | SFT | 63 | 0 | 100 | 1764 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0 | 0.99 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0 | 0.94 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100 | 1750 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0 | 0 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 0 | 115.89 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 0 | 133.21 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 0 | 67.31 | 0 | 0 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0 | 0 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0 | 0 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
MD GIYAS | RCC SURFACE HACKING | 141 | 10.76 | 206.732 | SQM | 206.73 | 0 | 100 | 2224.4148 | 0 | 0
MD GIYAS | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
MD GIYAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
MD GIYAS | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
MD GIYAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
MD GIYAS | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
MD GIYAS | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 100 | 53.39 | 65.193 | 19375.2 | 0 | 0
MD GIYAS | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 53.39 | SQM | 0 | 53.39 | 0 | 0 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 140.373 | SQM | 140.37 | 0 | 100 | 30218.8536 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 40.79 | SQM | 40.79 | 0 | 100 | 8781.2712 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 35.424 | SQM | 35.42 | 0 | 100 | 3812.6088 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 86.36 | SQM | 86.36 | 0 | 100 | 18591.5808 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 35.424 | SQM | 0 | 35.42 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 0 | 14 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 14 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | 0 | 100
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 58.71 | SQM | 52.85 | 5.86 | 90.019
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 59 | RMT | 50 | 9 | 84.746
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 52.7 | 7.04 | 88.213
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 57.16 | 12 | 82.649
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 0 | 5.6 | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 7.41 | SQM | 7.41 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 11.15 | RMT | 11.15 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 4.06 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 16.19 | SQM | 15 | 1.19 | 92.65
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 7 | 1.15 | 85.89
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 30.83 | SQM | 25 | 5.83 | 81.09
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 132.064 | SQM | 132.06 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 23.6 | RMT | 23.6 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
KRISHNAKUMAR SAHANI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 39.78 | RMT | 39.78 | 0 | 100
KRISHNAKUMAR SAHANI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 4.33 | SQM | 4.33 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0

## V67
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100 | 8160.48 | 0 | 0
SUBHASMITA DAS | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
SUBHASMITA DAS | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
SUBHASMITA DAS | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100 | 34958.952 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100 | 1816.54 | 0 | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100 | 19096.3584 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100 | 1934.7552 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 47.25 | CUM | 47.25 | 0 | 100 | 6667.92 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 15.55 | CUM | 15.55 | 0 | 100 | 2194.416 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100 | 3324.64 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 151.12 | 0 | 100 | 6498.16 | 0 | 0
SUBHASMITA DAS | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 15.63 | 0 | 100 | 2205.7056 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0 | 100 | 5680 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0 | 100 | 4570 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | 0 | 100 | 15110 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100 | 4550 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100 | 5250 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100 | 7000 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.9 | MT | 0.9 | 0 | 100 | 6300 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.8 | MT | 2.8 | 0 | 100 | 19600 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100 | 15105.767 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100 | 9545.0846 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100 | 31679.3131 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100 | 18056.3947 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100 | 78786.8827 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100 | 4394.2954 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 18.25 | 0 | 100 | 5500.404 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100 | 5240.25 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100 | 3930 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100 | 6669 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100 | 7020 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | 0 | 100 | 6754.5 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0.8 | 0 | 100 | 1200 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 1 | MT | 1 | 0 | 100 | 7000 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 2.4 | MT | 2.4 | 0 | 100 | 16800 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100 | 18505.4688 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100 | 73262.3674 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100 | 4394.2954 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 20.55 | 0 | 100 | 6193.6056 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | 0 | 100 | 7180 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | 0 | 100 | 6099.75 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 1.28 | 0 | 100 | 1920 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100 | 1750 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.04 | MT | 0.04 | 0 | 100 | 280 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100 | 8854.897 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 3.81 | 0 | 100 | 1148.3035 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | 0 | 100 | 636.75 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100 | 2600 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100 | 37173.2587 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100 | 39438.2196 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100 | 16906.7995 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 47.7 | 0 | 100 | 3129.12 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 64.23 | 0 | 100 | 4213.488 | 0 | 0
SUBHASMITA DAS | RCC SURFACE HACKING | 140 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100 | 3962.5852 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 119.78 | 0 | 100 | 16761.055 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100 | 37443.0046 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100 | 60041.8073 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100 | 15000 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100 | 16556.7542 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100 | 51264.0882 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100 | 40515.4807 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 0 | 14.1 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 0 | 37.29 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100 | 34983.8611 | 0 | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 68 | SQM | 68 | 0 | 100 | 29278.08 | 0 | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 124.278 | SQM | 124.28 | 0 | 100 | 53509.9968 | 0 | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 22.29 | SQM | 22.29 | 0 | 100 | 4798.5912 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 51.09 | SQM | 51.09 | 0 | 100 | 10998.6552 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 19 | SQM | 19 | 0 | 100 | 3800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 27.313 | SQM | 27.31 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 531.773 | SQM | 531.77 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 531.77 | SQM | 531.77 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 609.07 | SQM | 609.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 609.07 | SQM | 609.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 609.07 | SQM | 609.07 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 31.14 | SQM | 31.14 | 0 | 100
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 5 | NOS | 0 | 5 | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 21 | NOS | 5 | 16 | 23.81
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 43.44 | RMT | 43.44 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 130.32 | RMT | 130.32 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 32.22 | RMT | 32.22 | 0 | 100
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 6 | NOS | 4 | 2 | 66.667
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 84.56 | SQM | 65 | 19.56 | 76.868
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 85.8 | RMT | 65 | 20.8 | 75.758
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 84.38 | SQM | 65 | 19.38 | 77.032
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 96.78 | RMT | 96.78 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.698 | SQM | 0 | 3.7 | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.86 | RMT | 0 | 5.86 | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 7.3 | SQM | 7.3 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 12.8 | RMT | 12.8 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 25.7 | SQM | 25.7 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 43.7 | RMT | 43.7 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 33.63 | SQM | 33.63 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1843 | SFT | 1843 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 7.49 | SQM | 7.49 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 34.903 | SQM | 34.9 | 0 | 99.991
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 11.93 | SQM | 11.93 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 52.68 | SQM | 52.68 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 225.058 | SQM | 0 | 225.06 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 2 | LUMP SUM | 2 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 4000 | 1 | LUMP SUM | 0.5 | 0.5 | 50
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 30.15 | RMT | 25.41 | 4.74 | 84.279
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 6 | NOS | 6 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 81.132 | SQM | 0 | 81.13 | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 81.132 | SQM | 0 | 81.13 | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 81.132 | SQM | 0 | 81.13 | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 24.091 | SQM | 0 | 24.09 | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 24.091 | SQM | 0 | 24.09 | 0
SHOKAT | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 3.625 | SQM | 3.63 | 0 | 100
SHOKAT | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 6.7845 | SQM | 6.78 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 10000 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION FLOOR INTERNAL CEILING THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERNAL EMULSION PAINTING WORK | 482 | 91.49 | 24.82 | SQM | 17.37 | 7.45 | 70
RUPAK NAYAK | CUSTOMIZATION FLOOR INTERNAL WALL THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERNAL EMULSION PAINTING WORK | 483 | 91.494 | 54.06 | SQM | 37.84 | 16.22 | 70
RUPAK NAYAK | CUSTOMIZATION FLOOR EXTERNAL WALL ONE COAT PRIMER, TWO COATS EXTERNAL EMULSION PAINTING WORK | 484 | 48.438 | 30.95 | SQM | 21.67 | 9.29 | 70

## V68
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
RABIUL MOLLA | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
RABIUL MOLLA | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
RABIUL MOLLA | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
RABIUL MOLLA | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
RABIUL MOLLA | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
RABIUL MOLLA | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
RABIUL MOLLA | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
RABIUL MOLLA | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
RABIUL MOLLA | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0 | 0 | 0 | 0
RABIUL MOLLA | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
RABIUL MOLLA | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
RABIUL MOLLA | FOOTING REINFORCEMENT | 23 | 7500 | 0.4 | MT | 0.4 | 0 | 100 | 3000 | 0 | 0
RABIUL MOLLA | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
RABIUL MOLLA | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.6 | MT | 0.6 | 0 | 100 | 4500 | 0 | 0
RABIUL MOLLA | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 0 | 1.45 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0 | 0.17 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
RABIUL MOLLA | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
RABIUL MOLLA | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
RABIUL MOLLA | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
RABIUL MOLLA | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 45.16 | 2.38 | 95 | 13610.8627 | 0 | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 0 | 153.89 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 0 | 12.78 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0 | 0 | 0 | 0
RABIUL MOLLA | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
RABIUL MOLLA | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
RABIUL MOLLA | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
RABIUL MOLLA | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.21 | 0.17 | 95 | 6420 | 0 | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 0 | 17.15 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 0 | 1.81 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0 | 0.63 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0 | 0.55 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 0 | 1.2 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0 | 0.17 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 0 | 39.44 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 0 | 128.66 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 0 | 12.78 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.5 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 0 | 2.29 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 0 | 13.96 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 0 | 1.81 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0 | 0.7 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0 | 0.2 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 10000 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 0 | 28.13 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.46 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0 | 0.71 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 0 | 2.67 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0 | 0.2 | 0 | 0 | 0 | 0
RABIUL MOLLA | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 0 | 41 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 0 | 112.22 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 0 | 133.46 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 0 | 71.27 | 0 | 0 | 0 | 0
RABIUL MOLLA | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 0 | 32.74 | 0 | 0 | 0 | 0
RABIUL MOLLA | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0 | 0 | 0 | 0
RABIUL MOLLA | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0 | 0.66 | 0 | 0 | 0 | 0
RABIUL MOLLA | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 0 | 201.86 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 0 | 72.04 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 0 | 187.02 | 0 | 0 | 0 | 0
RABIUL MOLLA | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 0 | 201.85 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 0 | 64.64 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 0 | 206.23 | 0 | 0 | 0 | 0
RABIUL MOLLA | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 0 | 132.03 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 0 | 12.3 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 0 | 39.21 | 0 | 0 | 0 | 0
RABIUL MOLLA | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 0 | 138.78 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RABIUL MOLLA | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 252.861 | SFT | 125 | 127.86 | 49.434 | 38750 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V69
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SHEKAR T | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 0 | 78.8 | 0% | 0 |  | 0 | AAIDHUL MIAH | 0
SHEKAR T | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
SHEKAR T | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
SHEKAR T | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0.004 | 100% | 24110.352 |  | 0 | KRIUTTIBAS DAS | 0
SHEKAR T | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0.002 | 100% | 1252.9 |  | 0 | LEGENDRY LANDSCAPE | 0
SHEKAR T | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0.004 | 100% | 13692.8736 |  | 0 | MANJUNATHA P | 0
SHEKAR T | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0.002 | 99.97% | 1318.7664 |  | 0 | NAGARAJ | 0
SHEKAR T | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0.002 | 99.99% | 5560.128 |  | 0 | PRAKASH H N | 0
SHEKAR T | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100% | 1733.6 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SHEKAR T | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
SHEKAR T | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0.001 | 99.98% | 4130 |  | 0 | SANTOSH KUMAR | 0
SHEKAR T | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | -0.004 | 100.1% | 3120 |  | 0 | SARAT BARMAN | 0
SHEKAR T | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100% | 7880 |  | 0 | SAVITA DEVI | 0
SHEKAR T | FOOTING REINFORCEMENT | 23 | 7500 | 0.4 | MT | 0.4 | 0 | 100% | 3000 |  | 0 | SHOKAT | 0
SHEKAR T | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100% | 3375 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SHEKAR T | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.6 | MT | 0.6 | 0 | 100% | 4500 |  | 0 | SK ANSAR HOSSIAN | 0
SHEKAR T | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 1.45 | 0 | 100% | 10875 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0 | SUBHASMITA DAS | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.1 | MT | 0 | 0.1 | 0% | 0 |  | 0 | UDHABHAI R PARMAR | 0
SHEKAR T | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | -0.005 | 100% | 10627.0819 |  | 0 | V VENKATANARAYANA | 0
SHEKAR T | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100% | 8336.5027 |  | 0 | YELLAPPA C | 0
SHEKAR T | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | -0.001 | 100% | 20145.0413 |  | 0 | RABIUL MOLLA | 0
SHEKAR T | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | -0.005 | 100% | 14328.1757 |  | 0 | KOUSHIK MANDAL | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0.004 | 100% | 46381.2149 |  | 0 | SHEKAR T | 80260.4114
SHEKAR T | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0.0044 | 99.97% | 3851.7898 |  | 0 | TOTAL | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0% | 0 |  | 0
SHEKAR T | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0.001 | 99.99% | 2493 |  | 0
SHEKAR T | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100% | 2400 |  | 0
SHEKAR T | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0.004 | 99.91% | 4203 |  | 0
SHEKAR T | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0.001 | 99.97% | 6760 |  | 0
SHEKAR T | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | -0.001 | 100% | 3858.75 |  | 0
SHEKAR T | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | -0.002 | 100.1% | 3620 |  | 0
SHEKAR T | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0 | 0.626 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHEKAR T | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0 | 0.55 | 0% | 0 | 100% | 4125
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 0 | 1.2 | 0% | 0 | 100% | 9000
SHEKAR T | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0 | 0.17 | 0% | 0 | 100% | 1275
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 0 | 39.435 | 0% | 0 | 100% | 11885.3935
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 0 | 128.662 | 0% | 0 | 100% | 38777.6975
SHEKAR T | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 0 | 12.784 | 0% | 0 | 100% | 3852.9953
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.495 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 0 | 2.294 | 0% | 0 | 100% | 4588
SHEKAR T | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 0 | 13.957 | 0% | 0 | 100% | 3140.325
SHEKAR T | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 0 | 1.808 | 0% | 0 | 100% | 3616
SHEKAR T | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0 | 0.699 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0 | 0.2 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 10000 | 0.02 | MT | 0 | 0.02 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 0 | 28.129 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.455 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0 | 0.709 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 0 | 2.668 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0 | 0.196 | 0% | 0 |  | 0
SHEKAR T | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 0 | 41 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHEKAR T | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 0 | 112.22 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 0 | 133.46 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 0 | 71.27 | 0% | 0 |  | 0
SHEKAR T | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 0 | 32.74 | 0% | 0 |  | 0
SHEKAR T | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0% | 0 |  | 0
SHEKAR T | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0 | 0.66 | 0% | 0 |  | 0
SHEKAR T | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 0 | 201.86 | 0% | 0 |  | 0
SHEKAR T | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 0 | 72.04 | 0% | 0 |  | 0
SHEKAR T | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 0 | 187.02 | 0% | 0 |  | 0
SHEKAR T | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 0 | 201.853 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 0 | 64.644 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 0 | 206.23 | 0% | 0 |  | 0
SHEKAR T | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 0 | 132.03 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 0 | 12.3 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 0 | 39.21 | 0% | 0 |  | 0
SHEKAR T | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 0 | 138.781 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHEKAR T | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 252.86 | SFT | 96.09 | 156.77 | 38% | 29787.9 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
80260.4114

## V70
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
RABIUL MOLLA | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 0 | 78.8 | 0% | 0 |  | 0 | AAIDHUL MIAH | 0
DEEPA B | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
DEEPA B | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
DEEPA B | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0.004 | 100% | 24110.352 |  | 0 | KRIUTTIBAS DAS | 0
DEEPA B | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0.002 | 100% | 1252.9 |  | 0 | LEGENDRY LANDSCAPE | 0
RABIUL MOLLA | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0.004 | 100% | 13692.8736 |  | 0 | MANJUNATHA P | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0.002 | 99.97% | 1318.7664 |  | 0 | NAGARAJ | 0
RABIUL MOLLA | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0.002 | 99.99% | 5560.128 |  | 0 | PRAKASH H N | 2000
RABIUL MOLLA | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 0 | 78.8 | 0% | 0 |  | 0 | RAMAKRUSHNA PRADHAN | 0
RABIUL MOLLA | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
DEEPA B | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0.001 | 99.98% | 4130 |  | 0 | SANTOSH KUMAR | 0
RABIUL MOLLA | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | -0.004 | 100.1% | 3120 |  | 0 | SARAT BARMAN | 0
RABIUL MOLLA | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 0 | 7.88 | 0% | 0 |  | 0 | SAVITA DEVI | 0
DEEPA B | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100% | 2800 |  | 0 | SHOKAT | 0
DEEPA B | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100% | 3150 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
RABIUL MOLLA | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100% | 4200 |  | 0 | SK ANSAR HOSSIAN | 0
RABIUL MOLLA | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.48 | 0.02 | 96% | 3360 | 4% | 140 | SREE VINAYAKA ELECTRICALS | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 0 | 1.45 | 0% | 0 | 100% | 10150 | SRI CHOWDESHWARI WATER SUPPLY | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.16 | 0.01 | 94.12% | 1120 | 5.882% | 70 | SUBHASMITA DAS | 0
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0 | 0.1 | 0% | 0 |  | 0 | UDHABHAI R PARMAR | 0
DEEPA B | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | -0.005 | 100% | 10627.0819 |  | 0 | V VENKATANARAYANA | 0
RABIUL MOLLA | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100% | 8336.5027 |  | 0 | YELLAPPA C | 0
RABIUL MOLLA | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | -0.001 | 100% | 20145.0413 |  | 0 | RABIUL MOLLA | 21402.4441
RABIUL MOLLA | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 45.16 | 2.375 | 95% | 13610.8627 | 4.996% | 715.806 | KOUSHIK MANDAL | 0
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 146.2 | 7.694 | 95% | 44063.5104 | 5% | 2318.91 | SHEKAR T | 0
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.15 | 0.6344 | 95.04% | 3661.9128 | 4.962% | 191.2031 | TOTAL | 23402.4441
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0% | 0 |  | 0
DEEPA B | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0.001 | 99.99% | 2493 |  | 0
RABIUL MOLLA | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100% | 2400 |  | 0
RABIUL MOLLA | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0.004 | 99.91% | 4203 |  | 0
RABIUL MOLLA | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.21 | 0.171 | 94.94% | 6420 | 5.058% | 342
RABIUL MOLLA | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 0 | 17.149 | 0% | 0 | 100% | 3858.525
RABIUL MOLLA | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 0 | 1.808 | 0% | 0 | 100% | 3616
RABIUL MOLLA | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0 | 0.626 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
RABIUL MOLLA | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.55 | MT | 0 | 0.55 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.2 | MT | 0 | 1.2 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.17 | MT | 0 | 0.17 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 0 | 39.435 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 0 | 128.662 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 0 | 12.784 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.495 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 0 | 2.294 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 0 | 13.957 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 0 | 1.808 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0 | 0.699 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0 | 0.2 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0 | 0.02 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 0 | 28.129 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.455 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0 | 0.709 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 0 | 2.668 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0 | 0.196 | 0% | 0 |  | 0
RABIUL MOLLA | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 0 | 41 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 0 | 112.22 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 0 | 133.46 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 0 | 71.27 | 0% | 0 |  | 0
RABIUL MOLLA | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 0 | 32.74 | 0% | 0 |  | 0
RABIUL MOLLA | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0% | 0 |  | 0
RABIUL MOLLA | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0 | 0.66 | 0% | 0 |  | 0
RABIUL MOLLA | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 0 | 201.86 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 0 | 72.04 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 0 | 187.02 | 0% | 0 |  | 0
RABIUL MOLLA | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 0 | 201.853 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 0 | 64.644 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 0 | 206.23 | 0% | 0 |  | 0
RABIUL MOLLA | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 0 | 132.03 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 0 | 12.3 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 0 | 39.21 | 0% | 0 |  | 0
RABIUL MOLLA | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 0 | 138.781 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
DEEPA B | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 65.55 | SFT | 65 | 0.55 | 99.16% | 20150 |  | 0
RABIUL MOLLA | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 494.02 | SFT | 100 | 394.02 | 20.24% | 31000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
23402.4441

## V71
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 0 | 78.8 | 0% | 0 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0.004 | 100% | 24110.352 |  | 0 | KRIUTTIBAS DAS | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0.002 | 100% | 1252.9 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 78 | 19.034 | 80.38% | 11007.36 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0.002 | 99.97% | 1318.7664 |  | 0 | NAGARAJ | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 0 | 39.402 | 0% | 0 |  | 0 | PRAKASH H N | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 0 | 78.8 | 0% | 0 |  | 0 | RAMAKRUSHNA PRADHAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SANTOSH KUMAR | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0.001 | 99.98% | 4130 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | -0.004 | 100.1% | 3120 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 0 | 7.88 | 0% | 0 |  | 0 | SHOKAT | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100% | 2800 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100% | 3150 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100% | 4200 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100% | 3500 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 1.45 | 0 | 100% | 10150 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.17 | 0 | 100% | 1190 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | -0.005 | 100% | 10627.0819 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100% | 8336.5027 |  | 0 | YELLAPPA C | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | -0.001 | 100% | 20145.0413 |  | 0 | RABIUL MOLLA | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | -0.005 | 100% | 14328.1757 |  | 0 | KOUSHIK MANDAL | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0.004 | 100% | 46381.2149 |  | 0 | SHEKAR T | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0.0044 | 99.97% | 3851.7898 |  | 0 | TOTAL | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0.001 | 99.99% | 2493 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100% | 2400 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0.004 | 99.91% | 4203 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0.001 | 99.97% | 6760 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | -0.001 | 100% | 3858.75 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | -0.002 | 100.1% | 3620 |  | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.626 | CUM | 0.63 | -0.004 | 100.6% | 1890 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.55 | MT | 0.55 | 0 | 100% | 3850 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.2 | MT | 1.2 | 0 | 100% | 8400 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.17 | MT | 0.17 | 0 | 100% | 1190 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.43 | 0.005 | 99.99% | 11883.8866 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0.002 | 100% | 38777.0947 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0.004 | 99.97% | 3851.7898 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0.004 | 99.83% | 4580 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | -0.003 | 100% | 3141 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | -0.002 | 100.1% | 3620 |  | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.699 | CUM | 0.7 | -0.001 | 100.1% | 2100 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0 | 0.2 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | -0.001 | 100% | 8478.157 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | -0.001 | 100.1% | 1420 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 600.75 |  | 0
CHIRANJEEVI | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.196 | CUM | 0.2 | -0.004 | 102% | 600 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100% | 2050 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 121 | 193.752 | 117.0569 | SQM | 117.06 | -0.0031438 | 100% | 22680.6091 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 125 | 193.752 | 137.031 | SQM | 137.03 | 0.001 | 100% | 26549.8366 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 130 | 193.752 | 67.819 | SQM | 67.82 | -0.001 | 100% | 13140.2606 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100% | 4736.976 |  | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 8.3 | SQM | 8.3 | 0 | 100% | 1340.118 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 141 | 10.76 | 371.6 | SQM | 371.6 | 0 | 100% | 3998.416 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100% | 27220.972 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 149 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100% | 40362.4166 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 89.92 | SQM | 89.92 | 0 | 100% | 12582.6854 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 268.42 | SQM | 268.42 | 0 | 100% | 37560.5474 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 157 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100% | 27543.7843 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100% | 4677.9268 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 75.29 | SQM | 75.29 | 0 | 100% | 14587.5881 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 142.31 | SQM | 142.31 | 0 | 100% | 30636.4968 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 61.741 | SQM | 61.74 | 0.001 | 100% | 13291.3872 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 29.957 | SQM | 29.96 | -0.003 | 100% | 3224.8944 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 76.679 | SQM | 76.68 | -0.001 | 100% | 16507.6704 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 29.957 | SQM | 29.96 | -0.003 | 100% | 3224.8944 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0.004 | 99.98% | 4299.1416 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | -0.004 | 100% | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100% | 6462.0995 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100% | 12920.998 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100% | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100% | 29641.1497 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100% | 9882.831 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100% | 16467.3054 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 18.85 | SQM | 18.85 | 0 | 100% | 5681.2392 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100% | 1350 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 13 | 0 | 100% | 4550 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.08 | RMT | 46.08 | 0 | 100% | 3778.56 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111 | RMT | 111 | 0 | 100% | 3640.8 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.93 | RMT | 23.93 | 0 | 100% | 3139.616 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100% | 3000 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 56.93 | SQM | 56.93 | 0 | 100% | 10418.19 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.49 | RMT | 47.49 | 0 | 100% | 2336.508 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 52.2 | SQM | 52.2 | 0 | 100% | 9552.6 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.84 | RMT | 50.84 | 0 | 100% | 2501.328 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.63 | SQM | 3.63 | 0 | 100% | 664.29 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.64 | RMT | 5.64 | 0 | 100% | 277.488 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.96 | SQM | 0 | 2.96 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 6.75 | RMT | 0 | 6.75 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 10.85 | SQM | 10.85 | 0 | 100% | 1985.55 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 12.81 | 5.49 | 70% | 630.252 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 20.12 | SQM | 20.12 | 0 | 100% | 3681.96 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1232 | SFT | 1232 | 0 | 100% | 3080 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.74 | 0 | 100% | 684.42 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 18.12 | 0 | 100% | 3315.96 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.57 | SQM | 7.28 | 1.29 | 84.95% | 1332.24 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.43 | SQM | 38.43 | 0 | 100% | 7032.69 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 139.18 | SQM | 139.18 | 0 | 100% | 8988.2444 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 31.37 | RMT | 31.37 | 0 | 100% | 173632.95 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100% | 1350 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100% | 5625 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
CHIRANJEEVI | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 3 | NOS | 3 | 0 | 100% | 2250 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 2750 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 2 | NOS | 1 | 1 | 50% | 1000 |  | 0
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100% | 800 |  | 0

## V72
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 78.8 | SQM | 78.8 | 0 | 100 | 3388.4 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100 | 2800 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100 | 4200 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 1.45 | 0 | 100 | 10150 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100 | 3779.4557 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0.63 | 0 | 100 | 945 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 15.5 | 0 | 100 | 4671.576 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0.7 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 2.46 | 0 | 100 | 741.4243 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100 | 4736.976 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100 | 106.5636 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0 | 100 | 26888.9026 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 177.84 | SQM | 177.84 | 0 | 100 | 38285.3952 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 44.738 | SQM | 44.74 | 0 | 100 | 9631.6272 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 33.599 | SQM | 33.6 | 0 | 100 | 3616.704 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 99.327 | SQM | 99.33 | 0 | 100 | 21383.7624 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 33.599 | SQM | 33.6 | 0 | 100 | 3616.704 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 22 | NOS | 22 | 0 | 100 | 4400 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 18.85 | SQM | 18.85 | 0 | 100
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 10 | 3 | 76.923
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.08 | RMT | 46.08 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111 | RMT | 111 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.93 | RMT | 23.93 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 56.93 | SQM | 56.93 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.49 | RMT | 47.49 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 52.2 | SQM | 52.2 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.84 | RMT | 50.84 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.63 | SQM | 3.63 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.64 | RMT | 5.64 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.96 | SQM | 0 | 2.96 | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 6.75 | RMT | 0 | 6.75 | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 10.85 | SQM | 10.85 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 18.3 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 20.12 | SQM | 20.12 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1232 | SFT | 1232 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.74 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 18.12 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.57 | SQM | 8.57 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.43 | SQM | 38.43 | 0 | 100
TANMAY | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 136.904 | SQM | 109.52 | 27.38 | 80
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 31.22 | RMT | 30.22 | 1 | 96.797
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
KRISHNAKUMAR SAHANI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 25 | RMT | 0 | 25 | 0
KRISHNAKUMAR SAHANI | SILL GRANITE | 289 | 75 | 73 | RFT | 73 | 0 | 100
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 224 | 191 | SFT | 191 | 0 | 100
YELLAPPA C | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 174 | 290 | SFT | 290 | 0 | 100
KRISHNAKUMAR SAHANI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 2.787 | SQM | 0 | 2.79 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 5250 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION FLOOR ROOF CONDUIT WORK | 457 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100
YELLAPPA C | CUSTOMIZATION UTILITY ROOF SLAB EXTENSION WORK | 485 | 230 | 105 | SFT | 105 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASH BASIN POINT WORK | 486 | 1000 | 1 | NOS | 1 | 0 | 100
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100

## V73
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
YELLAPPA C | BASE FLOOR SOLING WORK | 15 | 43 | 78.8 | SQM | 78.8 | 0 | 100 | 3388.4 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100 | 2800 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100 | 4200 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 1.45 | 0 | 100 | 10150 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100 | 3779.4557 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0.63 | 0 | 100 | 945 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 15.5 | 0 | 100 | 4671.576 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0.7 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 2.46 | 0 | 100 | 741.4243 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100 | 4736.976 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100 | 106.5636 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0 | 100 | 26888.9026 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 172.778 | SQM | 172.78 | 0 | 100 | 37196.0784 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 44.738 | SQM | 44.74 | 0 | 100 | 9631.6272 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 33.599 | SQM | 33.6 | 0 | 100 | 3616.704 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 99.327 | SQM | 99.33 | 0 | 100 | 21383.7624 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 33.599 | SQM | 33.6 | 0 | 100 | 3616.704 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100 | 3400 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 18.85 | SQM | 18.85 | 0 | 100
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 10 | 3 | 76.923
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.08 | RMT | 46.08 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111 | RMT | 111 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.93 | RMT | 23.93 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 56.93 | SQM | 56.93 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.49 | RMT | 47.49 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 52.2 | SQM | 52.2 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.84 | RMT | 50.84 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.63 | SQM | 3.63 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.64 | RMT | 5.64 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.96 | SQM | 0 | 2.96 | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 6.75 | RMT | 0 | 6.75 | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 10.85 | SQM | 10.85 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 18.3 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 20.12 | SQM | 20.12 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1232 | SFT | 1232 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.74 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 18.12 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.57 | SQM | 8.57 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.43 | SQM | 38.43 | 0 | 100
TANMAY | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 136.904 | SQM | 109.52 | 27.38 | 80
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 31.22 | RMT | 30.22 | 1 | 96.797
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
KRISHNAKUMAR SAHANI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 25 | RMT | 0 | 25 | 0
KRISHNAKUMAR SAHANI | SILL GRANITE | 289 | 75 | 73 | RFT | 73 | 0 | 100
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 232 | 215 | SFT | 215 | 0 | 100
YELLAPPA C | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 174 | 290 | SFT | 290 | 0 | 100
KRISHNAKUMAR SAHANI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 2.787 | SQM | 0 | 2.79 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 5700 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION FLOOR ROOF CONDUIT WORK | 457 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100
YELLAPPA C | CUSTOMIZATION UTILITY ROOF SLAB EXTENSION WORK | 485 | 230 | 105 | SFT | 105 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASH BASIN POINT WORK | 486 | 1000 | 1 | NOS | 1 | 0 | 100
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100

## V74
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100 | 2800 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100 | 4200 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 1.45 | 0 | 100 | 10150 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100 | 3779.4557 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0.63 | 0 | 100 | 945 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 15.5 | 0 | 100 | 4671.576 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0.7 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 2.46 | 0 | 100 | 741.4243 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100 | 4736.976 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100 | 106.5636 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0 | 100 | 26888.9026 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 142.31 | SQM | 142.31 | 0 | 100 | 30636.4968 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 61.741 | SQM | 61.74 | 0 | 100 | 13291.3872 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 29.957 | SQM | 29.96 | 0 | 100 | 3224.8944 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 76.679 | SQM | 76.68 | 0 | 100 | 16507.6704 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 29.957 | SQM | 29.96 | 0 | 100 | 3224.8944 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100 | 3400 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 18.85 | SQM | 18.85 | 0 | 100
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 13 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.08 | RMT | 46.08 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111 | RMT | 111 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.93 | RMT | 23.93 | 0 | 100
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 56.93 | SQM | 56.93 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.49 | RMT | 47.49 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 52.2 | SQM | 52.2 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.84 | RMT | 50.84 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.63 | SQM | 3.63 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.64 | RMT | 5.64 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.96 | SQM | 0 | 2.96 | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 6.75 | RMT | 0 | 6.75 | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 10.85 | SQM | 10.85 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 18.3 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 20.12 | SQM | 20.12 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1232 | SFT | 1232 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.74 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 18.12 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.57 | SQM | 8.57 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.43 | SQM | 38.43 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 138.88 | SQM | 138.88 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 30.55 | RMT | 17.47 | 13.08 | 57.185
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 304 | 290 | 136.06 | SQM | 136.06 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 8650 | 1 | LUMP SUM | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASH BASIN POINT WORK | 486 | 1000 | 1 | NOS | 1 | 0 | 100

## V75
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 10.28 | 0 | 100 | 1450.7136 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100 | 2800 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100 | 4200 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 1.45 | 0 | 100 | 10150 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100 | 3779.4557 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0.63 | 0 | 100 | 945 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 15.5 | 0 | 100 | 4671.576 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0.7 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 2.46 | 0 | 100 | 741.4243 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100 | 4736.976 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100 | 106.5636 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0 | 100 | 26888.9026 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 146.85 | SQM | 140 | 6.85 | 95.335 | 30139.2 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 52.01 | SQM | 45.16 | 6.85 | 86.833 | 9722.0448 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 28.859 | SQM | 28.86 | 0 | 100 | 3106.4904 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 74.494 | SQM | 74.49 | 0 | 100 | 16036.2072 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 28.859 | SQM | 28.86 | 0 | 100 | 3106.4904 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100 | 3400 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 18.85 | SQM | 18.85 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 13 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.08 | RMT | 46.08 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111 | RMT | 111 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.93 | RMT | 23.93 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 56.93 | SQM | 45.54 | 11.39 | 80
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.49 | RMT | 37.99 | 9.5 | 80
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 52.2 | SQM | 41.76 | 10.44 | 80
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.84 | RMT | 40.67 | 10.17 | 80
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 3.63 | SQM | 3.63 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.64 | RMT | 5.64 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.96 | SQM | 0 | 2.96 | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 6.75 | RMT | 0 | 6.75 | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 10.85 | SQM | 10.85 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 18.3 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 20.12 | SQM | 0 | 20.12 | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1232 | SFT | 1232 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 2.99 | 0.75 | 80
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 14.5 | 3.62 | 80
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.57 | SQM | 6.86 | 1.71 | 80
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.43 | SQM | 30.74 | 7.69 | 80
TANMAY | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 136.904 | SQM | 109.52 | 27.38 | 80
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.91 | RMT | 0 | 25.91 | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 0 | 12.5 | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 307 | 290 | 136.06 | SQM | 136.06 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION WATERPROOFING COATING FOR INDIAN TOILET WORK | 487 | 215.28 | 6.844 | SQM | 6.84 | 0 | 100

## V76
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
YELLAPPA C | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
YELLAPPA C | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
YELLAPPA C | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
YELLAPPA C | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
YELLAPPA C | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
YELLAPPA C | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0 | 100 | 1318.7664 | 0 | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
YELLAPPA C | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
YELLAPPA C | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 10.28 | 0 | 100 | 1450.7136 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
YELLAPPA C | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
YELLAPPA C | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
YELLAPPA C | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100 | 2800 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
YELLAPPA C | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.6 | MT | 0.6 | 0 | 100 | 4200 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 1.45 | 0 | 100 | 10150 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100 | 3779.4557 | 0 | 0
YELLAPPA C | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
YELLAPPA C | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0.63 | 0 | 100 | 945 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 15.5 | 0 | 100 | 4671.576 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0.7 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 2.46 | 0 | 100 | 741.4243 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 | 0 | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100 | 4736.976 | 0 | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100 | 106.5636 | 0 | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 | 0 | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 | 0 | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 | 0 | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0 | 100 | 26888.9026 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 151.38 | SQM | 151.38 | 0 | 100 | 32589.0864 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 53.98 | SQM | 53.98 | 0 | 100 | 11620.8144 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 36.9 | SQM | 36.9 | 0 | 100 | 3971.916 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 77.33 | SQM | 77.33 | 0 | 100 | 16647.6024 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 36.9 | SQM | 36.9 | 0 | 100 | 3971.916 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 22 | NOS | 22 | 0 | 100 | 4400 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 18.85 | SQM | 18.85 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 1 | NOS | 1 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 13 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.08 | RMT | 46.08 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111 | RMT | 111 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.93 | RMT | 23.93 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 56.93 | SQM | 45.54 | 11.39 | 80
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 11.3856 | SQM | 11.39 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.49 | RMT | 37.99 | 9.5 | 80
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 9.498 | RMT | 9.5 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 52.2 | SQM | 41.76 | 10.44 | 80
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 10.44 | SQM | 10.44 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.84 | RMT | 40.67 | 10.17 | 80
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 10.168 | RMT | 10.17 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 3.63 | SQM | 2.9 | 0.73 | 80
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 0.726 | SQM | 0.73 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.64 | RMT | 4.51 | 1.13 | 80
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 1.128 | RMT | 1.13 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.96 | SQM | 0 | 2.96 | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 6.75 | RMT | 0 | 6.75 | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 10.85 | SQM | 10.85 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 18.3 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 20.12 | SQM | 20.12 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1232 | SFT | 1232 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 2.99 | 0.75 | 80
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.12 | SQM | 14.5 | 3.62 | 80
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.57 | SQM | 6.86 | 1.71 | 80
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 38.43 | SQM | 30.74 | 7.69 | 80
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 138.88 | SQM | 138.88 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 31.31 | RMT | 31.31 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
INDAL SAHNI | SILL GRANITE | 289 | 75 | 105 | RFT | 105 | 0 | 100
YELLAPPA C | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 304 | 290 | 286.06 | SQM | 286.06 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0
RUPAK NAYAK | ALL FLOOR INTERNAL WALL & CEILING TWO COATS PUTTY REWORK AFTER CRACK TREATMENT | 370 | 32.292 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INTERNAL WALL & CEILING ONE COAT PRIMER REWORK AFTER CRACK TREATMENT | 375 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 7550 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100
INDAL SAHNI | CAR PARKING BOUNDARY WALL TOP COPING GRANITE | 550 | 78 | 32.54 | RFT | 32.54 | 0 | 100

## V77
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 137.52 | SQM | 137.52 | 0 | 100 | 7426.08 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 135.57 | CUM | 135.57 | 0 | 100 | 28697.4576 | 0 | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 67.79 | SQM | 67.79 | 0 | 100 | 1491.38 | 0 | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 73.15 | SQM | 73.15 | 0 | 100 | 3145.45 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 114.59 | CUM | 114.59 | 0 | 100 | 16170.9408 | 0 | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100 | 2500 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 45.09 | SQM | 45.09 | 0 | 100 | 1938.87 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 65.48 | CUM | 65.48 | 0 | 100 | 9240.5376 | 0 | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 137.52 | SQM | 137.52 | 0 | 100 | 3025.44 | 0 | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 137.52 | SQM | 137.52 | 0 | 100 | 5913.36 | 0 | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 4.566 | CUM | 4.57 | 0 | 100 | 4570 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.923 | CUM | 2.92 | 0 | 100 | 2920 | 0 | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 13.752 | CUM | 13.75 | 0 | 100 | 13750 | 0 | 0
NARESH PURTY | FOOTING REINFORCEMENT | 23 | 6800 | 0.5 | MT | 0.5 | 0 | 100 | 3400 | 0 | 0
NARESH PURTY | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.7 | MT | 0.7 | 0 | 100 | 4760 | 0 | 0
NARESH PURTY | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.5 | MT | 0.5 | 0 | 100 | 3400 | 0 | 0
NARESH PURTY | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.9 | MT | 0.9 | 0 | 100 | 6120 | 0 | 0
NARESH PURTY | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 2 | MT | 2 | 0 | 100 | 13600 | 0 | 0
NARESH PURTY | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 6800 | 0.17 | MT | 0.17 | 0 | 100 | 1156 | 0 | 0
NARESH PURTY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 6800 | 0.15 | MT | 0.15 | 0 | 100 | 1020 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 43.26 | SQM | 43.26 | 0 | 100 | 13038.2179 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 28.8 | SQM | 28.8 | 0 | 100 | 8680.0896 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 64.28 | SQM | 64.28 | 0 | 100 | 19373.4778 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.51 | SQM | 51.51 | 0 | 100 | 15524.7019 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 187.91 | SQM | 187.91 | 0 | 100 | 56634.5707 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 13.1328 | SQM | 13.13 | 0 | 100 | 3957.277 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.61 | SQM | 15.61 | 0 | 100 | 4704.7291 | 0 | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 15.37 | CUM | 15.37 | 0 | 100 | 3458.25 | 0 | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 2.56 | CUM | 2.56 | 0 | 100 | 3840 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4.38 | CUM | 4.38 | 0 | 100 | 3942 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.05 | CUM | 3.05 | 0 | 100 | 6100 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 21.874 | CUM | 21.87 | 0 | 100 | 4920.75 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 2.233 | CUM | 2.23 | 0 | 100 | 4460 | 0 | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 1.1 | CUM | 1.1 | 0 | 100 | 1650 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
NARESH PURTY | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 6800 | 0.75 | MT | 0.75 | 0 | 100 | 5100 | 0 | 0
NARESH PURTY | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 6800 | 1.3 | MT | 1.3 | 0 | 100 | 8840 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
NARESH PURTY | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 6800 | 0.03 | MT | 0.03 | 0 | 100 | 204 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 47.03 | SQM | 47.03 | 0 | 100 | 14174.4658 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 165.84 | SQM | 165.84 | 0 | 100 | 49982.8493 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 13.1328 | SQM | 13.13 | 0 | 100 | 3957.277 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 18.21 | SQM | 15.03 | 3.18 | 82.563 | 4529.9218 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.784 | CUM | 2.78 | 0 | 100 | 5560 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 18.898 | CUM | 18.9 | 0 | 100 | 4252.5 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 2.233 | CUM | 2.23 | 0 | 100 | 4460 | 0 | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.153 | CUM | 1.15 | 0 | 100 | 1725 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.05 | MT | 0.05 | 0 | 100 | 375 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.47 | SQM | 29.47 | 0 | 100 | 8882.0222 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.88 | SQM | 0 | 3.88 | 0 | 0 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.81 | CUM | 0.81 | 0 | 100 | 1620 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 3.352 | CUM | 3.35 | 0 | 100 | 753.75 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.26 | CUM | 0.26 | 0 | 100 | 390 | 0 | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 139.91 | SQM | 139.91 | 0 | 100 | 27107.8423 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 178.84 | SQM | 178.84 | 0 | 100 | 34650.6077 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 75.48 | SQM | 74.13 | 1.35 | 98.216 | 14362.8358 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 38.284 | RMT | 38.28 | 0 | 100 | 2511.168 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 49.952 | RMT | 49.95 | 0 | 100 | 3276.72 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 19.045 | SQM | 19.05 | 0 | 100 | 3075.813 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 483 | SQM | 483 | 0 | 100 | 3899.259 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 81.36 | SQM | 81.36 | 0 | 100 | 11384.8675 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.704 | SQM | 187.7 | 0 | 100 | 26265.2364 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 228.17 | SQM | 228.17 | 0 | 100 | 44208.3938 | 0 | 0
SALLAUDDIN ANSARI | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 0.73333 | LUMP SUM | 0.73 | 0 | 100 | 8760 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 0.26667 | LUMP SUM | 0.27 | 0 | 100 | 3240 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100 | 11425.4478 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 304.83 | SQM | 304.83 | 0 | 100 | 42655.4716 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 160.44 | SQM | 160.44 | 0 | 100 | 31085.5709 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.87 | SQM | 14.87 | 0 | 100 | 2080.7888 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 38.01 | SQM | 38.01 | 0 | 100 | 5318.8153 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 158.39 | SQM | 148.37 | 10.02 | 93.671 | 28746.9842 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 33.91 | SQM | 33.91 | 0 | 100 | 7300.1448 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 108.7 | SQM | 108.7 | 0 | 100 | 10530.856 | 0 | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 259.98 | SQM | 259.98 | 0 | 100 | 12592.9112 | 0 | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 131.38 | SQM | 131.38 | 0 | 100 | 6363.7844 | 0 | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 145.63 | SQM | 145.63 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.5 | 187.71 | SQM | 187.71 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.5 | 81.36 | SQM | 81.36 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.5 | 262.86 | SQM | 262.86 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.5 | 81.65 | SQM | 81.65 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.5 | 38.01 | SQM | 38.01 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.5 | 14.87 | SQM | 14.87 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 183 | 13.666 | SQM | 0 | 13.67 | 0
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 5 | NOS | 1 | 4 | 20
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 22 | NOS | 22 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 42.69 | RMT | 0 | 42.69 | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 135.36 | RMT | 0 | 135.36 | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 30.69 | RMT | 0 | 30.69 | 0
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 5 | NOS | 5 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 73.62 | SQM | 73.62 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 54.61 | RMT | 54.61 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 67.18 | SQM | 67.18 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 86.72 | RMT | 86.72 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 6.86 | SQM | 6.86 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 6.98 | RMT | 6.98 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 7.3 | SQM | 7.3 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 9.74 | RMT | 9.74 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 25.57 | SQM | 25.57 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 31.58 | RMT | 31.58 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 34.17 | SQM | 34.17 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1700 | SFT | 1700 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 5.57 | SQM | 5.57 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 49.35 | SQM | 49.35 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 12.9 | SQM | 11.15 | 1.75 | 86.457
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 91.414 | SQM | 91.41 | 0 | 100
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 337.699 | SQM | 337.7 | 0 | 100
H R ENGINEERS | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 16000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 249 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
BICHITRA CHOUDHURI | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 1 | 0 | 100
BICHITRA CHOUDHURI | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 1500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 26.06 | RMT | 0 | 26.06 | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | ENTRANCE STEPS SS RAILING | 269 | 5535 | 1.37 | RMT | 1.37 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 137 | RFT | 137 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 20 | RFT | 20 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 228 | SFT | 228 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 363 | 16.5 | RFT | 16.5 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
CHIRANJEEVI | ADDITIONAL SCAFFOLDING WORK OF EXTERNAL PLASTERING | 300 | 35 | 406 | SQM | 406 | 0 | 100
SAVITA DEVI | MS STAIRCASE WORK | 346 | 50000 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | CUSTOMIZATION MS STAIRCASE PAINTING AND STEP WOOD POLISHING WORK | 424 | 30000 | 1 | LUMP SUM | 1 | 0 | 100
INDAL SAHNI | CUSTOMIZATION TOILET TILE WORK | 436 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 8250 | 1 | LUMP SUM | 1 | 0 | 100
INDAL SAHNI | CUSTOMIZATION TERRACE TERRACOTTA TILE WORK | 488 | 183 | 95.69 | SQM | 95.69 | 0 | 100
INDAL SAHNI | CUSTOMIZATION GRANITE WORK | 489 | 2500 | 1 | LUMP SUM | 1 | 0 | 100

## V78
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.4 | MT | 0.4 | 0 | 100 | 3000 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.6 | MT | 0.6 | 0 | 100 | 4500 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 1.45 | 0 | 100 | 10875 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | 0 | 100 | 525 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 31.44 | 3.81 | 89.192 | 9475.7645 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 57.14 | 9.7 | 85.486 | 17221.5389 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100 | 3779.4557 | 0 | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 80 | SFT | 80 | 0 | 100 | 2240 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0.63 | 0 | 100 | 945 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 7.37 | 8.13 | 47.548 | 2221.259 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0.7 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100 | 150 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.46 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100 | 4736.976 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100 | 106.5636 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0 | 100 | 26888.9026 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 254.03 | 177.8 | SQM | 177.8 | 0 | 100 | 45166.534 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 254.03 | 17.1 | SQM | 17.1 | 0 | 100 | 4343.913 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 190.52 | 13.32 | SQM | 13.32 | 0 | 100 | 2537.7264 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 254.03 | 71.16 | SQM | 71.16 | 0 | 100 | 18076.7748 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 254.03 | 101.62 | SQM | 101.62 | 0 | 100 | 25814.5286 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 290 | 8 | NOS | 8 | 0 | 100 | 2320 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100 | 4299.1416 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100 | 6003.6536 | 0 | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100 | 6462.0995 | 0 | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100 | 12920.998 | 0 | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100 | 937.8305 | 0 | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100 | 29641.1497 | 0 | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 21.82 | SQM | 21.82 | 0 | 100
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 18 | NOS | 0 | 18 | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.62 | RMT | 41.62 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 78 | RMT | 78 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 20.82 | RMT | 20.82 | 0 | 100
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 52.85 | SQM | 52.85 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 37.54 | RMT | 37.54 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 52.624 | SQM | 38.65 | 13.97 | 73.446
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 52.572 | RMT | 39.21 | 13.36 | 74.587
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 4.18 | SQM | 4.18 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8.16 | RMT | 8.16 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 7.37 | SQM | 0 | 7.37 | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 17.1 | RMT | 0 | 17.1 | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 19.88 | SQM | 0 | 19.88 | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 34.45 | RMT | 0 | 34.45 | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 20.32 | SQM | 20.32 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1700 | SFT | 0 | 1700 | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.74 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 16.839 | SQM | 16.84 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.208 | SQM | 8.21 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.943 | SQM | 35.94 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 150.675 | SQM | 150.68 | 0 | 100
PRAKASH JANA | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 223.46 | SQM | 145.25 | 78.21 | 65
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 35.122 | RMT | 35.12 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 12850 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 68.2 | RFT | 68.2 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 33 | RFT | 33 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 16.25 | RFT | 16.25 | 0 | 100
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 456 | CFT | 456 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 456 | SFT | 456 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
KRISHNAKUMAR SAHANI | SILL GRANITE | 289 | 75 | 98 | RFT | 98 | 0 | 100
PRAKASH JANA | LAYING FLOOR PROTECTOR SHEET & TILE CLEANING | 341 | 1.5 | 1182 | SFT | 1182 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 432 | 750 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 8350 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASH BASIN POINT WORK | 486 | 1000 | 1 | NOS | 1 | 0 | 100
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100

## V79
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 69.29 | SQM | 69.29 | 0 | 100 | 2979.47 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100 | 2500 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 37.2 | SQM | 37.2 | 0 | 100 | 1599.6 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 78.8 | SQM | 78.8 | 0 | 100 | 3388.4 | 0 | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
BISWO RANJAN ROUT | FOOTING REINFORCEMENT | 23 | 6800 | 0.4 | MT | 0.4 | 0 | 100 | 2720 | 0 | 0
BISWO RANJAN ROUT | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.45 | MT | 0.45 | 0 | 100 | 3060 | 0 | 0
BISWO RANJAN ROUT | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.6 | MT | 0.6 | 0 | 100 | 4080 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.5 | MT | 0.5 | 0 | 100 | 3400 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 0.05 | MT | 0.05 | 0 | 100 | 340 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.4 | MT | 1.4 | 0 | 100 | 10500 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | 0 | 100 | 525 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100 | 3779.4557 | 0 | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 63 | SFT | 63 | 0 | 100 | 1764 | 0 | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 15.5 | 0 | 100 | 4671.576 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100 | 150 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 2.46 | 0 | 100 | 741.4243 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100 | 4736.976 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100 | 106.5636 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0 | 100 | 26888.9026 | 0 | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 59.83 | SQM | 59.83 | 0 | 100 | 25760.4048 | 0 | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 171 | 430.56 | 79.989 | SQM | 79.75 | 0.24 | 99.699 | 34337.16 | 0 | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 12.077 | SQM | 12.08 | 0 | 100 | 2600.5824 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.18 | 27.494 | SQM | 27.49 | 0 | 100 | 5915.2982 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 16 | NOS | 16 | 0 | 100 | 3200 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 61.95 | SQM | 61.95 | 0 | 100
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 183.89 | SQM | 183.89 | 0 | 100
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 110.81 | SQM | 110.81 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 105.43 | SQM | 105.43 | 0 | 99.998
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 193.455 | SQM | 193.45 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 75.06 | SQM | 75.06 | 0 | 99.999
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 213.23 | SQM | 213.23 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 68.644 | SQM | 68.64 | 0 | 99.996
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 46.21 | SQM | 46.21 | 0 | 99.999
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 15.3 | SQM | 15.3 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 16.26 | SQM | 16.26 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 39.64 | RMT | 39.64 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 86.891 | RMT | 86.89 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 24.696 | RMT | 24.7 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 52.85 | SQM | 52.85 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 37.54 | RMT | 37.54 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 57.426 | SQM | 57.43 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 52.572 | RMT | 52.57 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 4.18 | SQM | 4.18 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8.16 | RMT | 8.16 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 3.53 | SQM | 3.53 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 4.573 | RMT | 4.57 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 17.187 | SQM | 17.19 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 25.61 | RMT | 25.61 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 20.32 | SQM | 20.32 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1232 | SFT | 1232 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.74 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 14.74 | SQM | 14.74 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.41 | SQM | 7.41 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 51.686 | SQM | 51.69 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 135.173 | SQM | 135.17 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 0.5 | LUMP SUM | 0 | 0.5 | 0
BICHITRA CHOUDHURI | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 0.5 | LUMP SUM | 0.5 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 31.1 | RMT | 31.1 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 12850 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 68.2 | RFT | 68.2 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 33 | RFT | 33 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 16.25 | RFT | 16.25 | 0 | 100
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 368 | CFT | 368 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
LEGENDRY LANDSCAPES | SHADE GRASS DIBBLING AROUND VILLA | 284 | 23.75 | 368 | SFT | 368 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
YELLAPPA C | ADDITIONAL SHUTTERING WORK | 303 | 301.392 | 106.4016 | SFT | 106.4 | 0 | 100
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
INDAL SAHNI | CUSTOMIZATION TOILET TILE WORK | 436 | 1280.92 | 3.72 | SQM | 3.72 | 0 | 100
INDAL SAHNI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 248.38 | 17.94 | SQM | 17.94 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 13750 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION FLOOR INTERNAL WALL THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERNAL EMULSION PAINTING WORK | 490 | 91.494 | 83.52 | SQM | 83.52 | 0 | 99.998
RUPAK NAYAK | CUSTOMIZATION FLOOR EXTERNAL WALL ONE COAT PRIMER, TWO COATS EXTERNAL EMULSION PAINTING WORK | 491 | 48.438 | 29.792 | SQM | 29.79 | 0 | 99.995

## V80
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100 | 4255.2 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0 | 100 | 24110.352 | 0 | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 66.37 | SQM | 66.37 | 0 | 100 | 2853.91 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0 | 100 | 13692.8736 | 0 | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100 | 2500 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 37.2 | SQM | 37.2 | 0 | 100 | 1599.6 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0 | 100 | 5560.128 | 0 | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100 | 1733.6 | 0 | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 78.8 | SQM | 78.8 | 0 | 100 | 3388.4 | 0 | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0 | 100 | 4130 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | 0 | 100 | 3120 | 0 | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100 | 7880 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.4 | MT | 0.4 | 0 | 100 | 3000 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
BISWO RANJAN ROUT | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.6 | MT | 0.6 | 0 | 100 | 4080 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.1 | MT | 0.1 | 0 | 100 | 680 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.4 | MT | 0.4 | 0 | 100 | 3000 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 1.45 | 0 | 100 | 10875 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | 0 | 100 | 525 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | 0 | 100 | 10627.0819 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100 | 8336.5027 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | 0 | 100 | 20145.0413 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | 0 | 100 | 14328.1757 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0 | 100 | 46381.2149 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100 | 3779.4557 | 0 | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 99 | SFT | 99 | 0 | 100 | 2772 | 0 | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0 | 100 | 2493 | 0 | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100 | 2400 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0 | 100 | 4203 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0 | 100 | 6760 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | 0 | 100 | 3858.75 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
NARESH PURTY | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 6800 | 1.2 | MT | 1.2 | 0 | 100 | 8160 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | 0 | 100 | 11886.9005 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0 | 100 | 38777.0947 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0 | 100 | 3851.7898 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 15.5 | 0 | 100 | 4671.576 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0 | 100 | 4580 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | 0 | 100 | 3141 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | 0 | 100 | 3620 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100 | 150 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | 0 | 100 | 8478.157 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 2.46 | 0 | 100 | 741.4243 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | 0 | 100 | 1420 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | 0 | 100 | 600.75 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | 0 | 100 | 300 | 0 | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100 | 2050 | 0 | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100 | 21742.8494 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100 | 25858.1419 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100 | 13808.705 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100 | 2147.744 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100 | 4736.976 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100 | 106.5636 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100 | 2172.0136 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100 | 10080.7013 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100 | 26170.0826 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0 | 100 | 39108.8412 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0 | 100 | 9045.2045 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100 | 28858.1764 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100 | 25581.0766 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100 | 1721.1636 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100 | 5486.7337 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0 | 100 | 26888.9026 | 0 | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 59.83 | SQM | 59.83 | 0 | 100 | 25760.4048 | 0 | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 171 | 430.56 | 79.748 | SQM | 79.75 | 0 | 100 | 34337.16 | 0 | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 12.077 | SQM | 12.08 | 0 | 100 | 2600.5824 | 0 | 0
SHOKAT KHATRI | BEDROOM SCREED CONCRETE | 176 | 215.28 | 15.22 | SQM | 0 | 15.22 | 0 | 0 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.18 | 27.494 | SQM | 27.49 | 0 | 100 | 5915.2982 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 16 | NOS | 16 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 61.95 | SQM | 61.95 | 0 | 100
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 183.89 | SQM | 183.89 | 0 | 100
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 110.81 | SQM | 110.81 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 105.43 | SQM | 105.43 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 193.455 | SQM | 193.46 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 75.06 | SQM | 75.06 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 213.23 | SQM | 213.23 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 68.644 | SQM | 68.64 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 46.21 | SQM | 46.21 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 15.3 | SQM | 15.3 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 27.42 | SQM | 0 | 27.42 | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 18 | NOS | 0 | 18 | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.62 | RMT | 0 | 41.62 | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 124.86 | RMT | 0 | 124.86 | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 28.329 | RMT | 0 | 28.33 | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 52.85 | SQM | 52.85 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 37.54 | RMT | 37.54 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 52.624 | SQM | 43.21 | 9.41 | 82.113
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 52.572 | RMT | 52.57 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 4.18 | SQM | 0 | 4.18 | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8.16 | RMT | 2.57 | 5.59 | 31.507
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 9.38 | SQM | 9.38 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 17.1 | RMT | 17.1 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 19.98 | SQM | 19.98 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 34.45 | RMT | 34.45 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 20.32 | SQM | 0 | 20.32 | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1700 | SFT | 1034 | 666 | 60.824
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.74 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 11.45 | SQM | 11.45 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.208 | SQM | 8.21 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 44.02 | SQM | 44.02 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 150.675 | SQM | 150.68 | 0 | 100
PRAKASH JANA | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 223.46 | SQM | 223.46 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 0.5 | LUMP SUM | 0 | 0.5 | 0
BICHITRA CHOUDHURI | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 0.5 | LUMP SUM | 0.5 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 31.22 | RMT | 31.22 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 12850 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 1 | NOS | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 68.2 | RFT | 68.2 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 33 | RFT | 33 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 16.25 | RFT | 16.25 | 0 | 100
LEGENDRY LANDSCAPES | SOIL FILLING OF EXTERNAL LAWN AROUND VILLA | 281 | 8.826 | 368 | CFT | 368 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | MS STAIRCASE STEPS RUBBER WOOD LAYING | 336 | 49000 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS STAIRCASE WORK | 346 | 50000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
YELLAPPA C | ADDITIONAL SHUTTERING WORK/CUSTOMIZATION WORK - 1932/- | 358 | 301.392 | 11.1824 | SFT | 11.18 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION MS STAIRCASE PAINTING AND STEP WOOD POLISHING REWORK | 387 | 30000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION MS STAIRCASE PAINTING AND STEP WOOD POLISHING WORK | 424 | 30000 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMISATION TERRACE EPOXY GROUTING AND SOAP WASH CLEANING WORK | 427 | 64.58 | 22.031 | SQM | 22.03 | 0 | 100
KRISHNAKUMAR SAHANI | CUSTOMIZATION TOILET TILE WORK | 436 | 959.3 | 4.598 | SQM | 4.6 | 0 | 100
KRISHNAKUMAR SAHANI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 250.7 | 16.908 | SQM | 16.91 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION FLOOR INTERNAL WALL THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERNAL EMULSION PAINTING WORK | 490 | 91.494 | 81.301 | SQM | 81.3 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION FLOOR EXTERNAL WALL ONE COAT PRIMER, TWO COATS EXTERNAL EMULSION PAINTING WORK | 491 | 48.438 | 29.792 | SQM | 29.79 | 0 | 100

## V81
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100% | 4255.2 |  | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0.004 | 100% | 24110.352 |  | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0.002 | 100% | 1252.9 |  | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 67.8 | SQM | 67.8 | 0 | 100% | 2915.4 |  | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0.004 | 100% | 13692.8736 |  | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 37.2 | SQM | 37.2 | 0 | 100% | 1599.6 |  | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0.002 | 99.99% | 5560.128 |  | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100% | 1733.6 |  | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 78.8 | SQM | 78.8 | 0 | 100% | 3388.4 |  | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0.001 | 99.98% | 4130 |  | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | -0.004 | 100.1% | 3120 |  | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100% | 7880 |  | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.4 | MT | 0.4 | 0 | 100% | 3000 |  | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100% | 3375 |  | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.6 | MT | 0.6 | 0 | 100% | 4500 |  | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 1.45 | 0 | 100% | 10875 |  | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.1 | MT | 0.1 | 0 | 100% | 750 |  | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | -0.004 | 106.1% | 525 |  | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | -0.005 | 100% | 10627.0819 |  | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100% | 8336.5027 |  | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | -0.001 | 100% | 20145.0413 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | -0.005 | 100% | 14328.1757 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.894 | SQM | 153.89 | 0.004 | 100% | 46381.2149 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0.0044 | 99.97% | 3851.7898 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 12.54 | 0 | 100% | 3779.4557 |  | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 99 | SFT | 99 | 0 | 100% | 2772 |  | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0.001 | 99.99% | 2493 |  | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100% | 2400 |  | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0.004 | 99.91% | 4203 |  | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0.001 | 99.97% | 6760 |  | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | -0.001 | 100% | 3858.75 |  | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | -0.002 | 100.1% | 3620 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | -0.005 | 100% | 11886.9005 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 128.662 | SQM | 128.66 | 0.002 | 100% | 38777.0947 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0.004 | 99.97% | 3851.7898 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 15.5 | -0.005 | 100% | 4671.576 |  | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0.004 | 99.83% | 4580 |  | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | -0.003 | 100% | 3141 |  | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | -0.002 | 100.1% | 3620 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100% | 150 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 28.13 | -0.001 | 100% | 8478.157 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 2.46 | -0.005 | 100.2% | 741.4243 |  | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0.71 | -0.001 | 100.1% | 1420 |  | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 600.75 |  | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | -0.004 | 102% | 300 |  | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100% | 2050 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100% | 21742.8494 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100% | 25858.1419 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 71.27 | 0 | 100% | 13808.705 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 32.74 | 0 | 100% | 2147.744 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 72.21 | 0 | 100% | 4736.976 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0.66 | 0 | 100% | 106.5636 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 201.86 | 0 | 100% | 2172.0136 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 72.04 | 0 | 100% | 10080.7013 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 187.02 | 0 | 100% | 26170.0826 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 201.85 | 0.003 | 100% | 39108.8412 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 64.64 | 0.004 | 99.99% | 9045.2045 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 206.23 | 0 | 100% | 28858.1764 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 132.03 | 0 | 100% | 25581.0766 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 12.3 | 0 | 100% | 1721.1636 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 39.21 | 0 | 100% | 5486.7337 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 138.78 | 0.001 | 100% | 26888.9026 |  | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 47.136 | SQM | 47.14 | -0.004 | 100% | 20296.5984 |  | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 85.145 | SQM | 85.15 | -0.005 | 100% | 36662.184 |  | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 22.29 | SQM | 22.29 | 0 | 100% | 4798.5912 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 26.838 | SQM | 26.84 | -0.002 | 100% | 5778.1152 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 19 | SQM | 19 | 0 | 100% | 3800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0.004 | 99.98% | 4299.1416 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | -0.004 | 100% | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 400.13 | SQM | 400.13 | 0 | 100% | 6462.0995 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 400.13 | SQM | 400.13 | 0 | 100% | 12920.998 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100% | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 611.94 | SQM | 611.94 | 0 | 100% | 29641.1497 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 611.94 | SQM | 611.94 | 0 | 100% | 9882.831 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 611.94 | SQM | 611.94 | 0 | 100% | 16467.3054 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 21.82 | SQM | 21.82 | 0 | 100% | 6576.3734 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 18 | NOS | 13 | 5 | 72.22% | 4550 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.62 | RMT | 41.62 | 0 | 100% | 3412.84 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 78 | RMT | 78 | 0 | 100% | 2558.4 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 20.82 | RMT | 20.82 | 0 | 100% | 2731.584 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 52.85 | SQM | 52.85 | 0 | 100% | 9671.55 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 37.54 | RMT | 37.54 | 0 | 100% | 1846.968 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 52.624 | SQM | 52.62 | 0.004 | 99.99% | 9629.46 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 52.572 | RMT | 52.57 | 0.002 | 100% | 2586.444 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 4.18 | SQM | 4.18 | 0 | 100% | 764.94 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8.16 | RMT | 8.16 | 0 | 100% | 401.472 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 7.37 | SQM | 7.37 | 0 | 100% | 1348.71 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 17.1 | RMT | 17.1 | 0 | 100% | 841.32 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 19.88 | SQM | 19.88 | 0 | 100% | 3638.04 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 34.45 | RMT | 34.45 | 0 | 100% | 1694.94 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 20.32 | SQM | 20.32 | 0 | 100% | 3718.56 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1700 | SFT | 1700 | 0 | 100% | 4250 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.74 | SQM | 3.74 | 0 | 100% | 684.42 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 8.21 | SQM | 8.21 | 0 | 100% | 1502.43 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 16.839 | SQM | 16.84 | -0.001 | 100% | 3081.72 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.943 | SQM | 35.94 | 0.003 | 99.99% | 6577.02 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 136.904 | SQM | 136.9 | 0.004 | 100% | 8841.002 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 30.4658 | RMT | 30.47 | -0.0042 | 100% | 168651.45 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100% | 1350 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 68.2 | RFT | 68.2 | 0 | 100% | 2318.8 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 33 | RFT | 33 | 0 | 100% | 2541 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 16.25 | RFT | 16.25 | 0 | 100% | 2453.75 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
YELLAPPA C | ADDITIONAL SHUTTERING WORK OF LINTEL AND CHEJJA | 309 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
YELLAPPA C | ADDITIONAL SHUTTERING WORK/CUSTOMIZATION UTILITY EXTENSION- 1564/- | 359 | 301.392 | 15.1441 | SFT | 15.14 | 0.0041 | 99.97% | 4563.0749 |  | 0
RUPAK NAYAK | GROUND FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 379 | 16.146 | 88.739 | SQM | 0 | 88.739 | 0% | 0 |  | 0
RUPAK NAYAK | FIRST FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 380 | 16.146 | 19.43 | SQM | 0 | 19.43 | 0% | 0 |  | 0
RUPAK NAYAK | TERRACE FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 381 | 16.146 | 12.55 | SQM | 0 | 12.55 | 0% | 0 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 4630 | 1 | LUMP SUM | 1 | 0 | 100% | 4630 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 468 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100% | 800 |  | 0

## V82
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 43454.9138
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 47457.052
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 22300
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 75.32 | CUM | 75.32 | 0 | 100% | 10629.1584 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | PRAKASH H N | 14500
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | RAMAKRUSHNA PRADHAN | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 4.17 | CUM | 4.17 | 0 | 100% | 588.4704 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | SARAT BARMAN | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 5500 | SAVITA DEVI | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SHOKAT | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100% | 2775 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100% | 3375 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100% | 9375 |  | 0 | V VENKATANARAYANA | 5500
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0 | YELLAPPA C | 142239.6092
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.14 | MT | 0 | 0.14 | 0% | 0 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 | SHEKAR T | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | TOTAL | 275451.575
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.2505 | 0% | 0 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
AAIDHUL MIAH | FOOTING RCC | 50 | 225 | 0.812 | CUM | 0 | 0.812 | 0% | 0 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
AAIDHUL MIAH | PEDESTAL COLUMN RCC | 51 | 1500 | 0.742 | CUM | 0 | 0.742 | 0% | 0 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
AAIDHUL MIAH | PLINTH BEAM RCC | 53 | 900 | 0.33 | CUM | 0 | 0.33 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
AAIDHUL MIAH | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 1.537 | CUM | 0 | 1.537 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0 | 0.99 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100% | 8250 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100% | 34810.776 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.815 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
AAIDHUL MIAH | FIRST FLOOR COLUMN RCC | 88 | 2000 | 0.733 | CUM | 0 | 0.733 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
AAIDHUL MIAH | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 1.57 | CUM | 0 | 1.57 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.8 | CUM | 1.8 | 0 | 100% | 3600 |  | 0
AAIDHUL MIAH | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 0.19 | CUM | 0 | 0.19 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0 | 0.937 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100% | 750 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0 | 0.02 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100% | 3487.536 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 24.14 | 0 | 100% | 7795.2888 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0.002 | 99.92% | 542.25 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0% | 0 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
INDAL TANTI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 89.53 | 22.382 | 80% | 17346.6166 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 90 | 33.14 | 73.09% | 17437.68 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 50.16 | 12.542 | 80% | 9718.6003 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 215.28 | 111.912 | SQM | 89.53 | 22.382 | 80% | 19274.0184 | 20% | 4818.397
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 215.28 | 123.14 | SQM | 90 | 33.14 | 73.09% | 19375.2 | 26.91% | 7134.3792
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 215.28 | 62.702 | SQM | 50.16 | 12.542 | 80% | 10798.4448 | 20% | 2700.0418
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0% | 0 |  | 0
YELLAPPA C | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 0 | 268.5 | 0% | 0 | 100% | 9397.5
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 0 | 177.42 | 0% | 0 | 100% | 1909.0392
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 0 | 60.55 | 0% | 0 | 100% | 8472.8826
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0% | 0 | 100% | 23335.0603
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 215.28 | 201.853 | SQM | 0 | 201.853 | 0% | 0 | 100% | 43454.9138
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 14500
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 0 | 61.662 | 0% | 0 | 100% | 8628.487
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 0 | 175.883 | 0% | 0 | 100% | 24611.66
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 215.28 | 136.67 | SQM | 0 | 136.67 | 0% | 0 | 100% | 29422.3176
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 0 | 8.87 | 0% | 0 | 100% | 1241.1968
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 0 | 36.94 | 0% | 0 | 70% | 3618.3617
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 215.28 | 112.48 | SQM | 0 | 112.48 | 0% | 0 | 70% | 16950.2861
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 89.56 | SQM | 0 | 89.56 | 0% | 0 | 100% | 19280.4768
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 57.87 | SQM | 0 | 57.87 | 0% | 0 | 100% | 12458.2536
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 31.53 | SQM | 0 | 31.53 | 0% | 0 | 100% | 3393.8892
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 25.69 | SQM | 0 | 25.69 | 0% | 0 | 100% | 5530.5432
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 31.53 | SQM | 0 | 31.53 | 0% | 0 | 100% | 3393.8892
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 0 | 17 | 0% | 0 | 100% | 3400
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 12000
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 8000
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 500
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1800
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 9100 | 1 | LUMP SUM | 1 | 0 | 100% | 9100 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
SARAT BARMAN | CUSTOMISATION FLOOR REINFORCEMENT WORK | 492 | 7500 | 0.554 | MT | 0.55 | 0.004 | 99.28% | 4125 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 3.806 | CUM | 3.81 | -0.004 | 100.1% | 857.25 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 4 | NOS | 4 | 0 | 100% | 200 |  | 0
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 37.921 | SQM | 37.92 | 0.001 | 100% | 12245.1264 |  | 0
NAGARAJ | CUSTOMIZATION ROOM LINTEL CHAJJA SHUTTERING | 497 | 322.92 | 4.5 | SQM | 4.5 | 0 | 100% | 1453.14 |  | 0
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 14.003 | SQM | 14 | 0.003 | 99.98% | 4520.88 |  | 0
275451.575

## V83
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 58.24 | SQM | 0 | 58.24 | 0 | 0 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 150.156 | SQM | 150.16 | 0 | 100 | 3303.52 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.47 | CUM | 93.47 | 0 | 100 | 13190.4864 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100 | 1934.7552 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100 | 3324.64 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0 | 0 | 0 | 0
SUBHASMITA DAS | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | 15.63 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 0 | 1.2 | 0 | 0 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 0 | 15.17 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 0 | 3.04 | 0 | 0 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.24 | CUM | 0 | 13.24 | 0 | 0 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 0 | 1.77 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0 | 0.47 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0 | 0.88 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.13 | 0.05 | 70 | 975 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 0 | 129.97 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 0 | 16.19 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 0 | 2.94 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.7 | CUM | 0 | 12.7 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 0 | 1.99 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 10000 | 0.029 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 0 | 3.5 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0 | 0.41 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 0 | 2.41 | 0 | 0 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0 | 0 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
SARAT BARMAN | ADDITIONAL REINFORCEMENT WORK | 310 | 7500 | 0.7 | LUMP SUM | 0 | 0.7 | 0 | 0 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V84
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 3405.06 | 1 | LUMP SUM | 1 | 0 | 100% | 3405.06 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | KRIUTTIBAS DAS | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100% | 13191.8976 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0.002 | 99.97% | 1221.3936 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100% | 4925.088 |  | 0 | NAGARAJ | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 | PRAKASH H N | 2000
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100% | 3949.98 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | -0.004 | 100.1% | 3470 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | -0.004 | 100.1% | 2890 |  | 0 | SHOKAT | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | -0.004 | 100% | 9190 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100% | 2100 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100% | 3850 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 5600 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100% | 10500 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0 | YELLAPPA C | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0 | RABIUL MOLLA | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0 | KOUSHIK MANDAL | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0.0047 | 99.99% | 19144.4198 |  | 0 | SHEKAR T | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100% | 15578.9525 |  | 0 | TOTAL | 2000
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100% | 46305.8669 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100% | 4813.2302 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0.002 | 99.98% | 2225.25 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0.002 | 99.92% | 3660 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100% | 1485 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100% | 7700 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100% | 15033.433 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100% | 39985.6766 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100% | 5087.497 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0.003 | 99.9% | 5880 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100% | 3082.5 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | -0.003 | 100.3% | 1410 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100% | 700 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0 | 0.03 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100% | 8176.765 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100% | 828.828 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0.002 | 99.92% | 542.25 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100% | 22453.9193 |  | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100% | 25809.7039 |  | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0% | 0 |  | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0% | 0 |  | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100% | 184.0644 |  | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0.002 | 100% | 2224.4148 |  | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100% | 27220.972 |  | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 50 | 158.32 | 24% | 9687.6 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0.002 | 100% | 10409.5415 |  | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | -0.003 | 100% | 30850.808 |  | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100% | 27543.7843 |  | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100% | 4677.9268 |  | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100% | 29719.6193 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 184.074 | SQM | 184.07 | 0.004 | 100% | 39626.5896 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 43.295 | SQM | 43.3 | -0.005 | 100% | 9321.624 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 38.356 | SQM | 38.36 | -0.004 | 100% | 4129.0704 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 101.909 | SQM | 101.91 | -0.001 | 100% | 21939.1848 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 38.356 | SQM | 38.36 | -0.004 | 100% | 4129.0704 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0.003 | 99.99% | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100% | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100% | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100% | 13137.0314 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0.004 | 99.99% | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0.004 | 100% | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0.003 | 100% | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0.001 | 100% | 15634.9791 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100% | 6413.6218 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 12 | 3 | 80% | 4200 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0.002 | 99.99% | 3040.56 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 0 | 111.25 | 0% | 0 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | -0.002 | 100% | 3581.76 |  | 0
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 58.71 | SQM | 46.97 | 11.74 | 80% | 8595.51 |  | 0
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 183 | 11.742 | SQM | 11.74 | 0.002 | 99.98% | 2148.42 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.43 | RMT | 47.54 | 11.89 | 79.99% | 2338.968 |  | 0
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 11.886 | RMT | 11.89 | -0.004 | 100% | 584.988 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 47.79 | 11.952 | 79.99% | 8745.57 |  | 0
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 183 | 11.9484 | SQM | 11.95 | -0.0016 | 100% | 2186.85 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 55.33 | 13.83 | 80% | 2722.236 |  | 0
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 13.832 | RMT | 13.83 | 0.002 | 99.99% | 680.436 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 2.95 | 0.74 | 79.95% | 539.85 |  | 0
SANTOSH KUMAR | TERRACE FLOOR TILING | 228 | 183 | 0.738 | SQM | 0.74 | -0.002 | 100.3% | 135.42 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 4.48 | 1.12 | 80% | 220.416 |  | 0
SANTOSH KUMAR | TERRACE FLOOR SKIRTING | 229 | 49.2 | 1.12 | RMT | 1.12 | 0 | 100% | 55.104 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 0 | 2.512 | 0% | 0 |  | 0
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0.002 | 99.92% | 459.33 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 0 | 7.61 | 0% | 0 |  | 0
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100% | 374.412 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 7.41 | SQM | 5.93 | 1.48 | 80.03% | 1085.19 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 183 | 1.428 | SQM | 1.43 | -0.002 | 100.1% | 261.69 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 11.15 | RMT | 8.92 | 2.23 | 80% | 438.864 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 2.23 | RMT | 2.23 | 0 | 100% | 109.716 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 0 | 27.18 | 0% | 0 |  | 0
SANTOSH KUMAR | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100% | 4973.94 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100% | 2955 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 3.25 | 0.812 | 80.01% | 594.75 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 0.8124 | SQM | 0.81 | 0.0024 | 99.7% | 148.23 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 16.191 | SQM | 12.95 | 3.241 | 79.98% | 2369.85 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 3.2382 | SQM | 3.24 | -0.0018 | 100.1% | 592.92 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 6.52 | 1.63 | 80% | 1193.16 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 1.63 | SQM | 1.63 | 0 | 100% | 298.29 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 30.83 | SQM | 24.66 | 6.17 | 79.99% | 4512.78 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 6.166 | SQM | 6.17 | -0.004 | 100.1% | 1129.11 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.564 | SQM | 126.56 | 0.004 | 100% | 8173.2448 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100% | 15500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 30.625 | RMT | 30.63 | -0.005 | 100% | 169537.05 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
INDAL SAHNI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 39 | RMT | 0 | 39 | 0% | 0 |  | 0
PRABHAKAR | CUSTOMIZATION TERRACE ROOF SLAB WORK | 298 | 210 | 290 | SFT | 290 | 0 | 100% | 60900 |  | 0
INDAL SAHNI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 4.185 | SQM | 0 | 4.185 | 0% | 0 |  | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 2300 | 1 | LUMP SUM | 1 | 0 | 100% | 2300 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 468 | 750 | 1 | NOS | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN SHIFTING POINT WORK | 503 | 1000 | 1 | NOS | 0 | 1 | 0% | 0 |  | 0
SANTOSH KUMAR | CAR PARKING BOUNDARY WALL TOP COPING GRANITE | 550 | 78 | 15.49 | RFT | 15.49 | 0 | 100% | 1208.22 |  | 0
2000

## V85
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 3405.06 | 1 | LUMP SUM | 1 | 0 | 100 | 3405.06 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100 | 3949.98 | 0 | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0 | 0 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100 | 2100 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100 | 5600 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100 | 10500 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100 | 4813.2302 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100 | 5087.497 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100 | 1750 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100 | 828.828 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0 | 0 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100 | 22453.9193 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100 | 2101.824 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100 | 2102.48 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0 | 100 | 2224.4148 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100 | 29719.6193 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 142.926 | SQM | 142.93 | 0 | 100 | 30769.9704 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 46.895 | SQM | 46.9 | 0 | 100 | 10096.632 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 22.98 | SQM | 22.98 | 0 | 100 | 2473.5672 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 96.031 | SQM | 96.03 | 0 | 100 | 20673.3384 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 22.98 | SQM | 22.98 | 0 | 100 | 2473.5672 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 14 | 0 | 100 | 2800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.159 | RMT | 41.16 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 107 | RMT | 107 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.29 | 0.01 | 99.971
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 55.826 | SQM | 55.83 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.148 | RMT | 48.15 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 52.927 | SQM | 52.93 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 53.838 | RMT | 53.84 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.6 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.973 | SQM | 2.97 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 11.148 | SQM | 11.15 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.1 | RMT | 16.1 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1223 | SFT | 1223 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.75 | SQM | 3.75 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.08 | SQM | 18.08 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.44 | SQM | 7.44 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 40.646 | SQM | 40.65 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.564 | SQM | 126.56 | 0 | 100
PRAKASH JANA | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 208.534 | SQM | 208.53 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 34.266 | RMT | 34.27 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | ENTRANCE STEPS SS RAILING | 268 | 5535 | 0.9753 | RMT | 0.98 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
INDAL SAHNI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 39 | RMT | 39 | 0 | 100
INDAL SAHNI | SILL GRANITE | 289 | 75 | 59 | RFT | 59 | 0 | 100
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 290 | 28.51 | SFT | 28.51 | 0 | 100
INDAL SAHNI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 4.185 | SQM | 4.19 | 0 | 100
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 89.526 | SQM | 89.53 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 89.526 | SQM | 89.53 | 0 | 100
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 89.526 | SQM | 89.53 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 14.102 | SQM | 14.1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 14.102 | SQM | 14.1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 432 | 750 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 8850 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY TAP POINT WORK | 448 | 750 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION TERRACE WASHING MACHINE TAP POINT WORK | 504 | 1500 | 1 | NOS | 1 | 0 | 100
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100

## V86
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 92.8856 | CUM | 92.89 | 0 | 100 | 13108.6368 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100 | 3949.98 | 0 | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0 | 0 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100 | 2100 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100 | 5600 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100 | 10500 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100 | 4813.2302 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100 | 5087.497 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100 | 1750 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0.03 | 0 | 100 | 210 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100 | 828.828 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100 | 22453.9193 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100 | 2101.824 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100 | 2102.48 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 0 | 206.73 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100 | 29719.6193 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 22.57 | SQM | 22.57 | 0 | 100 | 9717.7392 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 20.4385 | SQM | 20.44 | 0 | 100 | 8800.6464 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 87.142 | SQM | 87.14 | 0 | 100 | 37518.9984 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 20.4385 | SQM | 20.44 | 0 | 100 | 4400.3232 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 11.148 | SQM | 11.15 | 0 | 100 | 2400.372 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 11.89 | SQM | 11.89 | 0 | 100
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 19 | SQM | 19 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 18.161 | SQM | 18.16 | 0 | 100
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 0 | 15 | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.78 | RMT | 98.78 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.829 | RMT | 26.83 | 0 | 100
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 48.71 | SQM | 40 | 8.71 | 82.119
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.43 | RMT | 50 | 9.43 | 84.133
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 50 | 9.74 | 83.693
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 65 | 4.16 | 93.985
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.6 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.97 | SQM | 2.97 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 11.148 | SQM | 11.15 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 25.305 | RMT | 25.31 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 4.06 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 22.57 | SQM | 22.57 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 8.15 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 45.33 | SQM | 45.33 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 147.14 | SQM | 147.14 | 0 | 100
PRAKASH JANA | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 208.534 | SQM | 208.53 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 32.195 | RMT | 32.2 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
KRISHNAKUMAR SAHANI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 39.26 | RMT | 39.26 | 0 | 100
KRISHNAKUMAR SAHANI | SILL GRANITE | 289 | 75 | 106 | RFT | 106 | 0 | 100
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 191 | 417 | SFT | 417 | 0 | 100
KRISHNAKUMAR SAHANI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 4.273 | SQM | 4.27 | 0 | 100
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 99.047 | SQM | 99.05 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 99.047 | SQM | 99.05 | 0 | 100
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 99.047 | SQM | 99.05 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 23.99 | SQM | 23.99 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 23.99 | SQM | 23.99 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION AQUAGUARD TAP POINT WORK | 420 | 750 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 5500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WATER SOFTENER POINT WORK | 470 | 750 | 1 | NOS | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASH BASIN POINT WORK | 486 | 1000 | 1 | NOS | 1 | 0 | 100

## V87
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPA B | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 0 | 91.86 | 0 | 0 | 0 | 0
DEEPA B | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
DEEPA B | TREE CUTTING | 3 | 500 | 2 | NOS | 0 | 2 | 0 | 0 | 0 | 0
DEEPA B | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
DEEPA B | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
DEEPA B | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
DEEPA B | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
DEEPA B | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 0 | 34.9 | 0 | 0 | 0 | 0
DEEPA B | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 0 | 91.86 | 0 | 0 | 0 | 0
DEEPA B | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.46 | 0.01 | 99.827 | 3460 | 0 | 0
DEEPA B | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
DEEPA B | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 0 | 9.19 | 0 | 0 | 0 | 0
DEEPA B | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100 | 2100 | 0 | 0
DEEPA B | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
DEEPA B | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
DEEPA B | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0 | 0.8 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 0 | 1.5 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0 | 0.2 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
DEEPA B | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
DEEPA B | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
DEEPA B | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
DEEPA B | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 0 | 51.69 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 0 | 153.64 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 0 | 12.33 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0 | 0 | 0 | 0
DEEPA B | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 99.98 | 2225.25 | 0 | 0
DEEPA B | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 99.918 | 3660 | 0 | 0
DEEPA B | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
DEEPA B | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 0 | 3.04 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 0 | 16.87 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 0 | 1.77 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0 | 0.99 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0 | 0.7 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 0 | 1.1 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0 | 0.2 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 0 | 49.88 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 0 | 132.67 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 0 | 12.33 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 0 | 2.94 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 0 | 13.7 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 0 | 1.99 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0 | 0.94 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0 | 0.25 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 0 | 27.13 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0 | 0.41 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 0 | 2.41 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0 | 0 | 0 | 0
DEEPA B | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 0 | 115.89 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 0 | 133.21 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 0 | 67.31 | 0 | 0 | 0 | 0
DEEPA B | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0 | 0 | 0 | 0
DEEPA B | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0 | 0 | 0 | 0
DEEPA B | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
DEEPA B | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 0 | 206.73 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 0 | 71.63 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 0 | 194.53 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 0 | 208.32 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 0 | 74.39 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 0 | 220.47 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 0 | 142.16 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 0 | 11.61 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 0 | 33.43 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 0 | 153.39 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
DEEPA B | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 508.94 | SFT | 65 | 443.94 | 12.772 | 20150 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 4 | LUMP SUM | 0 | 4 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V88
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPA B | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 0 | 91.86 | 0 | 0 | 0 | 0
DEEPA B | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
DEEPA B | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
DEEPA B | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
DEEPA B | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
DEEPA B | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
DEEPA B | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
DEEPA B | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 0 | 34.9 | 0 | 0 | 0 | 0
DEEPA B | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 0 | 91.86 | 0 | 0 | 0 | 0
DEEPA B | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
DEEPA B | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
DEEPA B | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 0 | 9.19 | 0 | 0 | 0 | 0
DEEPA B | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100 | 2100 | 0 | 0
DEEPA B | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
DEEPA B | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
DEEPA B | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0 | 0.8 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 0 | 1.5 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0 | 0.2 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
DEEPA B | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
DEEPA B | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
DEEPA B | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
DEEPA B | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 0 | 51.69 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 0 | 153.64 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 0 | 12.33 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0 | 0 | 0 | 0
DEEPA B | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 99.98 | 2225.25 | 0 | 0
DEEPA B | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
DEEPA B | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
DEEPA B | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 0 | 3.04 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 0 | 16.87 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 0 | 1.77 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0 | 0.99 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0 | 0.7 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 0 | 1.1 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0 | 0.2 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 0 | 49.88 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 0 | 132.67 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 0 | 12.33 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 0 | 2.94 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 0 | 13.7 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 0 | 1.99 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0 | 0.94 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0 | 0.25 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 0 | 27.13 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0 | 0.41 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 0 | 2.41 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0 | 0 | 0 | 0
DEEPA B | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 0 | 115.89 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 0 | 133.21 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 0 | 67.31 | 0 | 0 | 0 | 0
DEEPA B | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0 | 0 | 0 | 0
DEEPA B | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0 | 0 | 0 | 0
DEEPA B | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
DEEPA B | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 0 | 206.73 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 0 | 71.63 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 0 | 194.53 | 0 | 0 | 0 | 0
DEEPA B | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 0 | 208.32 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 0 | 74.39 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 0 | 220.47 | 0 | 0 | 0 | 0
DEEPA B | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 0 | 142.16 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 0 | 11.61 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 0 | 33.43 | 0 | 0 | 0 | 0
DEEPA B | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 0 | 153.39 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
DEEPA B | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 508.94 | SFT | 75 | 433.94 | 14.737 | 23250 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V89
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100 | 3949.98 | 0 | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 10.81 | 0 | 100 | 1525.5072 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100 | 2100 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100 | 5600 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100 | 10500 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100 | 4813.2302 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100 | 5087.497 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100 | 1750 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0.03 | 0 | 100 | 210 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100 | 828.828 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100 | 22453.9193 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0 | 0 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100 | 2102.48 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 0 | 206.73 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 74.56 | 78.83 | 48.605 | 14446.1491 | 0 | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 54.705 | SQM | 54.71 | 0 | 100 | 23555.9376 | 0 | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 85.145 | SQM | 85.15 | 0 | 100 | 36662.184 | 0 | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 11.334 | SQM | 11.33 | 0 | 100 | 2439.1224 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 37.142 | SQM | 37.14 | 0 | 100 | 7995.4992 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 21 | SQM | 21 | 0 | 100 | 4200 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 25.084 | SQM | 25.08 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 27.128 | SQM | 27.13 | 0 | 100
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 184.69 | SQM | 184.69 | 0 | 100
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 118.63 | SQM | 118.63 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 103.5 | SQM | 103.5 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 190.528 | SQM | 190.53 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 65.58 | SQM | 65.58 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 212.47 | SQM | 212.47 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 70.392 | SQM | 70.39 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 30.43 | SQM | 30.43 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 11.61 | SQM | 11.61 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.2 | RMT | 41.2 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | 0 | 100
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 58.71 | SQM | 58.71 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 88.96 | RMT | 88.96 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 59.74 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 69.16 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.6 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 14.1 | SQM | 14.1 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 25.3 | RMT | 25.3 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 4.06 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 22.48 | SQM | 22.48 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 8.15 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 46.3 | SQM | 46.3 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 142.392 | SQM | 142.39 | 0 | 100
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 225.15 | SQM | 225.15 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 25 | RMT | 25 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 12850 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | ENTRANCE STEPS SS RAILING | 268 | 5535 | 1.0363 | RMT | 1.04 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 146.8235 | RFT | 146.82 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 42.2896 | RFT | 42.29 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 28.0377 | RFT | 28.04 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 180 | 373 | SFT | 373 | 0 | 100
KRISHNAKUMAR SAHANI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 4.149 | SQM | 4.15 | 0 | 100
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | PAINT REWORK IN VILLAS AFTER WALL CRACK TREATMENT | 369 | 3060 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMISATION TERRACE EPOXY GROUTING AND SOAP WASH CLEANING WORK | 427 | 64.58 | 17.315 | SQM | 17.32 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION INTERNAL WALL THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERIOR EMULSION PAINTING WORK | 466 | 91.494 | 32.516 | SQM | 32.52 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION EXTERNAL WALL AND CHEJJA ONE COAT PRIMER, TWO COAT EXTERIOR EMULSION PAINTING WORK | 476 | 48.438 | 40.877 | SQM | 40.88 | 0 | 100
RUPAK NAYAK | CUSTAMIZATION STUCCO PAINT WORK | 505 | 96.876 | 108.602 | SQM | 108.6 | 0 | 100

## V90
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 103.17 | SQM | 103.17 | 0 | 100% | 5571.18 |  | 0 | AAIDHUL MIAH | 350
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 46.12 | SQM | 46.12 | 0 | 100% | 1014.64 |  | 0 | EBI ABRAHAM | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 103.17 | SQM | 103.17 | 0 | 100% | 2269.74 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | KRIUTTIBAS DAS | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 7.53 | CUM | 7.53 | 0 | 100% | 7530 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.994 | CUM | 3.99 | 0.004 | 99.9% | 3990 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 10.32 | CUM | 10.32 | 0 | 100% | 10320 |  | 0 | PRAKASH H N | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100% | 5250 |  | 0 | RUPAK NAYAK | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.95 | MT | 0.95 | 0 | 100% | 7125 |  | 0 | SANTOSH KUMAR | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | SARAT BARMAN | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.6 | MT | 2.6 | 0 | 100% | 19500 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SHOKAT | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.16 | MT | 0.16 | 0 | 100% | 1200 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | -0.004 | 106.1% | 525 |  | 0 | SK ANSAR HOSSIAN | 1788.4297
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 65.78 | SQM | 65.78 | 0 | 100% | 19825.5658 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 37.11 | SQM | 37.11 | 0 | 100% | 11184.6571 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 79.884 | SQM | 79.88 | 0.004 | 99.99% | 24075.193 |  | 0 | SUBHASMITA DAS | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 67.86 | SQM | 67.86 | 0 | 100% | 20452.4611 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 218.06 | SQM | 218.06 | 0 | 100% | 65721.5395 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.793 | SQM | 12.79 | 0.003 | 99.98% | 3854.8037 |  | 0 | YELLAPPA C | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 11.65 | SQM | 11.65 | 0 | 100% | 3511.2168 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 132 | SFT | 132 | 0 | 100% | 3696 |  | 0 | KOUSHIK MANDAL | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 17.19 | CUM | 17.19 | 0 | 100% | 3867.75 |  | 0 | SHEKAR T | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.18 | CUM | 2.18 | 0 | 100% | 3270 |  | 0 | TOTAL | 2138.4297
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 5.991 | CUM | 5.99 | 0.001 | 99.98% | 5391 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.98 | CUM | 3.98 | 0 | 100% | 7960 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 23.5 | CUM | 23.5 | 0 | 100% | 5287.5 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.673 | CUM | 1.67 | 0.003 | 99.82% | 3340 |  | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100% | 1440 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.85 | MT | 1.85 | 0 | 100% | 13875 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 56.55 | SQM | 56.55 | 0 | 100% | 17043.7176 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 188.59 | SQM | 188.59 | 0 | 100% | 56839.5173 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.793 | SQM | 12.79 | 0.003 | 99.98% | 3854.8037 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 14.11 | SQM | 14.11 | 0 | 100% | 4252.6411 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.33 | CUM | 3.33 | 0 | 100% | 6660 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 19.19 | CUM | 19.19 | 0 | 100% | 4317.75 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.673 | CUM | 1.67 | 0.003 | 99.82% | 3340 |  | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.57 | CUM | 1.57 | 0 | 100% | 2355 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.3 | MT | 0.3 | 0 | 100% | 2250 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100% | 150 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 26.6 | SQM | 26.6 | 0 | 100% | 8017.0272 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.815 | SQM | 1.82 | -0.005 | 100.3% | 548.5334 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 3.07 | CUM | 3.07 | 0 | 100% | 690.75 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.17 | CUM | 0.17 | 0 | 100% | 255 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 53 | NOS | 53 | 0 | 100% | 2650 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 146.37 | SQM | 146.37 | 0 | 100% | 28359.4802 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 185.55 | SQM | 185.55 | 0 | 100% | 35950.6836 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 72.29 | SQM | 72.29 | 0 | 100% | 14006.3321 |  | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 49.17 | RMT | 0 | 49.17 | 0% | 0 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 33.82 | RMT | 0 | 33.82 | 0% | 0 |  | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 19.045 | SQM | 0 | 19.045 | 0% | 0 |  | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 405 | SQM | 0 | 405 | 0% | 0 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 483 | SQM | 0 | 483 | 0% | 0 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 94.21 | SQM | 0 | 94.21 | 0% | 0 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 266.24 | SQM | 266.24 | 0 | 100% | 37255.4957 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 261.11 | SQM | 30 | 231.11 | 11.49% | 5812.56 |  | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14000 | 1 | LUMP SUM | 1 | 0 | 100% | 14000 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 92.25 | SQM | 0 | 92.25 | 0% | 0 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 364.2 | SQM | 200 | 164.2 | 54.91% | 27986.4 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 163.72 | SQM | 0 | 163.72 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 13.2 | SQM | 0 | 13.2 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.271 | SQM | 37.27 | 0.001 | 100% | 5215.2656 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 163.58 | SQM | 0 | 163.58 | 0% | 0 |  | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 50.818 | SQM | 50.82 | -0.002 | 100% | 21881.0592 |  | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 146.32 | SQM | 116.69 | 29.63 | 79.75% | 50242.0464 |  | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 23.319 | SQM | 23.32 | -0.001 | 100% | 5020.3296 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 25.084 | SQM | 25.08 | 0.004 | 99.98% | 5399.2224 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 21 | NOS | 21 | 0 | 100% | 4200 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 27.32 | SQM | 27.32 | 0 | 100% | 5881.4496 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 229.37 | SQM | 229.37 | 0 | 100% | 11110.2241 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 143.3 | SQM | 143.3 | 0 | 100% | 6941.1654 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 150.93 | SQM | 150.93 | 0 | 100% | 7310.7473 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 148.64 | SQM | 148.64 | 0 | 100% | 2400.536 |  | 0
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 186.368 | SQM | 186.37 | -0.002 | 100% | 17051.7368 |  | 0
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 75.368 | SQM | 75.37 | -0.002 | 100% | 6895.9028 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 254.94 | SQM | 254.94 | 0 | 100% | 23325.4804 |  | 0
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 73.8 | SQM | 73.8 | 0 | 100% | 6752.2572 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 26.089 | SQM | 26.09 | -0.001 | 100% | 2387.0785 |  | 0
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 10.56 | SQM | 10.56 | 0 | 100% | 966.1766 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 31.14 | SQM | 31.14 | 0 | 100% | 9385.3469 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 5 | NOS | 2 | 3 | 40% | 900 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 21 | NOS | 10 | 11 | 47.62% | 3500 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 43.44 | RMT | 43.44 | 0 | 100% | 3562.08 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 130.32 | RMT | 130.32 | 0 | 100% | 4274.496 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 32.22 | RMT | 32.22 | 0 | 100% | 4227.264 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 6 | NOS | 5 | 1 | 83.33% | 5000 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 84.56 | SQM | 84.56 | 0 | 100% | 15474.48 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 85.8 | RMT | 85.8 | 0 | 100% | 4221.36 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 84.38 | SQM | 84.38 | 0 | 100% | 15441.54 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 96.78 | RMT | 96.78 | 0 | 100% | 4761.576 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.698 | SQM | 3.7 | -0.002 | 100.1% | 677.1 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.86 | RMT | 5.86 | 0 | 100% | 288.312 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 7.3 | SQM | 7.3 | 0 | 100% | 1335.9 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 12.8 | RMT | 12.8 | 0 | 100% | 629.76 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 25.7 | SQM | 25.7 | 0 | 100% | 4703.1 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 43.7 | RMT | 43.7 | 0 | 100% | 2150.04 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 33.637 | SQM | 33.64 | -0.003 | 100% | 6156.12 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1843 | SFT | 1843 | 0 | 100% | 4607.5 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 7.48 | SQM | 7.48 | 0 | 100% | 1368.84 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 34.903 | SQM | 25 | 9.903 | 71.63% | 4575 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 34.903 | SQM | 25 | 9.903 | 71.63% | 4575 | 28% | 1788.4297
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 11.93 | SQM | 11.93 | 0 | 100% | 2183.19 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 52.68 | SQM | 35 | 17.68 | 66.44% | 6405 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 15000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 2 | LUMP SUM | 0 | 2 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 7000 | 1 | LUMP SUM | 1 | 0 | 100% | 7000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 18.87 | RMT | 18.87 | 0 | 100% | 93481.98 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 12850 | 1 | LUMP SUM | 1 | 0 | 100% | 12850 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100% | 5625 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | ENTRANCE STEPS SS RAILING | 268 | 5535 | 1.0515 | RMT | 1.05 | 0.0015 | 99.86% | 5811.75 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100% | 225 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
CHIRANJEEVI | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100% | 1500 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 88 | RFT | 88 | 0 | 100% | 2992 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 31.9 | RFT | 31.9 | 0 | 100% | 2456.3 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 18.7 | RFT | 18.7 | 0 | 100% | 2823.7 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
KRISHNAKUMAR SAHANI | SILL GRANITE | 289 | 75 | 106 | RFT | 106 | 0 | 100% | 7950 |  | 0
SAVITA DEVI | MS STAIRCASE WORK | 346 | 50000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
YELLAPPA C | ADDITIONAL SHUTTERING WORK/CUSTOMIZATION ADDITIONAL ROOF IN TERRACE- 15904/-, PARGOLA -7500/- | 360 | 301.392 | 13.0217 | SFT | 13.02 | 0.00174 | 99.99% | 3924.1238 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 58.62 | SQM | 58.62 | 0 | 100% | 946.713 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 58.62 | SQM | 58.62 | 0 | 100% | 1892.957 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | CUSTOMISATION SS RALING FOR BALCONY & STAIRCASE(INCLUDING MATERIAL) | 506 | 4954 | 17.41 | RMT | 17.41 | 0 | 100% | 86249.14 |  | 0
2138.4297

## V91
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 |  | 0 | KRIUTTIBAS DAS | 1500
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 0 | 93.48 | 0 | 0 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 |  | 0 | NAGARAJ | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 |  | 0 | PRAKASH H N | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 |  | 0 | RAMAKRUSHNA PRADHAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100 | 2250 |  | 0 | SHOKAT | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100 | 6000 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100 | 11250 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 |  | 0 | UDHABHAI R PARMAR | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 |  | 0 | V VENKATANARAYANA | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 |  | 0 | YELLAPPA C | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 49.6378 | SQM | 49.64 | 0 | 100 | 14961.0989 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 142.0476 | SQM | 142.05 | 0 | 100 | 42812.7336 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 11.4874 | SQM | 11.49 | 0 | 100 | 3462.9941 |  | 0 | TOTAL | 1500
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0 | 99.995 | 2787.876 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 |  | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 118.822 | SQM | 118.82 | 0 | 100 | 35811.3974 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 11.4874 | SQM | 11.49 | 0 | 100 | 3462.9941 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | 0 | 100 | 2959.6694 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 |  | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100 | 1875 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0.03 | 0 | 100 | 225 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100 | 569.6309 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 |  | 0
KHALIL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100 | 22453.9193 |  | 0
KHALIL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 |  | 0
KHALIL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 |  | 0
KHALIL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 29.04 | RMT | 29.04 | 0 | 100 | 1905.024 |  | 0
KHALIL MIAH | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100 | 2102.48 |  | 0
KHALIL MIAH | ELEAVTION BLOCK WORK | 138 | 193.752 | 1.05 | SQM | 1.05 | 0 | 100 | 203.4396 |  | 0
KHALIL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 307 | SQM | 307 | 0 | 100 | 10745 |  | 0
KHALIL MIAH | RCC SURFACE HACKING | 140 | 8.07 | 449.8 | SQM | 449.8 | 0 | 100 | 3629.886 |  | 0
KHALIL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 |  | 0
KHALIL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 |  | 0
KHALIL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 |  | 0
KHALIL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 |  | 0
KHALIL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 |  | 0
KHALIL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 |  | 0
KHALIL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 |  | 0
KHALIL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 |  | 0
KHALIL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 105.8 | SQM | 105.8 | 0 | 100 | 20498.9616 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 132.486 | SQM | 132.49 | 0 | 100 | 28522.4472 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 36.3 | SQM | 36.3 | 0 | 100 | 7814.664 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 35.028 | SQM | 35.03 | 0 | 100 | 3770.6292 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 79.534 | SQM | 79.53 | 0 | 100 | 17121.2184 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 35.028 | SQM | 35.03 | 0 | 100 | 3770.6292 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 14 | 0 | 100 | 2800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100 | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100 | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100 | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100 | 13137.0314 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100 | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100 | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100 | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100 | 15634.9791 |  | 0
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100 | 6413.6218 |  | 0
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100 | 5250 |  | 0
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0 | 100 | 3040.56 |  | 0
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100 | 3649 |  | 0
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | 0 | 100 | 3581.76 |  | 0
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100 | 3000 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 58.71 | SQM | 58.71 | 0 | 100 | 10743.93 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.43 | RMT | 59.43 | 0 | 100 | 2923.956 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 59.74 | 0 | 100 | 10932.42 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 69.16 | 0 | 100 | 3402.672 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100 | 675.27 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.6 | 0 | 100 | 275.52 |  | 0
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0 | 100 | 459.33 |  | 0
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100 | 374.412 |  | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 7.41 | SQM | 7.41 | 0 | 100 | 1356.03 |  | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 11.15 | RMT | 11.15 | 0 | 100 | 548.58 |  | 0
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100 | 4973.94 |  | 0
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100 | 2955 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 4.06 | 0 | 100 | 742.98 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 16.191 | SQM | 16.19 | 0 | 100 | 2962.77 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 8.15 | 0 | 100 | 1491.45 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 30.83 | SQM | 30.83 | 0 | 100 | 5641.89 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 132.064 | SQM | 132.06 | 0 | 100 | 8528.4348 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100 | 14500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100 | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100 | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100 | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100 | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100 | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100 | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 26.06 | RMT | 26.06 | 0 | 100 | 144242.1 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100 | 1350 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100 | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100 | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100 | 5625 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | ENTRANCE STEPS SS RAILING | 268 | 5535 | 0.975 | RMT | 0.98 | 0 | 100 | 5424.3 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 100% | 1500
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100 | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100 | 350 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100 | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100 | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100 | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0 | 0 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100 | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100 | 400 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100 | 800 |  | 0
ANSAR HOSSAIAN SK | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 39 | RMT | 0 | 39 | 0 | 0 |  | 0
ANSAR HOSSAIAN SK | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 4.185 | SQM | 0 | 4.19 | 0 | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0 | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | CUSTOMISATION SS RALING FOR BALCONY & STAIRCASE(INCLUDING MATERIAL) | 507 | 5535 | 8.1073 | RMT | 8.11 | 0 | 100 | 44888.85 |  | 0
1500

## V92
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 | AAIDHUL MIAH | 350
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 13000
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | FOOTING SOILING | 7 | 22 | 58 | SQM | 58 | 0 | 100% | 1276 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100% | 13191.8976 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0.002 | 99.97% | 1221.3936 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM SOLING | 12 | 22 | 31.45 | SQM | 31.45 | 0 | 100% | 691.9 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 17.45 | 17.45 | 50% | 2462.544 |  | 0 | RUPAK NAYAK | 38723.4926
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 4.22 | SQM | 4.22 | 0 | 100% | 92.84 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 22 | 91.86 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 | SARAT BARMAN | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SAVITA DEVI | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SHOKAT | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | -0.004 | 100.1% | 3470 |  | 0 | SK ANSAR HOSSIAN | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | -0.004 | 100.1% | 2890 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 4.59 | 4.596 | 49.97% | 4590 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
MORSELIM KHAN | BASE FLOOR PCC | 22 | 1000 | 4.593 | CUM | 4.59 | 0.003 | 99.93% | 4590 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100% | 2250 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100% | 5250 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100% | 3850 |  | 0 | YELLAPPA C | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 5600 |  | 0 | RABIUL MOLLA | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100% | 11250 |  | 0 | KOUSHIK MANDAL | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0 | SHEKAR T | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0 | TOTAL | 52073.4926
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 62.24 | SQM | 62.24 | 0 | 100% | 18758.6381 |  | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 49.637 | SQM | 49.64 | -0.003 | 100% | 14961.0989 |  | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 142.0476 | SQM | 142.05 | -0.0024 | 100% | 42812.7336 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0.0005 | 99.99% | 2787.876 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0.002 | 99.98% | 2225.25 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.2 | CUM | 1.2 | 0 | 100% | 1800 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.96 | CUM | 15.96 | 0 | 100% | 3591 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100% | 5250 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 8000 | 1 | MT | 1 | 0 | 100% | 8000 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 8000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 48.4528 | SQM | 48.45 | 0.0027685 | 99.99% | 14602.4424 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 118.822 | SQM | 118.82 | 0.002 | 100% | 35811.3974 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | -0.005 | 100.1% | 2959.6694 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0.003 | 99.9% | 5880 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.46 | CUM | 13.46 | 0 | 100% | 3028.5 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 8000 | 0.1 | MT | 0.1 | 0 | 100% | 800 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 8000 | 0.25 | MT | 0.25 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 10000 | 0.03 | MT | 0 | 0.03 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100% | 8176.765 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100% | 569.6309 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 2000 | 2.412 | CUM | 2.41 | 0.002 | 99.92% | 4820 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 6.27 | CUM | 6.27 | 0 | 100% | 5016 |  | 0
KHALIL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100% | 22453.9193 |  | 0
KHALIL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100% | 25809.7039 |  | 0
KHALIL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
KHALIL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 29.04 | RMT | 0 | 29.04 | 0% | 0 |  | 0
MORSELIM KHAN | ELEVATION RCC BAND | 133 | 65.6 | 29.04 | RMT | 29.04 | 0 | 100% | 1905.024 |  | 0
KHALIL MIAH | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0% | 0 |  | 0
MORSELIM KHAN | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100% | 2102.48 |  | 0
KHALIL MIAH | ELEAVTION BLOCK WORK | 138 | 193.752 | 1.05 | SQM | 1.05 | 0 | 100% | 203.4396 |  | 0
KHALIL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 307 | SQM | 307 | 0 | 100% | 10745 |  | 0
KHALIL MIAH | RCC SURFACE HACKING | 140 | 8.07 | 449.8 | SQM | 449.8 | 0 | 100% | 3629.886 |  | 0
KHALIL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 60.89 | 10.74 | 85.01% | 8520.4595 |  | 0
MORSELIM KHAN | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 10.7445 | SQM | 10.74 | 0.0045 | 99.96% | 1502.8697 |  | 0
KHALIL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 165.35 | 29.18 | 85% | 23137.7562 |  | 0
MORSELIM KHAN | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 29.1795 | SQM | 29.18 | -0.0005 | 100% | 4083.2158 |  | 0
KHALIL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100% | 40362.4166 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
KHALIL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 63.23 | 11.162 | 85% | 8847.9004 |  | 0
MORSELIM KHAN | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 11.1588 | SQM | 11.16 | -0.0012 | 100% | 1561.6411 |  | 0
KHALIL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 187.4 | 33.067 | 85% | 26223.2568 |  | 0
MORSELIM KHAN | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 33.0701 | SQM | 33.07 | 5e-05 | 100% | 4627.5512 |  | 0
KHALIL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 120.84 | 21.32 | 85% | 23412.9917 |  | 0
MORSELIM KHAN | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 21.324 | SQM | 21.32 | 0.004 | 99.98% | 4130.7926 |  | 0
KHALIL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 9.87 | 1.74 | 85.01% | 1381.1288 |  | 0
MORSELIM KHAN | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 1.7415 | SQM | 1.74 | 0.0015 | 99.91% | 243.4817 |  | 0
KHALIL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 28.42 | 5.01 | 85.01% | 3976.8674 |  | 0
MORSELIM KHAN | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 5.0145 | SQM | 5.01 | 0.0045 | 99.91% | 701.0593 |  | 0
KHALIL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 105.8 | SQM | 105.8 | 0 | 100% | 20498.9616 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 159.29 | SQM | 159.29 | 0 | 100% | 34291.9512 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 57.38 | SQM | 57.38 | 0 | 100% | 12352.7664 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 36.09 | SQM | 36.09 | 0 | 100% | 3884.7276 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 79.37 | SQM | 79.37 | 0 | 100% | 17086.7736 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 39.16 | SQM | 39.16 | 0 | 100% | 4215.1824 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0.003 | 99.99% | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100% | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100% | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 0 | 406.82 | 0% | 0 | 100% | 13137.0314
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0.004 | 99.99% | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0.004 | 100% | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0.003 | 100% | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 0 | 581.011 | 0% | 0 | 100% | 15635.006
SANTOSH KUMAR | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100% | 6413.6218 |  | 0
SANTOSH KUMAR | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
SANTOSH KUMAR | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 0 | 15 | 0% | 0 |  | 0
SANTOSH KUMAR | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0.002 | 99.99% | 3040.56 |  | 0
SANTOSH KUMAR | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100% | 3649 |  | 0
SANTOSH KUMAR | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | -0.002 | 100% | 3581.76 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 183 | 57.801 | SQM | 54.91 | 2.891 | 95% | 10048.53 |  | 0
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 46.486 | RMT | 44.16 | 2.326 | 95% | 2172.672 |  | 0
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 183 | 55.106 | SQM | 52.35 | 2.756 | 95% | 9580.05 |  | 0
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 49.62 | RMT | 47.14 | 2.48 | 95% | 2319.288 |  | 0
SANTOSH KUMAR | TERRACE FLOOR TILING | 228 | 183 | 6.003 | SQM | 5.7 | 0.303 | 94.95% | 1043.1 |  | 0
SANTOSH KUMAR | TERRACE FLOOR SKIRTING | 229 | 49.2 | 7.188 | RMT | 6.83 | 0.358 | 95.02% | 336.036 |  | 0
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 3.237 | SQM | 3.24 | -0.003 | 100.1% | 592.92 |  | 0
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 7.025 | RMT | 7.03 | -0.005 | 100.1% | 345.876 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 183 | 11.441 | SQM | 10.87 | 0.571 | 95.01% | 1989.21 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.2 | RMT | 15.39 | 0.81 | 95% | 757.188 |  | 0
SANTOSH KUMAR | CAR PARKING AREA TILING | 234 | 183 | 20.189 | SQM | 20.19 | -0.001 | 100% | 3694.77 |  | 0
SANTOSH KUMAR | FLOOR CHIPPING | 235 | 2.5 | 1763.994 | SFT | 1675.79 | 88.204 | 95% | 4189.475 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.55 | 0.186 | 95.02% | 649.65 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.247 | SQM | 16.38 | 0.867 | 94.97% | 2997.54 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.208 | SQM | 7.8 | 0.408 | 95.03% | 1427.4 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.957 | SQM | 34.16 | 1.797 | 95% | 6251.28 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 132.064 | SQM | 0 | 132.064 | 0% | 0 | 100% | 8528.6931
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 6000
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 15.01 | RMT | 15.01 | 0 | 100% | 83080.35 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
NAGARAJ | CHAIN LINK STAIRCASE WORK | 334 | 20000 | 2 | LUMP SUM | 2 | 0 | 100% | 40000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 3000
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 5347.8 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 2673.9 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 0.5 | 0.5 | 50% | 500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 62.404 | SQM | 62.4 | 0.004 | 99.99% | 3022.5312 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 62.404 | SQM | 62.4 | 0.004 | 99.99% | 1007.76 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 62.404 | SQM | 0 | 62.404 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 74.591 | SQM | 0 | 74.591 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 74.591 | SQM | 0 | 74.591 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION BATHTUB WORK | 425 | 3000 | 1 | NOS | 0.5 | 0.5 | 50% | 1500 |  | 0
RUPAK NAYAK | CUSTOMISATION ROOM EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 22.031 | SQM | 0 | 22.031 | 0% | 0 | 100% | 1422.762
SANTOSH KUMAR | CUSTOMIZATION TOILET TILE WORK | 436 | 984.8602 | 4.103 | SQM | 3.9 | 0.203 | 95.05% | 3840.9548 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 3.07 | SQM | 3.07 | 0 | 100% | 660.9096 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 2.61 | SQM | 2.61 | 0 | 100% | 1123.7616 |  | 0
SANTOSH KUMAR | CUSTOMIZATION MAIN FLOORING WORK | 442 | 238.6186 | 17.814 | SQM | 16.92 | 0.894 | 94.98% | 4037.4267 |  | 0
KHALIL MIAH | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 47.76 | SQM | 47.76 | 0 | 100% | 9253.5 |  | 0
KHALIL MIAH | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 125.429 | SQM | 100.34 | 25.089 | 80% | 14040.7769 |  | 0
KHALIL MIAH | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 23.768 | SQM | 0 | 23.768 | 0% | 0 |  | 0
SARAT BARMAN | CUSTOMISATION FLOOR REINFORCEMENT WORK | 492 | 7500 | 0.554 | MT | 0.55 | 0.004 | 99.28% | 4125 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.16 | CUM | 4.16 | 0 | 100% | 936 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100% | 250 |  | 0
NAGARAJ | CUSTOMIZATION FLOOR SLAB AND BEAM SHUTTERING | 508 | 322.92 | 46.573 | SQM | 46.57 | 0.003 | 99.99% | 15038.3844 |  | 0
NAGARAJ | CUSTOMIZATION FLOOR COLUMN SHUTTERING | 509 | 322.92 | 20.55 | SQM | 20.55 | 0 | 100% | 6636.006 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.328 | MT | 0.33 | -0.002 | 100.6% | 2475 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.243 | MT | 0.24 | 0.003 | 98.77% | 1800 |  | 0
SANTOSH KUMAR | BALCONY UPSTAND TOP COPING GRANITE | 547 | 78 | 47.22 | RFT | 47.22 | 0 | 100% | 3683.16 |  | 0
52073.4926

## V93
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment |  | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100% | 4960.44 |  | 0 |  | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 |  | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 |  | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 |  | KRIUTTIBAS DAS | 8000
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 |  | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 0 | 93.48 | 0% | 0 |  | 0 |  | MANJUNATHA P | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100% | 2020.92 |  | 0 |  | NAGARAJ | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 |  | PRAKASH H N | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 |  | RAMAKRUSHNA PRADHAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 |  | RUPAK NAYAK | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | -0.004 | 100.1% | 3470 |  | 0 |  | SANTOSH KUMAR | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | -0.004 | 100.1% | 2890 |  | 0 |  | SARAT BARMAN | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | -0.004 | 100% | 9190 |  | 0 |  | SAVITA DEVI | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100% | 2250 |  | 0 |  | SHOKAT | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100% | 5250 |  | 0 |  | SHREE DM STEEL FURNITURE AND INTERIOR | 6088.5
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0 |  | SK ANSAR HOSSIAN | 6979.3773
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 |  | SREE VINAYAKA ELECTRICALS | 14832
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100% | 11250 |  | 0 |  | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0 |  | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0 |  | UDHABHAI R PARMAR | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | -0.004 | 106.1% | 525 |  | 0 |  | V VENKATANARAYANA | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0 |  | YELLAPPA C | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0 |  | RABIUL MOLLA | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0.0047 | 99.99% | 19144.4198 |  | 0 |  | KOUSHIK MANDAL | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100% | 15578.9525 |  | 0 |  | SHEKAR T | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100% | 46305.8669 |  | 0 |  | TOTAL | 35899.8773
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100% | 4813.2302 |  | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 63 | SFT | 63 | 0 | 100% | 1764 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0.002 | 99.98% | 2225.25 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0.002 | 99.92% | 3660 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100% | 3897 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100% | 1485 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100% | 5250 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100% | 8250 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100% | 15033.433 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100% | 39985.6766 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100% | 3716.1634 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100% | 5087.497 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0.003 | 99.9% | 5880 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100% | 3082.5 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100% | 3980 |  | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | -0.003 | 100.3% | 1410 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100% | 750 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0.03 | 0 | 100% | 225 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100% | 8176.765 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100% | 828.828 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0.002 | 99.92% | 542.25 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100% | 330 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100% | 22453.9193 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100% | 25809.7039 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100% | 2101.824 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100% | 2102.48 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100% | 184.0644 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0.002 | 100% | 2224.4148 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100% | 27220.972 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 140.4051 | SQM | 140.41 | -0.0048714 | 100% | 27204.7183 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0.002 | 100% | 10409.5415 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | -0.003 | 100% | 30850.808 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 113.0536 | SQM | 113.05 | 0.0036265 | 100% | 21903.6636 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100% | 4677.9268 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100% | 29719.6193 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 132.486 | SQM | 132.49 | -0.004 | 100% | 28522.4472 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 36.3 | SQM | 36.3 | 0 | 100% | 7814.664 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 35.028 | SQM | 35.03 | -0.002 | 100% | 3770.6292 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 79.534 | SQM | 79.53 | 0.004 | 99.99% | 17121.2184 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 35.028 | SQM | 35.03 | -0.002 | 100% | 3770.6292 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 14 | 0 | 100% | 2800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0.003 | 99.99% | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100% | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100% | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100% | 13137.0314 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0.004 | 99.99% | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0.004 | 100% | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0.003 | 100% | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0.001 | 100% | 15634.9791 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100% | 6413.6218 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 10 | 5 | 66.67% | 3500 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0.002 | 99.99% | 3040.56 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100% | 3649 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | -0.002 | 100% | 3581.76 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 0% | 0 |  | 0 | DEBIT TO SANTHOSH 3000/-
SK ANSAR HOSSIAN | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 0% | 0 | 100% | 3000
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 58.71 | SQM | 52.84 | 5.87 | 90% | 9669.72 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.43 | RMT | 53.49 | 5.94 | 90.01% | 2631.708 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 53.77 | 5.972 | 90% | 9839.91 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 62.24 | 6.92 | 89.99% | 3062.208 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.32 | 0.37 | 89.97% | 607.56 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.04 | 0.56 | 90% | 247.968 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TILING | 224 | 183 | 58.71 | SQM | 52.84 | 5.87 | 90% | 9669.72 | 10% | 1074.393
SK ANSAR HOSSIAN | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.43 | RMT | 53.49 | 5.94 | 90.01% | 2631.708 | 10% | 292.3956
SK ANSAR HOSSIAN | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 53.77 | 5.972 | 90% | 9839.91 | 10% | 1093.2786
SK ANSAR HOSSIAN | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 62.24 | 6.92 | 89.99% | 3062.208 | 10% | 340.2672
SK ANSAR HOSSIAN | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.32 | 0.37 | 89.97% | 607.56 | 10% | 67.527
SK ANSAR HOSSIAN | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.04 | 0.56 | 90% | 247.968 | 10% | 27.552
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0.002 | 99.92% | 459.33 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100% | 374.412 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 7.41 | SQM | 7.41 | 0 | 100% | 1356.03 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 11.15 | RMT | 11.15 | 0 | 100% | 548.58 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100% | 4973.94 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100% | 2955 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 3.66 | 0.402 | 90.1% | 669.78 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 16.191 | SQM | 14.57 | 1.621 | 89.99% | 2666.31 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 7.34 | 0.81 | 90.06% | 1343.22 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 30.83 | SQM | 27.75 | 3.08 | 90.01% | 5078.25 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 3.66 | 0.402 | 90.1% | 669.78 | 10% | 74.3346
SK ANSAR HOSSIAN | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 16.191 | SQM | 14.57 | 1.621 | 89.99% | 2666.31 | 10% | 296.2953
SK ANSAR HOSSIAN | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 7.34 | 0.81 | 90.06% | 1343.22 | 10% | 149.145
SK ANSAR HOSSIAN | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 30.83 | SQM | 27.75 | 3.08 | 90.01% | 5078.25 | 10% | 564.189
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 132.064 | SQM | 132.06 | 0.004 | 100% | 8528.4348 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 6000
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.04 | RMT | 25.04 | 0 | 100% | 138596.4 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100% | 1350 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 14832
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 0 | 12.5 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | FABRICATION AND ERECTION OF ENTRANCE STEPS RAILING | 268 | 5535 | 1.1 | RMT | 0 | 1.1 | 0% | 0 | 100% | 6088.5
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100% | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
KRISHNAKUMAR SAHANI | FRONT OF THE HOUSE RAMP GRANITE | 286 | 301.392 | 3.5525 | SQM | 0 | 3.5525 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 39 | RMT | 0 | 39 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 4.185 | SQM | 0 | 4.185 | 0% | 0 |  | 0
SANTOSH KUMAR | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 3.4 | SQM | 3.4 | 0 | 100% | 1024.7328 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 353 | 34.98 | 306.95 | SQM | 306.95 | 0 | 100% | 10737.111 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION TAP POINT WORK | 423 | 750 | 1 | NOS | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 4900 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 2450 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASH BASIN POINT WORK | 486 | 1000 | 2 | NOS | 1 | 1 | 50% | 1000 |  | 0
35899.8773

## V94
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 0 | 93.48 | 0 | 0 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100 | 2250 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100 | 6000 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100 | 11250 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | 0 | 100 | 525 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 22.96 | 6.85 | 77.009 | 6919.9603 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 62.24 | SQM | 62.24 | 0 | 100 | 18758.6381 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 49.637 | SQM | 49.64 | 0 | 100 | 14961.0989 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 142.0476 | SQM | 142.05 | 0 | 100 | 42812.7336 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0 | 100 | 2787.876 | 0 | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 63 | SFT | 63 | 0 | 100 | 1764 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 48.4528 | SQM | 48.45 | 0 | 100 | 14602.4424 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 118.822 | SQM | 118.82 | 0 | 100 | 35811.3974 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | 0 | 100 | 2959.6694 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100 | 1875 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100 | 569.6309 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100 | 22453.9193 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100 | 2101.824 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100 | 2102.48 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0 | 100 | 2224.4148 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100 | 29719.6193 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 132.486 | SQM | 132.49 | 0 | 100 | 28522.4472 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 36.3 | SQM | 36.3 | 0 | 100 | 7814.664 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 35.028 | SQM | 35.03 | 0 | 100 | 3770.6292 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 79.534 | SQM | 79.53 | 0 | 100 | 17121.2184 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 35.028 | SQM | 35.03 | 0 | 100 | 3770.6292 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 14 | 0 | 100 | 2800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 14 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | 0 | 100
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 58.71 | SQM | 50 | 8.71 | 85.164
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.43 | RMT | 50 | 9.43 | 84.133
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 55 | 4.74 | 92.063
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 60 | 9.16 | 86.755
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 0 | 3.69 | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 0 | 5.6 | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 7.41 | SQM | 7.41 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 11.15 | RMT | 11.15 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 0 | 27.18 | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1000 | 182 | 84.602
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 4.06 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 16.19 | SQM | 14.19 | 2 | 87.647
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 6.15 | 2 | 75.46
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 30.81 | SQM | 25.81 | 5 | 83.772
TANMAY | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 132.064 | SQM | 118.86 | 13.21 | 90
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.14 | RMT | 25.14 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 0 | 12.5 | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
KRISHNAKUMAR SAHANI | FRONT OF THE HOUSE RAMP GRANITE | 286 | 301.392 | 3.5525 | SQM | 3.55 | 0 | 100
KRISHNAKUMAR SAHANI | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 39 | RMT | 0 | 39 | 0
KRISHNAKUMAR SAHANI | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 4.185 | SQM | 0 | 4.19 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIORS | CUSTOMISATION SS RALING FOR BALCONY & STAIRCASE(INCLUDING MATERIAL) | 507 | 5535 | 8.1377 | RMT | 8.14 | 0 | 100

## V95
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100 | 2250 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100 | 6000 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100 | 11250 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | 0 | 100 | 525 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100 | 4813.2302 | 0 | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 63 | SFT | 63 | 0 | 100 | 1764 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100 | 5087.497 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100 | 1875 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100 | 828.828 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.88 | SQM | 108.88 | 0 | 100 | 21095.7178 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100 | 2101.824 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100 | 2102.48 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0 | 100 | 2224.4148 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 140.41 | SQM | 140.41 | 0 | 100 | 27204.7183 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 113.05 | SQM | 113.05 | 0 | 100 | 21903.6636 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100 | 29719.6193 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 140.373 | SQM | 140.37 | 0 | 100 | 30218.8536 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 36.88 | SQM | 36.88 | 0 | 100 | 7939.5264 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 32.73 | SQM | 32.73 | 0 | 100 | 3523.0572 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 124.611 | SQM | 87.66 | 36.95 | 70.346 | 18871.4448 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 32.73 | SQM | 32.73 | 0 | 100 | 3523.0572 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 14 | 0 | 100 | 2800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100 | 5399.2224 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100 | 2628.3544 | 0 | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 21.28 | 0 | 100
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 37.08 | 0 | 100
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | 0 | 100
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 58.71 | SQM | 58.71 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.43 | RMT | 59.43 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 59.742 | SQM | 59.74 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.16 | RMT | 69.16 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.6 | RMT | 5.6 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 7.41 | SQM | 7.41 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 11.15 | RMT | 11.15 | 0 | 100
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 1182 | SFT | 1182 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 4.06 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 16.191 | SQM | 16.19 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.15 | SQM | 8.15 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 30.83 | SQM | 30.83 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 132.064 | SQM | 132.06 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 27.48 | RMT | 27.48 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | ENTRANCE STEPS SS RAILING | 268 | 5535 | 1.0057 | RMT | 1.01 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
ANSAR HOSSAIAN SK | FRONT OF THE HOUSE RAMP GRANITE | 286 | 301.392 | 3.048 | SQM | 3.05 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
ANSAR HOSSAIAN SK | NON-SLIP GROOVES IN VILLA MAIN ENTRANCE GRANITE | 288 | 32.8 | 39 | RMT | 0 | 39 | 0
ANSAR HOSSAIAN SK | VILLA MAIN ENTRANCE GRANITE WORK | 313 | 301.392 | 4.185 | SQM | 0 | 4.19 | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 354 | 34.98 | 306.95 | SQM | 306.95 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 4500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASH BASIN POINT WORK | 486 | 1000 | 2 | NOS | 2 | 0 | 100
JMJ WATERPROOING ENTERPRISES | LIVING ROOM CUSTOMIZATION SCREED CONCRETE | 512 | 107.64 | 36.952 | SQM | 36.95 | 0 | 100

## V96
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
MORSELIM KHAN | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
MORSELIM KHAN | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MORSELIM KHAN | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MORSELIM KHAN | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
MORSELIM KHAN | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
MORSELIM KHAN | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
MORSELIM KHAN | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
MORSELIM KHAN | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
MORSELIM KHAN | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
MORSELIM KHAN | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
MORSELIM KHAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100 | 2250 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
MORSELIM KHAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100 | 6000 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100 | 11250 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
MORSELIM KHAN | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
MORSELIM KHAN | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0 | 0.99 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0 | 0.94 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0.01 | 95 | 750 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.24 | 0.01 | 95 | 1800 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 7.7 | 0.41 | 95 | 2320.7184 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 25.77 | 1.36 | 95 | 7766.8718 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.39 | 0.02 | 95 | 780 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.29 | 0.12 | 95 | 515.25 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0 | 0 | 0 | 0
MORSELIM KHAN | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
MORSELIM KHAN | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 0 | 115.89 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 0 | 133.21 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 0 | 67.31 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
MORSELIM KHAN | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 0 | 206.73 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 0 | 71.63 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 0 | 194.53 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 0 | 208.32 | 0 | 0 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 0 | 74.39 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 0 | 220.47 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 0 | 142.16 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 0 | 11.61 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 0 | 33.43 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 0 | 153.39 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100 | 800 | 0 | 0
MORSELIM KHAN | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 203.16 | SFT | 111.74 | 91.42 | 55
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0

## V97
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
MORSELIM KHAN | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
MORSELIM KHAN | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MORSELIM KHAN | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MORSELIM KHAN | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
MORSELIM KHAN | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
MORSELIM KHAN | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
MORSELIM KHAN | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
MORSELIM KHAN | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
MORSELIM KHAN | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
MORSELIM KHAN | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
MORSELIM KHAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100 | 2250 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
MORSELIM KHAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100 | 6000 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100 | 11250 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
MORSELIM KHAN | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
MORSELIM KHAN | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0 | 0.99 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0 | 0.94 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100 | 1875 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 0 | 27.13 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0 | 0 | 0 | 0
MORSELIM KHAN | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
MORSELIM KHAN | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 110.1 | 5.79 | 95 | 21332.0952 | 0 | 0
MORSELIM KHAN | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 99.91 | 33.3 | 75 | 19357.7623 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 0 | 67.31 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
MORSELIM KHAN | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 0 | 206.73 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 0 | 71.63 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 0 | 194.53 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 0 | 208.32 | 0 | 0 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 0 | 74.39 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 0 | 220.47 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 0 | 142.16 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 0 | 11.61 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 0 | 33.43 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 0 | 153.39 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
MORSELIM KHAN | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 203.16 | SFT | 111.74 | 91.42 | 55 | 34639.4 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0

## V98
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
MORSELIM KHAN | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MORSELIM KHAN | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
MORSELIM KHAN | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
MORSELIM KHAN | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
MORSELIM KHAN | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
MORSELIM KHAN | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
MORSELIM KHAN | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
MORSELIM KHAN | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
MORSELIM KHAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100 | 2250 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
MORSELIM KHAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100 | 6000 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.5 | MT | 1.5 | 0 | 100 | 11250 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
MORSELIM KHAN | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
MORSELIM KHAN | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0 | 0.99 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0 | 0.94 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0.01 | 95 | 750 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.24 | 0.01 | 95 | 1800 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.03 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 7.7 | 0.41 | 95 | 2320.7184 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 25.77 | 1.36 | 95 | 7766.8718 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.39 | 0.02 | 95 | 780 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.29 | 0.12 | 95 | 515.25 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0 | 0 | 0 | 0
MORSELIM KHAN | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
MORSELIM KHAN | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 110.1 | 5.79 | 95 | 21332.0952 | 0 | 0
MORSELIM KHAN | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 106.57 | 26.64 | 80 | 20648.1506 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 0 | 67.31 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
MORSELIM KHAN | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 0 | 206.73 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 0 | 71.63 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 0 | 194.53 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 0 | 208.32 | 0 | 0 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 0 | 74.39 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 0 | 220.47 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 0 | 142.16 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 0 | 11.61 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 0 | 33.43 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 0 | 153.39 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
MORSELIM KHAN | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 219.29 | SFT | 120.61 | 98.68 | 55 | 37389.1 | 0 | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0

## V99
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
MORSELIM KHAN | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100 | 8160.48 | 0 | 0
MORSELIM KHAN | FOOTING EXCAVATION | 4 | 211.68 | 164.85 | CUM | 164.85 | 0 | 100 | 34895.448 | 0 | 0
MORSELIM KHAN | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100 | 1816.54 | 0 | 0
MORSELIM KHAN | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100 | 19096.3584 | 0 | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100 | 1934.7552 | 0 | 0
MORSELIM KHAN | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 0 | 62.8 | 0 | 0 | 0 | 0
MORSELIM KHAN | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 0 | 151.12 | 0 | 0 | 0 | 0
MORSELIM KHAN | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | 15.63 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | 0 | 100 | 5680 | 0 | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | 0 | 100 | 4570 | 0 | 0
MORSELIM KHAN | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | 0 | 100 | 15110 | 0 | 0
MORSELIM KHAN | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100 | 4550 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100 | 5250 | 0 | 0
MORSELIM KHAN | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100 | 7000 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.9 | MT | 0.9 | 0 | 100 | 6300 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.8 | MT | 2.8 | 0 | 100 | 19600 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100 | 15105.767 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100 | 9545.0846 | 0 | 0
MORSELIM KHAN | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100 | 31679.3131 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100 | 18056.3947 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 217.05 | SQM | 217.05 | 0 | 100 | 65417.1336 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100 | 4394.2954 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 0 | 18.25 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100 | 5240.25 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100 | 3930 | 0 | 0
MORSELIM KHAN | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100 | 6669 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100 | 7020 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | 0 | 100 | 6754.5 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0 | 0.8 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 1 | MT | 0 | 1 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 2.4 | MT | 0 | 2.4 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0 | 0.2 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 0 | 61.4 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 235.37 | SQM | 0 | 235.37 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 0 | 14.58 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 0 | 20.55 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 0 | 3.59 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 0 | 27.11 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 0 | 1.77 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 0 | 1.28 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0 | 0.25 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.04 | MT | 0 | 0.04 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 0 | 29.38 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 0 | 3.81 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 0 | 2.83 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0 | 0 | 0 | 0
MORSELIM KHAN | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 0 | 52 | 0 | 0 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 0 | 191.86 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 0 | 203.55 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 0 | 87.26 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 0 | 47.7 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | 64.23 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 119.78 | SQM | 0 | 119.78 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 267.58 | SQM | 0 | 267.58 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 309.89 | SQM | 0 | 309.89 | 0 | 0 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 118.32 | SQM | 0 | 118.32 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 366.35 | SQM | 0 | 366.35 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 209.11 | SQM | 0 | 209.11 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 14.1 | SQM | 0 | 14.1 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.29 | SQM | 0 | 37.29 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 180.56 | SQM | 0 | 180.56 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V100
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
UPASANA CHAUDHARY | ATT IN PLINTH | 1 | 54 | 103.17 | SQM | 103.17 | 0 | 100% | 5571.18 |  | 0 | AAIDHUL MIAH | 0
UPASANA CHAUDHARY | FOOTING EXCAVATION | 4 | 211.68 | 150.56 | CUM | 150.56 | 0 | 100% | 31870.5408 |  | 0 | EBI ABRAHAM | 0
UPASANA CHAUDHARY | FOOTING EARTH DRESSING | 5 | 22 | 46.12 | SQM | 46.12 | 0 | 100% | 1014.64 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
UPASANA CHAUDHARY | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 116.13 | CUM | 116.13 | 0 | 100% | 16388.2656 |  | 0 | KRIUTTIBAS DAS | 11000
UPASANA CHAUDHARY | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 7.99 | CUM | 7.99 | 0 | 100% | 1691.3232 |  | 0 | LEGENDRY LANDSCAPE | 0
YELLAPPA C | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 56.74 | CUM | 0 | 56.74 | 0% | 0 |  | 0 | MANJUNATHA P | 0
UPASANA CHAUDHARY | BASE FLOOR EARTH DRESSING | 14 | 22 | 103.17 | SQM | 103.17 | 0 | 100% | 2269.74 |  | 0 | NAGARAJ | 0
UPASANA CHAUDHARY | BASE FLOOR SOLING WORK | 15 | 43 | 130.85 | SQM | 130.85 | 0 | 100% | 5626.55 |  | 0 | PRAKASH H N | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 5500 | RAMAKRUSHNA PRADHAN | 0
UPASANA CHAUDHARY | FOOTING PCC WORK | 20 | 1000 | 7.53 | CUM | 7.53 | 0 | 100% | 7530 |  | 0 | RUPAK NAYAK | 0
UPASANA CHAUDHARY | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.994 | CUM | 3.99 | 0.004 | 99.9% | 3990 |  | 0 | SANTOSH KUMAR | 0
UPASANA CHAUDHARY | BASE FLOOR PCC | 22 | 1000 | 10.32 | CUM | 10.32 | 0 | 100% | 10320 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.41 | MT | 0.41 | 0 | 100% | 2870 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | FOOTING REINFORCEMENT | 23 | 7000 | 0.39 | MT | 0.39 | 0 | 100% | 2730 |  | 0 | SHOKAT | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100% | 4900 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.95 | MT | 0.95 | 0 | 100% | 6650 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 5600 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.6 | MT | 2.6 | 0 | 100% | 18200 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.16 | MT | 0 | 0.16 | 0% | 0 |  | 0 | UDHABHAI R PARMAR | 0
UPASANA CHAUDHARY | FOOTING SHUTTERING | 41 | 301.392 | 65.78 | SQM | 65.78 | 0 | 100% | 19825.5658 |  | 0 | V VENKATANARAYANA | 5500
UPASANA CHAUDHARY | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 37.11 | SQM | 37.11 | 0 | 100% | 11184.6571 |  | 0 | YELLAPPA C | 0
UPASANA CHAUDHARY | PLINTH BEAM SHUTTERING | 43 | 301.392 | 79.884 | SQM | 79.88 | 0.004 | 99.99% | 24075.193 |  | 0 | RABIUL MOLLA | 0
UPASANA CHAUDHARY | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 67.86 | SQM | 67.86 | 0 | 100% | 20452.4611 |  | 0 | KOUSHIK MANDAL | 0
UPASANA CHAUDHARY | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 190 | SQM | 190 | 0 | 100% | 57264.48 |  | 0 | SHEKAR T | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 28.06 | SQM | 0 | 28.06 | 0% | 0 |  | 0 | TOTAL | 16500
UPASANA CHAUDHARY | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.793 | SQM | 12.79 | 0.003 | 99.98% | 3854.8037 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 11.65 | SQM | 0 | 11.65 | 0% | 0 |  | 0
UPASANA CHAUDHARY | FOOTING RCC | 50 | 225 | 17.19 | CUM | 17.19 | 0 | 100% | 3867.75 |  | 0
UPASANA CHAUDHARY | PEDESTAL COLUMN RCC | 51 | 1500 | 2.18 | CUM | 2.18 | 0 | 100% | 3270 |  | 0
UPASANA CHAUDHARY | PLINTH BEAM RCC | 53 | 900 | 5.991 | CUM | 5.99 | 0.001 | 99.98% | 5391 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.98 | CUM | 3.98 | 0 | 100% | 7960 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 23.5 | CUM | 23.5 | 0 | 100% | 5287.5 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.673 | CUM | 1.67 | 0.003 | 99.82% | 3340 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100% | 1440 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.8 | MT | 0 | 0.8 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 70 | 7000 | 0.8 | MT | 0.8 | 0 | 100% | 5600 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.85 | MT | 0 | 1.85 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 74 | 7000 | 1.85 | MT | 1.85 | 0 | 100% | 12950 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 78 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0 | 0.2 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 82 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 56.55 | SQM | 56.55 | 0 | 100% | 17043.7176 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 188.59 | SQM | 188.59 | 0 | 100% | 56839.5173 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.793 | SQM | 12.79 | 0.003 | 99.98% | 3854.8037 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 14.11 | SQM | 14.11 | 0 | 100% | 4252.6411 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.33 | CUM | 3.33 | 0 | 100% | 6660 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 19.19 | CUM | 19.19 | 0 | 100% | 4317.75 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.673 | CUM | 1.67 | 0.003 | 99.82% | 3340 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.57 | CUM | 1.57 | 0 | 100% | 2355 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 98 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.3 | MT | 0 | 0.3 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 101 | 7000 | 0.3 | MT | 0.3 | 0 | 100% | 2100 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0 | 0.02 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 104 | 7000 | 0.02 | MT | 0.02 | 0 | 100% | 140 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 26.6 | SQM | 26.6 | 0 | 100% | 8017.0272 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.815 | SQM | 1.82 | -0.005 | 100.3% | 548.5334 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 3.07 | CUM | 3.07 | 0 | 100% | 690.75 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.17 | CUM | 0.17 | 0 | 100% | 255 |  | 0
YELLAPPA C | ALL LEVEL COLUMN STARTER | 116 | 50 | 53 | NOS | 53 | 0 | 100% | 2650 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 146.37 | SQM | 146.37 | 0 | 100% | 28359.4802 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 185.55 | SQM | 185.55 | 0 | 100% | 35950.6836 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 72.29 | SQM | 72.29 | 0 | 100% | 14006.3321 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 49.17 | RMT | 49.17 | 0 | 100% | 3225.552 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 33.82 | RMT | 33.82 | 0 | 100% | 2218.592 |  | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.38 | SQM | 1.38 | 0 | 100% | 222.8148 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 10.76 | 259.56 | SQM | 259.56 | 0 | 100% | 2792.8656 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 94.21 | SQM | 94.21 | 0 | 100% | 13182.9937 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 266.24 | SQM | 266.24 | 0 | 100% | 37255.4957 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 261.11 | SQM | 261.11 | 0 | 100% | 50590.5847 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 1 | 0 | 100% | 16500 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 92.25 | SQM | 92.25 | 0 | 100% | 12908.727 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 364.2 | SQM | 364.2 | 0 | 100% | 50963.2344 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 163.72 | SQM | 163.72 | 0 | 100% | 31721.0774 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 13.2 | SQM | 13.2 | 0 | 100% | 1847.1024 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 37.271 | SQM | 37.27 | 0.001 | 100% | 5215.2656 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 163.58 | SQM | 163.58 | 0 | 100% | 31693.9522 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 175.184 | SQM | 175.18 | 0.004 | 100% | 37712.7504 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 28.865 | SQM | 28.87 | -0.005 | 100% | 6215.1336 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 35.246 | SQM | 35.25 | -0.004 | 100% | 3794.31 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 216.28 | 111.064 | SQM | 111.06 | 0.004 | 100% | 24020.0568 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 35.346 | SQM | 35.35 | -0.004 | 100% | 3805.074 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 13 | NOS | 13 | 0 | 100% | 2600 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 49.1314 | SQM | 49.13 | 0.00142 | 100% | 10576.7064 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 16.05 | SQM | 16.05 | 0 | 100% | 1554.924 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 108.2749 | SQM | 43.31 | 64.9649 | 40% | 2097.8498 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 126.7773 | SQM | 50.71 | 76.0673 | 40% | 2456.291 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 48.6843 | SQM | 19.47 | 29.2143 | 39.99% | 943.0879 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 103.968 | SQM | 103.97 | -0.002 | 100% | 1679.1155 |  | 0
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 226.3623 | SQM | 135.82 | 90.5423 | 60% | 12426.7151 |  | 0
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 99.991 | SQM | 59.99 | 40.001 | 60% | 5488.7251 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 294.5224 | SQM | 176.71 | 117.8124 | 60% | 16167.9047 |  | 0
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 93.461 | SQM | 56.08 | 37.381 | 60% | 5130.9835 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 44.094 | SQM | 26.46 | 17.634 | 60.01% | 2420.9312 |  | 0
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 10.175 | SQM | 6.11 | 4.065 | 60.05% | 559.0283 |  | 0
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 27.898 | SQM | 27.9 | -0.002 | 100% | 8408.8368 |  | 0
ANSAR HOSSAIAN SK | LEDGE WALL GRANITE | 217 | 450 | 5 | NOS | 0 | 5 | 0% | 0 |  | 0
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 20 | NOS | 20 | 0 | 100% | 7000 |  | 0
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 48.7 | RMT | 48.7 | 0 | 100% | 3993.4 |  | 0
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 116.4 | RMT | 116.4 | 0 | 100% | 3817.92 |  | 0
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 17.78 | RMT | 17.78 | 0 | 100% | 2332.736 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 76.164 | SQM | 76.16 | 0.004 | 99.99% | 13937.28 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 56.398 | RMT | 56.4 | -0.002 | 100% | 2774.88 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 70.462 | SQM | 70.46 | 0.002 | 100% | 12894.18 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 73.138 | RMT | 73.14 | -0.002 | 100% | 3598.488 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 3.433 | SQM | 3.43 | 0.003 | 99.91% | 627.69 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 5.48 | RMT | 5.48 | 0 | 100% | 269.616 |  | 0
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 3.584 | SQM | 3.58 | 0.004 | 99.89% | 655.14 |  | 0
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 6.56 | RMT | 6.56 | 0 | 100% | 322.752 |  | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 17.06 | SQM | 17.06 | 0 | 100% | 3121.98 |  | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.105 | RMT | 18.11 | -0.005 | 100% | 891.012 |  | 0
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 18.655 | SQM | 18.66 | -0.005 | 100% | 3414.78 |  | 0
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 1978.219 | SFT | 1978.22 | -0.001 | 100% | 4945.55 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 6.008 | SQM | 6.01 | -0.002 | 100% | 1099.83 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 29.5683 | SQM | 29.57 | -0.00166 | 100% | 5411.31 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 10.637 | SQM | 10.64 | -0.003 | 100% | 1947.12 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 49.3876 | SQM | 49.39 | -0.00244 | 100% | 9038.37 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100% | 15500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 0.375 | 0.625 | 37.5% | 4500 | 62.5% | 7500
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 1500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 12600 | 1 | LUMP SUM | 1 | 0 | 100% | 12600 |  | 0
SUNIL | STRUCTURAL ENGINEER SITE VISIT | 317 | 3500 | 2 | PER DAY | 2 | 0 | 100% | 7000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 1500 | 50% | 1500
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 2787.75 | 1 | LUMP SUM | 1 | 0 | 100% | 2787.75 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 31.4656 | SQM | 31.47 | -0.0044 | 100% | 1524.3439 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 31.4656 | SQM | 31.47 | -0.0044 | 100% | 508.2405 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 31.4656 | SQM | 0 | 31.4656 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 15.5568 | SQM | 15.56 | -0.0032 | 100% | 251.294 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 15.5568 | SQM | 0 | 15.5568 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
ANSAR HOSSAIAN SK | CUSTOMIZATION MAIN FLOORING WORK | 442 | 228.9281 | 16.511 | SQM | 16.51 | 0.001 | 99.99% | 3779.6029 |  | 0
16500

## V101
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100 | 12441.1392 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100 | 2952.81 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7000 | 0.27 | MT | 0.27 | 0 | 100 | 1890 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.42 | MT | 0.42 | 0 | 100 | 2940 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.53 | MT | 0.53 | 0 | 100 | 3710 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0.49 | 0 | 100 | 3430 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100 | 975 | 0 | 0
BHASKAR | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100 | 7980.8602 | 0 | 0
BHASKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
BHASKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100 | 16492.1702 | 0 | 0
BHASKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100 | 13653.0576 | 0 | 0
BHASKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100 | 38912.7211 | 0 | 0
BHASKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
MANJUNATHA R | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0 | 100 | 2787.876 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.76 | CUM | 0.76 | 0 | 100 | 2280 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100 | 3525 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.67 | 0.21 | 76.136 | 5025 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 9766 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
BHASKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100 | 11826.6221 | 0 | 0
BHASKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 107.8 | SQM | 107.8 | 0 | 100 | 32490.0576 | 0 | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
MANJUNATHA R | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | 0 | 100 | 2959.6694 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.82 | CUM | 0.82 | 0 | 100 | 2460 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 10000 | 0.029 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100 | 7275.6029 | 0 | 0
MANJUNATHA R | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100 | 569.6309 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 2000 | 2.37 | CUM | 2.37 | 0 | 100 | 4740 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 93.08 | SQM | 93.08 | 0 | 100 | 18034.4362 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100 | 25056.0086 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0 | 100 | 12200.5634 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 30.1 | 0 | 100 | 1974.56 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 66.89 | 0 | 100 | 4387.984 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0.5 | 0 | 100 | 80.73 | 0 | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 8 | 348 | SQM | 348 | 0 | 100 | 2784 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100 | 8373.5309 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100 | 24731.5817 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 147.87 | SQM | 126 | 21.87 | 85.21 | 24412.752 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100 | 11425.4478 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.15 | SQM | 228.15 | 0 | 100 | 31925.4858 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 110.32 | SQM | 110.32 | 0 | 100 | 21374.7206 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.86 | SQM | 8.86 | 0 | 100 | 1239.7975 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100 | 4780.0771 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 77.1 | SQM | 77.1 | 0 | 100 | 14938.2792 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 124.995 | SQM | 125 | 0 | 100 | 26910 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 37.457 | SQM | 37.46 | 0 | 100 | 8064.3888 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 20.048 | SQM | 20.05 | 0 | 100 | 2158.182 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 68.409 | SQM | 68.41 | 0 | 100 | 14727.3048 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 20.048 | SQM | 20.05 | 0 | 100 | 2158.182 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 15 | NOS | 15 | 0 | 100 | 3000 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.81 | RMT | 37.81 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 108.232 | RMT | 108.23 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 34.15 | RMT | 34.15 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.018 | SQM | 51.02 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.42 | RMT | 47.42 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 46.72 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 35.755 | RMT | 35.76 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 2.67 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 4.67 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 8.92 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 19.18 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 5.56 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 15.422 | SQM | 15.42 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.74 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 17.51 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 7.5 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 35.08 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.121 | SQM | 0 | 126.12 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 30.204 | RMT | 27.23 | 2.97 | 90.154
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
INDAL SAHNI | SILL GRANITE | 289 | 75 | 30 | RFT | 30 | 0 | 100
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 1553.1 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | CUSTOMIZATION WASH BASIN POINT WORK | 486 | 1000 | 1 | NOS | 0.5 | 0.5 | 50
ANSAR HOSSAIAN SK | BALCONY UPSTAND TOP COPING GRANITE | 547 | 78 | 35.854 | RFT | 35.85 | 0 | 100
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100

## V102
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | EBI ABRAHAM | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18 | CUM | 18 | 0 | 100% | 2540.16 |  | 0 | KRIUTTIBAS DAS | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70.16 | CUM | 70.16 | 0 | 100% | 9900.9792 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 20 | CUM | 20 | 0 | 100% | 2822.4 |  | 0 | NAGARAJ | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 10.73 | CUM | 10.73 | 0 | 100% | 1514.2176 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100% | 1510.74 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 77 | SQM | 70 | 7 | 90.91% | 3010 |  | 0 | RUPAK NAYAK | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100% | 1121.904 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SARAT BARMAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SAVITA DEVI | 1350
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SHOKAT | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | YELLAPPA C | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0.13 | 0 | 100% | 1300 |  | 0 | RABIUL MOLLA | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100% | 7980.8602 |  | 0 | KOUSHIK MANDAL | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | SHEKAR T | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100% | 16492.1702 |  | 0 | TOTAL | 1350
MANJUNATHA R | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0
MANJUNATHA R | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100% | 38912.7211 |  | 0
MANJUNATHA R | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
MANJUNATHA R | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.25 | SQM | 9.25 | 0 | 100% | 2787.876 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.14 | CUM | 1.14 | 0 | 100% | 1710 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100% | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0.15 | 0 | 100% | 1500 |  | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 107.8 | SQM | 107.8 | 0 | 100% | 32490.0576 |  | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
MANJUNATHA R | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | -0.005 | 100.1% | 2959.6694 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.83 | CUM | 0.83 | 0 | 100% | 2490 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0.03 | -0.001 | 103.4% | 210 |  | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100% | 7275.6029 |  | 0
MANJUNATHA R | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100% | 569.6309 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 1.665 | CUM | 1.67 | -0.005 | 100.3% | 3340 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 7 | CUM | 7 | 0 | 100% | 1575 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.17 | CUM | 0.17 | 0 | 100% | 510 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 49 | NOS | 0 | 49 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 94.59 | 0 | 100% | 18327.0017 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100% | 25056.0086 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100% | 2119.72 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100% | 24731.5817 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 120 | 11.565 | 91.21% | 23250.24 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 228.24 | 0 | 100% | 31938.0797 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.17 | SQM | 109.17 | 0 | 100% | 21151.9058 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100% | 1365.7363 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100% | 4780.0771 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 99.15 | 0 | 100% | 19210.5108 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 106.779 | SQM | 106.78 | -0.001 | 100% | 22987.5984 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 34.035 | SQM | 34.04 | -0.005 | 100% | 7328.1312 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 13.115 | SQM | 13.12 | -0.005 | 100% | 1412.2368 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 85.724 | SQM | 85.72 | 0.004 | 100% | 18453.8016 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 13.115 | SQM | 13.12 | -0.005 | 100% | 1412.2368 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 18 | NOS | 18 | 0 | 100% | 3600 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0.004 | 99.98% | 4299.1416 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | -0.004 | 100% | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0.004 | 100% | 5579.825 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0.004 | 100% | 11156.886 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100% | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0.003 | 100% | 25402.3403 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100% | 8648.325 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | -0.001 | 100% | 14565.0375 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100% | 5768.6429 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100% | 5600 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.81 | RMT | 37.81 | 0 | 100% | 3100.42 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 108.232 | RMT | 108.23 | 0.002 | 100% | 3549.944 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 34.15 | RMT | 34.15 | 0 | 100% | 0 |  | 0
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100% | 4000 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.018 | SQM | 51.02 | -0.002 | 100% | 9336.66 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.42 | RMT | 47.42 | 0 | 100% | 2333.064 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 46.72 | 0.003 | 99.99% | 8549.76 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 35.755 | RMT | 35.76 | -0.005 | 100% | 1759.392 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 2.14 | 0.53 | 80.15% | 391.62 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 3.74 | 0.93 | 80.09% | 184.008 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 0 | 8.92 | 0% | 0 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 0 | 19.18 | 0% | 0 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 4.45 | 1.109 | 80.05% | 814.35 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 8.55 | 2.134 | 80.03% | 420.66 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 15.422 | SQM | 0 | 15.422 | 0% | 0 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100% | 2712.5 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 2.8 | 0.936 | 74.95% | 512.4 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 12.25 | 5.255 | 69.98% | 2241.75 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 5.25 | 2.245 | 70.05% | 960.75 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 24.56 | 10.522 | 70.01% | 4494.48 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.564 | SQM | 126.56 | 0.004 | 100% | 8173.2448 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 30.1 | RMT | 30.1 | 0 | 100% | 166603.5 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 0 | 3 | 0% | 0 | 100% | 1350
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100% | 1500 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100% | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 89.526 | SQM | 89.53 | -0.004 | 100% | 4336.6541 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 89.526 | SQM | 89.53 | -0.004 | 100% | 1445.9095 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 89.526 | SQM | 89.53 | -0.004 | 100% | 2409.2523 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 14.102 | SQM | 14.1 | 0.002 | 99.99% | 227.715 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 14.102 | SQM | 14.1 | 0.002 | 99.99% | 455.3172 |  | 0
MANJUNATHA R | CUSTOMIZATION SHUTTERING OF TERRACE COLUMN, BEAM AND SLAB, LINTEL AND CHAJJA | 458 | 301.392 | 59.6 | SQM | 59.6 | 0 | 100% | 17962.9632 |  | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 38.65 | SQM | 30 | 8.65 | 77.62% | 5812.5 |  | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 66.8 | SQM | 66.8 | 0 | 100% | 9347.4576 |  | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 28.122 | SQM | 28.12 | 0.002 | 99.99% | 5448.3062 |  | 0
RUPAK NAYAK | CUSTOMISATION EPOXY GROUTING & SOAP WASH | 480 | 64.58 | 21.676 | SQM | 21.68 | -0.004 | 100% | 1400.0944 |  | 0
SARAT BARMAN | CUSTOMISATION FLOOR REINFORCEMENT WORK | 492 | 7500 | 0.554 | MT | 0.55 | 0.004 | 99.28% | 4125 |  | 0
AAIDHUL MIAH | CUSTOMISATION UTILITY WALL OF HEIGHT ABOVE 5FT | 513 | 193.752 | 2.857 | SQM | 2.86 | -0.003 | 100.1% | 554.1307 |  | 0
AAIDHUL MIAH | UTILITY CUSTOMISATION WALL PLASTERING ABOVE 5 FT | 514 | 193.752 | 7.666 | SQM | 7.67 | -0.004 | 100.1% | 1486.0778 |  | 0
SHOKAT | CUSTOMIZATION TOILET FLOOR CHIPPING AND 2 COATS OF WATERPROOFING | 515 | 430.56 | 6.525 | SQM | 6.53 | -0.005 | 100.1% | 2811.5568 |  | 0
SHOKAT | CUSTOMIZATION TOILET SCREED CONCRETE | 516 | 215.28 | 10.125 | SQM | 10.13 | -0.005 | 100% | 2180.7864 |  | 0
1350

## V103
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 35651.7243
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 6000
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100% | 9878.4 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | PRAKASH H N | 17000
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100% | 1121.904 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SAVITA DEVI | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SHOKAT | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR, FIRST FLOOR & TERRACE FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 38 | 7000 | 1 | LUMP SUM | 1 | 0 | 100% | 7000 |  | 0 | YELLAPPA C | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 | RABIUL MOLLA | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 | KOUSHIK MANDAL | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | SHEKAR T | 0
MANJUNATHA R | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0 | TOTAL | 58651.7243
MANJUNATHA R | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0
MANJUNATHA R | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 0 | 9.2505 | 0% | 0 |  | 0
NAGARAJ | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA SHUTTERING | 48 | 25000 | 1 | LUMP SUM | 1 | 0 | 100% | 25000 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA RCC | 67 | 10000 | 1 | LUMP SUM | 1 | 0 | 100% | 10000 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 107.8 | SQM | 107.8 | 0 | 100% | 32490.0576 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100% | 3487.536 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 0 | 10.8 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 24.14 | 0 | 100% | 7795.2888 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 0 | 24.14 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 80.4 | 14.19 | 85% | 15577.6608 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 109.92 | 19.4 | 85% | 21297.2198 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 56.68 | 6.293 | 90.01% | 10981.8634 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 0 | 268.5 | 0% | 0 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 0 | 197 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 0 | 59.84 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 0 | 176.74 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 0 | 131.565 | 0% | 0 | 50% | 12745.4909
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 14500
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 0 | 228.24 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.177 | SQM | 0 | 109.177 | 0% | 0 | 50% | 10576.6311
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 0 | 99.15 | 0% | 0 | 50% | 9605.2554
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 50% | 4500
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 50% | 1500
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2500
AAIDHUL MIAH | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 38.65 | SQM | 34.79 | 3.86 | 90.01% | 6740.5625 |  | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 109.944 | SQM | 0 | 109.944 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 28.122 | SQM | 0 | 28.122 | 0% | 0 | 50% | 2724.3469
SARAT BARMAN | CUSTOMISATION FLOOR REINFORCEMENT WORK | 492 | 7500 | 0.554 | MT | 0.55 | 0.004 | 99.28% | 4125 |  | 0
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 24.195 | SQM | 24.2 | -0.005 | 100% | 7814.664 |  | 0
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 7.44 | SQM | 7.44 | 0 | 100% | 2402.5248 |  | 0
SUBHASMITA DAS | TERRACE FLOOR CUSTOMISATION COLUMN RCC | 517 | 2000 | 0.483 | CUM | 0.48 | 0.003 | 99.38% | 960 |  | 0
SUBHASMITA DAS | TERRACE FLOOR CUSTOMISATION BEAM AND SLAB RCC | 518 | 225 | 4.738 | CUM | 4.74 | -0.002 | 100% | 1066.5 |  | 0
58651.7243

## V104
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 30 | 38.67 | 43.69% | 1620 |  | 0 | AAIDHUL MIAH | 75324.2422
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100% | 9878.4 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | PRAKASH H N | 14500
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100% | 1121.904 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SAVITA DEVI | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SHOKAT | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0 | YELLAPPA C | 0
SARAT BARMAN | GROUND FLOOR, FIRST FLOOR & TERRACE FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 38 | 7000 | 1 | LUMP SUM | 0.4 | 0.6 | 40% | 2800 |  | 0 | RABIUL MOLLA | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 | KOUSHIK MANDAL | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 | SHEKAR T | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | TOTAL | 89824.2422
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 9.25 | 0.0005 | 99.99% | 2987.01 |  | 0
NAGARAJ | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA SHUTTERING | 48 | 25000 | 1 | LUMP SUM | 0.32 | 0.68 | 32% | 8000 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100% | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100% | 34810.776 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.815 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.83 | CUM | 0.83 | 0 | 100% | 2490 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.17 | CUM | 0 | 0.17 | 0% | 0 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 94.59 | 0 | 100% | 18327.0017 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 109.92 | 19.4 | 85% | 21297.2198 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.973 | 0% | 0 | 90% | 10981.0302
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 0 | 268.5 | 0% | 0 | 100% | 9397.5
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 0 | 197 | 0% | 0 | 100% | 2119.72
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 0 | 59.84 | 0% | 0 | 80% | 6698.8247
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 0 | 176.74 | 0% | 0 | 80% | 19785.2653
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 0 | 131.565 | 0% | 0 | 40% | 10196.3928
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 14500
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 0 | 228.24 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.177 | SQM | 0 | 109.177 | 0% | 0 | 40% | 8461.3048
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 0 | 99.15 | 0% | 0 | 40% | 7684.2043
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 4500 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 8552 | 1 | LUMP SUM | 1 | 0 | 100% | 8552 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
89824.2422

## V105
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 29.53 | 39.14 | 43 | 1594.62 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100 | 2562.7392 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100 | 9878.4 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100 | 630.74 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | GROUND FLOOR, FIRST FLOOR & TERRACE FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 38 | 7000 | 1 | LUMP SUM | 0.4 | 0.6 | 40 | 2800 | 0 | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100 | 8550.9216 | 0 | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100 | 8321.6484 | 0 | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100 | 17670.1824 | 0 | 0
MANJUNATHA R | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100 | 14628.276 | 0 | 0
MANJUNATHA R | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100 | 41692.2012 | 0 | 0
MANJUNATHA R | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100 | 3962.2284 | 0 | 0
MANJUNATHA R | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
NAGARAJ | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA SHUTTERING | 48 | 25000 | 1 | LUMP SUM | 0.4 | 0.6 | 40 | 10000 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
AAIDHUL MIAH | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA RCC | 67 | 10000 | 1 | LUMP SUM | 1 | 0 | 100 | 10000 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100 | 3525 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100 | 6600 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0.15 | 0 | 100 | 1500 | 0 | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100 | 12671.3808 | 0 | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100 | 34810.776 | 0 | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100 | 3962.2284 | 0 | 0
MANJUNATHA R | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 9.82 | 0 | 100 | 3171.0744 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100 | 975 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100 | 1425 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100 | 3487.536 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 24.14 | 0 | 100 | 7795.2888 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100 | 533.25 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 108.15 | 0 | 100 | 20954.2788 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 107 | 26.75 | 80 | 20731.464 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 56.68 | 6.3 | 90 | 10981.8634 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 38.65 | SQM | 34.79 | 3.87 | 90
AAIDHUL MIAH | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 109.944 | SQM | 0 | 109.94 | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 28.122 | SQM | 0 | 28.12 | 0
SARAT BARMAN | CUSTOMISATION FLOOR REINFORCEMENT WORK | 492 | 7500 | 0.554 | MT | 0.55 | 0 | 100
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 24.195 | SQM | 24.2 | 0 | 100
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 7.44 | SQM | 7.44 | 0 | 100
SUBHASMITA DAS | TERRACE FLOOR CUSTOMISATION COLUMN RCC | 517 | 2000 | 0.483 | CUM | 0.48 | 0 | 100
SUBHASMITA DAS | TERRACE FLOOR CUSTOMISATION BEAM AND SLAB RCC | 518 | 225 | 4.738 | CUM | 4.74 | 0 | 100

## V106
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 0 | 68.67 | 0 | 0 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100 | 2562.7392 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100 | 9878.4 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.76 | SQM | 28.76 | 0 | 100 | 632.72 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 5.84 | 1.03 | 85 | 5840 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100 | 8550.9216 | 0 | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100 | 8321.6484 | 0 | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100 | 17670.1824 | 0 | 0
MANJUNATHA R | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100 | 14628.276 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
MANJUNATHA R | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100 | 41692.2012 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
MANJUNATHA R | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100 | 3962.2284 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
MANJUNATHA R | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0 | 0.47 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0 | 0.88 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
MANJUNATHA R | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 0 | 2.21 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0 | 0 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0 | 0 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0

## V107
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 0 | 68.67 | 0 | 0 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100 | 2562.7392 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100 | 9878.4 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100 | 630.74 | 0 | 0
MANJUNATHA P | BASE FLOOR EARTH DRESSING | 14 | 22 | 40 | SQM | 40 | 0 | 100 | 880 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0 | 0 | 0 | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100 | 1121.904 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 3.78 | 3.09 | 55 | 3780 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100 | 8550.9216 | 0 | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100 | 8321.6484 | 0 | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100 | 17670.1824 | 0 | 0
MANJUNATHA R | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100 | 14628.276 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
MANJUNATHA R | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100 | 41692.2012 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
MANJUNATHA R | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100 | 3962.2284 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
MANJUNATHA R | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0 | 0.47 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0 | 0.88 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
MANJUNATHA R | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 0 | 2.21 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0 | 0 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0 | 0 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0

## V108
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 0 | 68.67 | 0 | 0 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100 | 2562.7392 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100 | 9878.4 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100 | 630.74 | 0 | 0
MANJUNATHA P | BASE FLOOR EARTH DRESSING | 14 | 22 | 40 | SQM | 40 | 0 | 100 | 880 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0 | 0 | 0 | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100 | 1121.904 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 4.81 | 2.06 | 70 | 4810 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100 | 8550.9216 | 0 | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100 | 8321.6484 | 0 | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100 | 17670.1824 | 0 | 0
MANJUNATHA R | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100 | 14628.276 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
MANJUNATHA R | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100 | 41692.2012 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
MANJUNATHA R | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100 | 3962.2284 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
MANJUNATHA R | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0 | 0.47 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0 | 0.88 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
MANJUNATHA R | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 0 | 2.21 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
MANJUNATHA R | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0 | 0 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0 | 0 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0

## V109
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
MORSELIM KHAN | ATT IN PLINTH | 1 | 54 | 103.17 | SQM | 103.17 | 0 | 100 | 5571.18 | 0 | 0
MORSELIM KHAN | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MORSELIM KHAN | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MORSELIM KHAN | FOOTING EXCAVATION | 4 | 211.68 | 150.56 | CUM | 113.9 | 36.66 | #VALUE! | 24110.352 | 0 | 0
MORSELIM KHAN | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0 | 100 | 1252.9 | 0 | 0
MORSELIM KHAN | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 116.13 | CUM | 97.03 | 19.1 | #VALUE! | 13692.8736 | 0 | 0
MORSELIM KHAN | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 56.74 | CUM | 56.74 | 0 | 100 | 8007.1488 | 0 | 0
MORSELIM KHAN | BASE FLOOR EARTH DRESSING | 14 | 22 | 103.17 | SQM | 103.17 | 0 | 100 | 2269.74 | 0 | 0
MORSELIM KHAN | BASE FLOOR SOLING WORK | 15 | 43 | 130.85 | SQM | 130.85 | 0 | 100 | 5626.55 | 0 | 0
MORSELIM KHAN | FOOTING PCC WORK | 20 | 1000 | 7.53 | CUM | 4.13 | 3.4 | #VALUE! | 4130 | 0 | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.994 | CUM | 3.99 | 0 | 100 | 3990 | 0 | 0
MORSELIM KHAN | BASE FLOOR PCC | 22 | 1000 | 10.32 | CUM | 0 | 10.32 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.8 | MT | 0.4 | 0.4 | #VALUE! | 3000 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.45 | 0.25 | #VALUE! | 3375 | 0 | 0
MORSELIM KHAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.95 | MT | 0.95 | 0 | 100 | 7125 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.6 | MT | 0 | 2.6 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.16 | MT | 0 | 0.16 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING SHUTTERING | 41 | 301.392 | 65.7 | SQM | 35.26 | 30.45 | #VALUE! | 10627.0819 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 37.11 | SQM | 27.66 | 9.45 | #VALUE! | 8336.5027 | 0 | 0
MORSELIM KHAN | PLINTH BEAM SHUTTERING | 43 | 301.392 | 79.884 | SQM | 79.88 | 0 | 100 | 24075.193 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 67.86 | SQM | 64.47 | 3.39 | 95 | 19430.7422 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 218.06 | SQM | 0 | 218.06 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.793 | SQM | 0 | 12.79 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0 | 0 | 0 | 0
MORSELIM KHAN | FOOTING RCC | 50 | 225 | 17.19 | CUM | 11.08 | 6.11 | #VALUE! | 2493 | 0 | 0
MORSELIM KHAN | PEDESTAL COLUMN RCC | 51 | 1500 | 2.18 | CUM | 1.6 | 0.58 | #VALUE! | 2400 | 0 | 0
MORSELIM KHAN | PLINTH BEAM RCC | 53 | 900 | 5.991 | CUM | 5.99 | 0 | 100 | 5391 | 0 | 0
MORSELIM KHAN | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.98 | CUM | 3.78 | 0.2 | 95 | 7560 | 0 | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 23.5 | CUM | 0 | 23.5 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 0 | 1.81 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0 | 0.96 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.8 | MT | 0 | 0.8 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.85 | MT | 0 | 1.85 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0 | 0.2 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 56.55 | SQM | 0 | 56.55 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 188.59 | SQM | 0 | 188.59 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 0 | 12.78 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.5 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.33 | CUM | 0 | 3.33 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 19.19 | CUM | 0 | 19.19 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 0 | 1.81 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.3 | MT | 0 | 0.3 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 28.129 | SQM | 0 | 28.13 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.46 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0 | 0.71 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 3.07 | CUM | 0 | 3.07 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0 | 0.2 | 0 | 0 | 0 | 0
MORSELIM KHAN | ALL LEVEL COLUMN STARTER | 116 | 50 | 53 | NOS | 0 | 53 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 146.37 | SQM | 0 | 146.37 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 185.55 | SQM | 0 | 185.55 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 72.29 | SQM | 0 | 72.29 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEVATION RCC BAND | 133 | 65.6 | 49.17 | RMT | 0 | 49.17 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0 | 0 | 0 | 0
MORSELIM KHAN | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.38 | SQM | 0 | 1.38 | 0 | 0 | 0 | 0
MORSELIM KHAN | RCC SURFACE HACKING | 140 | 10.76 | 259.56 | SQM | 0 | 259.56 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 94.21 | SQM | 0 | 94.21 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 266.24 | SQM | 0 | 266.24 | 0 | 0 | 0 | 0
MORSELIM KHAN | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 261.11 | SQM | 0 | 261.11 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 92.25 | SQM | 0 | 92.25 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 364.2 | SQM | 0 | 364.2 | 0 | 0 | 0 | 0
MORSELIM KHAN | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 163.72 | SQM | 0 | 163.72 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 13.2 | SQM | 0 | 13.2 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 0 | 39.21 | 0 | 0 | 0 | 0
MORSELIM KHAN | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 163.58 | SQM | 0 | 163.58 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 100 | RFT | 0 | 100 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 27 | 0 | 100 | 2079 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 249 | SFT | 0 | 249 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 0 | 15 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
MORSELIM KHAN | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 296 | 310 | 451 | SFT | 50 | 401 | 11.086 | 15500 | 0 | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 14260 | 1 | LUMP SUM | 1 | 0 | 100 | 14260 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V110
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 350
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | EBI ABRAHAM | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100% | 1510.74 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | KRIUTTIBAS DAS | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | PRAKASH H N | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | RUPAK NAYAK | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SANTOSH KUMAR | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SARAT BARMAN | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SHOKAT | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | -0.004 | 106.1% | 525 |  | 0 | SK ANSAR HOSSIAN | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100% | 8270.1965 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100% | 17414.4298 |  | 0 | SUBHASMITA DAS | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0 | UDHABHAI R PARMAR | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100% | 38912.7211 |  | 0 | V VENKATANARAYANA | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0 | YELLAPPA C | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 15.17 | 0 | 100% | 4572.1166 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 48 | SFT | 48 | 0 | 100% | 1344 |  | 0 | KOUSHIK MANDAL | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0 | SHEKAR T | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0 | TOTAL | 350
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100% | 1440 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100% | 39171.9182 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 16.19 | 0 | 100% | 4879.5365 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100% | 1305 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0.03 | -0.001 | 103.4% | 225 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100% | 7275.6029 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 3.5 | 0 | 100% | 1054.872 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100% | 570 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 108.15 | -0.003 | 100% | 20954.2788 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 133.76 | -0.004 | 100% | 25916.2675 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 30.1 | 0 | 100% | 1974.56 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 66.89 | 0 | 100% | 4387.984 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0.5 | 0 | 100% | 80.73 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100% | 2119.72 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100% | 24731.5817 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 177.87 | 0 | 100% | 34462.6682 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 258.15 | 0 | 100% | 36123.4458 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100% | 24474.7526 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100% | 1365.7363 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100% | 4780.0771 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 117.1 | 0 | 100% | 22688.3592 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 25.265 | SQM | 25.27 | -0.005 | 100% | 10880.2512 |  | 0
JMJ WATERPROOING ENTERPRISES | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 84.828 | SQM | 84.83 | -0.002 | 100% | 36524.4048 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 7.897 | SQM | 7.9 | -0.003 | 100% | 1700.712 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 14.023 | SQM | 14.02 | 0.003 | 99.98% | 3018.2256 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 19 | SQM | 19 | 0 | 100% | 3800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0.004 | 99.98% | 4299.1416 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | -0.004 | 100% | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0.004 | 100% | 5579.825 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0.004 | 100% | 11156.886 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100% | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0.003 | 100% | 25402.3403 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100% | 8648.325 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | -0.001 | 100% | 14565.0375 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100% | 5768.6429 |  | 0
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100% | 900 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 12 | 4 | 75% | 4200 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 40.76 | RMT | 40.76 | 0 | 100% | 3342.32 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 122.28 | RMT | 122.28 | 0 | 100% | 4010.784 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 29.59 | RMT | 29.59 | 0 | 100% | 3882.208 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 48.2 | SQM | 48.2 | 0 | 100% | 8820.6 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 49.944 | RMT | 49.94 | 0.004 | 99.99% | 2457.048 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 49.384 | SQM | 49.38 | 0.004 | 99.99% | 9036.54 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.11 | RMT | 50.11 | 0 | 100% | 2465.412 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 4.15 | SQM | 4.15 | 0 | 100% | 759.45 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 14.2 | RMT | 14.2 | 0 | 100% | 698.64 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 8.92 | 0 | 100% | 1632.36 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 19.18 | 0 | 100% | 943.656 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 7.49 | SQM | 7.49 | 0 | 100% | 1370.67 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | 0.004 | 99.96% | 525.456 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 13.6 | SQM | 13.6 | 0 | 100% | 2488.8 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100% | 2712.5 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.502 | SQM | 3.5 | 0.002 | 99.94% | 640.5 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 13.395 | SQM | 13.4 | -0.005 | 100% | 2452.2 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.148 | SQM | 7.15 | -0.002 | 100% | 1308.45 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 29.614 | SQM | 29.61 | 0.004 | 99.99% | 5418.63 |  | 0
PRAKASH JANA | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 189.15 | SQM | 0 | 189.15 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 29.15 | RMT | 29.15 | 0 | 100% | 161345.25 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100% | 5625 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 3 | NOS | 3 | 0 | 100% | 2250 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 100 | RFT | 100 | 0 | 100% | 3400 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 27 | 0 | 100% | 2079 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 249 | SFT | 249 | 0 | 100% | 5727 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 15 | 0 | 100% | 2265 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
PRAKASH JANA | LAYING FLOOR PROTECTOR SHEET & TILE CLEANING | 341 | 1.5 | 1055 | SFT | 1055 | 0 | 100% | 1582.5 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 3.625 | SQM | 3.63 | -0.005 | 100.1% | 781.4664 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 6.7845 | SQM | 6.78 | 0.0045 | 99.93% | 2919.1968 |  | 0
RUPAK NAYAK | CUSTOMIZATION FLOOR INTERNAL CEILING THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERNAL EMULSION PAINTING WORK | 482 | 91.49 | 21.3 | SQM | 21.3 | 0 | 100% | 1948.737 |  | 0
RUPAK NAYAK | CUSTOMIZATION FLOOR INTERNAL WALL THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERNAL EMULSION PAINTING WORK | 483 | 91.494 | 49.788 | SQM | 49.79 | -0.002 | 100% | 4555.4863 |  | 0
RUPAK NAYAK | CUSTOMIZATION FLOOR EXTERNAL WALL ONE COAT PRIMER, TWO COATS EXTERNAL EMULSION PAINTING WORK | 484 | 48.438 | 28.2375 | SQM | 28.24 | -0.0025 | 100% | 1367.8891 |  | 0
SARAT BARMAN | CUSTOMISATION FLOOR REINFORCEMENT WORK | 492 | 7500 | 0.554 | MT | 0.55 | 0.004 | 99.28% | 4125 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION BALCONY WATERPROOFING | 519 | 430.56 | 11.7 | SQM | 11.7 | 0 | 100% | 5037.552 |  | 0
RUPAK NAYAK | CUSTOMIZATION FLOOR EXTERNAL WALL STUCCO PAINTING | 520 | 96.88 | 10.105 | SQM | 10.11 | -0.005 | 100% | 979.4568 |  | 0
350

## V111
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment |  | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 |  | AAIDHUL MIAH | 350
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 |  | EBI ABRAHAM | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 |  | JMJ WATERPROOING ENTERPRISES | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18 | CUM | 18 | 0 | 100% | 2540.16 |  | 0 |  | KRIUTTIBAS DAS | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70.16 | CUM | 70.16 | 0 | 100% | 9900.9792 |  | 0 |  | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 |  | MANJUNATHA P | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 20 | CUM | 20 | 0 | 100% | 2822.4 |  | 0 |  | NAGARAJ | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 10.73 | CUM | 10.73 | 0 | 100% | 1514.2176 |  | 0 |  | PRAKASH H N | 2600
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100% | 1510.74 |  | 0 |  | RAMAKRUSHNA PRADHAN | 6743.6865
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 77 | SQM | 70 | 7 | 90.91% | 3010 |  | 0 |  | RUPAK NAYAK | 37937.3328
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100% | 1121.904 |  | 0 |  | SANTOSH KUMAR | 8642.5946
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 |  | SARAT BARMAN | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 |  | SAVITA DEVI | 1350
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 |  | SHOKAT | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 4 | 2.867 | 58.25% | 4000 |  | 0 |  | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 4 | 2.867 | 58.25% | 4000 | 41.75% | 2867 | Released for final touchup work | SK ANSAR HOSSIAN | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 |  | SREE VINAYAKA ELECTRICALS | 14832
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 |  | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 |  | SUBHASMITA DAS | 2867
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 |  | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 |  | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 |  | YELLAPPA C | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0.13 | 0 | 100% | 1300 |  | 0 |  | RABIUL MOLLA | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100% | 7980.8602 |  | 0 |  | KOUSHIK MANDAL | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 |  | SHEKAR T | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100% | 16492.1702 |  | 0 |  | TOTAL | 75322.6138
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100% | 38912.7211 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0.0005 | 99.99% | 2787.876 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100% | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0.15 | 0 | 100% | 1500 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 107.8 | SQM | 107.8 | 0 | 100% | 32490.0576 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | -0.005 | 100.1% | 2959.6694 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.83 | CUM | 0.83 | 0 | 100% | 2490 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0.03 | -0.001 | 103.4% | 210 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100% | 7275.6029 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100% | 569.6309 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
CHIRANJEEVI | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.17 | CUM | 0.17 | 0 | 100% | 510 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 93.08 | SQM | 85 | 8.08 | 91.32% | 16468.92 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 8.08 | SQM | 8.08 | 0 | 100% | 1565.5162 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100% | 25056.0086 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 30.1 | 0 | 100% | 1974.56 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 66.89 | 0 | 100% | 4387.984 |  | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0.5 | 0 | 100% | 80.73 |  | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8 | 348 | SQM | 348 | 0 | 100% | 2784 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100% | 24731.5817 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 147.87 | SQM | 125.69 | 22.18 | 85% | 24352.6889 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 22.1805 | SQM | 22.18 | 0.0005 | 100% | 4297.4194 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.15 | SQM | 228.15 | 0 | 100% | 31925.4858 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 110.32 | SQM | 110.32 | 0 | 100% | 21374.7206 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.86 | SQM | 8.86 | 0 | 100% | 1239.7975 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100% | 4780.0771 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 77.211 | SQM | 77.21 | 0.001 | 100% | 14959.5919 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 143.25 | SQM | 143.25 | 0 | 100% | 30838.86 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 52.92 | SQM | 52.92 | 0 | 100% | 11392.6176 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 25.69 | SQM | 25.69 | 0 | 100% | 2765.2716 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 68.07 | SQM | 68.07 | 0 | 100% | 14654.1096 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 25.69 | SQM | 25.69 | 0 | 100% | 2765.2716 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0.004 | 99.98% | 4299.1416 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | -0.004 | 100% | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0.004 | 100% | 5579.825 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 0 | 345.504 | 0% | 0 | 100% | 11157.0152
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100% | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0.003 | 100% | 25402.3403 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100% | 8648.325 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 0 | 541.249 | 0% | 0 | 100% | 14565.0106
SANTOSH KUMAR | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100% | 5768.6429 |  | 0
SANTOSH KUMAR | DOOR OPENING GRANITE | 218 | 350 | 7 | NOS | 7 | 0 | 100% | 2450 |  | 0
SANTOSH KUMAR | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 40.76 | RMT | 40.76 | 0 | 100% | 3342.32 |  | 0
SANTOSH KUMAR | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.78 | RMT | 98.78 | 0 | 100% | 3239.984 |  | 0
SANTOSH KUMAR | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 26.83 | 0 | 100% | 3520.096 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0% | 0 | 100% | 3000
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 183 | 51.944 | SQM | 51.94 | 0.004 | 99.99% | 9505.02 |  | 0
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 46.766 | RMT | 46.77 | -0.004 | 100% | 2301.084 |  | 0
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 183 | 45.599 | SQM | 45.6 | -0.001 | 100% | 8344.8 |  | 0
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 44.576 | RMT | 44.58 | -0.004 | 100% | 2193.336 |  | 0
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 3.202 | SQM | 3.2 | 0.002 | 99.94% | 585.6 |  | 0
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 8.2 | RMT | 8.2 | 0 | 100% | 403.44 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 183 | 7.722 | SQM | 7.72 | 0.002 | 99.97% | 1412.76 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.625 | RMT | 16.63 | -0.005 | 100% | 818.196 |  | 0
SANTOSH KUMAR | FLOOR CHIPPING | 235 | 2.5 | 1323.5414 | SFT | 1323.54 | 0.0014 | 100% | 3308.85 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.55 | 0.186 | 95.02% | 649.65 | 5% | 34.1844
SANTOSH KUMAR | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.247 | SQM | 16.38 | 0.867 | 94.97% | 2997.54 | 5% | 157.8101
SANTOSH KUMAR | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.491 | SQM | 3.37 | 4.121 | 44.99% | 616.71 | 55% | 753.9692
SANTOSH KUMAR | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 46.663 | SQM | 21 | 25.663 | 45% | 3843 | 55% | 4696.631
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 245 | 64.58 | 189.15 | SQM | 0 | 189.15 | 0 | 0 | 100% | 12215.307
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100% | 15500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 0 | 1 | 0% | 0 | 100% | 600
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
UDHABHAI R PARMAR | BALCONY & STAIRCASE SS RAILING | 260 | 5528.485 | 27.83 | RMT | 27.83 | 0 | 100% | 153857.7375 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 0 | 3 | 0% | 0 | 100% | 1350
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 14832
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 350
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 | 100% | 2601.986
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 | 100% | 1518
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 | 100% | 2623.7005
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 2364 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 1182 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 0.5 | 0.5 | 50% | 750 |  | 0
75322.6138

## V112
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment |  | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 |  | AAIDHUL MIAH | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 |  | EBI ABRAHAM | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 |  | JMJ WATERPROOING ENTERPRISES | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 |  | KRIUTTIBAS DAS | 8300
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100% | 9878.4 |  | 0 |  | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 |  | MANJUNATHA P | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 |  | NAGARAJ | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 |  | PRAKASH H N | 2600
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 | 100% | 2952.81 | Released for final touchup work | RAMAKRUSHNA PRADHAN | 6743.6865
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100% | 1121.904 |  | 0 |  | RUPAK NAYAK | 12215.307
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 |  | SANTOSH KUMAR | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 |  | SARAT BARMAN | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 |  | SAVITA DEVI | 1350
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 |  | SHOKAT | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 |  | SHREE DM STEEL FURNITURE AND INTERIOR | 81906.93
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 |  | SK ANSAR HOSSIAN | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 |  | SREE VINAYAKA ELECTRICALS | 14832
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 |  | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 |  | SUBHASMITA DAS | 9396.084
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 |  | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0 |  | V VENKATANARAYANA | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 |  | YELLAPPA C | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 |  | RABIUL MOLLA | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 |  | KOUSHIK MANDAL | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0 |  | SHEKAR T | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0 |  | TOTAL | 137344.0075
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 9.25 | 0.0005 | 99.99% | 2987.01 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.67 | CUM | 0.67 | 0 | 100% | 2010 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100% | 34810.776 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 9.82 | -0.005 | 100.1% | 3171.0744 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.83 | CUM | 0.83 | 0 | 100% | 2490 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0.03 | -0.001 | 103.4% | 225 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100% | 3487.536 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 24.14 | 0 | 100% | 7795.2888 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 1.89 | 0 | 100% | 610.3188 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
CHIRANJEEVI | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.17 | CUM | 0.17 | 0 | 100% | 510 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 93.08 | SQM | 80 | 13.08 | 85.95% | 15500.16 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 13.08 | SQM | 13.08 | 0 | 100% | 2534.2762 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100% | 25056.0086 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
SUBHASMITA DAS | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 | 100% | 1974.56 | Released for final touchup work
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
SUBHASMITA DAS | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 | 100% | 4387.984 | Released for final touchup work
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
SUBHASMITA DAS | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 | 100% | 80.73 | Released for final touchup work
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8 | 348 | SQM | 348 | 0 | 100% | 2784 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100% | 24731.5817 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 147.87 | SQM | 120 | 27.87 | 81.15% | 23250.24 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 27.87 | SQM | 27.87 | 0 | 100% | 5399.8682 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.15 | SQM | 228.15 | 0 | 100% | 31925.4858 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 110.32 | SQM | 110.32 | 0 | 100% | 21374.7206 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.86 | SQM | 8.86 | 0 | 100% | 1239.7975 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100% | 4780.0771 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 77.211 | SQM | 77.21 | 0.001 | 100% | 14959.5919 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 134.327 | SQM | 134.33 | -0.003 | 100% | 28918.5624 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 37.85 | SQM | 37.85 | 0 | 100% | 8148.348 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 47.154 | SQM | 47.15 | 0.004 | 99.99% | 5075.226 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 70.824 | SQM | 70.82 | 0.004 | 99.99% | 15246.1296 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 47.154 | SQM | 47.15 | 0.004 | 99.99% | 5075.226 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 13 | NOS | 13 | 0 | 100% | 2600 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0.004 | 99.98% | 4299.1416 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | -0.004 | 100% | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0.004 | 100% | 5579.825 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0.004 | 100% | 11156.886 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100% | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0.003 | 100% | 25402.3403 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100% | 8648.325 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | -0.001 | 100% | 14565.0375 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 0 | 19.14 | 0% | 0 |  | 0
SANTOSH KUMAR | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100% | 5768.6429 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
SANTOSH KUMAR | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 0 | 15 | 0% | 0 |  | 0
SANTOSH KUMAR | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 7 | 8 | 46.67% | 2450 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 40.76 | RMT | 0 | 40.76 | 0% | 0 |  | 0
SANTOSH KUMAR | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 40.76 | RMT | 40.76 | 0 | 100% | 3342.32 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.78 | RMT | 0 | 98.78 | 0% | 0 |  | 0
SANTOSH KUMAR | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.78 | RMT | 98.78 | 0 | 100% | 3239.984 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 0 | 26.83 | 0% | 0 |  | 0
SANTOSH KUMAR | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 26.83 | 0 | 100% | 3520.096 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 51.942 | SQM | 0 | 51.942 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 183 | 51.942 | SQM | 51.94 | 0.002 | 100% | 9505.02 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.098 | RMT | 0 | 47.098 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.098 | RMT | 47.1 | -0.002 | 100% | 2317.32 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 49.616 | SQM | 0 | 49.616 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 183 | 49.616 | SQM | 49.62 | -0.004 | 100% | 9080.46 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 49.264 | RMT | 0 | 49.264 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 49.264 | RMT | 49.26 | 0.004 | 99.99% | 2423.592 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 2.675 | SQM | 0 | 2.675 | 0% | 0 |  | 0
SANTOSH KUMAR | TERRACE FLOOR TILING | 228 | 183 | 2.675 | SQM | 2.68 | -0.005 | 100.2% | 490.44 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 3.775 | RMT | 0 | 3.775 | 0% | 0 |  | 0
SANTOSH KUMAR | TERRACE FLOOR SKIRTING | 229 | 49.2 | 3.775 | RMT | 3.78 | -0.005 | 100.1% | 185.976 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 3.465 | SQM | 0 | 3.465 | 0% | 0 |  | 0
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 3.465 | SQM | 3.47 | -0.005 | 100.1% | 635.01 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.95 | RMT | 0 | 7.95 | 0% | 0 |  | 0
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 7.95 | RMT | 7.95 | 0 | 100% | 391.14 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 7.864 | SQM | 0 | 7.864 | 0% | 0 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 183 | 7.864 | SQM | 7.86 | 0.004 | 99.95% | 1438.38 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 7.05 | RMT | 0 | 7.05 | 0% | 0 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 7.05 | RMT | 7.05 | 0 | 100% | 346.86 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 172.224 | 13.454 | SQM | 0 | 13.454 | 0% | 0 |  | 0
SANTOSH KUMAR | CAR PARKING AREA TILING | 234 | 172.224 | 13.454 | SQM | 13.45 | 0.004 | 99.97% | 2316.4128 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1327.9869 | SFT | 0 | 1327.9869 | 0% | 0 |  | 0
SANTOSH KUMAR | FLOOR CHIPPING | 235 | 2.5 | 1327.9869 | SFT | 1327.99 | -0.0031 | 100% | 3319.975 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.502 | SQM | 0 | 3.502 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.502 | SQM | 3.5 | 0.002 | 99.94% | 640.5 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 13.395 | SQM | 0 | 13.395 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 13.395 | SQM | 13.4 | -0.005 | 100% | 2452.2 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.148 | SQM | 0 | 7.148 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.148 | SQM | 7.15 | -0.002 | 100% | 1308.45 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 29.614 | SQM | 0 | 29.614 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 29.614 | SQM | 29.61 | 0.004 | 99.99% | 5418.63 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 245 | 64.58 | 189.15 | SQM | 0 | 189.15 | 0 | 0 | 100% | 12215.307
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100% | 15500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 0 | 1 | 0% | 0 | 100% | 600
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 500
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 6000
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1800
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 29.988 | RMT | 15.19 | 14.798 | 50.65% | 84076.65 | 49.35% | 81906.93
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 0 | 3 | 0% | 0 | 100% | 1350
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 14832
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 | 100% | 2601.986
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 | 100% | 1518
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 | 100% | 2623.7005
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 1738.35 | 1 | LUMP SUM | 1 | 0 | 100% | 1738.35 |  | 0
SANTOSH KUMAR | BALCONY UPSTAND TOP COPING GRANITE | 547 | 78 | 49.07 | RFT | 49.07 | 0 | 100% | 3827.46 |  | 0
137344.0075

## V113
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | EBI ABRAHAM | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | KRIUTTIBAS DAS | 6000
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100% | 9878.4 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | PRAKASH H N | 2600
MANJUNATHA P | BASE FLOOR EARTH DRESSING | 14 | 22 | 40 | SQM | 40 | 0 | 100% | 880 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100% | 2952.81 |  | 0 | RUPAK NAYAK | 37937.3328
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100% | 1121.904 |  | 0 | SANTOSH KUMAR | 16702.6446
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SAVITA DEVI | 1350
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SHOKAT | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SREE VINAYAKA ELECTRICALS | 14832
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | UDHABHAI R PARMAR | 56888.1107
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0.13 | 0 | 100% | 1300 |  | 0 | YELLAPPA C | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100% | 7980.8602 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100% | 16492.1702 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0 | TOTAL | 136310.088
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100% | 38912.7211 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0.0005 | 99.99% | 2787.876 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
KHALIL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100% | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0.15 | 0 | 100% | 1500 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 107.8 | SQM | 107.8 | 0 | 100% | 32490.0576 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | -0.005 | 100.1% | 2959.6694 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
KHALIL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.83 | CUM | 0.83 | 0 | 100% | 2490 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0.03 | -0.001 | 103.4% | 225 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100% | 7275.6029 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100% | 569.6309 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
KHALIL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.17 | CUM | 0.17 | 0 | 100% | 510 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
KHALIL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 94.59 | 0 | 100% | 18327.0017 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 13.557 | SQM | 13.56 | -0.003 | 100% | 2627.2771 |  | 0
KHALIL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 110 | 19.32 | 85.06% | 21312.72 |  | 0
KHALIL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
KHALIL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
KHALIL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
KHALIL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100% | 2119.72 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100% | 24731.5817 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 17.87 | SQM | 17.87 | 0 | 100% | 3462.3482 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 160 | SQM | 160 | 0 | 100% | 31000.32 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13500 | 1 | LUMP SUM | 1 | 0 | 100% | 13500 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 258.15 | 0 | 100% | 36123.4458 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100% | 24474.7526 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100% | 1365.7363 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100% | 4780.0771 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 117.1 | 0 | 100% | 22688.3592 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 139.04 | SQM | 139.04 | 0 | 100% | 29932.5312 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 52.93 | SQM | 52.93 | 0 | 100% | 11394.7704 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 29.04 | SQM | 29.04 | 0 | 100% | 3125.8656 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 71.05 | SQM | 71.05 | 0 | 100% | 15295.644 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 29.04 | SQM | 29.04 | 0 | 100% | 3125.8656 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0.004 | 99.98% | 4299.1416 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | -0.004 | 100% | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0.004 | 100% | 5579.825 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 0 | 345.504 | 0% | 0 | 100% | 11157.0152
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100% | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0.003 | 100% | 25402.3403 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100% | 8648.325 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 0 | 541.249 | 0% | 0 | 100% | 14565.0106
SANTOSH KUMAR | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 17.23 | 1.91 | 90.02% | 5192.9842 | 10% | 576.8643
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 21.28 | SQM | 0 | 21.28 | 0% | 0 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 0 | 19.14 | 0% | 0 |  | 0
SANTOSH KUMAR | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
SANTOSH KUMAR | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 0 | 15 | 0% | 0 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 0 | 14 | 0% | 0 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 0 | 15 | 0% | 0 |  | 0
SANTOSH KUMAR | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 40.76 | RMT | 36.68 | 4.08 | 89.99% | 3007.76 | 10% | 334.232
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.082 | RMT | 0 | 37.082 | 0% | 0 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 40.76 | RMT | 0 | 40.76 | 0% | 0 |  | 0
SANTOSH KUMAR | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.78 | RMT | 88.9 | 9.88 | 90% | 2915.92 | 10% | 323.9984
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 0 | 111.25 | 0% | 0 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.78 | RMT | 0 | 98.78 | 0% | 0 |  | 0
SANTOSH KUMAR | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 24.15 | 2.68 | 90.01% | 3168.48 | 10% | 352.0096
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 0 | 27.298 | 0% | 0 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 0 | 26.83 | 0% | 0 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0% | 0 | 100% | 3000
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 183 | 51.944 | SQM | 49.35 | 2.594 | 95.01% | 9031.05 | 5% | 475.2876
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.944 | SQM | 0 | 51.944 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 46.776 | RMT | 42.1 | 4.676 | 90% | 2071.32 | 10% | 230.1379
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 46.776 | RMT | 0 | 46.776 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 183 | 45.599 | SQM | 43.32 | 2.279 | 95% | 7927.56 | 5% | 417.2309
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 45.599 | SQM | 0 | 45.599 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 44.576 | RMT | 40.12 | 4.456 | 90% | 1973.904 | 10% | 219.3139
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 44.576 | RMT | 0 | 44.576 | 0% | 0 |  | 0
SANTOSH KUMAR | TERRACE FLOOR TILING | 228 | 183 | 2.675 | SQM | 2.54 | 0.135 | 94.95% | 464.82 | 5% | 24.4763
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.675 | SQM | 0 | 2.675 | 0% | 0 |  | 0
SANTOSH KUMAR | TERRACE FLOOR SKIRTING | 229 | 49.2 | 3.775 | RMT | 3.4 | 0.375 | 90.07% | 167.28 | 10% | 18.573
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 3.775 | RMT | 0 | 3.775 | 0% | 0 |  | 0
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 3.202 | SQM | 0 | 3.202 | 0% | 0 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 3.202 | SQM | 0 | 3.202 | 0% | 0 |  | 0
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 8.2 | RMT | 0 | 8.2 | 0% | 0 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 8.2 | RMT | 0 | 8.2 | 0% | 0 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 183 | 7.722 | SQM | 7.34 | 0.382 | 95.05% | 1343.22 | 5% | 70.6563
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 7.722 | SQM | 0 | 7.722 | 0% | 0 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.625 | RMT | 14.96 | 1.665 | 89.98% | 736.032 | 10% | 81.795
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.625 | RMT | 0 | 16.625 | 0% | 0 |  | 0
SANTOSH KUMAR | CAR PARKING AREA TILING | 234 | 183 | 13.464 | SQM | 0 | 13.464 | 0% | 0 | 100% | 2463.912
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 13.464 | SQM | 0 | 13.464 | 0% | 0 |  | 0
SANTOSH KUMAR | FLOOR CHIPPING | 235 | 2.5 | 1323.541 | SFT | 1257.36 | 66.181 | 95% | 3143.4 | 5% | 165.4426
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1323.541 | SFT | 0 | 1323.541 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 0 | 3.736 | 0% | 0 | 100% | 683.688
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 0 | 3.736 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.3593 | SQM | 0 | 17.3593 | 0% | 0 | 100% | 3176.7519
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.3593 | SQM | 0 | 17.3593 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 3.913 | SQM | 0 | 3.913 | 0% | 0 | 100% | 716.079
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 3.913 | SQM | 0 | 3.913 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 18.4273 | SQM | 0 | 18.4273 | 0% | 0 | 100% | 3372.1959
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 18.4273 | SQM | 0 | 18.4273 | 0% | 0 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 245 | 64.58 | 189.15 | SQM | 0 | 189.15 | 0% | 0 | 100% | 12215.307
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100% | 15500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 0 | 1 | 0% | 0 | 100% | 600
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 6000
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
UDHABHAI R PARMAR | BALCONY & STAIRCASE SS RAILING | 260 | 5528.485 | 24.94 | RMT | 14.65 | 10.29 | 58.74% | 80992.3052 | 41.26% | 56888.1107
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 0 | 3 | 0% | 0 | 100% | 1350
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 14832
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 1829.85 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 914.925 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 0.5 | 0.5 | 50% | 500 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY TAP POINT WORK | 448 | 600 | 1 | NOS | 0.5 | 0.5 | 50% | 300 |  | 0
136310.088

## V114
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 2000
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100% | 9878.4 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | PRAKASH H N | 600
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100% | 2952.81 |  | 0 | SANTOSH KUMAR | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100% | 1121.904 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SAVITA DEVI | 1800
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SHOKAT | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0 | YELLAPPA C | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0 | TOTAL | 4400
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 9.25 | 0.0005 | 99.99% | 2987.01 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100% | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100% | 34810.776 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 9.82 | -0.005 | 100.1% | 3171.0744 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.83 | CUM | 0.83 | 0 | 100% | 2490 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0.03 | -0.001 | 103.4% | 225 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100% | 3487.536 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 24.14 | 0 | 100% | 7795.2888 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 1.89 | 0 | 100% | 610.3188 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.17 | CUM | 0.17 | 0 | 100% | 510 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 75.67 | 18.92 | 80% | 14661.2138 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100% | 25056.0086 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100% | 2119.72 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100% | 24731.5817 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 111.83 | 19.735 | 85% | 21667.2862 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 228.24 | 0 | 100% | 31938.0797 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.177 | SQM | 109.18 | -0.003 | 100% | 21153.8434 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100% | 1365.7363 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100% | 4780.0771 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 99.15 | 0 | 100% | 19210.5108 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 139.61 | SQM | 139.61 | 0 | 100% | 30055.2408 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 52.37 | SQM | 52.37 | 0 | 100% | 11274.2136 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 29.94 | SQM | 29.94 | 0 | 100% | 3222.7416 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 70.86 | SQM | 70.86 | 0 | 100% | 15254.7408 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 29.94 | SQM | 29.94 | 0 | 100% | 3222.7416 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 19 | NOS | 19 | 0 | 100% | 3800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0.004 | 99.98% | 4299.1416 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | -0.004 | 100% | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0.004 | 100% | 5579.825 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0.004 | 100% | 11156.886 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100% | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0.003 | 100% | 25402.3403 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100% | 8648.325 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | -0.001 | 100% | 14565.0375 |  | 0
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 17.23 | 1.91 | 90.02% | 5192.9842 |  | 0
ANSAR HOSSAIAN SK | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100% | 900 |  | 0
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 13 | 0 | 100% | 4550 |  | 0
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 40.76 | RMT | 36.68 | 4.08 | 89.99% | 3007.76 |  | 0
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.78 | RMT | 88.9 | 9.88 | 90% | 2915.92 |  | 0
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 24.15 | 2.68 | 90.01% | 3168.48 |  | 0
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 51.942 | SQM | 51.94 | 0.002 | 100% | 9505.02 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.098 | RMT | 42.39 | 4.708 | 90% | 2085.588 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 49.616 | SQM | 49.62 | -0.004 | 100% | 9080.46 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 49.264 | RMT | 44.34 | 4.924 | 90% | 2181.528 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 2.675 | SQM | 2.68 | -0.005 | 100.2% | 490.44 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 3.775 | RMT | 3.4 | 0.375 | 90.07% | 167.28 |  | 0
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 3.465 | SQM | 3.47 | -0.005 | 100.1% | 635.01 |  | 0
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 7.95 | RMT | 7.16 | 0.79 | 90.06% | 352.272 |  | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 7.864 | SQM | 7.86 | 0.004 | 99.95% | 1438.38 |  | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 7.05 | RMT | 6.35 | 0.7 | 90.07% | 312.42 |  | 0
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 172.224 | 13.454 | SQM | 13.45 | 0.004 | 99.97% | 2316.4128 |  | 0
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 1327.9869 | SFT | 1327.99 | -0.0031 | 100% | 3319.975 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.502 | SQM | 3.5 | 0.002 | 99.94% | 640.5 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 13.395 | SQM | 13.4 | -0.005 | 100% | 2452.2 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.148 | SQM | 7.15 | -0.002 | 100% | 1308.45 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 29.614 | SQM | 29.61 | 0.004 | 99.99% | 5418.63 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.121 | SQM | 126.12 | 0.001 | 100% | 8144.8296 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100% | 15500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 0 | 1 | 0% | 0 | 100% | 600
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
UDHABHAI R PARMAR | BALCONY & STAIRCASE SS RAILING | 260 | 5528.485 | 28.07 | RMT | 28.07 | 0 | 100% | 155184.5739 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 0 | 4 | 0% | 0 | 100% | 1800
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 1117.2 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 558.6 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 0.5 | 0.5 | 50% | 500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 89.526 | SQM | 89.53 | -0.004 | 100% | 4336.6541 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 89.526 | SQM | 89.53 | -0.004 | 100% | 1445.9095 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 89.526 | SQM | 89.53 | -0.004 | 100% | 2409.2523 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 14.102 | SQM | 14.1 | 0.002 | 99.99% | 227.715 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 14.102 | SQM | 14.1 | 0.002 | 99.99% | 455.3172 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 0.5 | 0.5 | 50% | 750 |  | 0
RUPAK NAYAK | CUSTOMISATION TERRACE EPOXY GROUTING AND SOAP WASH CLEANING WORK | 427 | 64.58 | 21.302 | SQM | 21.3 | 0.002 | 99.99% | 1375.554 |  | 0
ANSAR HOSSAIAN SK | CUSTOMIZATION TOILET TILE WORK | 436 | 1280.92 | 3.054 | SQM | 3.05 | 0.004034 | 99.87% | 3906.806 |  | 0
ANSAR HOSSAIAN SK | CUSTOMIZATION MAIN FLOORING WORK | 442 | 248.38 | 13.0306 | SQM | 13.03 | 0.00064 | 100% | 3236.3914 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.349 | CUM | 4.35 | -0.001 | 100% | 978.75 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100% | 250 |  | 0
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 41.887 | SQM | 41.89 | -0.003 | 100% | 13527.1188 |  | 0
NAGARAJ | CUSTOMIZATION ROOM LINTEL CHAJJA SHUTTERING | 497 | 322.92 | 3.62 | SQM | 3.62 | 0 | 100% | 1168.9704 |  | 0
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 16.5 | SQM | 16.5 | 0 | 100% | 5328.18 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR INTERNAL WALL PLASTERING | 500 | 139.932 | 64.585 | SQM | 64.59 | -0.005 | 100% | 9038.2079 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR EXTERNAL WALL PLASTERING | 501 | 193.752 | 64.438 | SQM | 64.44 | -0.002 | 100% | 12485.3789 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR BLOCK WORK | 502 | 193.752 | 38.314 | SQM | 38.31 | 0.004 | 99.99% | 7422.6391 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.35613 | MT | 0.36 | -0.003869 | 101.1% | 2700 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.26878 | MT | 0.27 | -0.001218 | 100.5% | 2025 |  | 0
NAGARAJ | CUSTOMIZATION UTILITY ADDITIONAL PLINTH BEAM SHUTTERING | 521 | 322.92 | 5.808 | SQM | 5.81 | -0.002 | 100% | 1876.1652 |  | 0
AAIDHUL MIAH | CUSTOMISATION UTILITY EXTENSION PLASTERING | 522 | 139.93 | 29.477 | SQM | 29.48 | -0.003 | 100% | 4125.1364 |  | 0
AAIDHUL MIAH | CUSTOMISATION UTLITY EXTENSION BLOCK WORK | 523 | 193.75 | 14.292 | SQM | 14.29 | 0.002 | 99.99% | 2768.6875 |  | 0
4400

## V115
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | EBI ABRAHAM | 4000
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
YELLAPPA C | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | NAGARAJ | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | PRAKASH H N | 2000
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | RUPAK NAYAK | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0 | 0.49 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
YELLAPPA C | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0 | 0.49 | 0% | 0 | 100% | 3430 | SARAT BARMAN | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 0 | 1.2 | 0% | 0 |  | 0 | SAVITA DEVI | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.2 | MT | 0 | 1.2 | 0% | 0 | 100% | 8400 | SHOKAT | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0 | 0.18 | 0% | 0 | 100% | 1260 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 | SUBHASMITA DAS | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 | UDHABHAI R PARMAR | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | V VENKATANARAYANA | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0 | YELLAPPA C | 68810.051
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 0 | 129.11 | 0% | 0 | 100% | 38912.7211 | RABIUL MOLLA | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 0 | 12.27 | 0% | 0 | 100% | 3698.0798 | KOUSHIK MANDAL | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 0 | 15.17 | 0% | 0 |  | 0 | SHEKAR T | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0 | TOTAL | 74810.051
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 0 | 3.26 | 0% | 0 | 100% | 6520
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 0 | 15.33 | 0% | 0 | 100% | 3449.25
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 0 | 1.57 | 0% | 0 | 100% | 3140
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0 | 0.96 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0 | 0.47 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.47 | MT | 0 | 0.47 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0 | 0.88 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 0.88 | MT | 0 | 0.88 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 0 | 39.24 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 0 | 129.97 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 0 | 12.27 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 0 | 16.19 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 0 | 2.21 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0 | 0.87 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.19 | MT | 0 | 0.19 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 0 | 10.8 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 0 | 24.14 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 0 | 3.5 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0 | 0.38 | 0% | 0 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 11 | NOS | 11 | 0 | 100% | 550 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 0 | 108.147 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 0 | 133.756 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.973 | 0% | 0 |  | 0
YELLAPPA C | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
YELLAPPA C | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
YELLAPPA C | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
YELLAPPA C | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 0 | 268.5 | 0% | 0 |  | 0
YELLAPPA C | RCC SURFACE HACKING | 140 | 8 | 348 | SQM | 0 | 348 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 0 | 59.84 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 0 | 176.74 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 0 | 177.87 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 0 | 258.15 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 0 | 126.32 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0% | 0 |  | 0
YELLAPPA C | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 0 | 117.1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 4000
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
74810.051

## V116
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V117
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 58.24 | SQM | 58.24 | 0 | 100% | 3144.96 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | EBI ABRAHAM | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 58.24 | SQM | 58.24 | 0 | 100% | 1281.28 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | KRIUTTIBAS DAS | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 117.16 | CUM | 117.16 | 0 | 100% | 16533.6192 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 18.12 | CUM | 18.12 | 0 | 100% | 2557.0944 |  | 0 | NAGARAJ | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 44.68 | CUM | 44.68 | 0 | 100% | 6305.2416 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100% | 2952.81 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.13 | CUM | 3.13 | 0 | 100% | 3130 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 7.7 | CUM | 7.7 | 0 | 100% | 7700 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.65 | MT | 0.65 | 0 | 100% | 4875 |  | 0 | SHOKAT | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.75 | MT | 0.75 | 0 | 100% | 5625 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.9 | MT | 0.9 | 0 | 100% | 6750 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 2.8 | MT | 2.8 | 0 | 100% | 21000 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | UDHABHAI R PARMAR | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100% | 7980.8602 |  | 0 | V VENKATANARAYANA | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100% | 7124.9069 |  | 0 | YELLAPPA C | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100% | 16492.1702 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100% | 12441.4618 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100% | 37972.3781 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100% | 3695.0659 |  | 0 | TOTAL | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0.0005 | 99.99% | 2787.876 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 14 | CUM | 14 | 0 | 100% | 3150 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.42 | CUM | 4.42 | 0 | 100% | 3978 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.31 | CUM | 2.31 | 0 | 100% | 4620 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.24 | CUM | 13.24 | 0 | 100% | 2979 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.32 | CUM | 1.32 | 0 | 100% | 2640 |  | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100% | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 1 | MT | 1 | 0 | 100% | 7500 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 2.4 | MT | 2.4 | 0 | 100% | 18000 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.2 | MT | 0.2 | 0 | 100% | 1500 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100% | 12531.8794 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100% | 37737.2923 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100% | 3695.0659 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | -0.005 | 100.1% | 2959.6694 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.31 | CUM | 2.31 | 0 | 100% | 4620 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.7 | CUM | 12.7 | 0 | 100% | 2857.5 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0.84 | 0.003 | 99.64% | 2520 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.04 | MT | 0.04 | 0 | 100% | 300 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100% | 6895.849 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100% | 569.6309 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | 0.002 | 99.93% | 636.75 |  | 0
CHIRANJEEVI | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0.07 | 0 | 100% | 210 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 93.08 | SQM | 93.08 | 0 | 100% | 18034.4362 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100% | 25056.0086 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | 64.23 | 0% | 0 |  | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8 | 348 | SQM | 348 | 0 | 100% | 2784 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 47.87 | 11.97 | 80% | 6698.5448 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 141.39 | 35.35 | 80% | 19784.9855 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 147.87 | SQM | 147.87 | 0 | 100% | 28650.1082 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 65.32 | 16.33 | 80% | 9140.3582 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.15 | SQM | 182.52 | 45.63 | 80% | 25540.3886 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 110.32 | SQM | 110.32 | 0 | 100% | 21374.7206 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.86 | SQM | 8.86 | 0 | 100% | 1239.7975 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 27.33 | 6.83 | 80.01% | 3824.3416 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 77.211 | SQM | 77.21 | 0.001 | 100% | 14959.5919 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 100.27 | SQM | 100.27 | 0 | 100% | 21586.1256 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 32.34 | SQM | 32.34 | 0 | 100% | 6962.1552 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 21.95 | SQM | 21.95 | 0 | 100% | 2362.698 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 54.93 | SQM | 54.93 | 0 | 100% | 11825.3304 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 21.95 | SQM | 21.95 | 0 | 100% | 2362.698 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 14 | 0 | 100% | 2800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 25.39 | SQM | 25.39 | 0 | 100% | 5465.9592 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.88 | 11.885 | SQM | 11.89 | -0.005 | 100% | 1151.9032 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 128.594 | SQM | 128.59 | 0.004 | 100% | 6228.6424 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 119.085 | SQM | 119.09 | -0.005 | 100% | 5768.4814 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 74.288 | SQM | 74.29 | -0.002 | 100% | 3598.459 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 50.103 | SQM | 50.1 | 0.003 | 99.99% | 809.115 |  | 0
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 126.643 | SQM | 126.64 | 0.003 | 100% | 11586.8002 |  | 0
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 38.771 | SQM | 38.77 | 0.001 | 100% | 3547.2224 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 148.907 | SQM | 148.91 | -0.003 | 100% | 13624.3715 |  | 0
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 38.771 | SQM | 38.77 | 0.001 | 100% | 3547.2224 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 69.779 | SQM | 69.78 | -0.001 | 100% | 6384.4513 |  | 0
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 19.999 | SQM | 20 | -0.001 | 100% | 1829.88 |  | 0
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 20.496 | SQM | 20.5 | -0.004 | 100% | 6178.536 |  | 0
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100% | 5600 |  | 0
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 42.41 | RMT | 42.41 | 0 | 100% | 3477.62 |  | 0
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 120.57 | RMT | 120.57 | 0 | 100% | 3954.696 |  | 0
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 22.951 | RMT | 22.95 | 0.001 | 100% | 3011.04 |  | 0
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100% | 4000 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 40.963 | SQM | 40.96 | 0.003 | 99.99% | 7495.68 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 37.745 | RMT | 37.75 | -0.005 | 100% | 1857.3 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 42.27 | SQM | 42.27 | 0 | 100% | 7735.41 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 52.007 | RMT | 52.01 | -0.003 | 100% | 2558.892 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 2.081 | SQM | 2.08 | 0.001 | 99.95% | 380.64 |  | 0
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 2.36 | RMT | 2.36 | 0 | 100% | 116.112 |  | 0
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 9.802 | SQM | 9.8 | 0.002 | 99.98% | 1793.4 |  | 0
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 918.322 | SFT | 918.32 | 0.002 | 100% | 2295.8 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.137 | SQM | 3.14 | -0.003 | 100.1% | 574.62 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 15.993 | SQM | 15.99 | 0.003 | 99.98% | 2926.17 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 6.298 | SQM | 6.3 | -0.002 | 100% | 1152.9 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 31.986 | SQM | 31.99 | -0.004 | 100% | 5854.17 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 109.655 | SQM | 109.66 | -0.005 | 100% | 7081.8428 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 1 | 0 | 100% | 18500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 20.8473 | RMT | 20.85 | -0.0027 | 100% | 115404.75 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
MD GIYAS | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100% | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
ANSAR HOSSAIAN SK | CUSTOMIZATION TOILET TILE WORK | 436 | 1185.21 | 3.141 | SQM | 3.14 | 0.001 | 99.97% | 3721.5594 |  | 0
ANSAR HOSSAIAN SK | CUSTOMIZATION MAIN FLOORING WORK | 442 | 251.26 | 11.765 | SQM | 11.77 | -0.005 | 100% | 2957.3302 |  | 0
CHIRANJEEVI | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 25.502 | SQM | 25.5 | 0.002 | 99.99% | 4940.625 |  | 0
CHIRANJEEVI | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 74.226 | SQM | 74.23 | -0.004 | 100% | 10387.1524 |  | 0
CHIRANJEEVI | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 19.945 | SQM | 19.95 | -0.005 | 100% | 3865.3524 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.573 | CUM | 4.57 | 0.003 | 99.93% | 1028.25 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100% | 250 |  | 0
NAGARAJ | CUSTOMIZATION FLOOR SLAB AND BEAM SHUTTERING | 508 | 301.392 | 33.26 | SQM | 33.26 | 0 | 100% | 10024.2979 |  | 0
NAGARAJ | CUSTOMIZATION FLOOR COLUMN SHUTTERING | 509 | 301.392 | 30.1 | SQM | 30.1 | 0 | 100% | 9071.8992 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.262 | MT | 0.26 | 0.002 | 99.24% | 1950 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.178 | MT | 0.18 | -0.002 | 101.1% | 1350 |  | 0
0

## V118
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 0 | 59.29 | 0 | 0 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18 | CUM | 18 | 0 | 100 | 2540.16 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 0 | 151.12 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 4.74 | 1.19 | 80 | 4740 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100 | 2775 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 0 | 1.25 | 0 | 0 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.09 | 0.05 | 64.286 | 675 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.14 | MT | 0 | 0.14 | 0 | 0 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 33.923 | SQM | 33.92 | 0 | 100 | 10953.4464 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 23.64 | SQM | 23.64 | 0 | 100 | 7633.8288 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 59.9517 | SQM | 59.95 | 0 | 100 | 19359.054 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 41.28 | SQM | 0 | 41.28 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 125.99 | SQM | 0 | 125.99 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.26 | SQM | 0 | 12.26 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 16.11 | SQM | 0 | 16.11 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 0 | 2.85 | 0 | 0 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 0 | 13.08 | 0 | 0 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 0 | 1.7 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0 | 0.5 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 0 | 1.1 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0 | 0.14 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 41.58 | SQM | 0 | 41.58 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 125.21 | SQM | 0 | 125.21 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.26 | SQM | 0 | 12.26 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 17.63 | SQM | 0 | 17.63 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 0 | 2.32 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 0 | 13.56 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 0 | 1.41 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0 | 0.17 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 5000 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 22.88 | SQM | 0 | 22.88 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.92 | SQM | 0 | 1.92 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0 | 0.41 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 0 | 1.98 | 0 | 0 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 0 | 43 | 0 | 0 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V119
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 0 | 59.29 | 0 | 0 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18 | CUM | 18 | 0 | 100 | 2540.16 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 0 | 151.12 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100 | 2775 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 0 | 1.25 | 0 | 0 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.09 | 0.05 | 64.286 | 675 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.14 | MT | 0 | 0.14 | 0 | 0 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 33.923 | SQM | 33.92 | 0 | 100 | 10953.4464 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 23.64 | SQM | 23.64 | 0 | 100 | 7633.8288 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 59.9517 | SQM | 59.95 | 0 | 100 | 19359.054 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 41.28 | SQM | 0 | 41.28 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 125.99 | SQM | 0 | 125.99 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.26 | SQM | 0 | 12.26 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 16.11 | SQM | 0 | 16.11 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 0 | 2.85 | 0 | 0 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 0 | 13.08 | 0 | 0 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 0 | 1.7 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0 | 0.5 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 0 | 1.1 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0 | 0.14 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 41.58 | SQM | 0 | 41.58 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 125.21 | SQM | 0 | 125.21 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.26 | SQM | 0 | 12.26 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 17.63 | SQM | 0 | 17.63 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 0 | 2.32 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 0 | 13.56 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 0 | 1.41 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0 | 0.17 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 5000 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 22.88 | SQM | 0 | 22.88 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.92 | SQM | 0 | 1.92 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0 | 0.41 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 0 | 1.98 | 0 | 0 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 0 | 43 | 0 | 0 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V120
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100 | 2775 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100 | 9375 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 37 | 1500 | 2 | NOS | 2 | 0 | 100 | 3000 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0 | 100 | 18068.4504 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100 | 4855.4251 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100 | 915 | 0 | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 65 | 3000 | 0.61 | CUM | 0 | 0.61 | 0 | 0 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100 | 5313.541 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0 | 100 | 1260 | 0 | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 95 | 3000 | 0.843 | CUM | 0 | 0.84 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100 | 150 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100 | 578.6726 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100 | 105 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR LINTEL BEAM & CHEJJA RCC | 115 | 3000 | 0.07 | CUM | 0 | 0.07 | 0 | 0 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 106.054 | SQM | 90 | 16.05 | 84.862 | 17437.68 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 113.2014 | SQM | 113.2 | 0 | 100 | 21932.7264 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 69.96 | SQM | 0 | 69.96 | 0 | 0 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 27.15 | RMT | 0 | 27.15 | 0 | 0 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 43.88 | RMT | 0 | 43.88 | 0 | 0 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 348.385 | SQM | 0 | 348.39 | 0 | 0 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 65.55 | SQM | 0 | 65.55 | 0 | 0 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0 | 0 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 173.109 | SQM | 0 | 173.11 | 0 | 0 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13500 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 0 | 61.66 | 0 | 0 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 185.883 | SQM | 0 | 185.88 | 0 | 0 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 150.161 | SQM | 0 | 150.16 | 0 | 0 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 10.287 | SQM | 0 | 10.29 | 0 | 0 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 66.94 | SQM | 0 | 66.94 | 0 | 0 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 87.48 | SQM | 0 | 87.48 | 0 | 0 | 0 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0

## V121
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption)
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100%
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100%
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100%
MANJUNATHA P | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100%
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100%
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100%
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100%
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100%
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100%
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 0 | 1.25 | 0%
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100%
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.14 | MT | 0 | 0.14 | 0%
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100%
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 23.64 | SQM | 23.64 | 0 | 100%
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100%
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 41.28 | SQM | 0 | 41.28 | 0%
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 125.99 | SQM | 0 | 125.99 | 0%
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.26 | SQM | 0 | 12.26 | 0%
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.2505 | 0%
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0 | 0.5 | 0%
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 0 | 1.1 | 0%
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0 | 0.14 | 0%
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0%
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 41.58 | SQM | 0 | 41.58 | 0%
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 125.21 | SQM | 0 | 125.21 | 0%
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.26 | SQM | 0 | 12.26 | 0%
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.815 | 0%
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0 | 0.1 | 0%
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0 | 0.17 | 0%
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0 | 0.02 | 0%
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0%
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 22.88 | SQM | 0 | 22.88 | 0%
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.92 | SQM | 0 | 1.92 | 0%
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0%
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99%
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0%
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0%
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0%
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0%

## V122
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 22 | 77 | SQM | 77 | 0 | 100 | 1694 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100 | 2775 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100 | 9375 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.14 | MT | 0.14 | 0 | 100 | 1400 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100 | 7980.8602 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100 | 16492.1702 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.25 | SQM | 9.25 | 0 | 100 | 2787.876 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100 | 1830 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0.15 | 0 | 100 | 1500 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | 0 | 100 | 2959.6694 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0.84 | 0 | 100 | 2520 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100 | 569.6309 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 2000 | 1.975 | CUM | 1.98 | 0 | 100 | 3960 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0.07 | 0 | 100 | 210 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.912 | SQM | 108.91 | 0 | 100 | 21101.5303 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 40.54 | RMT | 40.54 | 0 | 100 | 2659.424 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 96.15 | SQM | 96.15 | 0 | 100 | 18629.2548 | 0 | 0
CLENSTACK LLP | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 118.089 | SQM | 118.09 | 0 | 100 | 25422.4152 | 0 | 0
CLENSTACK LLP | WATERPROOF PLASTERING | 170 | 215.28 | 28.584 | SQM | 28.58 | 0 | 100 | 6152.7024 | 0 | 0
CLENSTACK LLP | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100 | 1533.87 | 0 | 0
CLENSTACK LLP | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 70.641 | SQM | 70.64 | 0 | 100 | 15207.3792 | 0 | 0
CLENSTACK LLP | CINDER FILLING ALL FLOOR | 178 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100
CLENSTACK LLP | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 508.36 | 0 | 100
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 18.16 | SQM | 18.16 | 0 | 100
ANSAR HOSSAIAN SK | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 14 | 0 | 100
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 19.57 | 0 | 100
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 51.68 | SQM | 51.68 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 45.26 | RMT | 45.26 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 43.7 | SQM | 43.7 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 42.77 | RMT | 42.77 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 2.12 | SQM | 2.12 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.15 | RMT | 4.15 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 3.89 | SQM | 3.89 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 8.42 | RMT | 8.42 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 10.19 | SQM | 10.19 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 13.87 | RMT | 13.87 | 0 | 100
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 11.38 | SQM | 11.38 | 0 | 100
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 1068.49 | SFT | 1068.49 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.64 | SQM | 3.64 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.95 | SQM | 17.95 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.22 | SQM | 7.22 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.71 | SQM | 35.71 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 125.805 | SQM | 125.81 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.67 | RMT | 25.67 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
CHIRANJEEVI | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 3 | NOS | 3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0

## V123
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
SUBHASMITA DAS | FOOTING SOILING | 7 | 22 | 58 | SQM | 58 | 0 | 100 | 1276 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM SOLING | 12 | 22 | 31.45 | SQM | 31.45 | 0 | 100 | 691.9 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 22 | 77 | SQM | 70 | 7 | 90.909 | 1540 | 0 | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 9.27 | CUM | 9.27 | 0 | 100 | 1308.1824 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 3 | 2.93 | 50.599 | 3000 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100 | 2775 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100 | 9375 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0 | 100 | 18068.4504 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100 | 4855.4251 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100 | 1830 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100 | 5313.541 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0.84 | 0 | 100 | 2520 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100 | 150 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100 | 578.6726 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 2000 | 1.975 | CUM | 1.98 | 0 | 100 | 3960 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0.07 | 0 | 100 | 210 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 28 | 15 | 65.116 | 1400 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.912 | SQM | 108.91 | 0 | 100 | 21101.5303 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 40.54 | RMT | 40.54 | 0 | 100 | 2659.424 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100 | 15000 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 96.15 | SQM | 96.15 | 0 | 100 | 18629.2548 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 125.638 | SQM | 125.64 | 0 | 100 | 27047.7792 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 33.896 | SQM | 33.9 | 0 | 100
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 19.306 | SQM | 19.31 | 0 | 100
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 71.456 | SQM | 71.46 | 0 | 100
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 7.182 | SQM | 7.18 | 0 | 100
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 18 | NOS | 18 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 37.161 | SQM | 37.16 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 113.155 | SQM | 113.16 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 508.36 | 0 | 100
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 20.12 | SQM | 20.12 | 0 | 100
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 19.57 | 0 | 100
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 49.52 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 48.42 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 46 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 50.44 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2.5 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 0 | 4.01 | 0
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 0 | 9.98 | 0
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 12.635 | SQM | 12.64 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.8 | RMT | 16.8 | 0 | 100
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 12.821 | SQM | 12.82 | 0 | 100
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.66 | SQM | 3.29 | 0.37 | 90
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 17.34 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.44 | SQM | 7.44 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 34.9 | SQM | 34.9 | 0 | 100
TANMAY | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 144.788 | SQM | 115.83 | 28.96 | 80
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 23.68 | RMT | 10.05 | 13.63 | #VALUE!
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 13.62 | RMT | 13.62 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING (INCUDING MATERIAL) | 261 | 1600 | 4 | NOS | 1.12 | 2.88 | #VALUE!
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 100 | RFT | 100 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 27 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 249 | SFT | 249 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 15 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 9800 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 3.625 | SQM | 3.63 | 0 | 100
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 6.7845 | SQM | 6.78 | 0 | 100
CHIRANJEEVI | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 45.43 | SQM | 45.43 | 0 | 100
CHIRANJEEVI | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 80.112 | SQM | 80.11 | 0 | 100
CHIRANJEEVI | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 48.47 | SQM | 48.47 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION INTERNAL WALL THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERIOR EMULSION PAINTING WORK | 466 | 91.494 | 102.01 | SQM | 102.01 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION EXTERNAL WALL ONE COAT PRIMER, TWO COATS EXTERIOR EMULSION PAINTING WORK | 467 | 48.438 | 8.64 | SQM | 8.64 | 0 | 100
SARAT BARMAN | CUSTOMISATION FLOOR REINFORCEMENT WORK | 492 | 7500 | 0.589 | MT | 0.59 | 0 | 100

## V124
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
NARESH PURTY | FOOTING REINFORCEMENT | 23 | 6800 | 0.37 | MT | 0.37 | 0 | 100 | 2516 | 0 | 0
NARESH PURTY | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.45 | MT | 0.45 | 0 | 100 | 3060 | 0 | 0
NARESH PURTY | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.18 | MT | 0.18 | 0 | 100 | 1224 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.37 | MT | 0.37 | 0 | 100 | 2775 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100 | 9375 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0 | 100 | 18068.4504 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100 | 4855.4251 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100 | 915 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100 | 5313.541 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0 | 100 | 1260 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100 | 150 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 0 | 22.88 | 0 | 0 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100 | 578.6726 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100 | 105 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 0 | 100 | 21682.7863 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 46.88 | 0 | 100 | 3075.328 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 112.48 | 0 | 100 | 21793.225 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 254.03 | 153.36 | SQM | 153.36 | 0 | 100 | 38958.0408 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 254.03 | 13.973 | SQM | 13.97 | 0 | 100 | 3548.7991 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 190.52 | 15.87 | SQM | 15.87 | 0 | 100 | 3023.5524 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 254.03 | 66.37 | SQM | 66.37 | 0 | 100 | 16859.9711 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 254.03 | 93.098 | SQM | 93.1 | 0 | 100 | 23650.193 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 295 | 8 | NOS | 8 | 0 | 100 | 2360 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 37.16 | SQM | 37.16 | 0 | 100 | 7999.8048 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.89 | 113.16 | SQM | 113.16 | 0 | 100 | 10964.0724 | 0 | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 147.94 | SQM | 147.94 | 0 | 100
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 112.08 | SQM | 112.08 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 102.36 | SQM | 102.36 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.5 | 166.76 | SQM | 166.76 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.5 | 60.55 | SQM | 60.55 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.5 | 175.88 | SQM | 175.88 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.5 | 61.66 | SQM | 61.66 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.5 | 36.94 | SQM | 36.94 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.5 | 8.87 | SQM | 8.87 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 20.12 | SQM | 20.12 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 26.83 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 172.224 | 45.952 | SQM | 45.95 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 48.42 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 46 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 50.44 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2.5 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 12.635 | SQM | 12.64 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.8 | RMT | 16.8 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 12.821 | SQM | 12.82 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.7 | SQM | 3.7 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 17.34 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.44 | SQM | 7.44 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 34.9 | SQM | 34.9 | 0 | 100
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 190.914 | SQM | 190.91 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 0 | 1 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 0.5 | LUMP SUM | 0 | 0.5 | 0
BICHITRA CHOUDHURI | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 0.5 | LUMP SUM | 0.5 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 24.39 | RMT | 24.39 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING (INCUDING MATERIAL) | 261 | 1600 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 12850 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 4 | NOS | 4 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 60 | RFT | 60 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 24 | RFT | 24 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 111 | SFT | 111 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 363 | 8.5 | RFT | 8.5 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
KHALIL MIAH | LAYING FLOOR PROTECTOR SHEET & TILE CLEANING | 341 | 1.5 | 1055 | SFT | 1055 | 0 | 100
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION INTERNAL WALL THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERIOR EMULSION PAINTING WORK | 466 | 91.494 | 102.01 | SQM | 102.01 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION EXTERNAL WALL ONE COAT PRIMER, TWO COATS EXTERIOR EMULSION PAINTING WORK | 467 | 48.438 | 8.64 | SQM | 8.64 | 0 | 100
INDAL SAHNI | CUSTOMIZATION WORK IN TERRACE/FLOOR CHIPPING/MAIN FLOORING/SKIRTING/TOILET FLOOR AND WALL/GRANITE SILL | 524 | 495.45 | 21.94 | SQM | 21.94 | 0 | 100

## V125
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 100.11 | 1.77 | 98.267 | 21191.2848 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
SUBHASMITA DAS | FOOTING SOILING | 7 | 22 | 58 | SQM | 58 | 0 | 100 | 1276 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM SOLING | 12 | 22 | 31.45 | SQM | 31.45 | 0 | 100 | 691.9 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 22 | 77 | SQM | 77 | 0 | 100 | 1694 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7000 | 0.37 | MT | 0.37 | 0 | 100 | 2590 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100 | 9375 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.14 | MT | 0 | 0.14 | 0 | 0 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100 | 7980.8602 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100 | 16492.1702 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0 | 100 | 2787.876 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100 | 1830 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | 0 | 100 | 2959.6694 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0.84 | 0 | 100 | 2520 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 10000 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100 | 569.6309 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 2000 | 1.975 | CUM | 1.98 | 0 | 100 | 3960 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0.07 | 0 | 100 | 210 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.912 | SQM | 108.91 | 0 | 100 | 21101.5303 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 40.54 | RMT | 40.54 | 0 | 100 | 2659.424 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 133.41 | 33.35 | 80 | 18668.3281 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 29.55 | 7.39 | 80 | 4134.9906 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 96.15 | SQM | 96.15 | 0 | 100 | 18629.2548 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 126.441 | SQM | 126.44 | 0 | 100 | 27220.0032 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.18 | 36.874 | SQM | 36.87 | 0 | 100 | 7933.6866 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 14.137 | SQM | 14.14 | 0 | 100 | 1522.0296 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 70.705 | SQM | 70.71 | 0 | 100
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 14.137 | SQM | 14.14 | 0 | 100
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 20 | NOS | 20 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 508.36 | 0 | 100
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 17.75 | SQM | 17.75 | 0 | 100
ANSAR HOSSAIAN SK | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.4 | RMT | 46.4 | 0 | 100
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.07 | RMT | 23.07 | 0 | 100
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 49.52 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 48.42 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 46 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 50.44 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2.5 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 10.18 | SQM | 10.18 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 14 | RMT | 14 | 0 | 100
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 11.138 | SQM | 11.14 | 0 | 100
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.41 | SQM | 3.41 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 17.34 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 6.62 | SQM | 6.62 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 33.99 | SQM | 33.99 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 125.805 | SQM | 125.81 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.231 | RMT | 25.23 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
CHIRANJEEVI | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 3 | NOS | 3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
ANSAR HOSSAIAN SK | SILL GRANITE | 289 | 75 | 70 | RFT | 70 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY & TERRACE PARAPIT WALL TOP COPING GRANITE | 290 | 78 | 93.64 | RFT | 93.64 | 0 | 100
PRAKASH H N | LIFT ELECTRICAL WORK | 349 | 1 | 3 | LUMP SUM | 0 | 3 | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0
ANSAR HOSSAIAN SK | CAR PARKING BOUNDARY WALL TOP COPING GRANITE | 550 | 78 | 15 | RFT | 15 | 0 | 100

## V126
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100% | 3201.66 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 0 | 101.87 | 0% | 0 |  | 0 | KRIUTTIBAS DAS | 8000
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100% | 1120.46 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 0 | 78.55 | 0% | 0 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0.004 | 99.93% | 1176.9408 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100% | 3882.2112 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 0 | 59.29 | 0% | 0 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 22 | 77 | SQM | 70 | 7 | 90.91% | 1540 |  | 0 | RUPAK NAYAK | 31636.5639
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0.003 | 99.94% | 5090 |  | 0 | SAVITA DEVI | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0.002 | 99.93% | 2780 |  | 0 | SHOKAT | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | -0.001 | 100% | 5930 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.525 | MT | 0.53 | -0.005 | 101% | 3975 |  | 0 | SK ANSAR HOSSIAN | 9713.1892
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.473 | MT | 0.47 | 0.003 | 99.37% | 3525 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.506 | MT | 0.51 | -0.004 | 100.8% | 3825 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.561 | MT | 0.56 | 0.001 | 99.82% | 4200 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.527 | MT | 1.53 | -0.003 | 100.2% | 11475 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.215 | MT | 0.22 | -0.005 | 102.3% | 1650 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0 | YELLAPPA C | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100% | 7980.8602 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100% | 7124.9069 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100% | 16492.1702 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100% | 12441.4618 |  | 0 | TOTAL | 49349.7531
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100% | 37972.3781 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100% | 3695.0659 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0.0005 | 99.99% | 2787.876 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100% | 2227.5 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100% | 1980 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100% | 4266 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100% | 5700 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0.003 | 99.98% | 2943 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0.001 | 99.94% | 3400 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100% | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.56 | MT | 0.56 | 0 | 100% | 4200 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.212 | MT | 1.21 | 0.002 | 99.83% | 9075 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.215 | MT | 0.22 | -0.005 | 102.3% | 1650 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100% | 12531.8794 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100% | 37737.2923 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100% | 3695.0659 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | -0.005 | 100.1% | 2959.6694 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0.004 | 99.83% | 4640 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0.001 | 99.99% | 3051 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | -0.004 | 100.3% | 2820 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0.84 | 0.003 | 99.64% | 2520 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.388 | MT | 0.39 | -0.002 | 100.5% | 2925 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.548 | MT | 0.55 | -0.002 | 100.4% | 4125 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100% | 150 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100% | 6895.849 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100% | 569.6309 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | -0.005 | 100.3% | 445.5 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0.07 | 0 | 100% | 210 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100% | 2150 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.91 | SQM | 108.91 | 0 | 100% | 21101.5303 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100% | 23858.6213 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0.002 | 100% | 12148.2504 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100% | 2000.144 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 40.54 | RMT | 40.54 | 0 | 100% | 2659.424 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100% | 184.0644 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100% | 1909.0392 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100% | 8472.8826 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100% | 23335.0603 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0.001 | 100% | 31998.1428 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0.002 | 100% | 8628.2071 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0.003 | 100% | 24611.2402 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100% | 26480.0858 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100% | 1241.1968 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.16 | SQM | 36.16 | 0 | 100% | 5059.9411 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 96.15 | SQM | 96.15 | 0 | 100% | 18629.2548 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 123.524 | SQM | 123.52 | 0.004 | 100% | 26591.3856 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 28.584 | SQM | 28.58 | 0.004 | 99.99% | 6152.7024 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 14.246 | SQM | 14.25 | -0.004 | 100% | 1533.87 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 70.64 | SQM | 70.64 | 0 | 100% | 15207.3792 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 14.246 | SQM | 14.25 | -0.004 | 100% | 1533.87 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0.003 | 99.99% | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100% | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100% | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 0 | 406.82 | 0% | 0 | 100% | 13137.0314
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0.004 | 99.99% | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0.004 | 100% | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0.003 | 100% | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 0 | 581.011 | 0% | 0 | 100% | 15635.006
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 18.16 | SQM | 18.16 | 0 | 100% | 5473.2787 |  | 0
SK ANSAR HOSSIAN | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 0 | 14 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100% | 3375.94 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100% | 3395.784 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 19.57 | 0 | 100% | 2567.584 |  | 0
SK ANSAR HOSSIAN | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 | 100% | 4000
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 51.68 | SQM | 51.68 | 0 | 100% | 9457.44 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 45.26 | RMT | 45.26 | 0 | 100% | 2226.792 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 43.7 | SQM | 43.7 | 0 | 100% | 7997.1 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 42.77 | RMT | 42.77 | 0 | 100% | 2104.284 |  | 0
SK ANSAR HOSSIAN | TERRACE FLOOR TILING | 228 | 183 | 2.12 | SQM | 0 | 2.12 | 0% | 0 | 90% | 349.164
SK ANSAR HOSSIAN | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.15 | RMT | 0 | 4.15 | 0% | 0 | 90% | 183.762
SK ANSAR HOSSIAN | UTILITY FLOOR TILING | 230 | 183 | 3.89 | SQM | 0 | 3.89 | 0% | 0 | 90% | 640.683
SK ANSAR HOSSIAN | UTILITY SKIRTING | 231 | 49.2 | 8.42 | RMT | 0 | 8.42 | 0% | 0 | 90% | 372.8376
SK ANSAR HOSSIAN | BALCONY & SITOUT TILING | 232 | 183 | 10.19 | SQM | 0 | 10.19 | 0% | 0 | 90% | 1678.293
SK ANSAR HOSSIAN | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 13.87 | RMT | 0 | 13.87 | 0% | 0 | 90% | 614.1636
SK ANSAR HOSSIAN | CAR PARKING AREA TILING | 234 | 183 | 11.38 | SQM | 0 | 11.38 | 0% | 0 | 90% | 1874.286
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1068.49 | SFT | 1068.49 | 0 | 100% | 2671.225 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.64 | SQM | 3.64 | 0 | 100% | 666.12 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.95 | SQM | 17.95 | 0 | 100% | 3284.85 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.22 | SQM | 7.22 | 0 | 100% | 1321.26 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.71 | SQM | 35.71 | 0 | 100% | 6534.93 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 8000
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 35.6957 | RMT | 35.7 | -0.0043 | 100% | 197599.5 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100% | 1500 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 1250 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 89.526 | SQM | 89.53 | -0.004 | 100% | 4336.6541 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 89.526 | SQM | 89.53 | -0.004 | 100% | 1445.9095 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 89.526 | SQM | 0 | 89.526 | 0% | 0 | 100% | 2409.1447
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 14.102 | SQM | 14.1 | 0.002 | 99.99% | 227.715 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 14.102 | SQM | 0 | 14.102 | 0% | 0 | 100% | 455.3818
AAIDHUL MIAH | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 33.023 | SQM | 20 | 13.023 | 60.56% | 3875 |  | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 100.83 | SQM | 80 | 20.83 | 79.34% | 11194.56 |  | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 15.227 | SQM | 15.23 | -0.003 | 100% | 2950.843 |  | 0
SARAT BARMAN | CUSTOMISATION FLOOR REINFORCEMENT WORK | 492 | 7500 | 0.589 | MT | 0.59 | -0.001 | 100.2% | 4425 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.573 | CUM | 4.57 | 0.003 | 99.93% | 1028.25 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100% | 250 |  | 0
NAGARAJ | CUSTOMIZATION FLOOR SLAB AND BEAM SHUTTERING | 508 | 322.92 | 44.44 | SQM | 44.44 | 0 | 100% | 14350.5648 |  | 0
NAGARAJ | CUSTOMIZATION FLOOR COLUMN SHUTTERING | 509 | 322.92 | 16.5 | SQM | 16.5 | 0 | 100% | 5328.18 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.362 | MT | 0.36 | 0.002 | 99.45% | 2700 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.234 | MT | 0.23 | 0.004 | 98.29% | 1725 |  | 0
SHOKAT | CUSTOMIZATION BALCONY WATERPROOFING WORK | 525 | 215.28 | 11.54 | SQM | 11.54 | 0 | 100% | 2484.3312 |  | 0
SHOKAT | CUSTOMISATION BALCONY WATER PROOF SCREED CONCRETE 50MM THICK | 526 | 107.64 | 4.68 | SQM | 4.68 | 0 | 100% | 503.7552 |  | 0
SHOKAT | CUSTOMISATION BALCONY CINDER FILLING | 527 | 107.64 | 4.68 | SQM | 4.68 | 0 | 100% | 503.7552 |  | 0
SHOKAT | CUSTOMISATION BALCONY BORE PACKING | 528 | 200 | 2 | SQM | 2 | 0 | 100% | 400 |  | 0
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100% | 800 |  | 0
49349.7531

## V127
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18 | CUM | 18 | 0 | 100 | 2540.16 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 60.55 | CUM | 60.55 | 0 | 100 | 8544.816 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 50 | 101.12 | 33.086 | 2150 | 0 | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 9.27 | CUM | 9.27 | 0 | 100 | 1308.1824 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100 | 2775 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100 | 9375 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.14 | MT | 0.14 | 0 | 100 | 1400 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100 | 7980.8602 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100 | 16492.1702 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0 | 100 | 2787.876 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0.15 | 0 | 100 | 1500 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | 0 | 100 | 2959.6694 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 5000 | 0.02 | MT | 0.02 | 0 | 100 | 100 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100 | 569.6309 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 0 | 100 | 21682.7863 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 46.88 | 0 | 100 | 3075.328 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 130 | 35.15 | 78.716 | 25187.76 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 112.48 | 0 | 100 | 21793.225 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 124.218 | SQM | 124.22 | 0 | 100 | 26742.0816 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 28.584 | SQM | 28.58 | 0 | 100 | 6152.7024 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100 | 1533.87 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 113.189 | SQM | 113.19 | 0 | 100 | 24367.5432 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100 | 1533.87 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 16 | NOS | 16 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 18.16 | SQM | 16.34 | 1.82 | 90
ANSAR HOSSAIAN SK | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 14 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 37.05 | 4.12 | 90
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 93.18 | 10.35 | 90
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 17.61 | 1.96 | 90
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 51.68 | SQM | 43.93 | 7.75 | 85
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 45.26 | RMT | 38.47 | 6.79 | 85
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 43.7 | SQM | 37.15 | 6.56 | 85
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 42.77 | RMT | 36.35 | 6.42 | 85
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 2.12 | SQM | 1.8 | 0.32 | 85
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.15 | RMT | 3.53 | 0.62 | 85
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 3.89 | SQM | 3.89 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 8.42 | RMT | 8.42 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 10.19 | SQM | 10.19 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 13.87 | RMT | 13.87 | 0 | 100
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 11.38 | SQM | 11.38 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1068.49 | SFT | 1068.49 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.64 | SQM | 3.64 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.95 | SQM | 17.95 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.22 | SQM | 7.22 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.71 | SQM | 35.71 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 122.44 | SQM | 122.44 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.09 | RMT | 25.09 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 4 | NOS | 4 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 0.5 | 0.5 | 50
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 89.526 | SQM | 89.53 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 89.526 | SQM | 89.53 | 0 | 100
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 89.526 | SQM | 89.53 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 14.102 | SQM | 14.1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 14.102 | SQM | 14.1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 4350 | 1 | LUMP SUM | 0.5 | 0.5 | 50
AAIDHUL MIAH | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 48.233 | SQM | 30 | 18.23 | 62.198
AAIDHUL MIAH | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 128.084 | SQM | 100 | 28.08 | 78.074
AAIDHUL MIAH | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 23.052 | SQM | 23.05 | 0 | 100
RUPAK NAYAK | CUSTOMISATION EPOXY GROUTING & SOAP WASH | 480 | 64.58 | 23.409 | SQM | 23.41 | 0 | 100
SARAT BARMAN | CUSTOMISATION FLOOR REINFORCEMENT WORK | 492 | 7500 | 0.589 | MT | 0.59 | 0 | 100
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.573 | CUM | 4.57 | 0 | 100
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100
NAGARAJ | CUSTOMIZATION FLOOR SLAB AND BEAM SHUTTERING | 508 | 322.92 | 56.843 | SQM | 56.84 | 0 | 100
NAGARAJ | CUSTOMIZATION FLOOR COLUMN SHUTTERING | 509 | 322.92 | 18.676 | SQM | 18.68 | 0 | 100
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.367 | MT | 0.37 | 0 | 100
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.256 | MT | 0.26 | 0 | 100
SHOKAT | CUSTOMIZATION TOILET FLOOR CHIPPING AND 2 COATS OF WATERPROOFING | 515 | 430.56 | 12.15 | SQM | 12.15 | 0 | 100
SHOKAT | CUSTOMIZATION TOILET SCREED CONCRETE | 516 | 215.28 | 5.625 | SQM | 5.63 | 0 | 100

## V128
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 52.38 | SQM | 52.38 | 0 | 100 | 2252.34 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 | 0 | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100 | 2500 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 31.36 | SQM | 31.36 | 0 | 100 | 1348.48 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 59.29 | SQM | 59.29 | 0 | 100 | 2549.47 | 0 | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
BISWO RANJAN ROUT | FOOTING REINFORCEMENT | 23 | 6800 | 0.37 | MT | 0.37 | 0 | 100 | 2516 | 0 | 0
BISWO RANJAN ROUT | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.45 | MT | 0.45 | 0 | 100 | 3060 | 0 | 0
BISWO RANJAN ROUT | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.55 | MT | 0.55 | 0 | 100 | 3740 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.5 | MT | 0.5 | 0 | 100 | 3400 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 0.13 | MT | 0.13 | 0 | 100 | 884 | 0 | 0
NARESH PURTY | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 1.12 | MT | 1.12 | 0 | 100 | 7616 | 0 | 0
NARESH PURTY | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 6800 | 0.14 | MT | 0.14 | 0 | 100 | 952 | 0 | 0
NARESH PURTY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 6800 | 0.14 | MT | 0.14 | 0 | 100 | 952 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0 | 100 | 18068.4504 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100 | 4855.4251 | 0 | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
NARESH PURTY | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 6800 | 0.5 | MT | 0.5 | 0 | 100 | 3400 | 0 | 0
NARESH PURTY | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 6800 | 1.1 | MT | 1.1 | 0 | 100 | 7480 | 0 | 0
NARESH PURTY | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 6800 | 0.14 | MT | 0.14 | 0 | 100 | 952 | 0 | 0
NARESH PURTY | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 6800 | 0.15 | MT | 0.15 | 0 | 100 | 1020 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 0 | 12.26 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 2.84 | 14.79 | 16.106 | 855.9533 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
NARESH PURTY | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 6800 | 0.1 | MT | 0.1 | 0 | 100 | 680 | 0 | 0
NARESH PURTY | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 6800 | 0.17 | MT | 0.17 | 0 | 100 | 1156 | 0 | 0
NARESH PURTY | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 6800 | 0.02 | MT | 0.02 | 0 | 100 | 136 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 0 | 1.92 | 0 | 0 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100 | 105 | 0 | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 0 | 100 | 21682.7863 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 46.88 | 0 | 100 | 3075.328 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
SALLAUDDIN ANSARI | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 0.73333 | LUMP SUM | 0.73 | 0 | 100 | 8760 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 0.26667 | LUMP SUM | 0.27 | 0 | 100 | 3240 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 112.48 | 0 | 100 | 21793.225 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 182 | 215.28 | 30 | SQM | 30 | 0 | 100 | 6458.4 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 34.38 | SQM | 34.38 | 0 | 100 | 3330.5969 | 0 | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 147.879 | SQM | 147.88 | 0 | 100 | 7163.0114 | 0 | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 112.08 | SQM | 112.08 | 0 | 100 | 5428.931 | 0 | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 102.36 | SQM | 102.36 | 0 | 100 | 4958.1137 | 0 | 0
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.5 | 166.76 | SQM | 166.76 | 0 | 100 | 15258.54 | 0 | 0
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.5 | 60.55 | SQM | 60.55 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.5 | 175.88 | SQM | 175.88 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.5 | 61.66 | SQM | 61.66 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.5 | 36.94 | SQM | 36.94 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.5 | 8.87 | SQM | 8.87 | 0 | 99.997
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 20.12 | SQM | 20.12 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 26.83 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 172.224 | 45.952 | SQM | 45.95 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 48.42 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 46 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 50.44 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2.5 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 12.635 | SQM | 12.64 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.8 | RMT | 16.8 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 12.821 | SQM | 12.82 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.7 | SQM | 3.7 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 17.34 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.44 | SQM | 7.44 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 34.9 | SQM | 31.81 | 3.09 | 91.146
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 190.914 | SQM | 190.91 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
BICHITRA CHOUDHURI | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6750 | 0.5 | LUMP SUM | 0 | 0.5 | 0
ANU P | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6750 | 0.5 | LUMP SUM | 0.5 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 20.78 | RMT | 0 | 20.78 | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING (INCUDING MATERIAL) | 261 | 1600 | 3 | NOS | 3 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 12850 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 60 | RFT | 60 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 24 | RFT | 24 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 111 | SFT | 111 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 363 | 8.5 | RFT | 8.5 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | GROUND FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 376 | 16.146 | 147.879 | SQM | 147.88 | 0 | 100
RUPAK NAYAK | FIRST FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 377 | 16.146 | 112.08 | SQM | 112.08 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 378 | 16.146 | 102.36 | SQM | 102.36 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 2640 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION TERRACE WASHING MACHINE TAP POINT WORK | 504 | 1500 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 529 | 1000 | 1 | NOS | 1 | 0 | 100

## V129
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 0 | 78.55 | 0 | 0 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 22 | 77 | SQM | 70 | 7 | 90.909 | 1540 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 |  | 0 | SAVITA DEVI | 5625
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 |  | 0 | SHOKAT | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 4 | 1.93 | 67.465 | 4000 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7000 | 0.37 | MT | 0.37 | 0 | 100 | 2590 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100 | 9375 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.14 | MT | 0 | 0.14 | 0 | 0 |  | 0 | YELLAPPA C | 0
BHASKAR | FOOTING SHUTTERING | 41 | 301.392 | 26.47 | SQM | 26.47 | 0 | 100 | 7977.8462 |  | 0 | RABIUL MOLLA | 0
BHASKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 |  | 0 | KOUSHIK MANDAL | 0
BHASKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100 | 16492.1702 |  | 0 | SHEKAR T | 0
BHASKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 |  | 0 | TOTAL | 5625
BHASKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 |  | 0
BHASKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 |  | 0
MANJUNATHA R | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.25 | SQM | 9.25 | 0 | 100 | 2787.876 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 |  | 0
KHALIL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100 | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 |  | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 |  | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 |  | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 |  | 0
MANJUNATHA R | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | 0 | 100 | 2959.6694 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 |  | 0
KHALIL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0.84 | 0 | 100 | 2520 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0 | 0.02 | 0 | 0 |  | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 |  | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 |  | 0
MANJUNATHA R | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100 | 569.6309 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 2000 | 1.975 | CUM | 1.98 | 0 | 100 | 3960 |  | 0
KHALIL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0.07 | 0 | 100 | 210 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 |  | 0
KHALIL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 106.054 | SQM | 106.05 | 0 | 100 | 20547.3996 |  | 0
KHALIL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 113.2014 | SQM | 113.2 | 0 | 100 | 21932.7264 |  | 0
KHALIL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 69.96 | SQM | 69.96 | 0 | 100 | 13554.8899 |  | 0
KHALIL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 27.15 | RMT | 27.15 | 0 | 100 | 1781.04 |  | 0
KHALIL MIAH | ELEVATION GROOVE | 137 | 65.6 | 43.88 | RMT | 43.88 | 0 | 100 | 2878.528 |  | 0
KHALIL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 |  | 0
KHALIL MIAH | RCC SURFACE HACKING | 140 | 8.073 | 348.385 | SQM | 348.39 | 0 | 100 | 2812.5525 |  | 0
KHALIL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 65.55 | SQM | 65.55 | 0 | 100 | 9172.5426 |  | 0
KHALIL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 |  | 0
KHALIL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 187.752 | 178.642 | SQM | 178.64 | 0 | 100 | 33540.0173 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 |  | 0
KHALIL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 |  | 0
KHALIL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 185.883 | SQM | 185.88 | 0 | 100 | 26010.5602 |  | 0
KHALIL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 150.161 | SQM | 150.16 | 0 | 99.999 | 29093.8003 |  | 0
KHALIL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 10.287 | SQM | 10.29 | 0 | 100 | 1439.9003 |  | 0
KHALIL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 66.94 | SQM | 66.94 | 0 | 100 | 9367.0481 |  | 0
KHALIL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 87.48 | SQM | 87.48 | 0 | 100 | 16949.425 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 118.09 | SQM | 118.09 | 0 | 100 | 25422.4152 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 28.584 | SQM | 28.58 | 0 | 100 | 6152.7024 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100 | 1533.87 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 70.64 | SQM | 70.64 | 0 | 100 | 15207.3792 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100 | 1533.87 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100 | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100 | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100 | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100 | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100 | 13137.0314 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100 | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100 | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100 | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100 | 15634.9791 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 20.12 | SQM | 20.12 | 0 | 100 | 6064.007 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 12 | 3 | 80 | 4200 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100 | 3375.94 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100 | 3395.784 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 19.57 | 0 | 100 | 2567.584 |  | 0
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0 | 0 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 49.52 | 0 | 100 | 9062.16 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 48.42 | 0 | 100 | 2382.264 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 46 | 0 | 100 | 8418 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 50.44 | 0 | 100 | 2481.648 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2.5 | 0 | 100 | 457.5 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100 | 206.148 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100 | 733.83 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100 | 491.016 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 12.635 | SQM | 12.64 | 0 | 100 | 2313.12 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.8 | RMT | 16.8 | 0 | 100 | 826.56 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 12.821 | SQM | 12.82 | 0 | 100 | 2346.06 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100 | 2637.5 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 172.224 | 3.66 | SQM | 3.66 | 0 | 100 | 630.3398 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 193.752 | 17.34 | SQM | 17.34 | 0 | 100 | 3359.6597 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 172.224 | 7.44 | SQM | 7.44 | 0 | 100 | 1281.3466 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 193.752 | 34.9 | SQM | 34.9 | 0 | 100 | 6761.9448 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 122.44 | SQM | 122.44 | 0 | 100 | 7907.1752 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100 | 14500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100 | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100 | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100 | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100 | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100 | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 |  | 0
UDHABHAI R PARMAR | BALCONY & STAIRCASE SS RAILING | 260 | 5528.485 | 17.6775 | RMT | 17.68 | 0 | 100 | 97743.6148 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100 | 1350 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100 | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100 | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 0 | 12.5 | 0 | 0 | 100% | 5625
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100 | 350 |  | 0
KHALIL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 1 | NOS | 1 | 0 | 100 | 750 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100 | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100 | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100 | 2624.38 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100 | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100 | 400 |  | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 9000 | 1 | LUMP SUM | 1 | 0 | 100 | 9000 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0 | 0 |  | 0
5625

## V130
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.5 | 0.05 | 99.936 | 11077.92 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 22 | 77 | SQM | 77 | 0 | 100 | 1694 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100 | 2775 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100 | 9375 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.14 | MT | 0.14 | 0 | 100 | 1400 | 0 | 0
BHASKAR | FOOTING SHUTTERING | 41 | 301.392 | 26.47 | SQM | 26.47 | 0 | 100 | 7977.8462 | 0 | 0
BHASKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
BHASKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100 | 16492.1702 | 0 | 0
MANJUNATHA R | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
MANJUNATHA R | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
MANJUNATHA R | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
MANJUNATHA R | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.25 | SQM | 9.25 | 0 | 100 | 2787.876 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100 | 1830 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0.15 | 0 | 100 | 1500 | 0 | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
MANJUNATHA R | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | 0 | 100 | 2959.6694 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0.84 | 0 | 100 | 2520 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
MANJUNATHA R | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100 | 569.6309 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 2000 | 1.975 | CUM | 1.98 | 0 | 100 | 3960 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0.07 | 0 | 100 | 210 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 0 | 43 | 0 | 0 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.91 | SQM | 108.91 | 0 | 100 | 21101.5303 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 40.54 | RMT | 40.54 | 0 | 100 | 2659.424 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 96.15 | SQM | 96.15 | 0 | 100 | 18629.2548 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 118.09 | SQM | 118.09 | 0 | 100 | 25422.4152 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 28.584 | SQM | 28.58 | 0 | 100 | 6152.7024 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100 | 1533.87 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 70.64 | SQM | 70.64 | 0 | 100 | 15207.3792 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 20.12 | SQM | 20.12 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 1 | NOS | 1 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 19.57 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 39.62 | 9.9 | 80
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 38.74 | 9.68 | 80
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 36.8 | 9.2 | 80
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 40.35 | 10.09 | 80
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2 | 0.5 | 80
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 3.35 | 0.84 | 80
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 12.635 | SQM | 10.11 | 2.53 | 80
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.8 | RMT | 13.44 | 3.36 | 80
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 12.821 | SQM | 0 | 12.82 | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.66 | SQM | 2.93 | 0.73 | 80
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 13.87 | 3.47 | 80
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.44 | SQM | 5.95 | 1.49 | 80
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 34.9 | SQM | 27.92 | 6.98 | 80
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 125.765 | SQM | 125.77 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 19.9 | RMT | 19.9 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 1 | NOS | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0

## V131
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 57.22 | SQM | 57.22 | 0 | 100 | 2460.46 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 | 0 | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100 | 2500 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 31.36 | SQM | 31.36 | 0 | 100 | 1348.48 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 59.29 | SQM | 59.29 | 0 | 100 | 2549.47 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
BISWO RANJAN ROUT | FOOTING REINFORCEMENT | 23 | 6800 | 0.37 | MT | 0.37 | 0 | 100 | 2516 | 0 | 0
BISWO RANJAN ROUT | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.45 | MT | 0.45 | 0 | 100 | 3060 | 0 | 0
BISWO RANJAN ROUT | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.55 | MT | 0.55 | 0 | 100 | 3740 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.5 | MT | 0.5 | 0 | 100 | 3400 | 0 | 0
BISWO RANJAN ROUT | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 0.13 | MT | 0.13 | 0 | 100 | 884 | 0 | 0
NARESH PURTY | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.12 | MT | 1.12 | 0 | 100 | 7840 | 0 | 0
NARESH PURTY | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 6800 | 0.14 | MT | 0.14 | 0 | 100 | 952 | 0 | 0
NARESH PURTY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 6800 | 0.14 | MT | 0.14 | 0 | 100 | 952 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0 | 100 | 18068.4504 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 0 | 16.11 | 0 | 0 | 0 | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
NARESH PURTY | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 6800 | 0.5 | MT | 0.5 | 0 | 100 | 3400 | 0 | 0
NARESH PURTY | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 6800 | 1.1 | MT | 1.1 | 0 | 100 | 7480 | 0 | 0
NARESH PURTY | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 6800 | 0.05 | MT | 0.05 | 0 | 100 | 340 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.09 | MT | 0.09 | 0 | 100 | 675 | 0 | 0
NARESH PURTY | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 6800 | 0.15 | MT | 0.15 | 0 | 100 | 1020 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 1.93 | 10.33 | 15.725 | 581.6866 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 0 | 17.63 | 0 | 0 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100 | 150 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 0 | 1.92 | 0 | 0 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100 | 105 | 0 | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 0 | 100 | 21682.7863 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 46.88 | 0 | 100 | 3075.328 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 112.48 | 0 | 100 | 21793.225 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 254.03 | 153.36 | SQM | 153.36 | 0 | 100 | 38958.0408 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 254.03 | 13.973 | SQM | 13.97 | 0 | 100 | 3548.7991 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 190.52 | 15.87 | SQM | 15.87 | 0 | 100 | 3023.5524 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 254.03 | 66.37 | SQM | 66.37 | 0 | 100 | 16859.9711 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 254.03 | 93.098 | SQM | 93.1 | 0 | 100
SHOKAT | BORE PACKING ALL FLOOR | 180 | 295 | 8 | NOS | 8 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 182 | 215.28 | 30 | SQM | 30 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 34.38 | SQM | 34.38 | 0 | 100
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 147.879 | SQM | 147.88 | 0 | 100
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 112.08 | SQM | 112.08 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 102.36 | SQM | 102.36 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.5 | 166.76 | SQM | 166.76 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.5 | 60.55 | SQM | 60.55 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.5 | 175.88 | SQM | 175.88 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.5 | 61.66 | SQM | 61.66 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.5 | 36.94 | SQM | 36.94 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.5 | 8.87 | SQM | 8.87 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 20.12 | SQM | 19.97 | 0.15 | 99.254
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 26.83 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 49.52 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 48.42 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 46 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 50.44 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2.5 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 12.635 | SQM | 12.64 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.8 | RMT | 16.8 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 12.821 | SQM | 12.82 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.7 | SQM | 3.7 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 17.34 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.44 | SQM | 7.44 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 34.9 | SQM | 34.9 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 125.805 | SQM | 0 | 125.81 | 0
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 190.914 | SQM | 190.91 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 0.5 | LUMP SUM | 0 | 0.5 | 0
BICHITRA CHOUDHURI | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 0.5 | LUMP SUM | 0.5 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 24.39 | RMT | 24.39 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 12850 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
KHALIL MIAH | LAYING FLOOR PROTECTOR SHEET & TILE CLEANING | 341 | 1.5 | 1055 | SFT | 1055 | 0 | 100

## V132
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.37 | MT | 0.37 | 0 | 100 | 2590 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.25 | MT | 1.25 | 0 | 100 | 8750 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.14 | MT | 0.14 | 0 | 100 | 980 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.14 | MT | 0.14 | 0 | 100 | 980 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0 | 100 | 18068.4504 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100 | 4855.4251 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100 | 915 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.14 | MT | 0.14 | 0 | 100 | 980 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100 | 5313.541 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100 | 578.6726 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100 | 105 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 0 | 100 | 21682.7863 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 46.88 | 0 | 100 | 3075.328 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 0 | 177.42 | 0 | 0 | 0 | 0
MD GIYAS | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
MD GIYAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
MD GIYAS | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
MD GIYAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
MD GIYAS | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
MD GIYAS | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 112.48 | 0 | 100 | 21793.225 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 118.09 | SQM | 118.09 | 0 | 100 | 25422.4152 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 28.584 | SQM | 28.58 | 0 | 100 | 6152.7024 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100 | 1533.87 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 70.64 | SQM | 70.64 | 0 | 100 | 15207.3792 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100 | 1533.87 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100 | 3400 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | 0 | 100 | 6441.1776 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 508.36 | 0 | 100
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 17.75 | SQM | 17.75 | 0 | 100
ANSAR HOSSAIAN SK | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100
ANSAR HOSSAIAN SK | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.4 | RMT | 46.4 | 0 | 100
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.07 | RMT | 23.07 | 0 | 100
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 49.52 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 48.42 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 46 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 50.44 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2.5 | 0 | 100
ANSAR HOSSAIAN SK | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT TILING | 232 | 183 | 10.18 | SQM | 10.18 | 0 | 100
ANSAR HOSSAIAN SK | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 14 | RMT | 14 | 0 | 100
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 11.138 | SQM | 11.14 | 0 | 100
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.41 | SQM | 3.41 | 0 | 100
ANSAR HOSSAIAN SK | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 17.34 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 6.62 | SQM | 6.62 | 0 | 100
ANSAR HOSSAIAN SK | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 33.99 | SQM | 33.99 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 145.174 | SQM | 145.17 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 29.24 | RMT | 18.18 | 11.06 | 62.175
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | ENTRANCE STEPS SS RAILING | 268 | 5535 | 1.0972 | RMT | 1.1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
ANSAR HOSSAIAN SK | SILL GRANITE | 289 | 75 | 46 | RFT | 46 | 0 | 100
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 10240 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 2020.8 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | CUSTOMIZATION BATHTUB WORK | 425 | 3000 | 1 | NOS | 0.5 | 0.5 | 50
ANSAR HOSSAIAN SK | CUSTOMIZATION TOILET TILE WORK | 436 | 873.67 | 4.187 | SQM | 4.19 | 0 | 100
ANSAR HOSSAIAN SK | CUSTOMIZATION MAIN FLOORING WORK | 442 | 222.425 | 16.452 | SQM | 16.45 | 0 | 100
MD GIYAS | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 33.023 | SQM | 33.02 | 0 | 100
MD GIYAS | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 100.83 | SQM | 100.83 | 0 | 100
MD GIYAS | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 15.227 | SQM | 15.23 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | CUSTOMIZATION WASH BASIN POINT WORK | 486 | 1000 | 1 | NOS | 0.5 | 0.5 | 50
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.362 | MT | 0.36 | 0 | 100
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.234 | MT | 0.23 | 0 | 100
SHOKAT | CUSTOMIZATION BALCONY WATERPROOFING WORK | 525 | 215.28 | 11.54 | SQM | 11.54 | 0 | 100
SHOKAT | CUSTOMISATION BALCONY WATER PROOF SCREED CONCRETE 50MM THICK | 526 | 107.64 | 4.68 | SQM | 4.68 | 0 | 100
SHOKAT | CUSTOMISATION BALCONY CINDER FILLING | 527 | 107.64 | 4.68 | SQM | 4.68 | 0 | 100
SHOKAT | CUSTOMISATION BALCONY BORE PACKING | 528 | 200 | 2 | SQM | 2 | 0 | 100
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100

## V133
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 0.01 | CUM | 0 | 0.01 | 0 | 0 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.5 | CUM | 27.5 | 0 | 100 | 3880.8 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 0 | 59.29 | 0 | 0 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 0 | 5.93 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.37 | MT | 0.37 | 0 | 100 | 2590 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.25 | MT | 1.25 | 0 | 100 | 8750 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.14 | MT | 0.14 | 0 | 100 | 980 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.14 | MT | 0.14 | 0 | 100 | 980 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 37.03 | 22.92 | 61.763 | 11160.5458 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100 | 4855.4251 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100 | 915 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.14 | MT | 0.14 | 0 | 100 | 980 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100 | 5313.541 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100 | 578.6726 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100 | 105 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 0 | 100 | 21682.7863 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 0 | 30.49 | 0 | 0 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 0 | 46.88 | 0 | 0 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
MD GIYAS | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 0 | 177.42 | 0 | 0 | 0 | 0
MD GIYAS | RCC SURFACE HACKING | 141 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 0 | 60.55 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0 | 0 | 0 | 0
MD GIYAS | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
MD GIYAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 0 | 165.15 | 0 | 0 | 0 | 0
MD GIYAS | GROUND FLOOR EXTERNAL WALL PLASTERING | 148 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 0 | 61.66 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 0 | 175.88 | 0 | 0 | 0 | 0
MD GIYAS | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
MD GIYAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 0 | 136.67 | 0 | 0 | 0 | 0
MD GIYAS | FIRST FLOOR EXTERNAL WALL PLASTERING | 158 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 0 | 8.87 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 0 | 36.94 | 0
MD GIYAS | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100
MD GIYAS | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 0 | 112.48 | 0
MD GIYAS | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 113 | SQM | 113 | 0 | 100
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 118.09 | SQM | 118.09 | 0 | 100
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 28.584 | SQM | 28.58 | 0 | 100
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 70.64 | SQM | 70.64 | 0 | 100
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 508.36 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 20.12 | SQM | 20.12 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 12 | 3 | 80
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 19.57 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 49.52 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 48.42 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 46 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 50.44 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2.5 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 12.635 | SQM | 12.64 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.8 | RMT | 16.8 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 12.821 | SQM | 12.82 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.7 | SQM | 3.7 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 17.34 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.44 | SQM | 7.44 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 34.9 | SQM | 34.9 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 125.805 | SQM | 125.81 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 29.36 | RMT | 18.18 | 11.18 | 61.921
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | ENTRANCE STEPS SS RAILING | 268 | 5535 | 1.0058 | RMT | 1.01 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
MD GIYAS | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
INDAL SAHNI | SILL GRANITE | 289 | 75 | 46 | RFT | 46 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 678.6 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | CUSTOMIZATION WASH BASIN POINT WORK | 486 | 1000 | 1 | NOS | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | CUSTOMIZATION CONNECTION FROM FF GEYSER TO GF GEYSER | 530 | 700 | 1 | NOS | 1 | 0 | 100
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100

## V134
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100 | 2952.81 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.3 | MT | 0.3 | 0 | 100 | 2250 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.7 | MT | 0.7 | 0 | 100 | 5250 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100 | 6000 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.15 | MT | 0.15 | 0 | 100 | 1500 | 0 | 0
BHASKAR | FOOTING SHUTTERING | 41 | 301.392 | 26.47 | SQM | 26.47 | 0 | 100 | 7977.8462 | 0 | 0
BHASKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
BHASKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100 | 16492.1702 | 0 | 0
BHASKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
BHASKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
BHASKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
MANJUNATHA R | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.25 | SQM | 9.25 | 0 | 100 | 2787.876 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
MD GIYAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100 | 1830 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.6 | MT | 0.6 | 0 | 100 | 4500 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.2 | MT | 0.2 | 0 | 100 | 1500 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0.15 | 0 | 100 | 1500 | 0 | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
MANJUNATHA R | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | 0 | 100 | 2959.6694 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
MD GIYAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0.84 | 0 | 100 | 2520 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.25 | MT | 0.25 | 0 | 100 | 1875 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0.03 | 0 | 100 | 210 | 0 | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 25.88 | SQM | 25.88 | 0 | 100 | 7800.025 | 0 | 0
MANJUNATHA R | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100 | 569.6309 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 2000 | 2.412 | CUM | 2.41 | 0 | 100 | 4820 | 0 | 0
MD GIYAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0.07 | 0 | 100 | 210 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
MD GIYAS | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 109.91 | SQM | 90 | 19.91 | 81.885 | 17437.68 | 0 | 0
MD GIYAS | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
MD GIYAS | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
MD GIYAS | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100 | 2101.824 | 0 | 0
MD GIYAS | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100 | 2102.48 | 0 | 0
MD GIYAS | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
MD GIYAS | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
MD GIYAS | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
MD GIYAS | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
MD GIYAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
MD GIYAS | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.15 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
MD GIYAS | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.66 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
MD GIYAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
MD GIYAS | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 139.27 | SQM | 139.27 | 0 | 100 | 26983.841 | 0 | 0
MD GIYAS | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
MD GIYAS | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
MD GIYAS | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 96.15 | SQM | 96.15 | 0 | 100 | 18629.2548 | 0 | 0
CLENSTACK LLP | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 137.755 | SQM | 137.76 | 0 | 100 | 29656.9728 | 0 | 0
CLENSTACK LLP | WATERPROOF PLASTERING | 170 | 215.28 | 34.065 | SQM | 34.07 | 0 | 100 | 7334.5896 | 0 | 0
CLENSTACK LLP | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 15.55 | SQM | 15.55 | 0 | 100 | 1673.802 | 0 | 0
CLENSTACK LLP | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 67.225 | SQM | 67.23 | 0 | 100 | 14473.2744 | 0 | 0
CLENSTACK LLP | CINDER FILLING ALL FLOOR | 178 | 107.64 | 15.55 | SQM | 15.55 | 0 | 100 | 1673.802 | 0 | 0
CLENSTACK LLP | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 14 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 18.16 | SQM | 18.16 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 14 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 19.57 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.68 | SQM | 51.68 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 45.26 | RMT | 45.26 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 43.7 | SQM | 43.7 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 42.77 | RMT | 42.77 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.12 | SQM | 2.12 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.15 | RMT | 4.15 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 3.89 | SQM | 3.89 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 8.42 | RMT | 8.42 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 10.19 | SQM | 10.19 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 13.87 | RMT | 13.87 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 11.38 | SQM | 11.38 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1068.49 | SFT | 1068.49 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.64 | SQM | 3.64 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.95 | SQM | 17.95 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.22 | SQM | 7.22 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.71 | SQM | 35.71 | 0 | 100
TANMAY | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 125.805 | SQM | 113.22 | 12.58 | 90
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 18.48 | RMT | 18.48 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
MD GIYAS | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
SUNIL | ODD SITE STRUCTURAL DESIGN WORK | 315 | 8500 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | FRONT ENTRANCE FLOOR CONCRETE JOINTING WITH CEMENT ROAD WORK | 340 | 1000 | 15 | CUM | 15 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
SARAT BARMAN | SARAT BARMAN LINTEL CHEJJA DIFFERENCE AMOUNT | 362 | 94172.12 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100

## V135
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
UPASANA CHAUDHARY | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 0
UPASANA CHAUDHARY | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
UPASANA CHAUDHARY | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
UPASANA CHAUDHARY | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 0
UPASANA CHAUDHARY | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
UPASANA CHAUDHARY | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100% | 12441.1392 |  | 0 | MANJUNATHA P | 0
UPASANA CHAUDHARY | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | NAGARAJ | 0
UPASANA CHAUDHARY | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | PRAKASH H N | 0
UPASANA CHAUDHARY | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100% | 1510.74 |  | 0 | RAMAKRUSHNA PRADHAN | 0
UPASANA CHAUDHARY | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 0 | 7.95 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 7116.2763
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
UPASANA CHAUDHARY | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SAVITA DEVI | 0
UPASANA CHAUDHARY | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SHOKAT | 0
UPASANA CHAUDHARY | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.42 | MT | 0.42 | 0 | 100% | 2940 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.53 | MT | 0.53 | 0 | 100% | 3710 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0.49 | 0 | 100% | 3430 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.2 | MT | 1.2 | 0 | 100% | 8400 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0 | YELLAPPA C | 0
UPASANA CHAUDHARY | FOOTING SHUTTERING | 41 | 301.392 | 25.44 | SQM | 25.44 | 0 | 100% | 7667.4125 |  | 0 | RABIUL MOLLA | 0
UPASANA CHAUDHARY | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | KOUSHIK MANDAL | 0
UPASANA CHAUDHARY | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100% | 17414.4298 |  | 0 | SHEKAR T | 0
UPASANA CHAUDHARY | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0 | TOTAL | 7116.2763
UPASANA CHAUDHARY | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 126.8 | SQM | 126.8 | 0 | 100% | 38216.5056 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 15.17 | 0 | 100% | 4572.1166 |  | 0
UPASANA CHAUDHARY | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
UPASANA CHAUDHARY | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
UPASANA CHAUDHARY | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0 | 0.96 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.47 | MT | 0.47 | 0 | 100% | 3290 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 0.88 | MT | 0.2 | 0.68 | 22.73% | 1400 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.01 | 0.17 | 5.556% | 70 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100% | 39171.9182 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 16.19 | 0 | 100% | 4879.5365 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0 | 0.87 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.19 | MT | 0 | 0.19 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
SARAT BARMAN | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100% | 7275.6029 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 3.5 | 0 | 100% | 1054.872 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SARAT BARMAN | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
MD GIYAS | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 80 | 14.59 | 84.58% | 15500.16 |  | 0
RUPAK NAYAK | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 28.147 | SQM | 0 | 28.147 | 0% | 0 |  | 0
MD GIYAS | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100% | 25056.0086 |  | 0
MD GIYAS | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
MD GIYAS | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100% | 2119.72 |  | 0
MD GIYAS | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
MD GIYAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100% | 24731.5817 |  | 0
MD GIYAS | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 111.83 | 19.735 | 85% | 21667.2862 |  | 0
RUPAK NAYAK | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 66.0397 | SQM | 0 | 66.0397 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
MD GIYAS | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
MD GIYAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 228.24 | 0 | 100% | 31938.0797 |  | 0
MD GIYAS | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.71 | SQM | 109.71 | 0 | 100% | 21256.5319 |  | 0
MD GIYAS | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100% | 1365.7363 |  | 0
MD GIYAS | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100% | 4780.0771 |  | 0
MD GIYAS | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 99.15 | 0 | 100% | 19210.5108 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 126.99 | SQM | 126.99 | 0 | 100% | 27338.4072 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 44.84 | SQM | 44.84 | 0 | 100% | 9653.1552 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 25.8 | SQM | 25.8 | 0 | 100% | 2777.112 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 66.4 | SQM | 66.4 | 0 | 100% | 14294.592 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 25.8 | SQM | 25.8 | 0 | 100% | 2777.112 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 15 | NOS | 15 | 0 | 100% | 3000 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0.004 | 99.98% | 4299.1416 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | -0.004 | 100% | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0.004 | 100% | 5579.825 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 0 | 345.504 | 0% | 0 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100% | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0.003 | 100% | 25402.3403 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100% | 8648.325 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 0 | 541.249 | 0% | 0 |  | 0
SANTOSH KUMAR | STAIRCASE GRANITE | 215 | 301.392 | 18.16 | SQM | 14.53 | 3.63 | 80.01% | 4379.2258 | 20% | 1094.6557
SANTOSH KUMAR | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
SANTOSH KUMAR | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 0 | 14 | 0% | 0 |  | 0
SANTOSH KUMAR | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 32.94 | 8.23 | 80.01% | 2701.08 | 15% | 506.391
SANTOSH KUMAR | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 82.82 | 20.71 | 80% | 2716.496 | 15% | 509.3676
SANTOSH KUMAR | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 15.66 | 3.91 | 80.02% | 2054.592 | 15% | 385.1376
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 183 | 51.68 | SQM | 41.34 | 10.34 | 79.99% | 7565.22 | 15% | 1418.616
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 45.26 | RMT | 36.21 | 9.05 | 80% | 1781.532 | 15% | 334.0188
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 183 | 43.7 | SQM | 34.96 | 8.74 | 80% | 6397.68 | 15% | 1199.565
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 42.77 | RMT | 34.22 | 8.55 | 80.01% | 1683.624 | 15% | 315.6426
SANTOSH KUMAR | TERRACE FLOOR TILING | 228 | 183 | 2.12 | SQM | 1.7 | 0.42 | 80.19% | 311.1 | 15% | 58.194
SANTOSH KUMAR | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.15 | RMT | 3.32 | 0.83 | 80% | 163.344 | 15% | 30.627
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 3.89 | SQM | 3.11 | 0.78 | 79.95% | 569.13 | 15% | 106.7805
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 8.42 | RMT | 6.74 | 1.68 | 80.05% | 331.608 | 15% | 62.1396
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 183 | 10.19 | SQM | 8.15 | 2.04 | 79.98% | 1491.45 | 15% | 279.7155
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 13.87 | RMT | 11.1 | 2.77 | 80.03% | 546.12 | 15% | 102.3606
SANTOSH KUMAR | CAR PARKING AREA TILING | 234 | 183 | 11.38 | SQM | 9.1 | 2.28 | 79.96% | 1665.3 | 15% | 312.381
SANTOSH KUMAR | FLOOR CHIPPING | 235 | 2.5 | 1068.49 | SFT | 854.79 | 213.7 | 80% | 2136.975 | 15% | 400.6837
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 11.353 | RMT | 11.35 | 0.003 | 99.97% | 62822.25 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 27 | 0 | 100% | 2079 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 89.3 | SFT | 0 | 89.3 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 0 | 15 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SANTOSH KUMAR | WINDOW SILL COPING GRANITE | 292 | 78 | 40.83 | RFT | 40.83 | 0 | 100% | 3184.74 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 1991.25 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 995.625 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 2 | NOS | 2 | 0 | 100% | 2000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
KRIUTTIBAS DAS | CUSTOMISATION COMMODE & SHOWER POINTS SWAP | 531 | 4500 | 1 | NOS | 1 | 0 | 100% | 4500 |  | 0
KRIUTTIBAS DAS | INDIAN COMMODE INSTALLATION | 532 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
SANTOSH KUMAR | BALCONY UPSTAND TOP COPING GRANITE | 547 | 78 | 46.79 | RFT | 46.79 | 0 | 100% | 3649.62 |  | 0
7116.2763

## V136
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100 | 12441.1392 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.27 | MT | 0.27 | 0 | 100 | 1890 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.42 | MT | 0.42 | 0 | 100 | 2940 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.53 | MT | 0.53 | 0 | 100 | 3710 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0.49 | 0 | 100 | 3430 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
MD GIYAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0.13 | 0 | 100 | 1300 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100 | 13653.0576 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100 | 38912.7211 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
MD GIYAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 8.75 | SQM | 8.75 | 0 | 100 | 2637.18 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.47 | MT | 0.47 | 0 | 100 | 3290 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 0.88 | MT | 0.88 | 0 | 100 | 6160 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
MD GIYAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0.15 | 0 | 100 | 1500 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100 | 11826.6221 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100 | 39171.9182 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
MD GIYAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.85 | SQM | 9.85 | 0 | 100 | 2968.7112 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.13 | MT | 0.13 | 0 | 100 | 910 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.19 | MT | 0.19 | 0 | 100 | 1330 | 0 | 0
MD GIYAS | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100 | 7275.6029 | 0 | 0
MD GIYAS | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.5 | SQM | 1.5 | 0 | 100 | 452.088 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100 | 533.25 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 108.15 | 0 | 100 | 20954.2788 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 133.76 | 0 | 100 | 25916.2675 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0 | 100 | 12200.5634 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0 | 0 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0 | 0 | 0 | 0
MD GIYAS | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
MD GIYAS | RCC SURFACE HACKING | 141 | 10.76 | 197 | SQM | 197 | 0 | 100 | 2119.72 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100 | 8373.5309 | 0 | 0
MD GIYAS | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 59.84 | SQM | 50 | 9.84 | 83.556 | 6996.6 | 0 | 0
MD GIYAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 176.74 | SQM | 170 | 6.74 | 96.186 | 23788.44 | 0 | 0
MD GIYAS | GROUND FLOOR EXTERNAL WALL PLASTERING | 149 | 193.752 | 131.565 | SQM | 131.57 | 0 | 100 | 25491.9506 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
MD GIYAS | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 81.65 | SQM | 75 | 6.65 | 91.855 | 10494.9 | 0 | 0
MD GIYAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 228.24 | SQM | 228.24 | 0 | 100 | 31938.0797 | 0 | 0
MD GIYAS | FIRST FLOOR EXTERNAL WALL PLASTERING | 157 | 193.752 | 109.17 | SQM | 109.17 | 0 | 100 | 21151.9058 | 0 | 0
MD GIYAS | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100 | 1365.7363 | 0 | 0
MD GIYAS | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100 | 4780.0771 | 0 | 0
MD GIYAS | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 99.15 | SQM | 99.15 | 0 | 100 | 19210.5108 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 146.6 | SQM | 146.6 | 0 | 100 | 31560.048 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 54.9 | SQM | 54.9 | 0 | 100 | 11818.872 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 36.35 | SQM | 36.35 | 0 | 100 | 3912.714 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 74.58 | SQM | 74.58 | 0 | 100 | 16055.5824 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 36.35 | SQM | 36.35 | 0 | 100 | 3912.714 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100 | 3400 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100 | 4299.1416 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100 | 6003.6536 | 0 | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0 | 100 | 5579.825 | 0 | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 13 | 3 | 81.25
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.81 | RMT | 37.81 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 108.232 | RMT | 108.23 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 34.15 | RMT | 34.15 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.018 | SQM | 51.02 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.42 | RMT | 47.42 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 46.72 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 35.755 | RMT | 35.76 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.7125 | SQM | 2.71 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 3.3 | RMT | 3.3 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 8.92 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 0 | 19.18 | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 5.56 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 15.422 | SQM | 15.42 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.74 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 17.51 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 7.5 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 35.08 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 32.0329 | RMT | 0 | 32.03 | #VALUE!
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 919.5 | 1 | LUMP SUM | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 71.252 | SQM | 71.25 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 71.252 | SQM | 71.25 | 0 | 100
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 71.252 | SQM | 71.25 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 39.22 | SQM | 39.22 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 39.22 | SQM | 39.22 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 432 | 600 | 2 | NOS | 2 | 0 | 100
INDAL SAHNI | CUSTOMIZATION TOILET TILE WORK | 436 | 1185.21 | 8.354 | SQM | 8.35 | 0 | 100
INDAL SAHNI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 251.26 | 14.069 | SQM | 14.07 | 0 | 100
MD GIYAS | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 38.65 | SQM | 38.65 | 0 | 100
MD GIYAS | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 66.8 | SQM | 66.8 | 0 | 100
MD GIYAS | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 28.122 | SQM | 28.12 | 0 | 100

## V137
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100 | 12441.1392 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.27 | MT | 0.27 | 0 | 100 | 1890 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.42 | MT | 0.42 | 0 | 100 | 2940 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.53 | MT | 0.53 | 0 | 100 | 3710 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0.49 | 0 | 100 | 3430 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.13 | MT | 0.13 | 0 | 100 | 910 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100 | 13653.0576 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100 | 38912.7211 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 15.17 | 0 | 100 | 4572.1166 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100 | 1440 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.47 | MT | 0.47 | 0 | 100 | 3290 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 0.88 | MT | 0.88 | 0 | 100 | 6160 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100 | 11826.6221 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100 | 39171.9182 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 16.19 | 0 | 100 | 4879.5365 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100 | 1305 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.13 | MT | 0.13 | 0 | 100 | 910 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.19 | MT | 0.19 | 0 | 100 | 1330 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0.03 | 0 | 100 | 210 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100 | 7275.6029 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 3.5 | 0 | 100 | 1054.872 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100 | 533.25 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100 | 570 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 108.15 | 0 | 100 | 20954.2788 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 133.76 | 0 | 100 | 25916.2675 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0 | 100 | 12200.5634 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0 | 0 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0 | 0 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0 | 0 | 0 | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 141 | 10.76 | 197 | SQM | 197 | 0 | 100 | 2119.72 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100 | 8373.5309 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100 | 24731.5817 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 149 | 193.752 | 131.565 | SQM | 131.57 | 0 | 100 | 25491.9506 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100 | 11425.4478 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 228.24 | SQM | 228.24 | 0 | 100 | 31938.0797 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 157 | 193.752 | 109.17 | SQM | 109.17 | 0 | 100 | 21151.9058 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100 | 1365.7363 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100 | 4780.0771 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 99.15 | SQM | 99.15 | 0 | 100 | 19210.5108 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 147.746 | SQM | 147.75 | 0 | 100 | 31807.62 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 29.65 | SQM | 29.65 | 0 | 100 | 6383.052 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 40.321 | SQM | 40.32 | 0 | 100 | 4340.0448 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 68.478 | SQM | 68.48 | 0 | 100 | 14742.3744 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 40.321 | SQM | 40.32 | 0 | 100 | 4340.0448 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 16 | NOS | 16 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 12 | 4 | 75
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.81 | RMT | 37.81 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 108.232 | RMT | 108.23 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 34.15 | RMT | 34.15 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.018 | SQM | 40.81 | 10.2 | 80
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.42 | RMT | 37.94 | 9.48 | 80
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 37.38 | 9.34 | 80
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 35.755 | RMT | 28.6 | 7.15 | 80
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 2.14 | 0.53 | 80
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 3.74 | 0.93 | 80
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 8.92 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 19.18 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 4.45 | 1.11 | 80
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 6.41 | 4.27 | 60
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 15.422 | SQM | 15.42 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.74 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 17.51 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 7.5 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 35.08 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.564 | SQM | 126.56 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 0.5 | 0.5 | 50
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.85 | RMT | 25.85 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 1 | NOS | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 4190 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100
AAIDHUL MIAH | CUSTOMISATION UTILITY EXTENSION PLASTERING | 522 | 139.93 | 29.477 | SQM | 29.48 | 0 | 100
AAIDHUL MIAH | CUSTOMISATION UTLITY EXTENSION BLOCK WORK | 523 | 193.75 | 14.292 | SQM | 14.29 | 0 | 100

## V138
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
UPASANA CHAUDHARY | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 27468.4363
UPASANA CHAUDHARY | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
UPASANA CHAUDHARY | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
UPASANA CHAUDHARY | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 6000
UPASANA CHAUDHARY | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
UPASANA CHAUDHARY | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100% | 12441.1392 |  | 0 | MANJUNATHA P | 0
UPASANA CHAUDHARY | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | NAGARAJ | 0
UPASANA CHAUDHARY | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | PRAKASH H N | 0
UPASANA CHAUDHARY | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100% | 1510.74 |  | 0 | RAMAKRUSHNA PRADHAN | 0
UPASANA CHAUDHARY | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 0 | 7.95 | 0% | 0 |  | 0 | RUPAK NAYAK | 38350.8134
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 9186.354
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
UPASANA CHAUDHARY | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SAVITA DEVI | 1350
UPASANA CHAUDHARY | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SHOKAT | 0
UPASANA CHAUDHARY | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
UPASANA CHAUDHARY | FOOTING REINFORCEMENT | 23 | 7000 | 0.27 | MT | 0.27 | 0 | 100% | 1890 |  | 0 | SK ANSAR HOSSIAN | 0
UPASANA CHAUDHARY | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.42 | MT | 0.42 | 0 | 100% | 2940 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
UPASANA CHAUDHARY | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.53 | MT | 0.53 | 0 | 100% | 3710 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
UPASANA CHAUDHARY | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0.49 | 0 | 100% | 3430 |  | 0 | SUBHASMITA DAS | 0
UPASANA CHAUDHARY | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.2 | MT | 1.2 | 0 | 100% | 8400 |  | 0 | UDHABHAI R PARMAR | 66065.3958
UPASANA CHAUDHARY | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | V VENKATANARAYANA | 0
UPASANA CHAUDHARY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0 | YELLAPPA C | 0
UPASANA CHAUDHARY | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100% | 8270.1965 |  | 0 | RABIUL MOLLA | 0
UPASANA CHAUDHARY | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | KOUSHIK MANDAL | 0
UPASANA CHAUDHARY | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100% | 17414.4298 |  | 0 | SHEKAR T | 0
UPASANA CHAUDHARY | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0 | TOTAL | 148420.9994
UPASANA CHAUDHARY | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100% | 38912.7211 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 8.16 | SQM | 8.16 | 0 | 100% | 2459.3587 |  | 0
UPASANA CHAUDHARY | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
UPASANA CHAUDHARY | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
UPASANA CHAUDHARY | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
UPASANA CHAUDHARY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0 | 0.96 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.47 | MT | 0.47 | 0 | 100% | 3290 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 0.88 | MT | 0.88 | 0 | 100% | 6160 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 97.15 | SQM | 97.15 | 0 | 100% | 29280.2328 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.16 | SQM | 9.16 | 0 | 100% | 2760.7507 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
UPASANA CHAUDHARY | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0 | 0.87 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR COLUMN REINFORCEMENT | 99 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 102 | 7500 | 0.25 | MT | 0.25 | 0 | 100% | 1875 |  | 0
AAIDHUL MIAH | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 105 | 7500 | 0.04 | MT | 0.04 | 0 | 100% | 300 |  | 0
AAIDHUL MIAH | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100% | 7275.6029 |  | 0
AAIDHUL MIAH | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.59 | SQM | 2.59 | 0 | 100% | 780.6053 |  | 0
AAIDHUL MIAH | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
AAIDHUL MIAH | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 80 | 28.147 | 73.97% | 15500.16 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 120 | 13.756 | 89.72% | 23250.24 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 141 | 10.76 | 197 | SQM | 197 | 0 | 100% | 2119.72 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100% | 24731.5817 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 149 | 193.752 | 177.87 | SQM | 150 | 27.87 | 84.33% | 29062.8 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13500 | 1 | LUMP SUM | 1 | 0 | 100% | 13500 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 258.15 | SQM | 258.15 | 0 | 100% | 36123.4458 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 157 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100% | 24474.7526 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100% | 1365.7363 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100% | 4780.0771 | 100% | 4780.0771
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 117.1 | SQM | 100 | 17.1 | 85.4% | 19375.2 | 100% | 22688.3592
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 146.56 | SQM | 146.56 | 0 | 100% | 31551.4368 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 36.69 | SQM | 36.69 | 0 | 100% | 7898.6232 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 25.51 | SQM | 25.51 | 0 | 100% | 2745.8964 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 71.87 | SQM | 71.87 | 0 | 100% | 15472.1736 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 25.51 | SQM | 25.51 | 0 | 100% | 2745.8964 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0.004 | 99.98% | 4299.1416 | 100% | 4300.0027
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | -0.004 | 100% | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0.004 | 100% | 5579.825 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0.004 | 100% | 11156.886 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100% | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0.003 | 100% | 25402.3403 | 100% | 25402.4857
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100% | 8648.325 | 100% | 8648.325
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | -0.001 | 100% | 14565.0375 |  | 0
ANSAR HOSSAIAN SK | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100% | 5768.6429 |  | 0
SANTOSH KUMAR | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
SANTOSH KUMAR | DOOR OPENING GRANITE | 218 | 350 | 12 | NOS | 11.4 | 0.6 | 95% | 3990 |  | 0
ANSAR HOSSAIAN SK | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.81 | RMT | 35.92 | 1.89 | 95% | 2945.44 |  | 0
ANSAR HOSSAIAN SK | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 108.232 | RMT | 102.82 | 5.412 | 95% | 3372.496 |  | 0
ANSAR HOSSAIAN SK | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 34.15 | RMT | 32.44 | 1.71 | 94.99% | 4256.128 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100% | 3000 |  | 0
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 183 | 51.942 | SQM | 51.94 | 0.002 | 100% | 9505.02 |  | 0
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 46.08 | RMT | 46.08 | 0 | 100% | 2267.136 |  | 0
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 183 | 48.888 | SQM | 48.89 | -0.002 | 100% | 8946.87 | 100% | 8946.504
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 51.914 | RMT | 51.91 | 0.004 | 99.99% | 2553.972 |  | 0
SANTOSH KUMAR | TERRACE FLOOR TILING | 228 | 183 | 4.146 | SQM | 4.15 | -0.004 | 100.1% | 759.45 |  | 0
SANTOSH KUMAR | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.875 | RMT | 4.88 | -0.005 | 100.1% | 240.096 | 100% | 239.85
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 5.986 | SQM | 5.99 | -0.004 | 100.1% | 1096.17 |  | 0
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 10.484 | RMT | 10.48 | 0.004 | 99.96% | 515.616 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 183 | 4.133 | SQM | 4.13 | 0.003 | 99.93% | 755.79 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.484 | RMT | 10.48 | 0.004 | 99.96% | 515.616 |  | 0
SANTOSH KUMAR | CAR PARKING AREA TILING | 234 | 183 | 13.454 | SQM | 13.45 | 0.004 | 99.97% | 2461.35 |  | 0
SANTOSH KUMAR | FLOOR CHIPPING | 235 | 2.5 | 121 | SFT | 0 | 121 | 0% | 0 |  | 0
ANSAR HOSSAIAN SK | FLOOR CHIPPING | 235 | 2.5 | 1164.578 | SFT | 1008.96 | 155.618 | 86.64% | 2522.4 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.74 | -0.004 | 100.1% | 684.42 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.3593 | SQM | 17.36 | -0.00067 | 100% | 3176.88 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.491 | SQM | 7.49 | 0.001 | 99.99% | 1370.67 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 34.782 | SQM | 34.78 | 0.002 | 99.99% | 6364.74 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.121 | SQM | 126.12 | 0.001 | 100% | 8144.8296 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100% | 15500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 6000
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
UDHABHAI R PARMAR | BALCONY & STAIRCASE SS RAILING | 260 | 5528.485 | 32.31 | RMT | 20.36 | 11.95 | 63.01% | 112559.9546 | 36.99% | 66065.3958
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 0 | 3 | 0% | 0 | 100% | 1350
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100% | 1500 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | LIFT ELECTRICAL WORK | 349 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 525 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 262.5 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASH BASIN POINT WORK | 486 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
AAIDHUL MIAH | CUSTOMISATION UTILITY EXTENSION PLASTERING | 522 | 139.93 | 19.676 | SQM | 19.68 | -0.004 | 100% | 2753.8224 |  | 0
AAIDHUL MIAH | CUSTOMISATION UTLITY EXTENSION BLOCK WORK | 523 | 193.75 | 9.54 | SQM | 9.54 | 0 | 100% | 1848.375 |  | 0
148420.9994

## V139
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 58 | SQM | 58 | 0 | 100% | 2494 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100% | 12441.1392 |  | 0 | NAGARAJ | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0 | PRAKASH H N | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 31.26 | SQM | 31.26 | 0 | 100% | 1344.18 |  | 0 | RAMAKRUSHNA PRADHAN | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | RUPAK NAYAK | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100% | 1510.74 |  | 0 | SANTOSH KUMAR | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100% | 2952.81 |  | 0 | SARAT BARMAN | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SAVITA DEVI | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SHOKAT | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SK ANSAR HOSSIAN | 376.3212
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
NARESH PURTY | FOOTING REINFORCEMENT | 23 | 6800 | 0.27 | MT | 0.27 | 0 | 100% | 1836 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
NARESH PURTY | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.42 | MT | 0.42 | 0 | 100% | 2856 |  | 0 | SUBHASMITA DAS | 0
NARESH PURTY | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.53 | MT | 0.53 | 0 | 100% | 3604 |  | 0 | UDHABHAI R PARMAR | 0
NARESH PURTY | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.49 | MT | 0.49 | 0 | 100% | 3332 |  | 0 | V VENKATANARAYANA | 0
NARESH PURTY | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 1.2 | MT | 1.2 | 0 | 100% | 8160 |  | 0 | YELLAPPA C | 0
NARESH PURTY | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 6800 | 0.18 | MT | 0.18 | 0 | 100% | 1224 |  | 0 | RABIUL MOLLA | 0
NARESH PURTY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 6800 | 0.13 | MT | 0.13 | 0 | 100% | 884 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100% | 8270.1965 |  | 0 | SHEKAR T | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | TOTAL | 376.3212
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100% | 17414.4298 |  | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100% | 38912.7211 |  | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 0 | 15.17 | 0% | 0 |  | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100% | 1440 |  | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
NARESH PURTY | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 6800 | 0.47 | MT | 0.47 | 0 | 100% | 3196 |  | 0
NARESH PURTY | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 6800 | 0.88 | MT | 0.88 | 0 | 100% | 5984 |  | 0
NARESH PURTY | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 6800 | 0.18 | MT | 0.18 | 0 | 100% | 1224 |  | 0
NARESH PURTY | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 6800 | 0.15 | MT | 0.15 | 0 | 100% | 1020 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 127.9 | 2.07 | 98.41% | 38548.0368 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 0 | 12.27 | 0% | 0 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 0 | 16.19 | 0% | 0 |  | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100% | 1305 |  | 0
NARESH PURTY | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 6800 | 0.13 | MT | 0.13 | 0 | 100% | 884 |  | 0
NARESH PURTY | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 6800 | 0.19 | MT | 0.19 | 0 | 100% | 1292 |  | 0
NARESH PURTY | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 6800 | 0.029 | MT | 0.03 | -0.001 | 103.4% | 204 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100% | 7275.6029 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 0 | 3.5 | 0% | 0 |  | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100% | 570 |  | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 83.61 | 24.537 | 77.31% | 16199.6047 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 126.92 | 6.836 | 94.89% | 24591.0038 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 30.1 | 0 | 100% | 1974.56 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 13.8 | 53.09 | 20.63% | 905.28 |  | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 18.673 | SQM | 18.67 | 0.003 | 99.98% | 3014.4582 |  | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 255.5 | SQM | 255.5 | 0 | 100% | 8942.5 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 348.5 | SQM | 348.5 | 0 | 100% | 2813.4405 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100% | 24731.5817 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 177.87 | 0 | 100% | 34462.6682 |  | 0
SALLAUDDIN ANSARI | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 0.91667 | LUMP SUM | 0.92 | -0.0033334 | 100.4% | 11040 |  | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 0.083333 | LUMP SUM | 0.08 | 0.0033334 | 96% | 960 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 185.58 | 72.57 | 71.89% | 25968.5806 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100% | 24474.7526 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 4.74 | 5.02 | 48.57% | 663.2777 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 26.08 | 91.02 | 22.27% | 5053.0522 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 19.98 | SQM | 19.98 | 0 | 100% | 4301.2944 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 61.97 | SQM | 61.97 | 0 | 100% | 6003.4057 |  | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 117.5 | SQM | 117.5 | 0 | 100% | 5691.465 |  | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 104.234 | SQM | 104.23 | 0.004 | 100% | 5048.6927 |  | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 106.963 | SQM | 106.96 | 0.003 | 100% | 5180.9285 |  | 0
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.5 | 176.74 | SQM | 176.74 | 0 | 100% | 16171.71 |  | 0
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.5 | 59.84 | SQM | 59.84 | 0 | 100% | 5475.36 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.5 | 258.15 | SQM | 179.25 | 78.9 | 69.44% | 16401.375 |  | 0
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.5 | 81.65 | SQM | 57.63 | 24.02 | 70.58% | 5273.145 |  | 0
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.5 | 34.16 | SQM | 0 | 34.16 | 0% | 0 |  | 0
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.5 | 9.76 | SQM | 0 | 9.76 | 0% | 0 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100% | 5768.6429 |  | 0
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100% | 900 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100% | 5600 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.16 | RMT | 41.16 | 0 | 100% | 3375.12 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.781 | RMT | 98.78 | 0.001 | 100% | 3239.984 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 26.83 | 0 | 100% | 3520.096 |  | 0
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100% | 0 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.41 | SQM | 49.52 | 1.89 | 96.32% | 0 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TILING | 224 | 183 | 51.41 | SQM | 49.52 | 1.89 | 96.32% | 0 | 4% | 376.3212
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 62.858 | RMT | 62.86 | -0.002 | 100% | 3092.712 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 46.72 | 0.003 | 99.99% | 8549.76 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 56.845 | RMT | 56.85 | -0.005 | 100% | 2797.02 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 2.67 | 0 | 100% | 488.61 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 4.67 | 0 | 100% | 229.764 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 8.92 | 0 | 100% | 1632.36 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 19.18 | 0 | 100% | 943.656 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 5.56 | -0.001 | 100% | 1017.48 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | 0.004 | 99.96% | 525.456 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 15.42 | SQM | 15.42 | 0 | 100% | 2821.86 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100% | 2712.5 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.8 | SQM | 3.8 | 0 | 100% | 695.4 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 17.51 | -0.005 | 100% | 3204.33 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 7.5 | -0.005 | 100.1% | 1372.5 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 35.08 | 0.002 | 99.99% | 6419.64 |  | 0
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 189.15 | SQM | 189.15 | 0 | 100% | 5090.0265 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
ANU P | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
ANU P | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
ANU P | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
ANU P | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
ANU P | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 17.37 | RMT | 0 | 17.37 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 1.56 | RMT | 1.56 | 0 | 100% | 7728.24 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100% | 1350 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 60 | RFT | 60 | 0 | 100% | 2040 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 10 | RFT | 10 | 0 | 100% | 770 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 106 | SFT | 106 | 0 | 100% | 2438 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 10 | RFT | 10 | 0 | 100% | 1510 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
SUBRAMANI | SSM & COPING CONCRETE WORK | 345 | 788.09 | 13.14 | CUM | 13.14 | 0 | 100% | 10355.5026 |  | 0
376.3212

## V140
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 58.5 | SQM | 58.5 | 0 | 100 | 2515.5 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100 | 12441.1392 | 0 | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100 | 2500 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 31.26 | SQM | 31.26 | 0 | 100 | 1344.18 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100 | 2952.81 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
NARESH PURTY | FOOTING REINFORCEMENT | 23 | 6800 | 0.27 | MT | 0.27 | 0 | 100 | 1836 | 0 | 0
NARESH PURTY | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.42 | MT | 0.42 | 0 | 100 | 2856 | 0 | 0
NARESH PURTY | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.53 | MT | 0.53 | 0 | 100 | 3604 | 0 | 0
NARESH PURTY | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.49 | MT | 0.49 | 0 | 100 | 3332 | 0 | 0
NARESH PURTY | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 1.2 | MT | 1.2 | 0 | 100 | 8160 | 0 | 0
NARESH PURTY | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 6800 | 0.18 | MT | 0.18 | 0 | 100 | 1224 | 0 | 0
NARESH PURTY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 6800 | 0.13 | MT | 0.13 | 0 | 100 | 884 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100 | 13653.0576 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100 | 38912.7211 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 10.15 | 2.12 | 82.729 | 3059.1288 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 0 | 15.17 | 0 | 0 | 0 | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100 | 1440 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
NARESH PURTY | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 6800 | 0.47 | MT | 0.47 | 0 | 100 | 3196 | 0 | 0
NARESH PURTY | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 6800 | 0.88 | MT | 0.88 | 0 | 100 | 5984 | 0 | 0
NARESH PURTY | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 6800 | 0.18 | MT | 0.18 | 0 | 100 | 1224 | 0 | 0
NARESH PURTY | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 6800 | 0.15 | MT | 0.15 | 0 | 100 | 1020 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100 | 11826.6221 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100 | 39171.9182 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 0 | 16.19 | 0 | 0 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100 | 1305 | 0 | 0
NARESH PURTY | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 6800 | 0.13 | MT | 0.13 | 0 | 100 | 884 | 0 | 0
NARESH PURTY | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 6800 | 0.19 | MT | 0.19 | 0 | 100 | 1292 | 0 | 0
NARESH PURTY | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 6800 | 0.029 | MT | 0.03 | 0 | 100 | 204 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100 | 7275.6029 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 0 | 3.5 | 0 | 0 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100 | 533.25 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100 | 570 | 0 | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 83.61 | 24.53 | 77.313 | 16199.6047 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 126.92 | 6.84 | 94.889 | 24591.0038 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0 | 100 | 12200.5634 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 20.5 | 9.6 | 68.106 | 1344.8 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 62.8 | 4.09 | 93.893 | 4119.68 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 18.673 | SQM | 18.67 | 0 | 100 | 3014.4582 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 255.5 | SQM | 255.5 | 0 | 100 | 8942.5 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 348.5 | SQM | 348.5 | 0 | 100 | 2813.4405 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100 | 8373.5309 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100 | 24731.5817 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 177.87 | 0 | 100 | 34462.6682 | 0 | 0
SALLAUDDIN ANSARI | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 0.875 | LUMP SUM | 0.88 | 0 | 100 | 10560 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 0.125 | LUMP SUM | 0.13 | 0 | 100 | 1560 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100 | 11425.4478 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 258.15 | 0 | 100 | 36123.4458 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100 | 24474.7526 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 8.92 | 0.84 | 91.38 | 1248.1934 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 5.1 | 29.06 | 14.915 | 713.6532 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 31.37 | 85.73 | 26.789 | 6078.0002 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 19.98 | SQM | 19.98 | 0 | 100 | 4301.2944 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 61.97 | SQM | 61.97 | 0 | 100 | 6003.4057 | 0 | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 117.5 | SQM | 117.5 | 0 | 100 | 5691.465 | 0 | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 104.234 | SQM | 104.23 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 106.963 | SQM | 106.96 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.5 | 176.74 | SQM | 176.74 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.5 | 59.84 | SQM | 59.84 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.5 | 258.15 | SQM | 258.15 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.5 | 81.65 | SQM | 81.65 | 0 | 99.999
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.5 | 34.16 | SQM | 34.16 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.5 | 9.76 | SQM | 9.76 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.16 | RMT | 41.16 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.781 | RMT | 98.78 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 26.83 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 172.224 | 51.018 | SQM | 22.21 | 28.81 | 43.534
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 62.858 | RMT | 21.04 | 41.82 | 33.472
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 0 | 46.72 | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 56.845 | RMT | 0 | 56.85 | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 0 | 2.67 | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 0 | 4.67 | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 8.92 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 19.18 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 5.56 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 15.42 | SQM | 15.42 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.8 | SQM | 3.8 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 17.51 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 7.2 | 0.3 | 95.997
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 32.08 | 3 | 91.449
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 189.15 | SQM | 189.15 | 0 | 100
H R ENGINEERS | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 0.5 | LUMP SUM | 0.5 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 0.5 | LUMP SUM | 0.5 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
ANU P | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
ANU P | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
ANU P | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
ANU P | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
ANU P | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 17.37 | RMT | 0 | 17.37 | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 60 | RFT | 60 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 10 | RFT | 10 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 106 | SFT | 106 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 10 | RFT | 10 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
RUPAK NAYAK | GROUND FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 379 | 16.146 | 183.89 | SQM | 183.89 | 0 | 100
RUPAK NAYAK | FIRST FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 380 | 16.146 | 110.81 | SQM | 110.81 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 381 | 16.146 | 128.79 | SQM | 128.79 | 0 | 100

## V141
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100% | 12441.1392 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100% | 1510.74 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100% | 2952.81 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SAVITA DEVI | 1350
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SHOKAT | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0 | YELLAPPA C | 0
BHASKAR | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100% | 7980.8602 |  | 0 | RABIUL MOLLA | 0
BHASKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | KOUSHIK MANDAL | 0
BHASKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100% | 16492.1702 |  | 0 | SHEKAR T | 0
MANJUNATHA R | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0 | TOTAL | 1350
MANJUNATHA R | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100% | 38912.7211 |  | 0
MANJUNATHA R | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
MANJUNATHA R | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.25 | SQM | 9.25 | 0 | 100% | 2787.876 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100% | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 107.8 | SQM | 107.8 | 0 | 100% | 32490.0576 |  | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
MANJUNATHA R | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | -0.005 | 100.1% | 2959.6694 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.83 | CUM | 0.83 | 0 | 100% | 2490 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100% | 7275.6029 |  | 0
MANJUNATHA R | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100% | 569.6309 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 2000 | 2.37 | CUM | 2.37 | 0 | 100% | 4740 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.17 | CUM | 0.17 | 0 | 100% | 510 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 94.59 | 0 | 100% | 18327.0017 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100% | 25056.0086 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100% | 2119.72 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100% | 24731.5817 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 110 | 21.565 | 83.61% | 21312.72 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 228.24 | 0 | 100% | 31938.0797 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.17 | SQM | 109.17 | 0 | 100% | 21151.9058 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100% | 1365.7363 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100% | 4780.0771 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 99.15 | 0 | 100% | 19210.5108 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 144.13 | SQM | 144.13 | 0 | 100% | 31028.3064 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 52.49 | SQM | 52.49 | 0 | 100% | 11300.0472 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 31.07 | SQM | 31.07 | 0 | 100% | 3344.3748 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 72.85 | SQM | 72.85 | 0 | 100% | 15683.148 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 21 | SQM | 21 | 0 | 100% | 2260.44 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 20 | NOS | 20 | 0 | 100% | 4000 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0.004 | 99.98% | 4299.1416 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | -0.004 | 100% | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0.004 | 100% | 5579.825 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0.004 | 100% | 11156.886 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100% | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0.003 | 100% | 25402.3403 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100% | 8648.325 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | -0.001 | 100% | 14565.0375 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 18.18 | 0.96 | 94.98% | 5479.3066 |  | 0
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 11 | 4 | 73.33% | 3850 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.81 | RMT | 35.92 | 1.89 | 95% | 2945.44 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 108.232 | RMT | 102.82 | 5.412 | 95% | 3372.496 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 34.15 | RMT | 32.44 | 1.71 | 94.99% | 4256.128 |  | 0
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0% | 0 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.942 | SQM | 49.34 | 2.602 | 94.99% | 9029.22 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 46.08 | RMT | 43.78 | 2.3 | 95.01% | 2153.976 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 43.864 | SQM | 41.67 | 2.194 | 95% | 7625.61 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 44.126 | RMT | 41.92 | 2.206 | 95% | 2062.464 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 4.146 | SQM | 3.94 | 0.206 | 95.03% | 721.02 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.875 | RMT | 4.63 | 0.245 | 94.97% | 227.796 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 5.986 | SQM | 0 | 5.986 | 0% | 0 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 13 | RMT | 0 | 13 | 0% | 0 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 13.369 | SQM | 12.7 | 0.669 | 95% | 2324.1 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 21.172 | RMT | 20.11 | 1.062 | 94.98% | 989.412 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 13.454 | SQM | 12.78 | 0.674 | 94.99% | 2338.74 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1129.96 | SFT | 1073.46 | 56.5 | 95% | 2683.65 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.55 | 0.186 | 95.02% | 649.65 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.3593 | SQM | 16.49 | 0.86933 | 94.99% | 3017.67 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.238 | SQM | 7.83 | 0.408 | 95.05% | 1432.89 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 36.245 | SQM | 34.43 | 1.815 | 94.99% | 6300.69 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.121 | SQM | 126.12 | 0.001 | 100% | 8144.8296 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100% | 15500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 28.375 | RMT | 28.38 | -0.005 | 100% | 157083.3 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 0 | 3 | 0% | 0 | 100% | 1350
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 9200 | 1 | LUMP SUM | 1 | 0 | 100% | 9200 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 0.5 | 0.5 | 50% | 500 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 2 | NOS | 1 | 1 | 50% | 1000 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 2450 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 1225 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.16 | CUM | 4.16 | 0 | 100% | 936 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100% | 250 |  | 0
1350

## V142
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100 | 12441.1392 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100 | 975 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100 | 13653.0576 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100 | 38912.7211 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 0 | 15.17 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100 | 1440 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100 | 3525 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100 | 6600 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100 | 11826.6221 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100 | 39171.9182 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 3.74 | 8.53 | 30.505 | 1127.2061 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 0 | 16.19 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100 | 1305 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100 | 975 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100 | 1425 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100 | 7275.6029 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 0 | 3.5 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100 | 533.25 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100 | 570 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 108.15 | 0 | 100 | 20954.2788 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 133.76 | 0 | 100 | 25916.2675 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0 | 100 | 12200.5634 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 30.1 | 0 | 100 | 1974.56 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 66.89 | 0 | 100 | 4387.984 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0.5 | 0 | 100 | 80.73 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100 | 2119.72 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100 | 8373.5309 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100 | 24731.5817 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 177.87 | 0 | 100 | 34462.6682 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100 | 11425.4478 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 258.15 | 0 | 100 | 36123.4458 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100 | 24474.7526 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100 | 1365.7363 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100 | 4780.0771 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 117.1 | 0 | 100 | 22688.3592 | 0 | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 31.122 | SQM | 31.12 | 0 | 100 | 13399.0272 | 0 | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 83.426 | SQM | 83.43 | 0 | 100 | 35921.6208 | 0 | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 7.897 | SQM | 7.9 | 0 | 100 | 1700.712 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 14.96 | SQM | 14.96 | 0 | 100 | 3220.5888 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 19 | NOS | 19 | 0 | 100 | 3800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100 | 4299.1416 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 61.966 | SQM | 61.97 | 0 | 100 | 6003.4057 | 0 | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 164.391 | SQM | 164.39 | 0 | 100
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 104.234 | SQM | 104.23 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 76.8785 | SQM | 76.88 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 145.1194 | SQM | 145.12 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 59.84 | SQM | 59.84 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 218.6243 | SQM | 218.62 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 81.65 | SQM | 81.65 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 26.2549 | SQM | 26.25 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 9.76 | SQM | 9.76 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 1 | 1 | 50
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 40.76 | RMT | 40.76 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 122.28 | RMT | 122.28 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 34.15 | RMT | 34.15 | 0 | 100
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 51.018 | SQM | 51.02 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 62.858 | RMT | 62.86 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 46.72 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 56.845 | RMT | 56.85 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 2.67 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 4.67 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 182.988 | 3.7161 | SQM | 3.72 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 19.18 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 5.56 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 15.42 | SQM | 15.42 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.74 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 17.51 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 7.5 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 35.08 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.121 | SQM | 126.12 | 0 | 100
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 189.15 | SQM | 189.15 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 22.5 | RMT | 22.5 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 52 | 52 | RFT | 52 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 92 | 16.417 | RFT | 16.42 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 42 | 45 | SFT | 45 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 250 | 11 | RFT | 11 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
KRISHNAKUMAR SAHANI | SILL GRANITE | 289 | 75 | 91 | RFT | 91 | 0 | 100
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 810 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION TERRACE WASHING MACHINE TAP POINT WORK | 504 | 1500 | 1 | NOS | 1 | 0 | 100
AAIDHUL MIAH | CUSTOMISATION UTILITY EXTENSION PLASTERING | 522 | 139.93 | 19.68 | SQM | 19.68 | 0 | 100
AAIDHUL MIAH | CUSTOMISATION UTLITY EXTENSION BLOCK WORK | 523 | 193.75 | 9.54 | SQM | 9.54 | 0 | 100

## V143
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100 | 975 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100 | 13653.0576 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100 | 38912.7211 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 0 | 15.17 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100 | 1440 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100 | 3525 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100 | 6600 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100 | 11826.6221 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100 | 39171.9182 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 2.24 | 10.03 | 18.255 | 675.1181 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 0 | 16.19 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100 | 1305 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100 | 975 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100 | 1425 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100 | 7275.6029 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 0 | 3.5 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100 | 533.25 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100 | 570 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 108.15 | 0 | 100 | 20954.2788 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 133.76 | 0 | 100 | 25916.2675 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0 | 100 | 12200.5634 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 30.1 | 0 | 100 | 1974.56 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 66.89 | 0 | 100 | 4387.984 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0.5 | 0 | 100 | 80.73 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100 | 2119.72 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100 | 8373.5309 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100 | 24731.5817 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 177.87 | 0 | 100 | 34462.6682 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100 | 11425.4478 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 258.15 | 0 | 100 | 36123.4458 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100 | 24474.7526 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100 | 1365.7363 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100 | 4780.0771 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 117.1 | 0 | 100 | 22688.3592 | 0 | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 31.122 | SQM | 31.12 | 0 | 100 | 13399.0272 | 0 | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 83.426 | SQM | 83.43 | 0 | 100 | 35921.6208 | 0 | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 7.897 | SQM | 7.9 | 0 | 100 | 1700.712 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 14.96 | SQM | 14.96 | 0 | 100 | 3220.5888 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 19 | NOS | 19 | 0 | 100 | 3800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100 | 4299.1416 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 61.966 | SQM | 61.97 | 0 | 100 | 6003.4057 | 0 | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 164.391 | SQM | 164.39 | 0 | 100 | 7962.7228 | 0 | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 104.234 | SQM | 104.23 | 0 | 100 | 5048.6927 | 0 | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 76.8785 | SQM | 76.88 | 0 | 100 | 3723.9134 | 0 | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100 | 937.8305 | 0 | 0
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 145.1194 | SQM | 145.12 | 0 | 100 | 13277.6093 | 0 | 0
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 59.84 | SQM | 59.84 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 218.6243 | SQM | 218.62 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 81.65 | SQM | 81.65 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 26.2549 | SQM | 26.25 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 9.76 | SQM | 9.76 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 0 | 2 | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 40.76 | RMT | 40.76 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 122.28 | RMT | 122.28 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 34.15 | RMT | 34.15 | 0 | 100
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 51.018 | SQM | 51.02 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 62.858 | RMT | 62.86 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 46.72 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 56.845 | RMT | 56.85 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 2.67 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 4.67 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 8.92 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 19.18 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 5.56 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 15.42 | SQM | 15.42 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.74 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 17.51 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 7.5 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 35.08 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.121 | SQM | 126.12 | 0 | 100
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 189.15 | SQM | 189.15 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 22.5 | RMT | 22.5 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 52 | 52 | RFT | 52 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 92 | 16.417 | RFT | 16.42 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 42 | 45 | SFT | 45 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 250 | 11 | RFT | 11 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
KRISHNAKUMAR SAHANI | SILL GRANITE | 289 | 75 | 61 | RFT | 61 | 0 | 100
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 5600 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY TAP POINT WORK | 448 | 750 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION TERRACE WASHING MACHINE TAP POINT WORK | 504 | 1500 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 529 | 1000 | 1 | NOS | 1 | 0 | 100

## V145
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100 | 12441.1392 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100 | 975 | 0 | 0
SARAT BARMAN | UTILITY PLINTH BEAM REINFORCEMENT | 39 | 7500 | 0.066 | KG | 0.07 | 0 | 100 | 525 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100 | 13653.0576 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100 | 38912.7211 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 2.17 | 10.1 | 17.702 | 654.0206 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 0 | 15.17 | 0 | 0 | 0 | 0
NAGARAJ | UTILITY PLINTH BEAM SHUTTERING | 49 | 28 | 54 | SFT | 54 | 0 | 100 | 1512 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100 | 1440 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100 | 3525 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100 | 6600 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100 | 11826.6221 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100 | 39171.9182 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 0 | 16.19 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100 | 1305 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100 | 975 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100 | 1425 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100 | 7275.6029 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 0 | 3.5 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100 | 533.25 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100 | 570 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 108.15 | 0 | 100 | 20954.2788 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 133.76 | 0 | 100 | 25916.2675 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.97 | 0 | 0 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 30.1 | 0 | 100 | 1974.56 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 66.89 | 0 | 100 | 4387.984 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 18.673 | SQM | 0 | 18.67 | 0 | 0 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 255.5 | SQM | 255.5 | 0 | 100 | 8942.5 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 348.5 | SQM | 348.5 | 0 | 100 | 2813.4405 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100 | 8373.5309 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 138 | 38.74 | 78.081 | 19310.616 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 110 | 67.87 | 61.843 | 21312.72 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100 | 11425.4478 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 258.15 | 0 | 100 | 36123.4458 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100 | 24474.7526 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0 | 0 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0 | 0 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 117.1 | 0 | 100 | 22688.3592 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 31.122 | SQM | 31.12 | 0 | 100 | 13399.0272 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 83.426 | SQM | 83.43 | 0 | 100 | 35921.6208 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 7.897 | SQM | 7.9 | 0 | 100 | 1700.712 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 14.96 | SQM | 14.96 | 0 | 100 | 3220.5888 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 19 | NOS | 19 | 0 | 100 | 3800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 103.091 | SQM | 103.09 | 0 | 100 | 22193.2152 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100 | 6003.6536 | 0 | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 221 | 124.5 | 63.965
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 40.76 | RMT | 40.76 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 122.28 | RMT | 122.28 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 29.59 | RMT | 29.59 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.018 | SQM | 51.01 | 0 | 99.993
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 62.858 | RMT | 62.86 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 46.72 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 56.845 | RMT | 56.85 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 2.67 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 4.67 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 8.92 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 19.18 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 5.56 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 13.6 | SQM | 13.6 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.502 | SQM | 3.5 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 13.395 | SQM | 13.4 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.148 | SQM | 7.15 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 29.614 | SQM | 29.61 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.121 | SQM | 126.12 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 24.93 | RMT | 24.93 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
CHIRANJEEVI | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 1 | NOS | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 100 | RFT | 100 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 27 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 249 | SFT | 249 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 15 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
NAGARAJ | ADDITIONAL SHUTTERING WORK OF LINTEL AND CHEJJA | 308 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | PAINT REWORK IN VILLAS AFTER WALL CRACK TREATMENT | 369 | 3060 | 1 | LUMP SUM | 1 | 0 | 100

## V144
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100 | 975 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100 | 13653.0576 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100 | 38912.7211 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 15.17 | 0 | 100 | 4572.1166 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100 | 1440 | 0 | 0
CHIRANJEEVI | ALL FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 66 | 3000 | 1.59 | CUM | 1.59 | 0 | 100 | 4770 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100 | 3525 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100 | 6600 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100 | 11826.6221 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100 | 39171.9182 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 16.19 | 0 | 100 | 4879.5365 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100 | 1305 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100 | 975 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100 | 1425 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100 | 7275.6029 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 3.5 | 0 | 100 | 1054.872 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100 | 533.25 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100 | 570 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 93.0881 | SQM | 93.09 | 0 | 100 | 18036.3737 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 130.8211 | SQM | 130.82 | 0 | 100 | 25346.6366 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0 | 100 | 12200.5634 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 43.9 | RMT | 43.9 | 0 | 100 | 2879.84 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 18.67 | SQM | 18.67 | 0 | 100 | 3014.4582 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 10.76 | 348.4 | SQM | 348.4 | 0 | 100 | 3748.784 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100 | 8373.5309 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 152.6917 | SQM | 152.69 | 0 | 100 | 21366.2171 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 150.536 | SQM | 150.54 | 0 | 100 | 29167.4261 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 76.63 | SQM | 76.63 | 0 | 100 | 10722.9892 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 202.0372 | SQM | 202.04 | 0 | 100 | 28271.8613 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100 | 24474.7526 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100 | 1365.7363 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100 | 4780.0771 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 53.384 | SQM | 53.38 | 0 | 100 | 10342.4818 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 108.197 | SQM | 108.2 | 0 | 100 | 23293.296 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 39.57 | SQM | 39.57 | 0 | 100 | 8518.6296 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 27.528 | SQM | 27.53 | 0 | 100 | 2963.3292 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 76.097 | SQM | 76.1 | 0 | 100 | 16382.808 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 27.528 | SQM | 27.53 | 0 | 100 | 2963.3292 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100 | 3400 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100 | 4299.1416 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100 | 6003.6536 | 0 | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0 | 100 | 5579.825 | 0 | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0 | 100 | 11156.886 | 0 | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100 | 937.8305 | 0 | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0 | 100 | 25402.3403 | 0 | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 12.8 | 3.2 | 80
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.81 | RMT | 37.81 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 108.232 | RMT | 108.23 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 34.15 | RMT | 34.15 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.018 | SQM | 51.02 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.42 | RMT | 47.42 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 46.72 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 35.755 | RMT | 35.76 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 2.67 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 4.67 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 0 | 8.92 | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 0 | 19.18 | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 3.34 | 2.22 | 60
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 6.41 | 4.27 | 60
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 15.422 | SQM | 15.42 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.74 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 17.51 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 7.5 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 35.08 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.564 | SQM | 126.56 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 29.39 | RMT | 29.39 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
INDAL SAHNI | SILL GRANITE | 289 | 75 | 30 | RFT | 0 | 30 | 0
YELLAPPA C | ADDITIONAL SHUTTERING WORK | 301 | 301.392 | 102.0996 | SFT | 102.1 | 0 | 100
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 0 | 1 | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 6800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 0 | 1 | 0

## V146
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 29.53 | 39.14 | 43 | 1594.62 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100 | 2562.7392 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100 | 9878.4 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100 | 630.74 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0 | 0 | 0 | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100 | 1121.904 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 0 | 1.2 | 0 | 0 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.14 | 0.04 | 80 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100 | 8550.9216 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100 | 8321.6484 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100 | 17670.1824 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 0 | 3.26 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 0 | 15.33 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0 | 0.96 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0 | 0.47 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0 | 0.88 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 0 | 2.21 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0 | 0.87 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0 | 0.38 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0 | 0 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 0 | 108.15 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 0 | 133.76 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.97 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 0 | 197 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 0 | 59.84 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 0 | 176.74 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 0 | 177.87 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 0 | 258.15 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 0 | 126.32 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 0 | 117.1 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V147
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 0 | 68.67 | 0 | 0 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100 | 2562.7392 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100 | 9878.4 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100 | 630.74 | 0 | 0
MANJUNATHA P | BASE FLOOR EARTH DRESSING | 14 | 22 | 40 | SQM | 40 | 0 | 100 | 880 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0 | 0 | 0 | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100 | 1121.904 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 5.49 | 1.37 | 80 | 5490 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 0 | 1.2 | 0 | 0 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.14 | 0.04 | 80 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100 | 8550.9216 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100 | 8321.6484 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100 | 17670.1824 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 0 | 3.26 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 0 | 15.33 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0 | 0.96 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0 | 0.47 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0 | 0.88 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 0 | 2.21 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0 | 0.87 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0 | 0.38 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0 | 0 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 0 | 108.15 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 0 | 133.76 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.97 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 0 | 197 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 0 | 59.84 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 0 | 176.74 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 0 | 177.87 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 0 | 258.15 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 0 | 126.32 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0 | 0 | 0 | 0
SAI GANESH GROUP OF INFRASTRUCTURES | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 0 | 117.1 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V148
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | NAGARAJ | 3169.4598
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SARAT BARMAN | 2800
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 5.84 | 1.027 | 85.04% | 5840 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SHOKAT | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0% | 0 | 100% | 1300 | UDHABHAI R PARMAR | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 | V VENKATANARAYANA | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 | YELLAPPA C | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0 | TOTAL | 5969.4598
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 9.25 | 0.0005 | 99.99% | 2987.01 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.24 | 0.23 | 51.06% | 1800 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0% | 0 | 100% | 1500
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100% | 34810.776 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.815 | 0% | 0 | 100% | 3169.4598
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0% | 0 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 108.15 | -0.003 | 100% | 20954.2788 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 66.88 | 66.876 | 50% | 12958.1338 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.973 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
5969.4598

## V149
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | EBI ABRAHAM | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | KRIUTTIBAS DAS | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100% | 9878.4 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SARAT BARMAN | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SHOKAT | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 0 | 1.2 | 0% | 0 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0 | SUBHASMITA DAS | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 | UDHABHAI R PARMAR | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 | V VENKATANARAYANA | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | YELLAPPA C | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 0 | 45.3 | 0% | 0 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 0 | 129.11 | 0% | 0 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0% | 0 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.2505 | 0% | 0 |  | 0 | TOTAL | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 0 | 3.26 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 0 | 15.33 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 0 | 1.57 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0 | 0.47 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0 | 0.88 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.815 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 0 | 2.21 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0% | 0 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0% | 0 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 4 | LUMP SUM | 0 | 4 | 0% | 0 |  | 0
0

## V150
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 2000
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100% | 12441.1392 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | NAGARAJ | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | PRAKASH H N | 600
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100% | 1510.74 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 0 | 7.95 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 5500 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 3000 | SARAT BARMAN | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SAVITA DEVI | 1350
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SHOKAT | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.27 | MT | 0.27 | 0 | 100% | 1890 |  | 0 | SK ANSAR HOSSIAN | 950.5386
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.42 | MT | 0.42 | 0 | 100% | 2940 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.53 | MT | 0.53 | 0 | 100% | 3710 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0.49 | 0 | 100% | 3430 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.2 | MT | 1.2 | 0 | 100% | 8400 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | V VENKATANARAYANA | 8500
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0 | YELLAPPA C | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 36 | 10000 | 0.13 | MT | 0.13 | 0 | 100% | 1300 |  | 0 | RABIUL MOLLA | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100% | 8270.1965 |  | 0 | KOUSHIK MANDAL | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | SHEKAR T | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100% | 17414.4298 |  | 0 | TOTAL | 13400.5386
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100% | 38912.7211 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 0 | 15.17 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.17 | SQM | 9.17 | 0 | 100% | 2763.7646 |  | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 6 | SQM | 6 | 0 | 100% | 1808.352 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0 | 0.96 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 64 | 1500 | 0.96 | CUM | 0.96 | 0 | 100% | 1440 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.47 | MT | 0.47 | 0 | 100% | 3290 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 0.88 | MT | 0.88 | 0 | 100% | 6160 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 83 | 10000 | 0.15 | MT | 0.15 | 0 | 100% | 1500 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100% | 39171.9182 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 0 | 16.19 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.17 | SQM | 9.17 | 0 | 100% | 2763.7646 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 7.02 | SQM | 7.02 | 0 | 100% | 2115.7718 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0 | 0.87 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 94 | 1500 | 0.87 | CUM | 0.87 | 0 | 100% | 1305 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.19 | MT | 0 | 0.19 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 105 | 7000 | 0.029 | MT | 0.03 | -0.001 | 103.4% | 210 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 0 | 10.8 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 0 | 24.14 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 0 | 3.5 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.57 | SQM | 1.57 | 0 | 100% | 473.1854 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.93 | SQM | 1.93 | 0 | 100% | 581.6866 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0 | 0.38 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 114 | 671 | 0.38 | CUM | 0.38 | 0 | 100% | 254.98 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 0 | 108.147 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 89.86 | 4.73 | 95% | 17410.5547 |  | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 0 | 133.756 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 120 | 9.32 | 92.79% | 23250.24 |  | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.973 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 0 | 197 | 0% | 0 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100% | 2119.72 |  | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 0 | 59.84 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 0 | 176.74 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 141.39 | 35.35 | 80% | 19784.9855 |  | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 0 | 177.87 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 131.57 | -0.005 | 100% | 25491.9506 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 0 | 258.15 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 228.24 | 0 | 100% | 31938.0797 |  | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 0 | 126.32 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.17 | SQM | 109.17 | 0 | 100% | 21151.9058 |  | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100% | 1365.7363 |  | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100% | 4780.0771 |  | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 0 | 117.1 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 99.15 | 0 | 100% | 19210.5108 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 170.28 | SQM | 170.28 | 0 | 100% | 36657.8784 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 44.84 | SQM | 44.84 | 0 | 100% | 9653.1552 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 25.8 | SQM | 25.8 | 0 | 100% | 2777.112 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 66.4 | SQM | 66.4 | 0 | 100% | 14294.592 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 25.8 | SQM | 25.8 | 0 | 100% | 2777.112 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0.004 | 99.98% | 4299.1416 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | -0.004 | 100% | 6003.6536 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0.004 | 100% | 5579.825 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0.004 | 100% | 11156.886 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100% | 937.8305 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0.003 | 100% | 25402.3403 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100% | 8648.325 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | -0.001 | 100% | 14565.0375 |  | 0
SK ANSAR HOSSIAN | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100% | 5768.6429 |  | 0
SK ANSAR HOSSIAN | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100% | 900 |  | 0
SK ANSAR HOSSIAN | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100% | 5600 |  | 0
SK ANSAR HOSSIAN | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 40.76 | RMT | 40.76 | 0 | 100% | 3342.32 |  | 0
SK ANSAR HOSSIAN | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.78 | RMT | 98.78 | 0 | 100% | 3239.984 |  | 0
SK ANSAR HOSSIAN | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 26.83 | 0 | 100% | 3520.096 |  | 0
SK ANSAR HOSSIAN | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100% | 3000 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TILING | 224 | 183 | 51.942 | SQM | 46.75 | 5.192 | 90% | 8555.25 | 10% | 950.5386
SK ANSAR HOSSIAN | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.098 | RMT | 47.1 | -0.002 | 100% | 2317.32 |  | 0
SK ANSAR HOSSIAN | FIRST FLOOR TILING | 226 | 183 | 49.616 | SQM | 49.62 | -0.004 | 100% | 9080.46 |  | 0
SK ANSAR HOSSIAN | FIRST FLOOR SKIRTING | 227 | 49.2 | 49.264 | RMT | 49.26 | 0.004 | 99.99% | 2423.592 |  | 0
SK ANSAR HOSSIAN | TERRACE FLOOR TILING | 228 | 183 | 2.675 | SQM | 2.68 | -0.005 | 100.2% | 490.44 |  | 0
SK ANSAR HOSSIAN | TERRACE FLOOR SKIRTING | 229 | 49.2 | 3.775 | RMT | 3.78 | -0.005 | 100.1% | 185.976 |  | 0
SK ANSAR HOSSIAN | UTILITY FLOOR TILING | 230 | 183 | 3.465 | SQM | 3.47 | -0.005 | 100.1% | 635.01 |  | 0
SK ANSAR HOSSIAN | UTILITY SKIRTING | 231 | 49.2 | 7.95 | RMT | 7.95 | 0 | 100% | 391.14 |  | 0
SK ANSAR HOSSIAN | BALCONY & SITOUT TILING | 232 | 183 | 7.864 | SQM | 7.86 | 0.004 | 99.95% | 1438.38 |  | 0
SK ANSAR HOSSIAN | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 7.05 | RMT | 7.05 | 0 | 100% | 346.86 |  | 0
SK ANSAR HOSSIAN | CAR PARKING AREA TILING | 234 | 172.224 | 13.454 | SQM | 13.45 | 0.004 | 99.97% | 2316.4128 |  | 0
SK ANSAR HOSSIAN | FLOOR CHIPPING | 235 | 2.5 | 1327.9869 | SFT | 1327.99 | -0.0031 | 100% | 3319.975 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.502 | SQM | 3.5 | 0.002 | 99.94% | 640.5 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 13.395 | SQM | 13.4 | -0.005 | 100% | 2452.2 |  | 0
SK ANSAR HOSSIAN | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.148 | SQM | 7.15 | -0.002 | 100% | 1308.45 |  | 0
SK ANSAR HOSSIAN | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 29.614 | SQM | 29.61 | 0.004 | 99.99% | 5418.63 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.121 | SQM | 126.12 | 0.001 | 100% | 8144.8296 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 0 | 1 | 0% | 0 | 100% | 600
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 28.2536 | RMT | 28.25 | 0.003581 | 99.99% | 156363.75 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 0 | 3 | 0% | 0 | 100% | 1350
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100% | 1500 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 295 | 290 | 19 | SFT | 10 | 9 | 52.63% | 2900 |  | 0
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 4 | LUMP SUM | 0 | 4 | 0% | 0 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 1740.6 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 870.3 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
SARAT BARMAN | CUSTOMIZATION SHUTTERING OF TERRACE COLUMN, BEAM AND SLAB, LINTEL AND CHAJJA | 458 | 301.392 | 59.6 | SQM | 59.6 | 0 | 100% | 17962.9632 |  | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 31.5166 | SQM | 31.52 | -0.0034 | 100% | 4410.6566 |  | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 7.6221 | SQM | 7.62 | 0.0021 | 99.97% | 1476.3902 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.16 | CUM | 4.16 | 0 | 100% | 936 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100% | 250 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.362 | MT | 0.36 | 0.002 | 99.45% | 2700 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.234 | MT | 0.23 | 0.004 | 98.29% | 1725 |  | 0
13400.5386

## V151
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100% | 9878.4 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | RUPAK NAYAK | 0
MANJUNATHA P | BASE FLOOR EARTH DRESSING | 14 | 22 | 40 | SQM | 40 | 0 | 100% | 880 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | SARAT BARMAN | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100% | 1121.904 |  | 0 | SAVITA DEVI | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 5500 | SHOKAT | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SK ANSAR HOSSIAN | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | V VENKATANARAYANA | 5500
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 0 | 1.2 | 0% | 0 |  | 0 | YELLAPPA C | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | RABIUL MOLLA | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 | SHEKAR T | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 | TOTAL | 5500
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 0 | 45.3 | 0% | 0 |  | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 0 | 129.11 | 0% | 0 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0% | 0 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.2505 | 0% | 0 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 0 | 3.26 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 0 | 15.33 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 0 | 1.57 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0 | 0.47 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0 | 0.88 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.815 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 0 | 2.21 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0% | 0 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0% | 0 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | EXCAVATED SOIL REWORK IN FOOTING | 390 | 7000 | 1 | LUMP SUM | 1 | 0 | 100% | 7000 |  | 0
5500

## V152
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment |  | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 |  | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 |  | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 |  | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 |  | KRIUTTIBAS DAS | 8000
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 |  | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 |  | MANJUNATHA P | 0
MANJUNATHA P | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 |  | NAGARAJ | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 |  | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 100 | 51.12 | 66.17% | 2200 |  | 0 |  | RAMAKRUSHNA PRADHAN | 6743.6865
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 50 | 18.67 | 72.81% | 2150 |  | 0 |  | RUPAK NAYAK | 19145.0346
SUBHASMITA DAS | SETBACK AREA SOIL FILLING | 16 | 141.12 | 15.63 | CUM | 0 | 15.63 | 0% | 0 |  | 0 |  | SANTOSH KUMAR | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 |  | SARAT BARMAN | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 |  | SAVITA DEVI | 1800
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 3.43 | 3.437 | 49.95% | 3430 | 50% | 3433.5 | Released for final touchup work | SHOKAT | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 |  | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 |  | SK ANSAR HOSSIAN | 2697.1125
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 |  | SREE VINAYAKA ELECTRICALS | 14832
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 |  | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 |  | SUBHASMITA DAS | 46741.1223
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 |  | UDHABHAI R PARMAR | 73047.8723
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0 |  | V VENKATANARAYANA | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 |  | YELLAPPA C | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 |  | RABIUL MOLLA | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 |  | KOUSHIK MANDAL | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0 |  | SHEKAR T | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0 |  | TOTAL | 173006.8282
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 9.25 | 0.0005 | 99.99% | 2987.01 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.573 | CUM | 1.57 | 0.003 | 99.81% | 3140 |  | 0
MD GIYAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100% | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100% | 34810.776 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 9.82 | -0.005 | 100.1% | 3171.0744 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 22.13 | CUM | 22.13 | 0 | 100% | 4979.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
MD GIYAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0.84 | 0.003 | 99.64% | 2520 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0.03 | -0.001 | 103.4% | 225 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100% | 3487.536 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 24.14 | 0 | 100% | 7795.2888 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 1.89 | 0 | 100% | 610.3188 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.372 | CUM | 2.37 | 0.002 | 99.92% | 533.25 |  | 0
MD GIYAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0.07 | 0 | 100% | 210 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
MD GIYAS | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 93.08 | SQM | 80 | 13.08 | 85.95% | 15500.16 |  | 0
SUBHASMITA DAS | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 13.08 | SQM | 0 | 13.08 | 0% | 0 | 100% | 2534.2762 | Released for final touchup work
MD GIYAS | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 110 | 19.32 | 85.06% | 21312.72 |  | 0
SUBHASMITA DAS | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 19.32 | SQM | 0 | 19.32 | 0% | 0 | 100% | 3743.2886 | Released for final touchup work
MD GIYAS | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 55 | 7.973 | 87.34% | 10656.36 |  | 0
SUBHASMITA DAS | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 7.973 | SQM | 0 | 7.973 | 0% | 0 | 100% | 1544.7847 | Released for final touchup work
MD GIYAS | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
SUBHASMITA DAS | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 | 100% | 1974.56 | Released for final touchup work
MD GIYAS | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | 64.23 | 0% | 0 |  | 0
SUBHASMITA DAS | ELEVATION GROOVE | 137 | 65.6 | 64.23 | RMT | 0 | 64.23 | 0% | 0 | 100% | 4213.488 | Released for final touchup work
MD GIYAS | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
MD GIYAS | RCC SURFACE HACKING | 140 | 8 | 348 | SQM | 348 | 0 | 100% | 2784 |  | 0
MD GIYAS | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 53.86 | 5.98 | 90.01% | 7536.7375 |  | 0
SUBHASMITA DAS | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 5.984 | SQM | 0 | 5.984 | 0% | 0 | 100% | 837.3531 | Released for final touchup work
MD GIYAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 141.39 | 35.35 | 80% | 19784.9855 |  | 0
SUBHASMITA DAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 35.348 | SQM | 0 | 35.348 | 0% | 0 | 100% | 4946.3163 | Released for final touchup work
MD GIYAS | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 147.87 | SQM | 103.51 | 44.36 | 70% | 20055.2695 |  | 0
SUBHASMITA DAS | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 44.361 | SQM | 0 | 44.361 | 0% | 0 | 100% | 8595.0325 | Released for final touchup work
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
MD GIYAS | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 73.49 | 8.16 | 90.01% | 10283.6027 |  | 0
SUBHASMITA DAS | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 8.165 | SQM | 0 | 8.165 | 0% | 0 | 100% | 1142.5448 | Released for final touchup work
MD GIYAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.15 | SQM | 182.52 | 45.63 | 80% | 25540.3886 |  | 0
SUBHASMITA DAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 45.63 | SQM | 0 | 45.63 | 0% | 0 | 100% | 6385.0972 | Released for final touchup work
MD GIYAS | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 110.32 | SQM | 88.26 | 22.06 | 80% | 17100.5515 |  | 0
SUBHASMITA DAS | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 22.064 | SQM | 0 | 22.064 | 0% | 0 | 100% | 4274.9441 | Released for final touchup work
MD GIYAS | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.86 | SQM | 7.97 | 0.89 | 89.95% | 1115.258 |  | 0
SUBHASMITA DAS | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 0.886 | SQM | 0 | 0.886 | 0% | 0 | 100% | 123.9798 | Released for final touchup work
MD GIYAS | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100% | 4780.0771 |  | 0
MD GIYAS | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 77.211 | SQM | 61.77 | 15.441 | 80% | 11968.061 |  | 0
SUBHASMITA DAS | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 15.4422 | SQM | 0 | 15.4422 | 0% | 0 | 100% | 2991.9571 | Released for final touchup work
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 122.39 | SQM | 122.39 | 0 | 100% | 26348.1192 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 52.42 | SQM | 52.42 | 0 | 100% | 11284.9776 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 33.44 | SQM | 33.44 | 0 | 100% | 3599.4816 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 54.93 | SQM | 54.93 | 0 | 100% | 11825.3304 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 33.44 | SQM | 33.44 | 0 | 100% | 3599.4816 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 19 | NOS | 19 | 0 | 100% | 3800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 34.813 | SQM | 34.81 | 0.003 | 99.99% | 7493.8968 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 4.932 | SQM | 4.93 | 0.002 | 99.96% | 477.6184 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 348.705 | SQM | 348.71 | -0.005 | 100% | 5631.6665 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 348.705 | SQM | 348.71 | -0.005 | 100% | 11260.5433 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 44.712 | SQM | 44.71 | 0.002 | 100% | 722.0665 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 447.372 | SQM | 447.37 | 0.002 | 100% | 21669.7081 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 447.372 | SQM | 447.37 | 0.002 | 100% | 7225.0255 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 447.372 | SQM | 0 | 447.372 | 0% | 0 | 100% | 12038.7805
SK ANSAR HOSSIAN | STAIRCASE GRANITE | 215 | 301.392 | 20.496 | SQM | 20.5 | -0.004 | 100% | 6178.536 |  | 0
SK ANSAR HOSSIAN | DOOR OPENING GRANITE | 218 | 350 | 13 | NOS | 11 | 2 | 84.62% | 3850 | 15% | 682.5
SK ANSAR HOSSIAN | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 42.41 | RMT | 38.17 | 4.24 | 90% | 3129.94 | 10% | 347.762
SK ANSAR HOSSIAN | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 120.57 | RMT | 108.51 | 12.06 | 90% | 3559.128 | 10% | 395.4696
SK ANSAR HOSSIAN | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 22.951 | RMT | 22.95 | 0.001 | 100% | 3011.04 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TILING | 224 | 183 | 37.617 | SQM | 35.74 | 1.877 | 95.01% | 6540.42 | 5% | 344.1955
SK ANSAR HOSSIAN | GROUND FLOOR SKIRTING | 225 | 49.2 | 32.354 | RMT | 29.12 | 3.234 | 90% | 1432.704 | 10% | 159.1817
SK ANSAR HOSSIAN | FIRST FLOOR TILING | 226 | 183 | 32.478 | SQM | 30.85 | 1.628 | 94.99% | 5645.55 | 5% | 297.1737
SK ANSAR HOSSIAN | FIRST FLOOR SKIRTING | 227 | 49.2 | 35.883 | RMT | 32.29 | 3.593 | 89.99% | 1588.668 | 10% | 176.5444
SK ANSAR HOSSIAN | TERRACE FLOOR TILING | 228 | 183 | 19.465 | SQM | 18.49 | 0.975 | 94.99% | 3383.67 | 5% | 178.1047
SK ANSAR HOSSIAN | TERRACE FLOOR SKIRTING | 229 | 49.2 | 23.614 | RMT | 21.25 | 2.364 | 89.99% | 1045.5 | 10% | 116.1809
SK ANSAR HOSSIAN | BALCONY & SITOUT TILING | 232 | 172.224 | 4.175 | SQM | 4.18 | -0.005 | 100.1% | 719.8963 |  | 0
SK ANSAR HOSSIAN | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 8.388 | RMT | 8.39 | -0.002 | 100% | 412.788 |  | 0
SK ANSAR HOSSIAN | CAR PARKING AREA TILING | 234 | 183 | 8.288 | SQM | 8.29 | -0.002 | 100% | 1517.07 |  | 0
SK ANSAR HOSSIAN | FLOOR CHIPPING | 235 | 2.5 | 1008.964 | SFT | 1008.96 | 0.004 | 100% | 2522.4 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 2.928 | SQM | 2.93 | -0.002 | 100.1% | 536.19 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 15.516 | SQM | 15.52 | -0.004 | 100% | 2840.16 |  | 0
SK ANSAR HOSSIAN | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 6.833 | SQM | 6.83 | 0.003 | 99.96% | 1249.89 |  | 0
SK ANSAR HOSSIAN | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 32.029 | SQM | 32.03 | -0.001 | 100% | 5861.49 |  | 0
SK ANSAR HOSSIAN | TERRACE FLOOR TOILET FLOOR TILING | 241 | 183 | 3.721 | SQM | 3.72 | 0.001 | 99.97% | 680.76 |  | 0
SK ANSAR HOSSIAN | TERRACE FLOOR TOILET WALL TILING | 242 | 183 | 17.198 | SQM | 17.2 | -0.002 | 100% | 3147.6 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 245 | 64.58 | 110.038 | SQM | 0 | 110.038 | 0% | 0 | 100% | 7106.254
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100% | 15500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 8000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 8000
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
UDHABHAI R PARMAR | BALCONY & STAIRCASE SS RAILING | 260 | 5528.485 | 18.363 | RMT | 5.15 | 13.213 | 28.05% | 28471.6977 | 71.95% | 73047.8723
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 0 | 4 | 0% | 0 | 100% | 1800
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 14832
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 | 100% | 2601.986
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 | 100% | 1518
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 | 100% | 2623.7005
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 8000 | 1 | LUMP SUM | 1 | 0 | 100% | 8000 |  | 0
MD GIYAS | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 31.944 | SQM | 31.94 | 0.004 | 99.99% | 6188.375 |  | 0
MD GIYAS | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 91.035 | SQM | 91.04 | -0.005 | 100% | 12739.4093 |  | 0
MD GIYAS | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 25.812 | SQM | 25.81 | 0.002 | 99.99% | 5000.7391 |  | 0
173006.8282

## V153
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100% | 3201.66 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100% | 21563.8416 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100% | 1120.46 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100% | 11084.976 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100% | 3882.2112 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100% | 1304.38 |  | 0 | PRAKASH H N | 2600
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | RAMAKRUSHNA PRADHAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0.003 | 99.94% | 5090 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0.002 | 99.93% | 2780 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | -0.001 | 100% | 5930 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100% | 2775 |  | 0 | SHOKAT | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100% | 3375 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0 | SK ANSAR HOSSIAN | 8881.883
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0 | SREE VINAYAKA ELECTRICALS | 14832
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100% | 9375 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.14 | MT | 0.14 | 0 | 100% | 980 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0.003 | 99.99% | 10223.2166 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100% | 7124.9069 |  | 0 | YELLAPPA C | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0.0017 | 100% | 18068.4504 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100% | 12441.4618 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100% | 37972.3781 |  | 0 | SHEKAR T | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100% | 3695.0659 |  | 0 | TOTAL | 26313.883
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100% | 4855.4251 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100% | 2227.5 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100% | 1980 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100% | 4266 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100% | 5700 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0.003 | 99.98% | 2943 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0.001 | 99.94% | 3400 |  | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100% | 915 |  | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100% | 8250 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100% | 12531.8794 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100% | 37737.2923 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100% | 3695.0659 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100% | 5313.541 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0.004 | 99.83% | 4640 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0.001 | 99.99% | 3051 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | -0.004 | 100.3% | 2820 |  | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0.003 | 99.64% | 1260 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100% | 750 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100% | 150 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100% | 6895.849 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100% | 578.6726 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | -0.005 | 100.3% | 445.5 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100% | 105 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100% | 2150 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 0.002 | 100% | 21682.7863 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 120.45 | 2.69 | 97.82% | 23337.4284 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0.002 | 100% | 12148.2504 |  | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100% | 2000.144 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 46.88 | 0 | 100% | 3075.328 |  | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 10.136 | SQM | 10.14 | -0.004 | 100% | 1964.6453 |  | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 348.5 | SQM | 348.5 | 0 | 100% | 2813.4405 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100% | 8472.8826 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0% | 0 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0.001 | 100% | 31998.1428 |  | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0.002 | 100% | 8628.2071 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 0 | 175.883 | 0% | 0 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100% | 26480.0858 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100% | 1241.1968 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 0 | 36.94 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 41.92 | 70.56 | 37.27% | 8122.0838 |  | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 42.484 | SQM | 42.48 | 0.004 | 99.99% | 18290.1888 |  | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 78.967 | SQM | 78.97 | -0.003 | 100% | 34001.3232 |  | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 12.077 | SQM | 12.08 | -0.003 | 100% | 2600.5824 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 23.226 | SQM | 23.23 | -0.004 | 100% | 5000.9544 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 18 | NOS | 18 | 0 | 100% | 3600 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | -0.005 | 100% | 6441.1776 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100% | 3330.7344 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | -0.001 | 100% | 5851.468 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 362.32 | -0.001 | 100% | 11700.0374 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0.0012 | 100% | 24623.9417 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0.0012 | 100% | 8210.014 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 508.36 | 0.0012 | 100% | 13679.9676 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 18.16 | SQM | 18.16 | 0 | 100% | 5473.2787 |  | 0
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100% | 1350 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 14 | 0 | 100% | 4900 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100% | 3375.94 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100% | 3395.784 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 19.57 | 0 | 100% | 2567.584 |  | 0
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 |  | 0
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 2 | 2 | 50% | 2000 |  | 0
SK ANSAR HOSSIAN | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 2 | 2 | 50% | 2000 | 50% | 2000
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.68 | SQM | 46.51 | 5.17 | 90% | 8511.33 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 45.26 | RMT | 40.73 | 4.53 | 89.99% | 2003.916 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 43.7 | SQM | 39.33 | 4.37 | 90% | 7197.39 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 42.77 | RMT | 38.49 | 4.28 | 89.99% | 1893.708 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.12 | SQM | 1.91 | 0.21 | 90.09% | 349.53 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.15 | RMT | 3.74 | 0.41 | 90.12% | 184.008 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 3.89 | SQM | 0 | 3.89 | 0% | 0 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 8.42 | RMT | 0 | 8.42 | 0% | 0 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 10.19 | SQM | 9.17 | 1.02 | 89.99% | 1678.11 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 13.87 | RMT | 12.48 | 1.39 | 89.98% | 614.016 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 11.38 | SQM | 0 | 11.38 | 0% | 0 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1068.49 | SFT | 1068.49 | 0 | 100% | 2671.225 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.64 | SQM | 3.28 | 0.36 | 90.11% | 600.24 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.95 | SQM | 16.16 | 1.79 | 90.03% | 2957.28 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.22 | SQM | 6.5 | 0.72 | 90.03% | 1189.5 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.71 | SQM | 32.14 | 3.57 | 90% | 5881.62 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TILING | 224 | 183 | 51.68 | SQM | 46.51 | 5.17 | 90% | 8511.33 | 10% | 945.744
SK ANSAR HOSSIAN | GROUND FLOOR SKIRTING | 225 | 49.2 | 45.26 | RMT | 40.73 | 4.53 | 89.99% | 2003.916 | 10% | 222.6792
SK ANSAR HOSSIAN | FIRST FLOOR TILING | 226 | 183 | 43.7 | SQM | 39.33 | 4.37 | 90% | 7197.39 | 10% | 799.71
SK ANSAR HOSSIAN | FIRST FLOOR SKIRTING | 227 | 49.2 | 42.77 | RMT | 38.49 | 4.28 | 89.99% | 1893.708 | 10% | 210.4284
SK ANSAR HOSSIAN | TERRACE FLOOR TILING | 228 | 183 | 2.12 | SQM | 1.91 | 0.21 | 90.09% | 349.53 | 10% | 38.796
SK ANSAR HOSSIAN | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.15 | RMT | 3.74 | 0.41 | 90.12% | 184.008 | 10% | 20.418
SK ANSAR HOSSIAN | UTILITY FLOOR TILING | 230 | 183 | 3.89 | SQM | 0 | 3.89 | 0% | 0 | 100% | 711.87
SK ANSAR HOSSIAN | UTILITY SKIRTING | 231 | 49.2 | 8.42 | RMT | 0 | 8.42 | 0% | 0 | 100% | 414.264
SK ANSAR HOSSIAN | BALCONY & SITOUT TILING | 232 | 183 | 10.19 | SQM | 9.17 | 1.02 | 89.99% | 1678.11 | 10% | 186.477
SK ANSAR HOSSIAN | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 13.87 | RMT | 12.48 | 1.39 | 89.98% | 614.016 | 10% | 68.2404
SK ANSAR HOSSIAN | CAR PARKING AREA TILING | 234 | 183 | 11.38 | SQM | 0 | 11.38 | 0% | 0 | 100% | 2082.54
SK ANSAR HOSSIAN | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.64 | SQM | 3.28 | 0.36 | 90.11% | 600.24 | 10% | 66.612
SK ANSAR HOSSIAN | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.95 | SQM | 16.16 | 1.79 | 90.03% | 2957.28 | 10% | 328.485
SK ANSAR HOSSIAN | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.22 | SQM | 6.5 | 0.72 | 90.03% | 1189.5 | 10% | 132.126
SK ANSAR HOSSIAN | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.71 | SQM | 32.14 | 3.57 | 90% | 5881.62 | 10% | 653.493
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 131.57 | SQM | 131.57 | 0 | 100% | 8496.7906 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 1 | LUMP SUM | 1 | 0 | 100% | 14000 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 0 | 1 | 0% | 0 | 100% | 600
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 21.62 | RMT | 21.62 | 0 | 100% | 119666.7 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100% | 1350 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 14832
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
INDAL SAHNI | SILL GRANITE | 289 | 75 | 37 | RFT | 0 | 37 | 0% | 0 |  | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
YELLAPPA C | ADDITIONAL SHUTTERING WORK/CUSTOMIZATION FLOOR EXTENSION- 19600/- | 361 | 301.392 | 17.0885 | SFT | 17.09 | -0.00149 | 100% | 5150.7893 |  | 0
RUPAK NAYAK | ALL FLOOR INTERNAL WALL & CEILING ONE COAT EMULSION PAINT REWORK | 384 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 96.574 | SQM | 96.57 | 0.004 | 100% | 4677.6577 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 96.574 | SQM | 96.57 | 0.004 | 100% | 1559.6055 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 96.574 | SQM | 96.57 | 0.004 | 100% | 2598.6987 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 18.848 | SQM | 18.85 | -0.002 | 100% | 304.4275 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 18.848 | SQM | 18.85 | -0.002 | 100% | 608.7042 |  | 0
RUPAK NAYAK | CUSTOMISATION TERRACE EPOXY GROUTING AND SOAP WASH CLEANING WORK | 427 | 64.58 | 19.465 | SQM | 19.47 | -0.005 | 100% | 1257.3726 |  | 0
INDAL SAHNI | CUSTOMIZATION TOILET TILE WORK | 436 | 1071.962 | 3.721 | SQM | 3.35 | 0.371 | 90.03% | 3591.0727 |  | 0
INDAL SAHNI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 255.067 | 15.63 | SQM | 14.07 | 1.56 | 90.02% | 3588.7927 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 8750 | 1 | LUMP SUM | 1 | 0 | 100% | 8750 |  | 0
CHIRANJEEVI | CUSTOMIZATION WORK/THE RATE IS INCLUSIVE OF MASONRY WORK/PLASTERING WORK/ELEVATION WORK | 462 | 23716 | 1 | LUMP SUM | 1 | 0 | 100% | 23716 |  | 0
SANTOSH KUMAR | BALCONY UPSTAND TOP COPING GRANITE | 547 | 78 | 25.29 | RFT | 25.29 | 0 | 100% | 1972.62 |  | 0
26313.883

## V154
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100 | 2775 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100 | 9375 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0 | 100 | 18068.4504 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 0 | 16.11 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100 | 915 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 6.65 | 5.61 | 54.204 | 2004.2568 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 0 | 17.63 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0 | 100 | 1260 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100 | 150 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 0 | 1.92 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100 | 105 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 96.26 | 15.65 | 86.011 | 18650.5675 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 120.45 | 2.69 | 97.819 | 23337.4284 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 0 | 30.49 | 0 | 0 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 10.136 | SQM | 10.14 | 0 | 100 | 1964.6453 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 0 | 268.5 | 0 | 0 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 348.5 | SQM | 0 | 348.5 | 0 | 0 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 0 | 60.55 | 0 | 0 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0 | 0 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 16 | 149.15 | 9.688 | 3100.032 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 0 | 61.66 | 0 | 0 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 0 | 175.88 | 0 | 0 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 0 | 136.67 | 0 | 0 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 0 | 8.87 | 0 | 0 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 0 | 36.94 | 0 | 0 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 0 | 112.48 | 0 | 0 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 430.56 | 42.484 | SQM | 42.48 | 0 | 100 | 18290.1888 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 215.28 | 15.87 | SQM | 15.87 | 0 | 100 | 3416.4936 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 430.56 | 79.896 | SQM | 79.9 | 0 | 100 | 34401.744 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 19 | NOS | 19 | 0 | 100 | 3800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | 0 | 100 | 6441.1776 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100 | 3330.7344 | 0 | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | 0 | 100 | 5851.468 | 0 | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 362.32 | 0 | 100 | 11700.0374 | 0 | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0 | 100 | 24623.9417 | 0 | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0 | 100 | 8210.014 | 0 | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 508.36 | 0 | 100 | 13679.9676 | 0 | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 20.12 | SQM | 20.12 | 0 | 100 | 6064.007 | 0 | 0
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 8 | 8 | 50
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.16 | RMT | 41.16 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 26.83 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 49.2 | SQM | 49.2 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 48.42 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.25 | SQM | 46.25 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 50.44 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.7 | SQM | 2.7 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 4.92 | SQM | 4.92 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 8.48 | RMT | 8.48 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 7.72 | SQM | 7.72 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 18.3 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 15.24 | SQM | 15.24 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.7 | SQM | 3.7 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 23.58 | SQM | 23.58 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.44 | SQM | 7.44 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 40.06 | SQM | 40.06 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 131.57 | SQM | 131.57 | 0 | 100
PRAKASH JANA | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 205.69 | SQM | 205.69 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 24.39 | RMT | 24.39 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 12850 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 68.2 | RFT | 68.2 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 33 | RFT | 33 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 16.25 | RFT | 16.25 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
PRAKASH JANA | LAYING FLOOR PROTECTOR SHEET & TILE CLEANING | 341 | 1.5 | 1055 | SFT | 1055 | 0 | 100
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 3940 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION TERRACE WASHING MACHINE TAP POINT WORK | 504 | 1500 | 1 | NOS | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 533 | 1000 | 1 | NOS | 1 | 0 | 100
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100

## V155
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
DEEPAK NAYAK | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 52.38 | SQM | 52.38 | 0 | 100 | 2252.34 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 | 0 | 0
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100 | 2500 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 59.29 | SQM | 59.29 | 0 | 100 | 2549.47 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
NARESH PURTY | FOOTING REINFORCEMENT | 23 | 6800 | 0.37 | MT | 0.37 | 0 | 100 | 2516 | 0 | 0
NARESH PURTY | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.45 | MT | 0.45 | 0 | 100 | 3060 | 0 | 0
NARESH PURTY | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.55 | MT | 0.55 | 0 | 100 | 3740 | 0 | 0
NARESH PURTY | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.5 | MT | 0.5 | 0 | 100 | 3400 | 0 | 0
NARESH PURTY | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 1.25 | MT | 1.25 | 0 | 100 | 8500 | 0 | 0
NARESH PURTY | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 6800 | 0.14 | MT | 0.14 | 0 | 100 | 952 | 0 | 0
NARESH PURTY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 6800 | 0.14 | MT | 0.14 | 0 | 100 | 952 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0 | 100 | 18068.4504 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 0 | 16.11 | 0 | 0 | 0 | 0
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100 | 915 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
NARESH PURTY | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 6800 | 0.5 | MT | 0.5 | 0 | 100 | 3400 | 0 | 0
NARESH PURTY | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 6800 | 1.1 | MT | 1.1 | 0 | 100 | 7480 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 1.93 | 10.33 | 15.725 | 581.6866 | 0 | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 0 | 17.63 | 0 | 0 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0 | 100 | 1260 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100 | 150 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 0 | 1.92 | 0 | 0 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 | 0 | 0
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100 | 105 | 0 | 0
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 92.9 | 19.01 | 83.014 | 17999.5608 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 120.45 | 2.69 | 97.819 | 23337.4284 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 0 | 30.49 | 0 | 0 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 43.9 | 2.98 | 93.649 | 2879.84 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 10.136 | SQM | 10.14 | 0 | 100 | 1964.6453 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 348.5 | SQM | 348.5 | 0 | 100 | 2813.4405 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
SALLAUDDIN ANSARI | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 0.73333 | LUMP SUM | 0.73 | 0 | 100 | 8760 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 0.26667 | LUMP SUM | 0.27 | 0 | 100 | 3240 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 60.5 | 51.98 | 53.785 | 11721.996 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 182 | 215.28 | 30 | SQM | 30 | 0 | 100 | 6458.4 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 34.38 | SQM | 34.38 | 0 | 100 | 3330.5969 | 0 | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 147.879 | SQM | 147.88 | 0 | 100
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 112.08 | SQM | 112.08 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 102.36 | SQM | 102.36 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.5 | 166.76 | SQM | 166.76 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.5 | 60.55 | SQM | 60.55 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.5 | 175.88 | SQM | 175.88 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.5 | 61.66 | SQM | 61.66 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.5 | 36.94 | SQM | 36.94 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.5 | 8.87 | SQM | 8.87 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 20.12 | SQM | 20.12 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.16 | RMT | 41.16 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 26.83 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 49.2 | SQM | 49.2 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 48.42 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.25 | SQM | 46.25 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 50.44 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.7 | SQM | 2.7 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 4.92 | SQM | 4.92 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 8.48 | RMT | 8.48 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 7.72 | SQM | 7.72 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 18.3 | RMT | 18.3 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 172.224 | 15.24 | SQM | 15.24 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.7 | SQM | 3.7 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 23.58 | SQM | 23.58 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.44 | SQM | 7.44 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 40.06 | SQM | 40.06 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 131.57 | SQM | 131.57 | 0 | 100
BIPIN RAM | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 190.914 | SQM | 190.91 | 0 | 100
H R ENGINEERS | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
BICHITRA CHOUDHURI | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
BICHITRA CHOUDHURI | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 20.78 | RMT | 0 | 20.78 | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING (INCUDING MATERIAL) | 261 | 1600 | 3 | NOS | 3 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 60 | RFT | 60 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 24 | RFT | 24 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 111 | SFT | 111 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 363 | 8.5 | RFT | 8.5 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
RUPAK NAYAK | ALL FLOOR INTERNAL WALL & CEILING TWO COATS INTERNAL EMULSION REWORK AFTER CRACK TREATMENT | 372 | 32.292 | 510.66 | SQM | 510.66 | 0 | 100
RUPAK NAYAK | GROUND FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 379 | 16.146 | 183.89 | SQM | 0 | 183.89 | 0
RUPAK NAYAK | FIRST FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 380 | 16.146 | 110.81 | SQM | 0 | 110.81 | 0
RUPAK NAYAK | TERRACE FLOOR EXTERNAL WALL & CHEJJA ONE COAT EXTERIOR PAINT REWORK | 381 | 16.146 | 128.79 | SQM | 0 | 128.79 | 0
RUPAK NAYAK | ALL FLOOR INTERNAL WALL & CEILING ONE COAT EMULSION PAINT REWORK | 384 | 15000 | 1 | LUMP SUM | 1 | 0 | 100

## V156
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
SUBHASMITA DAS | FOOTING SOILING | 7 | 22 | 58 | SQM | 58 | 0 | 100 | 1276 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM SOLING | 12 | 22 | 31.45 | SQM | 31.45 | 0 | 100 | 691.9 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 22 | 77 | SQM | 77 | 0 | 100 | 1694 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0 | 0.37 | 0 | 0 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.1 | 0.35 | 22.222 | 750 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.17 | 0.08 | 93.6 | 8775 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.14 | MT | 0.14 | 0 | 100 | 1400 | 0 | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100 | 7980.8602 | 0 | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100 | 16492.1702 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0 | 100 | 2787.876 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100 | 1830 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0.15 | 0 | 100 | 1500 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 9.82 | 0 | 100 | 2959.6694 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0.84 | 0 | 100 | 2520 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100 | 569.6309 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0 | 0.41 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 0 | 1.98 | 0 | 0 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0.07 | 0 | 100 | 210 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.582 | SQM | 108.58 | 0 | 100 | 21037.5922 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 118.14 | SQM | 118.14 | 0 | 100 | 22889.8613 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 40.88 | RMT | 40.88 | 0 | 100 | 2681.728 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100 | 15000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 98.38 | SQM | 98.38 | 0 | 100 | 19061.3218 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 120.716 | SQM | 120.72 | 0 | 100 | 25988.6016 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 34.11 | SQM | 34.11 | 0 | 100 | 7343.2008 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 23.924 | SQM | 23.92 | 0 | 100 | 2574.7488 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 68.36 | SQM | 68.36 | 0 | 100
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 23.924 | SQM | 23.92 | 0 | 100
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 508.36 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 17.75 | SQM | 17.75 | 0 | 100
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 11 | 4 | 73.333
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.4 | RMT | 46.4 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.07 | RMT | 23.07 | 0 | 100
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 3 | 1 | #VALUE!
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 39.62 | 9.9 | 80
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 38.74 | 9.68 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 36.8 | 9.2 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 40.35 | 10.09 | 80
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2 | 0.5 | 80
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 3.35 | 0.84 | 80
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 10.18 | SQM | 10.18 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 14 | RMT | 14 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 11.138 | SQM | 11.14 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.41 | SQM | 2.73 | 0.68 | 80
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 13.87 | 3.47 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 6.62 | SQM | 5.3 | 1.32 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 33.99 | SQM | 27.19 | 6.8 | 80
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 144.788 | SQM | 144.79 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 20.78 | RMT | 20.78 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 9800 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 3 | LUMP SUM | 0 | 3 | 0
RUPAK NAYAK | ALL FLOOR INTERNAL WALL & CEILING TWO COATS PUTTY REWORK | 371 | 32.292 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INTERNAL WALL & CEILING ONE COAT PRIMER REWORK | 373 | 16.15 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INTERNAL WALL & CEILING TWO COATS INTERNAL EMULSION REWORK AFTER CRACK TREATMENT | 374 | 26.91 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INTERNAL WALL & CEILING ONE COAT EMULSION PAINT REWORK | 384 | 15000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 96.574 | SQM | 96.57 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 96.574 | SQM | 96.57 | 0 | 100
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 96.574 | SQM | 96.57 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 18.848 | SQM | 18.85 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 18.848 | SQM | 18.85 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100
KRISHNAKUMAR SAHANI | CUSTOMIZATION TOILET TILE WORK | 436 | 1088.588 | 3.6 | SQM | 2.88 | 0.72 | 80
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 3.57 | SQM | 3.57 | 0 | 100
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 7.062 | SQM | 7.06 | 0 | 100
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION LIFT WALL WATERPROOFING WORK | 440 | 215.28 | 7.062 | SQM | 7.06 | 0 | 100
KRISHNAKUMAR SAHANI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 263.83 | 18.46 | SQM | 14.77 | 3.69 | 80
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | CUSTOMIZATION FLOOR BLOCK WORK | 459 | 193.75 | 38.13 | SQM | 38.13 | 0 | 100
AAIDHUL MIAH | CUSTOMIZATION FLOOR INTERNAL PLASTERING WORK | 460 | 139.932 | 92.626 | SQM | 92.62 | 0.01 | 99.994
AAIDHUL MIAH | CUSTOMIZATION FLOOR EXTERNAL PLASTERING WORK | 461 | 193.752 | 28.589 | SQM | 28.59 | 0 | 100
SARAT BARMAN | CUSTOMISATION FLOOR REINFORCEMENT WORK | 492 | 7500 | 0.589 | MT | 0.59 | 0 | 100
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.319 | CUM | 4.32 | 0 | 100
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.083 | CUM | 1.08 | 0 | 100
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 4 | NOS | 4 | 0 | 100
NAGARAJ | CUSTOMIZATION FLOOR SLAB AND BEAM SHUTTERING | 508 | 301.392 | 33.26 | SQM | 33.26 | 0 | 100
NAGARAJ | CUSTOMIZATION FLOOR COLUMN SHUTTERING | 509 | 301.392 | 30.1 | SQM | 30.1 | 0 | 100
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.175 | MT | 0.18 | 0 | 100
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.39 | MT | 0.39 | 0 | 100
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100

## V157
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 |  | 0 | KRIUTTIBAS DAS | 1500
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 |  | 0 | PRAKASH H N | 2000
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 |  | 0 | RAMAKRUSHNA PRADHAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 |  | 0 | SAVITA DEVI | 1500
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100 | 2775 |  | 0 | SHOKAT | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100 | 9375 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 |  | 0 | UDHABHAI R PARMAR | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 |  | 0 | V VENKATANARAYANA | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 |  | 0 | YELLAPPA C | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0 | 100 | 18068.4504 |  | 0 | RABIUL MOLLA | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 |  | 0 | KOUSHIK MANDAL | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 |  | 0 | SHEKAR T | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 |  | 0 | TOTAL | 5000
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 0 | 16.11 | 0 | 0 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 |  | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100 | 915 |  | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 |  | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 |  | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 |  | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 |  | 0
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100 | 5313.541 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 |  | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0 | 100 | 1260 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100 | 150 |  | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 |  | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 |  | 0
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100 | 578.6726 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100 | 105 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 83.61 | 28.3 | 74.712 | 16199.6047 |  | 0
SHEKAR T | GROUND FLOOR BLOCK WORK | 122 | 193.75 | 28.3 | SQM | 28.3 | 0 | 100 | 5483.125 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 120.45 | 2.69 | 97.819 | 23337.4284 |  | 0
SHEKAR T | FIRST FLOOR BLOCK WORK | 126 | 193.75 | 2.68 | SQM | 2.68 | 0 | 100 | 519.25 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 |  | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 0 | 30.49 | 0 | 0 |  | 0
SHEKAR T | ELEVATION RCC BAND | 135 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 43.9 | 2.98 | 93.649 | 2879.84 |  | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 193.752 | 10.136 | SQM | 10.14 | 0 | 100 | 1964.6453 |  | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.073 | 348.5 | SQM | 348.5 | 0 | 100 | 2813.4405 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0 | 0 |  | 0
MD GIYAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 144 | 139.93 | 166.76 | SQM | 166.76 | 0 | 100 | 23334.7268 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 |  | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 0 | 175.88 | 0 | 0 |  | 0
MD GIYAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 153 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 0 | 36.94 | 0 | 0 |  | 0
MD GIYAS | TERRACE FLOOR INTERNAL WALL PLASTERING | 164 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 60.5 | 51.98 | 53.785 | 11721.996 |  | 0
SHEKAR T | TERRACE FLOOR EXTERNAL WALL PLASTERING | 167 | 193.75 | 24.02 | SQM | 24.02 | 0 | 100 | 4653.875 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 153.831 | SQM | 153.83 | 0 | 100 | 33116.5224 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 36.166 | SQM | 36.17 | 0 | 100 | 7786.6776 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 17.916 | SQM | 17.92 | 0 | 100 | 1928.9088 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 91.498 | SQM | 91.5 | 0 | 100 | 19698.12 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 17.916 | SQM | 17.92 | 0 | 100 | 1928.9088 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 14 | 0 | 100 | 2800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | 0 | 100 | 6441.1776 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100 | 3330.7344 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | 0 | 100 | 5851.468 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 362.32 | 0 | 100 | 11700.0374 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0 | 100 | 24623.9417 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0 | 100 | 8210.014 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 508.36 | 0 | 100 | 13679.9676 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 20.12 | SQM | 20.12 | 0 | 100 | 6064.007 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 7 | 8 | 46.667 | 2450 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100 | 3375.94 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100 | 3395.784 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 19.57 | 0 | 100 | 2567.584 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0 | 0 |  | 0
ANSAR HOSSAIAN SK | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100 | 3000 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 45 | 4.52 | 90.872 | 8235 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR TILING | 224 | 183 | 4.52 | SQM | 4.52 | 0 | 100 | 827.16 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 45 | 3.42 | 92.937 | 2214 |  | 0
ANSAR HOSSAIAN SK | GROUND FLOOR SKIRTING | 225 | 49.2 | 3.42 | RMT | 3.42 | 0 | 100 | 168.264 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 40 | 6 | 86.957 | 7320 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR TILING | 226 | 183 | 6 | SQM | 6 | 0 | 100 | 1098 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 45 | 5.44 | 89.215 | 2214 |  | 0
ANSAR HOSSAIAN SK | FIRST FLOOR SKIRTING | 227 | 49.2 | 5.44 | RMT | 5.44 | 0 | 100 | 267.648 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2.5 | 0 | 100 | 457.5 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100 | 206.148 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 0 | 4.01 | 0 | 0 |  | 0
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100 | 733.83 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 0 | 9.98 | 0 | 0 |  | 0
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100 | 491.016 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 12.635 | SQM | 12.64 | 0 | 100 | 2313.12 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.8 | RMT | 16.8 | 0 | 100 | 826.56 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 12.821 | SQM | 0 | 12.82 | 0 | 0 |  | 0
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 12.821 | SQM | 12.82 | 0 | 100 | 2346.06 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100 | 2637.5 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.7 | SQM | 3.7 | 0 | 100 | 677.1 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 17.34 | 0 | 100 | 3173.22 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.44 | SQM | 7.44 | 0 | 100 | 1361.52 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 34.9 | SQM | 34.9 | 0 | 100 | 6386.7 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 131.57 | SQM | 131.57 | 0 | 100 | 8496.7906 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100 | 15500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100 | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 100% | 2000
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100 | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100 | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100 | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100 | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100 | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 23.67 | RMT | 23.67 | 0 | 100 | 131013.45 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1500
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1500
CHIRANJEEVI | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 3 | NOS | 3 | 0 | 100 | 2250 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100 | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100 | 151800 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100 | 2624.38 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 |  | 0
5000

## V158
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
MORSELIM KHAN | ATT IN PLINTH | 1 | 54 | 78.8 | SQM | 78.8 | 0 | 100% | 4255.2 |  | 0 | AAIDHUL MIAH | 0
MORSELIM KHAN | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MORSELIM KHAN | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MORSELIM KHAN | FOOTING EXCAVATION | 4 | 211.68 | 113.904 | CUM | 113.9 | 0.004 | 100% | 24110.352 |  | 0 | KRIUTTIBAS DAS | 7800
MORSELIM KHAN | FOOTING EARTH DRESSING | 5 | 22 | 56.952 | SQM | 56.95 | 0.002 | 100% | 1252.9 |  | 0 | LEGENDRY LANDSCAPE | 0
MORSELIM KHAN | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 97.034 | CUM | 97.03 | 0.004 | 100% | 13692.8736 |  | 0 | MANJUNATHA P | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 6.232 | CUM | 6.23 | 0.002 | 99.97% | 1318.7664 |  | 0 | NAGARAJ | 0
MORSELIM KHAN | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 39.402 | CUM | 39.4 | 0.002 | 99.99% | 5560.128 |  | 0 | PRAKASH H N | 0
MORSELIM KHAN | BASE FLOOR EARTH DRESSING | 14 | 22 | 78.8 | SQM | 78.8 | 0 | 100% | 1733.6 |  | 0 | RAMAKRUSHNA PRADHAN | 0
MORSELIM KHAN | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.28 | CUM | 0 | 10.28 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
MORSELIM KHAN | FOOTING PCC WORK | 20 | 1000 | 4.131 | CUM | 4.13 | 0.001 | 99.98% | 4130 |  | 0 | SANTOSH KUMAR | 0
MORSELIM KHAN | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 3.116 | CUM | 3.12 | -0.004 | 100.1% | 3120 |  | 0 | SARAT BARMAN | 0
MORSELIM KHAN | BASE FLOOR PCC | 22 | 1000 | 7.88 | CUM | 7.88 | 0 | 100% | 7880 |  | 0 | SAVITA DEVI | 0
MORSELIM KHAN | FOOTING REINFORCEMENT | 23 | 7000 | 0.4 | MT | 0.4 | 0 | 100% | 2800 |  | 0 | SHOKAT | 0
MORSELIM KHAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100% | 3150 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
MORSELIM KHAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.6 | MT | 0.6 | 0 | 100% | 4500 |  | 0 | SK ANSAR HOSSIAN | 0
MORSELIM KHAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100% | 3500 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.45 | MT | 1.45 | 0 | 100% | 10150 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.17 | MT | 0.17 | 0 | 100% | 1190 |  | 0 | SUBHASMITA DAS | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.1 | MT | 0 | 0.1 | 0% | 0 |  | 0 | UDHABHAI R PARMAR | 0
MORSELIM KHAN | FOOTING SHUTTERING | 41 | 301.392 | 35.255 | SQM | 35.26 | -0.005 | 100% | 10627.0819 |  | 0 | V VENKATANARAYANA | 0
MORSELIM KHAN | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 27.66 | SQM | 27.66 | 0 | 100% | 8336.5027 |  | 0 | YELLAPPA C | 0
MORSELIM KHAN | PLINTH BEAM SHUTTERING | 43 | 301.392 | 66.839 | SQM | 66.84 | -0.001 | 100% | 20145.0413 |  | 0 | RABIUL MOLLA | 0
MORSELIM KHAN | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 47.535 | SQM | 47.54 | -0.005 | 100% | 14328.1757 |  | 0 | KOUSHIK MANDAL | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 153.894 | SQM | 153.89 | 0.004 | 100% | 49694.1588 |  | 0 | SHEKAR T | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.7844 | SQM | 12.78 | 0.0044 | 99.97% | 3851.7898 |  | 0 | MORSELIM KHAN | 188168.9222
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 12.54 | SQM | 0 | 12.54 | 0% | 0 |  | 0 | TOTAL | 195968.9222
MORSELIM KHAN | FOOTING RCC | 50 | 225 | 11.081 | CUM | 11.08 | 0.001 | 99.99% | 2493 |  | 0
MORSELIM KHAN | PEDESTAL COLUMN RCC | 51 | 1500 | 1.6 | CUM | 1.6 | 0 | 100% | 2400 |  | 0
MORSELIM KHAN | PLINTH BEAM RCC | 53 | 900 | 4.674 | CUM | 4.67 | 0.004 | 99.91% | 4203 |  | 0
MORSELIM KHAN | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.381 | CUM | 3.38 | 0.001 | 99.97% | 6760 |  | 0
MORSELIM KHAN | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 17.149 | CUM | 17.15 | -0.001 | 100% | 3858.75 |  | 0
MORSELIM KHAN | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.808 | CUM | 1.81 | -0.002 | 100.1% | 3620 |  | 0
MORSELIM KHAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.626 | CUM | 0 | 0.626 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
MORSELIM KHAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
MORSELIM KHAN | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.435 | SQM | 39.44 | -0.005 | 100% | 11886.9005 |  | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 128.662 | SQM | 128.66 | 0.002 | 100% | 41546.8872 |  | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.784 | SQM | 12.78 | 0.004 | 99.97% | 3851.7898 |  | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 15.495 | SQM | 0 | 15.495 | 0% | 0 |  | 0
MORSELIM KHAN | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.294 | CUM | 2.29 | 0.004 | 99.83% | 4580 |  | 0
MORSELIM KHAN | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.957 | CUM | 13.96 | -0.003 | 100% | 3141 |  | 0
MORSELIM KHAN | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.808 | CUM | 1.81 | -0.002 | 100.1% | 3620 |  | 0
MORSELIM KHAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.699 | CUM | 0 | 0.699 | 0% | 0 |  | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.2 | MT | 0.2 | 0 | 100% | 1400 |  | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0 | 0.02 | 0% | 0 |  | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
MORSELIM KHAN | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 28.129 | SQM | 28.13 | -0.001 | 100% | 9083.7396 |  | 0
MORSELIM KHAN | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.455 | SQM | 0 | 2.455 | 0% | 0 |  | 0
MORSELIM KHAN | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.709 | CUM | 0 | 0.709 | 0% | 0 | 100% | 1418
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 600.75 |  | 0
MORSELIM KHAN | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.196 | CUM | 0.2 | -0.004 | 102% | 300 |  | 0
MORSELIM KHAN | ALL LEVEL COLUMN STARTER | 116 | 50 | 41 | NOS | 41 | 0 | 100% | 2050 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
MORSELIM KHAN | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 112.22 | SQM | 112.22 | 0 | 100% | 21742.8494 |  | 0
MORSELIM KHAN | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.46 | SQM | 133.46 | 0 | 100% | 25858.1419 |  | 0
MORSELIM KHAN | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 71.27 | SQM | 0 | 71.27 | 0% | 0 | 100% | 13808.705
MORSELIM KHAN | ELEVATION RCC BAND | 133 | 65.6 | 32.74 | RMT | 0 | 32.74 | 0% | 0 |  | 0
MORSELIM KHAN | ELEVATION GROOVE | 137 | 65.6 | 72.21 | RMT | 0 | 72.21 | 0% | 0 |  | 0
MORSELIM KHAN | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.66 | SQM | 0 | 0.66 | 0% | 0 |  | 0
MORSELIM KHAN | RCC SURFACE HACKING | 140 | 10.76 | 201.86 | SQM | 0 | 201.86 | 0% | 0 |  | 0
MORSELIM KHAN | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 72.04 | SQM | 0 | 72.04 | 0% | 0 | 100% | 10080.7013
MORSELIM KHAN | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 187.02 | SQM | 0 | 187.02 | 0% | 0 | 100% | 26170.0826
MORSELIM KHAN | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 201.853 | SQM | 0 | 201.853 | 0% | 0 | 100% | 39109.4225
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
MORSELIM KHAN | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 64.644 | SQM | 0 | 64.644 | 0% | 0 | 100% | 9045.7642
MORSELIM KHAN | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 206.23 | SQM | 0 | 206.23 | 0% | 0 | 100% | 28858.1764
MORSELIM KHAN | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 132.03 | SQM | 0 | 132.03 | 0% | 0 | 100% | 25581.0766
MORSELIM KHAN | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 12.3 | SQM | 0 | 12.3 | 0% | 0 | 100% | 1721.1636
MORSELIM KHAN | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 39.21 | SQM | 0 | 39.21 | 0% | 0 | 100% | 5486.7337
MORSELIM KHAN | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 138.781 | SQM | 0 | 138.781 | 0% | 0 | 100% | 26889.0963
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 50% | 4500
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1800
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 100 | RFT | 0 | 100 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 27 | 0 | 100% | 2079 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 249 | SFT | 0 | 249 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 0 | 15 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
MORSELIM KHAN | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 310 | 559.57 | SFT | 346.93 | 212.64 | 62% | 107548.3 |  | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 12300 | 1 | LUMP SUM | 1 | 0 | 100% | 12300 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 50% | 1500
195968.9222

## V159
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 91.86 | SQM | 91.86 | 0 | 100 | 4960.44 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100 | 1183.16 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 93.48 | CUM | 93.48 | 0 | 100 | 13191.8976 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.772 | CUM | 5.77 | 0 | 100 | 1221.3936 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 34.9 | CUM | 34.9 | 0 | 100 | 4925.088 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 91.86 | SQM | 91.86 | 0 | 100 | 2020.92 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 91.86 | SQM | 91.86 | 0 | 100 | 3949.98 | 0 | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 0 | 10.81 | 0 | 0 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.466 | CUM | 3.47 | 0 | 100 | 3470 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.886 | CUM | 2.89 | 0 | 100 | 2890 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 9.186 | CUM | 9.19 | 0 | 100 | 9190 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.3 | MT | 0.3 | 0 | 100 | 2100 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.8 | MT | 0.8 | 0 | 100 | 5600 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.5 | MT | 1.5 | 0 | 100 | 10500 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100 | 8342.5306 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100 | 8984.4955 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0 | 100 | 19144.4198 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 51.69 | SQM | 51.69 | 0 | 100 | 15578.9525 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 153.64 | 0 | 100 | 46305.8669 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 15.97 | 0 | 100 | 4813.2302 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.892 | CUM | 9.89 | 0 | 100 | 2225.25 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.442 | CUM | 2.44 | 0 | 100 | 3660 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.33 | CUM | 4.33 | 0 | 100 | 3897 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0 | 100 | 6080 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | 0 | 100 | 3795.75 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100 | 3540 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.99 | CUM | 0.99 | 0 | 100 | 1485 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.7 | MT | 0.7 | 0 | 100 | 4900 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.2 | MT | 0.2 | 0 | 100 | 1400 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 49.88 | 0 | 100 | 15033.433 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 132.67 | 0 | 100 | 39985.6766 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 12.33 | 0 | 100 | 3716.1634 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 16.88 | 0 | 100 | 5087.497 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.943 | CUM | 2.94 | 0 | 100 | 5880 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.7 | CUM | 13.7 | 0 | 100 | 3082.5 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.99 | CUM | 1.99 | 0 | 100 | 3980 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.937 | CUM | 0.94 | 0 | 100 | 1410 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100 | 1750 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.03 | MT | 0.03 | 0 | 100 | 210 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100 | 2441.2752 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 27.13 | 0 | 100 | 8176.765 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 2.75 | 0 | 100 | 828.828 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0 | 100 | 542.25 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0.22 | 0 | 100 | 330 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 115.89 | SQM | 115.89 | 0 | 100 | 22453.9193 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.21 | SQM | 133.21 | 0 | 100 | 25809.7039 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100 | 13041.4471 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 32.04 | 0 | 100 | 2101.824 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 32.05 | 0 | 100 | 2102.48 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0 | 100 | 2224.4148 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100 | 10023.3292 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100 | 27220.972 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100 | 40362.4166 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12500 | 1 | LUMP SUM | 1 | 0 | 100 | 12500 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0 | 100 | 10409.5415 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | 0 | 100 | 30850.808 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100 | 27543.7843 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100 | 1624.6105 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100 | 4677.9268 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100 | 29719.6193 | 0 | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 51.31 | SQM | 51.31 | 0 | 100 | 22092.0336 | 0 | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 86.135 | SQM | 86.14 | 0 | 100 | 37088.4384 | 0 | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 22.29 | SQM | 22.29 | 0 | 100 | 4798.5912 | 0 | 0
SHOKAT KHATRI | BEDROOM SCREED CONCRETE | 176 | 215.28 | 30.33 | SQM | 0 | 30.33 | 0 | 0 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 32.08 | SQM | 32.08 | 0 | 100 | 6906.1824 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 19 | SQM | 19 | 0 | 100 | 3800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 18.048 | SQM | 18.05 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 15 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 42.27 | RMT | 42.27 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 111.25 | RMT | 111.25 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 27.298 | RMT | 27.3 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 55.793 | SQM | 55.79 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 40.23 | RMT | 40.23 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 56.56 | SQM | 56.56 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.945 | RMT | 50.95 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.367 | RMT | 4.37 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 11.171 | SQM | 11.17 | 0 | 99.991
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 22.057 | RMT | 22.05 | 0.01 | 99.968
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1450 | SFT | 1450 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.062 | SQM | 4.06 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 15.16 | SQM | 15.16 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 6.912 | SQM | 6.91 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 33.074 | SQM | 33.07 | 0 | 100
PRAKASH JANA | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 208.534 | SQM | 0 | 208.53 | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 33.29 | RMT | 33.29 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 100 | RFT | 100 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 27 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 249 | SFT | 249 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 15 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 163 | 417 | SFT | 417 | 0 | 100
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0.5 | 0.5 | 50
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 78.296 | SQM | 78.3 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 78.296 | SQM | 78.3 | 0 | 100
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 78.296 | SQM | 78.3 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 26.716 | SQM | 26.72 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 26.716 | SQM | 26.72 | 0 | 100
INDAL SAHNI | CUSTOMIZATION TOILET TILE WORK | 436 | 1057.74 | 3.478 | SQM | 3.48 | 0 | 100
SHOKAT | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 3.806 | SQM | 3.81 | 0 | 100
SHOKAT | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 6.229 | SQM | 6.23 | 0 | 100
INDAL SAHNI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 228 | 16.908 | SQM | 16.91 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION FRONT ELEVATION STUCCO PAINT | 534 | 96.88 | 7.414 | SQM | 7.41 | 0 | 100
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100

## V160
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100 | 12441.1392 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 151.1 | SQM | 0 | 151.1 | 0 | 0 | 0 | 0
SUBHASMITA DAS | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 0 | 7.95 | 0 | 0 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100 | 9000 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0.13 | 0 | 100 | 1300 | 0 | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100 | 7980.8602 | 0 | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100 | 16492.1702 | 0 | 0
MANJUNATHA R | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100 | 13653.0576 | 0 | 0
MANJUNATHA R | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100 | 38912.7211 | 0 | 0
MANJUNATHA R | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
MANJUNATHA R | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0 | 100 | 2787.876 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100 | 1830 | 0 | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100 | 3525 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100 | 6600 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100 | 1350 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0.15 | 0 | 100 | 1500 | 0 | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100 | 11826.6221 | 0 | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 107.8 | SQM | 107.8 | 0 | 100 | 32490.0576 | 0 | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
MANJUNATHA R | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.81 | SQM | 9.81 | 0 | 100 | 2956.6555 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.83 | CUM | 0.83 | 0 | 100 | 2490 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100 | 975 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100 | 1425 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0.03 | 0 | 100 | 225 | 0 | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100 | 7275.6029 | 0 | 0
MANJUNATHA R | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 1.89 | 0 | 100 | 569.6309 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100 | 533.25 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.17 | CUM | 0.17 | 0 | 100 | 510 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 85 | 9.59 | 89.862 | 16468.92 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 13.557 | SQM | 13.56 | 0 | 100 | 2627.2771 | 0 | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100 | 25056.0086 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0 | 100 | 12200.5634 | 0 | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 30.1 | 0 | 100 | 1974.56 | 0 | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 66.89 | 0 | 100 | 4387.984 | 0 | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0.5 | 0 | 100 | 80.73 | 0 | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100 | 9397.5 | 0 | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100 | 2119.72 | 0 | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100 | 8373.5309 | 0 | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 150.23 | 26.51 | 85 | 21021.9844 | 0 | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 131.57 | 0 | 100 | 25491.9506 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13500 | 1 | LUMP SUM | 1 | 0 | 100 | 13500 | 0 | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100 | 11425.4478 | 0 | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 228.24 | 0 | 100 | 31938.0797 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 22.8 | SQM | 22.8 | 0 | 100 | 3190.4496 | 0 | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.17 | SQM | 109.17 | 0 | 100 | 21151.9058 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100 | 1365.7363 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100 | 4780.0771 | 0 | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 99.15 | 0 | 100 | 19210.5108 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 163.891 | SQM | 163.89 | 0 | 100 | 35282.2392 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 16.008 | SQM | 16.01 | 0 | 100
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 24.667 | SQM | 24.67 | 0 | 100
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 78.421 | SQM | 78.42 | 0 | 100
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 103.088 | SQM | 0 | 103.09 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 16 | NOS | 0 | 16 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 345.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 345.5 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 524.43 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 535.5 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 541.25 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 8 | 8 | #VALUE!
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.81 | RMT | 37.81 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 108.232 | RMT | 108.23 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 34.15 | RMT | 34.15 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 51.018 | SQM | 51.02 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.42 | RMT | 47.42 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 46.72 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 35.755 | RMT | 35.76 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 2.67 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 4.67 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 8.92 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 19.18 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 5.56 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 15.422 | SQM | 15.42 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.74 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 17.51 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 7.5 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 35.08 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.121 | SQM | 126.12 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5536.3594 | 29.0369 | RMT | 29.04 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | PU POLISH FOR MAIN DOOR | 355 | 147.4522 | 47.473 | SFT | 47.47 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 5456.4 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100

## V161
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
SUBHASMITA DAS | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
SUBHASMITA DAS | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100 | 12441.1392 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100 | 2952.81 | 0 | 0
SUBHASMITA DAS | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100 | 1121.904 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.27 | MT | 0.27 | 0 | 100 | 1890 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.42 | MT | 0.42 | 0 | 100 | 2940 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.53 | MT | 0.53 | 0 | 100 | 3710 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0.49 | 0 | 100 | 3430 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.13 | MT | 0.13 | 0 | 100 | 910 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100 | 13653.0576 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100 | 38912.7211 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 15.17 | 0 | 100 | 4572.1166 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100 | 1440 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.47 | MT | 0.47 | 0 | 100 | 3290 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 0.88 | MT | 0.88 | 0 | 100 | 6160 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100 | 11826.6221 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100 | 39171.9182 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 16.19 | 0 | 100 | 4879.5365 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100 | 1305 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.13 | MT | 0.13 | 0 | 100 | 910 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.19 | MT | 0.19 | 0 | 100 | 1330 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0.03 | 0 | 100 | 210 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100 | 7275.6029 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 3.5 | 0 | 100 | 1054.872 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100 | 533.25 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100 | 570 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 108.15 | 0 | 100 | 20954.2788 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 133.76 | 0 | 100 | 25916.2675 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0 | 100 | 12200.5634 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0 | 0 | 0 | 0
SUBHASMITA DAS | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 66.89 | 0 | 100 | 4387.984 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0 | 0 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100 | 2119.72 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100 | 8373.5309 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100 | 24731.5817 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 177.87 | 0 | 100 | 34462.6682 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100 | 11425.4478 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 258.15 | 0 | 100 | 36123.4458 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100 | 24474.7526 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100 | 1365.7363 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100 | 4780.0771 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 117.1 | 0 | 100 | 22688.3592 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 254.03 | 160.21 | SQM | 160.21 | 0 | 100 | 40698.1463 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 254.03 | 18.82 | SQM | 18.82 | 0 | 100 | 4780.8446 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 190.52 | 14.21 | SQM | 14.21 | 0 | 100 | 2707.2892 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 254.03 | 65.55 | SQM | 65.55 | 0 | 100 | 16651.6665 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 254.03 | 91.03 | SQM | 91.03 | 0 | 100 | 23124.3509 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 295 | 8 | NOS | 8 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 164.391 | SQM | 0 | 164.39 | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 104.234 | SQM | 0 | 104.23 | 0
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 76.8785 | SQM | 76.88 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 145.1194 | SQM | 145.12 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 59.84 | SQM | 59.84 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 218.6243 | SQM | 218.62 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 81.65 | SQM | 81.65 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 26.2549 | SQM | 26.25 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 9.76 | SQM | 9.76 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 12 | 4 | 75
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.81 | RMT | 37.81 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 108.232 | RMT | 108.23 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 34.15 | RMT | 34.15 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 0 | 3 | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.018 | SQM | 51.02 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.42 | RMT | 47.42 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 46.72 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 35.755 | RMT | 35.76 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 2.67 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 4.67 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 0 | 8.92 | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 0 | 19.18 | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 5.55 | 0.01 | 99.856
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 15.422 | SQM | 0 | 15.42 | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.74 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 17.51 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 7.5 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 35.08 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.121 | SQM | 126.12 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 23.906 | RMT | 23.3 | 0.6 | 97.473
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100

## V162
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100 | 2952.81 | 0 | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 5.5783 | CUM | 0.57 | 5.01 | 10.254 | 80.4384 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.27 | MT | 0.27 | 0 | 100 | 1890 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.42 | MT | 0.42 | 0 | 100 | 2940 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.53 | MT | 0.53 | 0 | 100 | 3710 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0.49 | 0 | 100 | 3430 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.13 | MT | 0.13 | 0 | 100 | 910 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100 | 13653.0576 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100 | 38912.7211 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 15.17 | 0 | 100 | 4572.1166 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100 | 1440 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.47 | MT | 0.47 | 0 | 100 | 3290 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 0.88 | MT | 0.88 | 0 | 100 | 6160 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100 | 11826.6221 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100 | 39171.9182 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 16.19 | 0 | 100 | 4879.5365 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100 | 1305 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.13 | MT | 0.13 | 0 | 100 | 910 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.19 | MT | 0.19 | 0 | 100 | 1330 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0.03 | 0 | 100 | 210 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100 | 7275.6029 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 3.5 | 0 | 100 | 1054.872 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100 | 533.25 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100 | 570 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 108.15 | 0 | 100 | 20954.2788 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 133.76 | 0 | 100 | 25916.2675 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 18.61 | 44.36 | 29.557 | 3605.7247 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 30.1 | 0 | 100 | 1974.56 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 66.89 | 0 | 100 | 4387.984 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0 | 0 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100 | 2119.72 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100 | 8373.5309 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100 | 24731.5817 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 177.87 | 0 | 100 | 34462.6682 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100 | 11425.4478 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 258.15 | 0 | 100 | 36123.4458 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100 | 24474.7526 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100 | 1365.7363 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100 | 4780.0771 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 117.1 | 0 | 100 | 22688.3592 | 0 | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 31.122 | SQM | 31.12 | 0 | 100 | 13399.0272 | 0 | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 83.426 | SQM | 83.43 | 0 | 100 | 35921.6208 | 0 | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 7.897 | SQM | 7.9 | 0 | 100 | 1700.712 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 14.96 | SQM | 14.96 | 0 | 100 | 3220.5888 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 19 | NOS | 19 | 0 | 100 | 3800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100 | 4299.1416 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 61.966 | SQM | 61.97 | 0 | 100 | 6003.4057 | 0 | 0
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 164.391 | SQM | 164.39 | 0 | 100 | 7962.7228 | 0 | 0
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 104.234 | SQM | 104.23 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 76.8785 | SQM | 76.88 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 145.1194 | SQM | 145.12 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 59.84 | SQM | 59.84 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 218.6243 | SQM | 218.62 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 81.65 | SQM | 81.65 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 26.2549 | SQM | 26.25 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 9.76 | SQM | 9.76 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 12 | 4 | 75
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 37.81 | RMT | 37.81 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 108.232 | RMT | 108.23 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 34.15 | RMT | 34.15 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.018 | SQM | 51.02 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 47.42 | RMT | 47.42 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 46.72 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 35.755 | RMT | 35.76 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 2.67 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 4.67 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 8.92 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 19.18 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 5.56 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 15.422 | SQM | 15.42 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.736 | SQM | 3.74 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 17.51 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 7.5 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 35.08 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.121 | SQM | 126.12 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 24.33 | RMT | 23.3 | 1.03 | 95.775
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100

## V163
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 65.38 | 3.29 | 95.209 | 3530.52 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100 | 2952.81 | 0 | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 5.5783 | CUM | 0 | 5.58 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 0 | 6.87 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.27 | MT | 0.27 | 0 | 100 | 1890 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.42 | MT | 0.42 | 0 | 100 | 2940 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.53 | MT | 0.53 | 0 | 100 | 3710 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0 | 0.49 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.2 | MT | 0 | 1.2 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 0 | 15.17 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 0 | 3.26 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 0 | 15.33 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0 | 0.96 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.47 | MT | 0 | 0.47 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 0.88 | MT | 0 | 0.88 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 0 | 129.97 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 0 | 16.19 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 0 | 2.21 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0 | 0.87 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.19 | MT | 0 | 0.19 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 0 | 3.5 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0 | 0.38 | 0 | 0 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 0 | 108.15 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 0 | 133.76 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.97 | 0 | 0 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0 | 0 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0 | 0 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0 | 0 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 0 | 197 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 0 | 59.84 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 0 | 176.74 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 0 | 177.87 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 0 | 258.15 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 0 | 126.32 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 0 | 117.1 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V164
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.03 | 0.64 | 99.064 | 2925.29 | 0 | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 5.5783 | CUM | 0 | 5.58 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 0 | 6.87 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.27 | MT | 0.27 | 0 | 100 | 1890 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.42 | MT | 0.42 | 0 | 100 | 2940 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.53 | MT | 0.53 | 0 | 100 | 3710 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0 | 0.49 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.2 | MT | 0 | 1.2 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 0 | 15.17 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 0 | 3.26 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 0 | 15.33 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0 | 0.96 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.47 | MT | 0 | 0.47 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 0.88 | MT | 0 | 0.88 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 0 | 129.97 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 0 | 16.19 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 0 | 2.21 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0 | 0.87 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.19 | MT | 0 | 0.19 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 0 | 3.5 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0 | 0.38 | 0 | 0 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 41 | 3 | 93.182 | 2050 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 0 | 108.15 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 0 | 133.76 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.97 | 0 | 0 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0 | 0 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0 | 0 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0 | 0 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 0 | 197 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 0 | 59.84 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 0 | 176.74 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 0 | 177.87 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 0 | 258.15 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 0 | 126.32 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 0 | 117.1 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V165
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 0 | 59.29 | 0% | 0 |  | 0 | AAIDHUL MIAH | 6766.1105
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 68653.5208
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100% | 21563.8416 |  | 0 | KRIUTTIBAS DAS | 15750
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100% | 1120.46 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100% | 11084.976 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0.004 | 99.93% | 1176.9408 |  | 0 | NAGARAJ | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100% | 3882.2112 |  | 0 | PRAKASH H N | 15750
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100% | 1304.38 |  | 0 | RAMAKRUSHNA PRADHAN | 7050.5078
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 100 | 51.12 | 66.17% | 4300 |  | 0 | RUPAK NAYAK | 55742.8815
SUBHASMITA DAS | SETBACK AREA SOIL FILLING | 16 | 141.12 | 9.27 | CUM | 0 | 9.27 | 0% | 0 |  | 0 | SANTOSH KUMAR | 58737.691
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0.003 | 99.94% | 5090 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0.002 | 99.93% | 2780 |  | 0 | SAVITA DEVI | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 2.96 | 2.969 | 49.92% | 2960 |  | 0 | SHOKAT | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100% | 2775 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100% | 3375 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100% | 9375 |  | 0 | SUBHASMITA DAS | 10800
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0 | V VENKATANARAYANA | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100% | 7980.8602 |  | 0 | YELLAPPA C | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100% | 7124.9069 |  | 0 | RABIUL MOLLA | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | KOUSHIK MANDAL | 0
MANJUNATHA R | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 41.28 | SQM | 41.28 | 0 | 100% | 13330.1376 |  | 0 | SHEKAR T | 0
MANJUNATHA R | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 125.99 | SQM | 125.99 | 0 | 100% | 40684.6908 |  | 0 | MORSELIM KHAN | 0
MANJUNATHA R | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.26 | SQM | 12.26 | 0 | 100% | 3958.9992 |  | 0 | TOTAL | 239250.7116
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100% | 4855.4251 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100% | 2227.5 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100% | 1980 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100% | 4266 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100% | 5700 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0.003 | 99.98% | 2943 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0.001 | 99.94% | 3400 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100% | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100% | 8250 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 41.58 | SQM | 41.58 | 0 | 100% | 13427.0136 |  | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 125.21 | SQM | 125.21 | 0 | 100% | 40432.8132 |  | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.26 | SQM | 12.26 | 0 | 100% | 3958.9992 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100% | 5313.541 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0.004 | 99.83% | 4640 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0.001 | 99.99% | 3051 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | -0.004 | 100.3% | 2820 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0.84 | 0.003 | 99.64% | 2520 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100% | 750 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100% | 150 |  | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100% | 3487.536 |  | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 22.88 | SQM | 22.88 | 0 | 100% | 7388.4096 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100% | 578.6726 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | -0.005 | 100.3% | 445.5 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0.07 | 0 | 100% | 210 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100% | 2150 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 106.054 | SQM | 100.75 | 5.304 | 95% | 19520.514 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 121.05 | SQM | 121.05 | 0 | 100% | 23453.6796 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0.002 | 100% | 12148.2504 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 27.15 | RMT | 24.44 | 2.71 | 90.02% | 1603.264 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 43.88 | RMT | 39.49 | 4.39 | 90% | 2590.544 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.03 | 0.11 | 90.35% | 166.3038 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100% | 1909.0392 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100% | 8472.8826 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100% | 23335.0603 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 156.89 | 8.261 | 95% | 30397.7513 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0.002 | 100% | 8628.2071 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0.003 | 100% | 24611.2402 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 129.84 | 6.83 | 95% | 25156.7597 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100% | 1241.1968 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100% | 5169.0881 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 98.5 | SQM | 93.58 | 4.92 | 95.01% | 18131.3122 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING (coating done for sunken as well) | 168 | 215.28 | 142.12 | SQM | 0 | 142.12 | 0% | 0 | 100% | 30595.5936
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 52.57 | SQM | 0 | 52.57 | 0% | 0 | 100% | 11317.2696
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 26.44 | SQM | 0 | 26.44 | 0% | 0 | 100% | 2846.0016
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 81.98 | SQM | 0 | 81.98 | 0% | 0 | 100% | 17648.6544
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 26.44 | SQM | 0 | 26.44 | 0% | 0 | 100% | 2846.0016
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 0 | 17 | 0% | 0 | 100% | 3400
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | -0.005 | 100% | 6441.1776 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100% | 3330.7344 | 95% | 3164.1977
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | -0.001 | 100% | 5851.468 | 95% | 5558.8793
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 0 | 362.319 | 0% | 0 | 95% | 11115.0049
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0.0012 | 100% | 24623.9417 | 95% | 23392.7998
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0.0012 | 100% | 8210.014 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 0 | 508.3612 | 0% | 0 | 90% | 12311.9999
SANTOSH KUMAR | STAIRCASE GRANITE | 215 | 301.392 | 17.75 | SQM | 0 | 17.75 | 0% | 0 | 100% | 5349.708
SANTOSH KUMAR | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
SANTOSH KUMAR | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 0 | 15 | 0% | 0 | 100% | 5250
SANTOSH KUMAR | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.4 | RMT | 0 | 46.4 | 0% | 0 | 100% | 3804.8
SANTOSH KUMAR | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 0 | 103.53 | 0% | 0 | 100% | 3395.784
SANTOSH KUMAR | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.07 | RMT | 0 | 23.07 | 0% | 0 | 100% | 3026.784
SANTOSH KUMAR | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 0 | 49.52 | 0% | 0 | 100% | 9062.16
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 0 | 48.42 | 0% | 0 | 90% | 2144.0376
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 0 | 46 | 0% | 0 | 100% | 8418
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 0 | 50.44 | 0% | 0 | 90% | 2233.4832
SANTOSH KUMAR | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 0 | 2.5 | 0% | 0 | 100% | 457.5
SANTOSH KUMAR | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 0 | 4.19 | 0% | 0 | 90% | 185.5332
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 0 | 4.01 | 0% | 0 |  | 0
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 0 | 9.98 | 0% | 0 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 183 | 10.18 | SQM | 0 | 10.18 | 0% | 0 | 100% | 1862.94
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 14 | RMT | 0 | 14 | 0% | 0 | 90% | 619.92
SANTOSH KUMAR | CAR PARKING AREA TILING | 234 | 183 | 11.138 | SQM | 0 | 11.138 | 0% | 0 |  | 0
SANTOSH KUMAR | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 0 | 1055 | 0% | 0 | 100% | 2637.5
SANTOSH KUMAR | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.41 | SQM | 0 | 3.41 | 0% | 0 | 100% | 624.03
SANTOSH KUMAR | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 0 | 17.34 | 0% | 0 | 90% | 2855.898
SANTOSH KUMAR | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 6.62 | SQM | 0 | 6.62 | 0% | 0 | 100% | 1211.46
SANTOSH KUMAR | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 33.99 | SQM | 0 | 33.99 | 0% | 0 | 90% | 5598.153
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100% | 15500 | 90% | 13950
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 90% | 1800
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 | 90% | 8100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 | 90% | 5400
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 90% | 450
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 90% | 1800
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 | 90% | 10800
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 | 90% | 2341.7874
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 | 90% | 2030.6702
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 | 90% | 1366.2
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 | 50% | 1311.8502
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 50% | 200
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 477.9 | 1 | LUMP SUM | 1 | 0 | 100% | 477.9 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 96.574 | SQM | 96.57 | 0.004 | 100% | 4677.6577 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 96.574 | SQM | 96.57 | 0.004 | 100% | 1559.6055 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 96.574 | SQM | 0 | 96.574 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 18.848 | SQM | 18.85 | -0.002 | 100% | 304.4275 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 18.848 | SQM | 0 | 18.848 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.624 | CUM | 4.62 | 0.004 | 99.91% | 1039.5 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100% | 250 |  | 0
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 45.091 | SQM | 45.09 | 0.001 | 100% | 14560.4628 |  | 0
NAGARAJ | CUSTOMIZATION ROOM LINTEL CHAJJA SHUTTERING | 497 | 322.92 | 3.178 | SQM | 3.18 | -0.002 | 100.1% | 1026.8856 |  | 0
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 16.5 | SQM | 16.5 | 0 | 100% | 5328.18 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR INTERNAL WALL PLASTERING | 500 | 139.932 | 65.546 | SQM | 0 | 65.546 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR EXTERNAL WALL PLASTERING | 501 | 193.752 | 69.843 | SQM | 34.92 | 34.923 | 50% | 6765.8198 | 50% | 6766.1105
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR BLOCK WORK | 502 | 193.752 | 40.26 | SQM | 40.26 | 0 | 100% | 7800.4555 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.36531 | MT | 0.37 | -0.004687 | 101.3% | 2775 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.25218 | MT | 0.25 | 0.002183 | 99.13% | 1875 |  | 0
239250.7116

## V166
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 0 | 59.29 | 0% | 0 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100% | 21563.8416 |  | 0 | EBI ABRAHAM | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100% | 1120.46 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18 | CUM | 18 | 0 | 100% | 2540.16 |  | 0 | KRIUTTIBAS DAS | 10000
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 60.55 | CUM | 60.55 | 0 | 100% | 8544.816 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0.004 | 99.93% | 1176.9408 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100% | 3882.2112 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100% | 1304.38 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 151.12 | SQM | 100 | 51.12 | 66.17% | 4300 |  | 0 | RAMAKRUSHNA PRADHAN | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 9.27 | CUM | 9.27 | 0 | 100% | 1308.1824 |  | 0 | RUPAK NAYAK | 50393.9606
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0.003 | 99.94% | 5090 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0.002 | 99.93% | 2780 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | -0.001 | 100% | 5930 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100% | 2775 |  | 0 | SHOKAT | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100% | 3375 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100% | 9375 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0 | SUBHASMITA DAS | 12000
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0 | UDHABHAI R PARMAR | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100% | 7980.8602 |  | 0 | V VENKATANARAYANA | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100% | 7124.9069 |  | 0 | YELLAPPA C | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | RABIUL MOLLA | 0
MANJUNATHA R | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 41.28 | SQM | 41.28 | 0 | 100% | 13330.1376 |  | 0 | KOUSHIK MANDAL | 0
MANJUNATHA R | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 125.99 | SQM | 125.99 | 0 | 100% | 40684.6908 |  | 0 | SHEKAR T | 0
MANJUNATHA R | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.26 | SQM | 12.26 | 0 | 100% | 3958.9992 |  | 0 | MORSELIM KHAN | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100% | 4855.4251 |  | 0 | TOTAL | 72393.9606
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100% | 2227.5 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100% | 1980 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100% | 4266 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100% | 5700 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0.003 | 99.98% | 2943 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0.001 | 99.94% | 3400 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100% | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100% | 8250 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 41.58 | SQM | 41.58 | 0 | 100% | 13427.0136 |  | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 125.21 | SQM | 125.21 | 0 | 100% | 40432.8132 |  | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.26 | SQM | 12.26 | 0 | 100% | 3958.9992 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100% | 5313.541 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0.004 | 99.83% | 4640 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0.001 | 99.99% | 3051 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | -0.004 | 100.3% | 2820 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0.84 | 0.003 | 99.64% | 2520 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100% | 750 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100% | 150 |  | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100% | 3487.536 |  | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 22.88 | SQM | 22.88 | 0 | 100% | 7388.4096 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100% | 578.6726 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | -0.005 | 100.3% | 445.5 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0.07 | 0 | 100% | 210 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100% | 2150 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 106.054 | SQM | 90.15 | 15.904 | 85% | 17466.7428 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 121.05 | SQM | 121.05 | 0 | 100% | 23453.6796 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0.002 | 100% | 12148.2504 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 27.15 | RMT | 24.44 | 2.71 | 90.02% | 1603.264 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 43.88 | RMT | 39.49 | 4.39 | 90% | 2590.544 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 193.752 | 1.14 | SQM | 1.03 | 0.11 | 90.35% | 199.5646 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100% | 1909.0392 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 51.47 | 9.08 | 85% | 7202.3 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 141.75 | 25.01 | 85% | 19835.361 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0.001 | 100% | 31998.1428 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0.002 | 100% | 8628.2071 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0.003 | 100% | 24611.2402 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100% | 26480.0858 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100% | 1241.1968 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100% | 5169.0881 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 98.5 | SQM | 98.5 | 0 | 100% | 19084.572 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 112.802 | SQM | 112.8 | 0.002 | 100% | 24283.584 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 15.608 | SQM | 15.61 | -0.002 | 100% | 3360.5208 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 14.979 | SQM | 14.98 | -0.001 | 100% | 1612.4472 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 82.216 | SQM | 82.22 | -0.004 | 100% | 17700.3216 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 14.979 | SQM | 14.98 | -0.001 | 100% | 1612.4472 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 12 | NOS | 12 | 0 | 100% | 2400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 0 | 29.915 | 0% | 0 | 100% | 6440.1012
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 0 | 34.38 | 0% | 0 | 100% | 3330.7344
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 0 | 362.319 | 0% | 0 | 100% | 5851.4518
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 0 | 362.319 | 0% | 0 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY (INCLUDING 30SQM FOR CHEJJA) | 192 | 48.438 | 538.3612 | SQM | 0 | 538.3612 | 0% | 0 | 100% | 26077.1398
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER (INCLUDING 30SQM FOR CHEJJA) | 193 | 16.15 | 538.3612 | SQM | 0 | 538.3612 | 0% | 0 | 100% | 8694.5334
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT (INCLUDING 30SQM FOR CHEJJA) | 194 | 26.91 | 538.3612 | SQM | 0 | 538.3612 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | STAIRCASE GRANITE | 215 | 301.392 | 17.75 | SQM | 0 | 17.75 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | DOOR OPENING GRANITE | 218 | 350 | 11 | NOS | 0 | 11 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.4 | RMT | 0 | 46.4 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 0 | 103.53 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.07 | RMT | 0 | 23.07 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 0 | 49.52 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 0 | 48.42 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 0 | 46 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 0 | 50.44 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 0 | 2.5 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 0 | 4.19 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 0 | 4.01 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 0 | 9.98 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | BALCONY & SITOUT TILING | 232 | 183 | 10.18 | SQM | 0 | 10.18 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 14 | RMT | 0 | 14 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | CAR PARKING AREA TILING | 234 | 183 | 11.138 | SQM | 0 | 11.138 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 0 | 1055 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.41 | SQM | 0 | 3.41 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 0 | 17.34 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 6.62 | SQM | 0 | 6.62 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 33.99 | SQM | 0 | 33.99 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100% | 15500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 4000
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 12000
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1000
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 3000
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 14425.32 | 1 | LUMP SUM | 1 | 0 | 100% | 14425.32 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 407 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION BALCONY TAP POINT WORK | 432 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
72393.9606

## V167
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100% | 3201.66 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100% | 21563.8416 |  | 0 | KRIUTTIBAS DAS | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100% | 1120.46 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.5291 | CUM | 78.53 | -0.0009 | 100% | 11082.1536 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0.004 | 99.93% | 1176.9408 |  | 0 | NAGARAJ | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100% | 3882.2112 |  | 0 | PRAKASH H N | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100% | 1304.38 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 59.29 | SQM | 59.29 | 0 | 100% | 2549.47 |  | 0 | RUPAK NAYAK | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 9.27 | CUM | 0 | 9.27 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SARAT BARMAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0.003 | 99.94% | 5090 |  | 0 | SHOKAT | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0.002 | 99.93% | 2780 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | -0.001 | 100% | 5930 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.37 | MT | 0.37 | 0 | 100% | 2590 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100% | 3150 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100% | 3850 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100% | 3500 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.25 | MT | 1.25 | 0 | 100% | 8750 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.14 | MT | 0.14 | 0 | 100% | 980 |  | 0 | YELLAPPA C | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.14 | MT | 0.14 | 0 | 100% | 980 |  | 0 | RABIUL MOLLA | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0.003 | 99.99% | 10223.2166 |  | 0 | KOUSHIK MANDAL | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100% | 7124.9069 |  | 0 | SHEKAR T | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0.0017 | 100% | 18068.4504 |  | 0 | MORSELIM KHAN | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100% | 12441.4618 |  | 0 | TOTAL | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100% | 37972.3781 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100% | 3695.0659 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100% | 4855.4251 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100% | 2227.5 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100% | 1980 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100% | 4266 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100% | 5700 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0.003 | 99.98% | 2943 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0.001 | 99.94% | 3400 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100% | 915 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.5 | MT | 0.5 | 0 | 100% | 3500 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100% | 7700 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.14 | MT | 0.14 | 0 | 100% | 980 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100% | 12531.8794 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100% | 37737.2923 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100% | 3695.0659 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100% | 5313.541 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0.004 | 99.83% | 4640 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0.001 | 99.99% | 3051 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | -0.004 | 100.3% | 2820 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0.003 | 99.64% | 1260 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100% | 700 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.17 | MT | 0.17 | 0 | 100% | 1190 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0 | 0.02 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100% | 6895.849 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100% | 578.6726 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | -0.005 | 100.3% | 445.5 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100% | 105 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100% | 2150 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 0.002 | 100% | 21682.7863 |  | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100% | 23858.6213 |  | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0.002 | 100% | 12148.2504 |  | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100% | 2000.144 |  | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 46.88 | 0 | 100% | 3075.328 |  | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100% | 184.0644 |  | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100% | 1909.0392 |  | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100% | 8472.8826 |  | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100% | 23335.0603 |  | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0.001 | 100% | 31998.1428 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100% | 13000 |  | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0.002 | 100% | 8628.2071 |  | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0.003 | 100% | 24611.2402 |  | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100% | 26480.0858 |  | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100% | 1241.1968 |  | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100% | 5169.0881 |  | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 112.48 | 0 | 100% | 21793.225 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 118.151 | SQM | 118.15 | 0.001 | 100% | 25435.332 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 28.587 | SQM | 28.59 | -0.003 | 100% | 6154.8552 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 15.078 | SQM | 15.08 | -0.002 | 100% | 1623.2112 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 70.812 | SQM | 70.81 | 0.002 | 100% | 15243.9768 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 15.087 | SQM | 15.09 | -0.003 | 100% | 1624.2876 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 30 | NOS | 18 | 12 | 60% | 3600 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | -0.005 | 100% | 6441.1776 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100% | 3330.7344 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | -0.001 | 100% | 5851.468 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 362.32 | -0.001 | 100% | 11700.0374 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0.0012 | 100% | 24623.9417 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0.0012 | 100% | 8210.014 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 508.36 | 0.0012 | 100% | 13679.9676 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 17.75 | SQM | 17.75 | 0 | 100% | 5349.708 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100% | 900 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 12 | 3 | 80% | 4200 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.4 | RMT | 46.4 | 0 | 100% | 3804.8 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100% | 3395.784 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.07 | RMT | 23.07 | 0 | 100% | 3026.784 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100% | 4000 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 39.62 | 9.9 | 80.01% | 7250.46 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 38.74 | 9.68 | 80.01% | 1906.008 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 36.8 | 9.2 | 80% | 6734.4 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 40.35 | 10.09 | 80% | 1985.22 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2.5 | 0 | 100% | 457.5 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100% | 206.148 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100% | 733.83 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100% | 491.016 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 10.18 | SQM | 10.18 | 0 | 100% | 1862.94 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 14 | RMT | 14 | 0 | 100% | 688.8 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 11.138 | SQM | 11.14 | -0.002 | 100% | 2038.62 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100% | 2637.5 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.41 | SQM | 3.07 | 0.34 | 90.03% | 561.81 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 15.61 | 1.73 | 90.02% | 2856.63 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 6.62 | SQM | 5.3 | 1.32 | 80.06% | 969.9 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 33.99 | SQM | 27.19 | 6.8 | 79.99% | 4975.77 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 144.788 | SQM | 144.79 | -0.002 | 100% | 9350.5382 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25 | RMT | 25 | 0 | 100% | 138375 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100% | 5625 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100% | 350 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100% | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100% | 800 |  | 0
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 227 | 354 | SFT | 354 | 0 | 100% | 80358 |  | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | PAINT REWORK IN VILLAS AFTER WALL CRACK TREATMENT | 369 | 3060 | 1 | LUMP SUM | 1 | 0 | 100% | 3060 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET BORE PACKING REWORK | 391 | 200 | 12 | NOS | 12 | 0 | 100% | 2400 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 96.574 | SQM | 96.57 | 0.004 | 100% | 4677.6577 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 96.574 | SQM | 96.57 | 0.004 | 100% | 1559.6055 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 96.574 | SQM | 96.57 | 0.004 | 100% | 2598.6987 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 18.848 | SQM | 18.85 | -0.002 | 100% | 304.4275 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 18.848 | SQM | 18.85 | -0.002 | 100% | 608.7042 |  | 0
KRISHNAKUMAR SAHANI | CUSTOMIZATION TOILET TILE WORK | 436 | 1088.588 | 3.6 | SQM | 3.24 | 0.36 | 90% | 3527.0251 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 3.625 | SQM | 3.63 | -0.005 | 100.1% | 781.4664 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 5.982 | SQM | 5.98 | 0.002 | 99.97% | 2574.7488 |  | 0
KRISHNAKUMAR SAHANI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 263.83 | 18.46 | SQM | 16.61 | 1.85 | 89.98% | 4382.2163 |  | 0
SUBHASMITA DAS | TERRACE WASHING MACHINE PLATFORM CONSTRUCTION | 549 | 800 | 1 | LUMP SUM | 1 | 0 | 100% | 800 |  | 0

## V168
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.5291 | CUM | 78.53 | 0 | 100 | 11082.1536 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 59.29 | SQM | 59.29 | 0 | 100 | 2549.47 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.37 | MT | 0.37 | 0 | 100 | 2590 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.25 | MT | 1.25 | 0 | 100 | 8750 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.14 | MT | 0.14 | 0 | 100 | 980 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.14 | MT | 0.14 | 0 | 100 | 980 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0 | 100 | 18068.4504 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100 | 4855.4251 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100 | 915 | 0 | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.14 | MT | 0.14 | 0 | 100 | 980 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100 | 5313.541 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100 | 140 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100 | 578.6726 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100 | 105 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 0 | 100 | 21682.7863 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 46.88 | 0 | 100 | 3075.328 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 65.31 | 47.17 | 58.064 | 12653.9431 | 0 | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 254.03 | 153.36 | SQM | 153.36 | 0 | 100 | 38958.0408 | 0 | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 254.03 | 13.973 | SQM | 13.97 | 0 | 100 | 3548.7991 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 190.52 | 15.87 | SQM | 15.87 | 0 | 100 | 3023.5524 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 254.03 | 66.37 | SQM | 66.37 | 0 | 100 | 16859.9711 | 0 | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 254.03 | 93.098 | SQM | 93.1 | 0 | 100 | 23650.193 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 290 | 8 | NOS | 8 | 0 | 100 | 2320 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 508.36 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 20.12 | SQM | 0 | 20.12 | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 0 | 15 | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 0 | 41.17 | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 0 | 103.53 | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 0 | 19.57 | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 0 | 49.52 | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 0 | 48.42 | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 0 | 46 | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 50.44 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2.5 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 12.635 | SQM | 12.64 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 16.8 | RMT | 16.8 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 12.821 | SQM | 12.82 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.7 | SQM | 3.7 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 17.34 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.44 | SQM | 7.44 | 0 | 100
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 34.9 | SQM | 34.9 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 144.788 | SQM | 144.79 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.59 | RMT | 25.59 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 0 | 1 | 0
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 227 | 354 | SFT | 354 | 0 | 100
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
RUPAK NAYAK | ALL FLOOR INTERNAL WALL & CEILING ONE COAT EMULSION PAINT REWORK | 384 | 15000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 96.574 | SQM | 0 | 96.57 | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 96.574 | SQM | 0 | 96.57 | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 96.574 | SQM | 0 | 96.57 | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 18.848 | SQM | 0 | 18.85 | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 18.848 | SQM | 0 | 18.85 | 0

## V169
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 0 | 59.29 | 0% | 0 |  | 0 | AAIDHUL MIAH | 19086.7
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100% | 21563.8416 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100% | 1120.46 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.707 | CUM | 18.71 | -0.003 | 100% | 2640.3552 |  | 0 | KRIUTTIBAS DAS | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0.004 | 99.93% | 1176.9408 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 0 | 27.51 | 0% | 0 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 0 | 59.29 | 0% | 0 |  | 0 | NAGARAJ | 10875.9456
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 59.29 | SQM | 0 | 59.29 | 0% | 0 |  | 0 | PRAKASH H N | 1000
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 9.27 | CUM | 0 | 9.27 | 0% | 0 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0.003 | 99.94% | 5090 |  | 0 | RUPAK NAYAK | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0.002 | 99.93% | 2780 |  | 0 | SANTOSH KUMAR | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 0 | 5.929 | 0% | 0 |  | 0 | SARAT BARMAN | 1890
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.37 | MT | 0.37 | 0 | 100% | 2590 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100% | 3150 |  | 0 | SHOKAT | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100% | 3850 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0 | 0.5 | 0% | 0 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 27 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.25 | MT | 0 | 1.25 | 0% | 0 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 30 | 7500 | 1.25 | MT | 1.25 | 0 | 100% | 9375 |  | 0 | SUBHASMITA DAS | 4490.4
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.14 | MT | 0 | 0.14 | 0% | 0 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 33 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.14 | MT | 0 | 0.14 | 0% | 0 |  | 0 | YELLAPPA C | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0.003 | 99.99% | 10223.2166 |  | 0 | RABIUL MOLLA | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100% | 7124.9069 |  | 0 | KOUSHIK MANDAL | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0.0017 | 100% | 18068.4504 |  | 0 | SHEKAR T | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 0 | 41.28 | 0% | 0 |  | 0 | MORSELIM KHAN | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 41.28 | SQM | 41.28 | 0 | 100% | 13330.1376 |  | 0 | TOTAL | 37343.0456
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 0 | 125.99 | 0% | 0 |  | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 125.99 | SQM | 125.99 | 0 | 100% | 40684.6908 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 0 | 12.26 | 0% | 0 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.26 | SQM | 12.26 | 0 | 100% | 3958.9992 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 0 | 16.11 | 0% | 0 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 16.11 | SQM | 0 | 16.11 | 0% | 0 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100% | 2227.5 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100% | 1980 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100% | 4266 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 0 | 2.85 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 57 | 2000 | 2.85 | CUM | 2.85 | 0 | 100% | 5700 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 0 | 13.083 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0.003 | 99.98% | 2943 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 0 | 1.701 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0.001 | 99.94% | 3400 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.5 | MT | 0 | 0.5 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 71 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 0 | 1.1 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 75 | 7500 | 1.1 | MT | 1.1 | 0 | 100% | 8250 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.14 | MT | 0 | 0.14 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 78 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 0 | 41.58 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 41.58 | SQM | 41.58 | 0 | 100% | 13427.0136 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 0 | 125.21 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 125.21 | SQM | 125.21 | 0 | 100% | 40432.8132 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 0 | 12.26 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.26 | SQM | 12.26 | 0 | 100% | 3958.9992 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 0 | 17.63 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 17.63 | SQM | 0 | 17.63 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 0 | 2.324 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 90 | 2000 | 2.324 | CUM | 2.32 | 0.004 | 99.83% | 4640 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 0 | 13.561 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0.001 | 99.99% | 3051 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 0 | 1.406 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | -0.004 | 100.3% | 2820 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0 | 0.843 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0 | 0.1 | 0% | 0 | 100% | 700
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.17 | MT | 0 | 0.17 | 0% | 0 | 100% | 1190
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0 | 0.02 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 0 | 10.8 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0% | 0 | 100% | 3487.536
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 0 | 22.88 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 22.88 | SQM | 0 | 22.88 | 0% | 0 | 100% | 7388.4096
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 0 | 1.92 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.92 | SQM | 0 | 1.92 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0 | 0.41 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 111 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 0 | 1.975 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | -0.005 | 100.3% | 445.5 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0 | 0.07 | 0% | 0 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100% | 2150 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 1000 | 50% | 1000
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 0 | 111.912 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 123 | 193.75 | 111.91 | SQM | 89.53 | 22.38 | 80% | 17346.4375 |  | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 0 | 123.14 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 128 | 193.75 | 123.14 | SQM | 0 | 123.14 | 0% | 0 | 80% | 19086.7
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 0 | 62.702 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 131 | 193.75 | 62.7 | SQM | 0 | 62.7 | 0% | 0 |  | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 0 | 30.49 | 0% | 0 |  | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 0 | 46.88 | 0% | 0 |  | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0% | 0 |  | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 0 | 177.42 | 0% | 0 |  | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 0 | 60.55 | 0% | 0 |  | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0% | 0 |  | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 0 | 165.151 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 0 | 61.662 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 0 | 175.883 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 0 | 136.67 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 0 | 8.87 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 0 | 36.94 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 0 | 112.48 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 294 | 290 | 62.73 | SFT | 53.43 | 9.3 | 85.17% | 15494.7 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.624 | CUM | 0 | 4.624 | 0% | 0 | 100% | 1040.4
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 0 | 1.6 | 0% | 0 | 100% | 3200
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 0 | 5 | 0% | 0 | 100% | 250
37343.0456

## V170
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 59.15 | 100% | 3201.66 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0.85 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | -39.58 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | -23.34 | 100% | 21563.8416 |  | 0 | KRIUTTIBAS DAS | 1500
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 38.67 | 100% | 1120.46 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 73.1294 | CUM | 73.13 | 55.4994 | 100% | 10320.1056 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 3.244 | 99.93% | 1176.9408 |  | 0 | NAGARAJ | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 13.95 | 100% | 3882.2112 |  | 0 | PRAKASH H N | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 57.88 | 100% | 1304.38 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 59.29 | SQM | 59.29 | 58.45 | 100% | 2549.47 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0.9 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0.83 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 5.073 | 99.94% | 5090 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | -8.018 | 99.93% | 2780 |  | 0 | SHOKAT | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | -16.951 | 100% | 5930 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.37 | MT | 0.37 | -1.55 | 100% | 2590 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0.04 | 100% | 3150 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | -1.43 | 100% | 3850 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0.43 | 100% | 3500 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.25 | MT | 1.25 | -41.75 | 100% | 8750 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.14 | MT | 0.14 | -0.86 | 100% | 980 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.14 | MT | 0.14 | -111.77 | 100% | 980 |  | 0 | YELLAPPA C | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | -89.217 | 99.99% | 10223.2166 |  | 0 | RABIUL MOLLA | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | -39.06 | 100% | 7124.9069 |  | 0 | KOUSHIK MANDAL | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 29.4617 | 100% | 18068.4504 |  | 0 | SHEKAR T | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | -5.6 | 100% | 12441.4618 |  | 0 | MORSELIM KHAN | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 124.85 | 100% | 37972.3781 |  | 0 | TOTAL | 1500
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | -165.16 | 100% | 3695.0659 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | -44.44 | 100% | 4855.4251 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | -156.86 | 100% | 2227.5 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | -163.83 | 100% | 1980 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 3.74 | 100% | 4266 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | -58.81 | 100% | 5700 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | -162.797 | 99.98% | 2943 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | -134.969 | 99.94% | 3400 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | -8.26 | 100% | 915 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | -35.94 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.5 | MT | 0.5 | -111.98 | 100% | 3500 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | -132.47 | 100% | 7700 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.14 | MT | 0.14 | -40.96 | 100% | 980 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | -16.62 | 100% | 1050 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | -32.28 | 100% | 12531.8794 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 108.44 | 100% | 37737.2923 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | -3.74 | 100% | 3695.0659 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | -7.45 | 100% | 5313.541 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | -24.806 | 99.83% | 4640 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | -393.259 | 99.99% | 3051 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | -405.414 | 100.3% | 2820 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | -57.217 | 99.64% | 1260 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | -562.14 | 100% | 700 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.17 | MT | 0.17 | -574.44 | 100% | 1190 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | -580.99 | 100% | 140 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | -8.34 | 100% | 3255.0336 |  | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 20.88 | 100% | 6895.849 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | -14.08 | 100% | 578.6726 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | -40.75 | 100% | 820 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | -96.805 | 100.3% | 445.5 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | -26.76 | 100% | 105 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 43 | 100% | 2150 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | -53.04 | 100% | 2000 |  | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 61.892 | 100% | 21682.7863 |  | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 78.01 | 100% | 23858.6213 |  | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 23.472 | 100% | 12148.2504 |  | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 26.8 | 100% | 2000.144 |  | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 46.88 | 38.88 | 100% | 3075.328 |  | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | -1.37 | 100% | 184.0644 |  | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 169.81 | 100% | 1909.0392 |  | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 50.68 | 100% | 8472.8826 |  | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 146.36 | 100% | 23335.0603 |  | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 137.971 | 100% | 31998.1428 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | -1367 | 100% | 13000 |  | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 58.212 | 100% | 8628.2071 |  | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 158.353 | 100% | 24611.2402 |  | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 125.54 | 100% | 26480.0858 |  | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | -33.92 | 100% | 1241.1968 |  | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | -88.87 | 100% | 5169.0881 |  | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 112.48 | 111.48 | 100% | 21793.225 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 133.568 | SQM | 133.57 | 132.568 | 100% | 28754.9496 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 41.095 | SQM | 41.1 | 40.095 | 100% | 8848.008 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 16.766 | SQM | 16.77 | 15.766 | 100% | 1805.1228 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 73.858 | SQM | 73.86 | 72.858 | 100% | 15900.5808 |  | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 16.766 | SQM | 16.77 | 15.766 | 100% | 1805.1228 |  | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 16 | NOS | 16 | 15 | 100% | 3200 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 24.083 | 99.99% | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 26.13 | 100% | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 406.82 | 100% | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 378.26 | 100% | 13137.0314 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 54.064 | 99.99% | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 561.244 | 100% | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 573.613 | 100% | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 568.511 | 100% | 15634.9791 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 18.14 | 100% | 5768.6429 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 1 | 100% | 900 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 15 | 100% | 5600 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.16 | RMT | 41.16 | 39.16 | 100% | 3375.12 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.781 | RMT | 98.78 | -1.219 | 100% | 3239.984 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 26.83 | -0.17 | 100% | 3520.096 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | -245 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 54.039 | SQM | 54.04 | 39.039 | 100% | 9889.32 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 50.02 | RMT | 50.02 | 50.02 | 100% | 2460.984 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 45.132 | SQM | 45.13 | 44.132 | 100% | 8258.79 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 39.23 | RMT | 39.23 | 38.23 | 100% | 1930.116 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 3.69 | SQM | 3.69 | -256.54 | 100% | 675.27 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 8 | RMT | 8 | 7 | 100% | 393.6 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 2.512 | SQM | 2.51 | 1.512 | 99.92% | 459.33 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 7.61 | RMT | 7.61 | 6.61 | 100% | 374.412 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 9.872 | SQM | 9.87 | 9.872 | 99.98% | 1806.21 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 20.402 | RMT | 20.4 | 19.402 | 99.99% | 1003.68 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 27.18 | SQM | 27.18 | 26.18 | 100% | 4973.94 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1368 | SFT | 1368 | 1367 | 100% | 3420 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.451 | SQM | 3.45 | -86.079 | 99.97% | 631.35 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.528 | SQM | 17.53 | -72.002 | 100% | 3207.99 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 11.13 | SQM | 11.13 | -78.4 | 100% | 2036.79 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 42.789 | SQM | 42.79 | 28.689 | 100% | 7830.57 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 125.805 | SQM | 125.81 | 111.705 | 100% | 8124.8098 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | -1.83 | 100% | 14500 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | -2.61 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | -6.01 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | -16.91 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | -23.12 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | -17.98 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 1 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 1 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 1 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 28.56 | RMT | 28.56 | 28.56 | 100% | 158079.6 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 4 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 1 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 1 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 12.5 | 100% | 5625 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 1 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 1 | 100% | 12000 |  | 0
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1500
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 350 | 1 | LUMP SUM | 1 | 1 | 100% | 350 |  | 0
MD GIYAS | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 2 | NOS | 2 | 2 | 100% | 1500 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 100 | RFT | 100 | 100 | 100% | 3400 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 27 | 27 | 100% | 2079 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 249 | SFT | 249 | 249 | 100% | 5727 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 15 | 15 | 100% | 2265 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 1 | 100% | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 1 | 100% | 400 |  | 0
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 290 | 320 | SFT | 260.23 | 320 | 81.32% | 75466.7 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 1 | 1 | 100% | 1000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 1 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 1 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 1 | 100% | 3000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 1 | 100% | 2500 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 1 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 89.526 | SQM | 89.53 | 89.526 | 100% | 4336.6541 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 89.526 | SQM | 89.53 | 89.526 | 100% | 1445.9095 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 89.526 | SQM | 89.53 | 89.526 | 100% | 2409.2523 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 14.102 | SQM | 14.1 | 14.102 | 99.99% | 227.715 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 14.102 | SQM | 14.1 | 14.102 | 99.99% | 455.3172 |  | 0
KRISHNAKUMAR SAHANI | CUSTOMIZATION TOILET TILE WORK | 436 | 1101 | 3.541 | SQM | 2.83 | 3.541 | 79.92% | 3115.83 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 3.6058 | SQM | 3.61 | 3.6058 | 100.1% | 777.1608 |  | 0
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 7.0123 | SQM | 7.01 | 7.0123 | 99.97% | 3018.2256 |  | 0
KRISHNAKUMAR SAHANI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 228.35 | 22.387 | SQM | 17.91 | 22.387 | 80% | 4089.7485 |  | 0
RUPAK NAYAK | CUSTOMISATION EPOXY GROUTING & SOAP WASH | 480 | 64.58 | 24.122 | SQM | 24.12 | 24.122 | 99.99% | 1557.6696 |  | 0
ANSAR HOSSAIAN SK | CAR PARKING BOUNDARY WALL TOP COPING GRANITE | 550 | 78 | 18.98 | RFT | 18.98 | 18.98 | 100% | 1480.44 |  | 0
1500

## V171
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.6842 | CUM | 3.68 | 0.0042 | 99.89% | 3680 |  | 0 | AAIDHUL MIAH | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.061 | CUM | 2.06 | 0.001 | 99.95% | 2060 |  | 0 | EBI ABRAHAM | 4000
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.7334 | CUM | 5.73 | 0.0034 | 99.94% | 5730 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.41771 | MT | 0.42 | -0.00229 | 100.5% | 3150 |  | 0 | KRIUTTIBAS DAS | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.28511 | MT | 0.29 | -0.0048919 | 101.7% | 2175 |  | 0 | LEGENDRY LANDSCAPE | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0 | MANJUNATHA P | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.8 | MT | 0.8 | 0 | 100% | 6000 |  | 0 | NAGARAJ | 49238.1958
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 0.945 | MT | 0 | 0.945 | 0% | 0 | 100% | 7087.5 | PRAKASH H N | 2000
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.142 | MT | 0 | 0.142 | 0% | 0 | 100% | 1065 | RAMAKRUSHNA PRADHAN | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 322.92 | 29.83 | SQM | 29.83 | 0 | 100% | 9632.7036 |  | 0 | RUPAK NAYAK | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 28.8 | SQM | 28.8 | 0 | 100% | 9300.096 |  | 0 | SANTOSH KUMAR | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 66.5063 | SQM | 66.51 | -0.0037 | 100% | 21477.4092 |  | 0 | SARAT BARMAN | 8152.5
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 46.08 | SQM | 46.08 | 0 | 100% | 14880.1536 |  | 0 | SAVITA DEVI | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 11.5966 | CUM | 11.6 | -0.0034 | 100% | 2610 |  | 0 | SHOKAT | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.62 | CUM | 1.62 | 0 | 100% | 2430 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.091 | CUM | 4.09 | 0.001 | 99.98% | 3681 |  | 0 | SK ANSAR HOSSIAN | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 57 | 2000 | 2.47 | CUM | 0 | 2.47 | 0% | 0 | 100% | 4940 | SREE VINAYAKA ELECTRICALS | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 9.171 | CUM | 0 | 9.171 | 0% | 0 | 100% | 2063.475 | SRI CHOWDESHWARI WATER SUPPLY | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 0.933 | CUM | 0 | 0.933 | 0% | 0 | 100% | 1866 | SUBHASMITA DAS | 8869.475
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000 | UDHABHAI R PARMAR | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.6 | SQM | 0 | 39.6 | 0% | 0 | 100% | 12787.632 | V VENKATANARAYANA | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 112.878 | SQM | 0 | 112.878 | 0% | 0 | 100% | 36450.5638 | YELLAPPA C | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.26 | SQM | 0 | 12.26 | 0% | 0 |  | 0 | RABIUL MOLLA | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 12 | NOS | 12 | 0 | 100% | 600 |  | 0 | KOUSHIK MANDAL | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 4.848 | CUM | 4.85 | -0.002 | 100% | 3880 |  | 0 | SHEKAR T | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0 | MORSELIM KHAN | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0 | TOTAL | 72260.1708
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 4000
72260.1708

## V172
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | EBI ABRAHAM | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | KRIUTTIBAS DAS | 11500
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100% | 9878.4 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100% | 2952.81 |  | 0 | RAMAKRUSHNA PRADHAN | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100% | 1121.904 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SHOKAT | 61267.6848
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | VILLA REINFORCEMENT | 40 | 7500 | 5.65 | MT | 5.65 | 0 | 100% | 42375 |  | 0 | V VENKATANARAYANA | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100% | 7980.8602 |  | 0 | YELLAPPA C | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | RABIUL MOLLA | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | KOUSHIK MANDAL | 0
MANJUNATHA R | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0 | SHEKAR T | 0
MANJUNATHA R | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0 | MORSELIM KHAN | 82614.4535
MANJUNATHA R | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0 | TOTAL | 155382.1383
MANJUNATHA R | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.2505 | 0% | 0 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0.61 | 0 | 100% | 1830 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100% | 1125 |  | 0
MANJUNATHA R | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
MANJUNATHA R | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100% | 34810.776 |  | 0
MANJUNATHA R | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
MANJUNATHA R | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.815 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.83 | CUM | 0.83 | 0 | 100% | 2490 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0.03 | -0.001 | 103.4% | 225 |  | 0
MANJUNATHA R | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
MANJUNATHA R | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100% | 7275.6029 |  | 0
MANJUNATHA R | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.17 | CUM | 0.17 | 0 | 100% | 510 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 89.86 | 4.73 | 95% | 17410.5547 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100% | 25056.0086 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0.003 | 100% | 12200.5634 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
MORSELIM KHAN | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
MORSELIM KHAN | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100% | 2119.72 |  | 0
MORSELIM KHAN | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 0 | 59.84 | 0% | 0 | 100% | 8373.5309
MORSELIM KHAN | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 0 | 176.74 | 0% | 0 | 100% | 24731.5817
MORSELIM KHAN | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 131.57 | -0.005 | 100% | 25491.9506 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
MORSELIM KHAN | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0% | 0 | 100% | 11425.4478
MORSELIM KHAN | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 0 | 228.24 | 0% | 0 | 100% | 31938.0797
MORSELIM KHAN | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.17 | SQM | 109.17 | 0 | 100% | 21151.9058 |  | 0
MORSELIM KHAN | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0% | 0 | 100% | 1365.7363
MORSELIM KHAN | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0% | 0 | 100% | 4780.0771
MORSELIM KHAN | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 99.15 | 0 | 100% | 19210.5108 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 135.31 | SQM | 0 | 0 | 0% | 0 | 100% | 29129.5368
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 27.38 | SQM | 0 | 0 | 0% | 0 | 100% | 5894.3664
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 27.95 | SQM | 0 | 0 | 0% | 0 | 100% | 3008.538
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 80.02 | SQM | 0 | 0 | 0% | 0 | 100% | 17226.7056
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 27.95 | SQM | 0 | 0 | 0% | 0 | 100% | 3008.538
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 15 | NOS | 0 | 0 | 0% | 0 | 100% | 3000
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 6000
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 500
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 3000
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.348 | CUM | 4.35 | -0.002 | 100% | 978.75 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100% | 250 |  | 0
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 41.862 | SQM | 41.86 | 0.002 | 100% | 13517.4312 |  | 0
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 16.5 | SQM | 16.5 | 0 | 100% | 5328.18 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR CEILING PLASTERING | 499 | 139.932 | 30.243 | SQM | 0 | 30.243 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR EXTERNAL WALL PLASTERING | 501 | 193.752 | 24.786 | SQM | 0 | 24.786 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR BLOCK WORK | 502 | 193.752 | 3.408 | SQM | 3.41 | -0.002 | 100.1% | 660.6943 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.30172 | MT | 0.3 | 0.001721 | 99.43% | 2250 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.16498 | MT | 0.16 | 0.004978 | 96.98% | 1200 |  | 0
155382.1383

## V173
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption)
DEEPAK NAYAK | ATT IN PLINTH | 1 | 69.1 | 68.67 | SQM | 68.67 | 0 | 100%
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100%
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100%
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100%
DEEPAK NAYAK | FOOTING EARTH DRESSING | 5 | 43 | 60 | SQM | 60 | 0 | 100%
DEEPAK NAYAK | FOOTING SOILING | 7 | 43 | 60 | SQM | 60 | 0 | 100%
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100%
DEEPAK NAYAK | BACKFILLING,CONSOLIDATION FOR FOOTINGS | 10 | 2500 | 1 | LUMP SUM | 1 | 0 | 100%
DEEPAK NAYAK | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100%
DEEPAK NAYAK | PLINTH BEAM BOTTOM SOLING | 12 | 43 | 45 | SQM | 45 | 0 | 100%
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100%
DEEPAK NAYAK | BASE FLOOR EARTH DRESSING | 14 | 43 | 75 | SQM | 75 | 0 | 100%
DEEPAK NAYAK | BASE FLOOR SOLING WORK | 15 | 43 | 75 | SQM | 75 | 0 | 100%
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100%
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100%
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100%
DEEPAK NAYAK | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | -0.001 | 99.97%
DEEPAK NAYAK | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0.002 | 100.1%
DEEPAK NAYAK | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0.003 | 100%
NARESH PURTY | FOOTING REINFORCEMENT | 23 | 6800 | 0.27 | MT | 0.27 | 0 | 100%
NARESH PURTY | PEDESTAL COLUMN REINFORCEMENT | 24 | 6800 | 0.42 | MT | 0.42 | 0 | 100%
NARESH PURTY | PLINTH BEAM REINFORCEMENT | 25 | 6800 | 0.53 | MT | 0.53 | 0 | 100%
NARESH PURTY | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 6800 | 0.49 | MT | 0.49 | 0 | 100%
NARESH PURTY | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 6800 | 1.2 | MT | 1.2 | 0 | 100%
NARESH PURTY | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 6800 | 0.18 | MT | 0.18 | 0 | 100%
NARESH PURTY | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 6800 | 0.13 | MT | 0.13 | 0 | 100%
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100%
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100%
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100%
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100%
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100%
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100%
YELLAPPA C | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 0 | -15.17 | 0% | -4572.1166
DEEPAK NAYAK | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100%
DEEPAK NAYAK | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100%
DEEPAK NAYAK | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100%
DEEPAK NAYAK | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100%
DEEPAK NAYAK | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100%
DEEPAK NAYAK | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100%
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100%
NARESH PURTY | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 6800 | 0.47 | MT | 0.47 | 0 | 100%
NARESH PURTY | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 6800 | 0.88 | MT | 0.88 | 0 | 100%
NARESH PURTY | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 6800 | 0.18 | MT | 0.18 | 0 | 100%
NARESH PURTY | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 6800 | 0.15 | MT | 0.15 | 0 | 100%
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100%
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100%
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 1.88 | -10.39 | 15.32% | -3131.4629
YELLAPPA C | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 0 | -16.19 | 0% | -4879.5365
DEEPAK NAYAK | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100%
DEEPAK NAYAK | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 349 | 12.13 | CUM | 12.13 | 0 | 100%
DEEPAK NAYAK | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100%
NARESH PURTY | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 6800 | 0.13 | MT | 0.13 | 0 | 100%
NARESH PURTY | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 6800 | 0.19 | MT | 0.19 | 0 | 100%
NARESH PURTY | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 6800 | 0.029 | MT | 0.03 | 0.001 | 103.4%
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100%
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100%
YELLAPPA C | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 0 | -3.5 | 0% | -1054.872
DEEPAK NAYAK | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100%
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 2000 | 2.37 | CUM | 2.37 | 0 | 100%
DEEPAK NAYAK | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100%
DEEPAK NAYAK | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100%
SALLAUDDIN ANSARI | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100%
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 108.15 | 0.003 | 100%
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 133.76 | 0.004 | 100%
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | -0.003 | 100%
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 30.1 | 0 | 100%
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 66.89 | 0 | 100%
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0.5 | 0 | 100%
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100%
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100%
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100%
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 177.87 | 0 | 100%
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100%
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100%
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 258.15 | 0 | 100%
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100%
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100%
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100%
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 117.1 | 0 | 100%
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 254.03 | 160.21 | SQM | 160.21 | 0 | 100%
SHOKAT | WATERPROOF PLASTERING | 170 | 254.03 | 18.82 | SQM | 18.82 | 0 | 100%
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 190.52 | 14.21 | SQM | 14.21 | 0 | 100%
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 254.03 | 65.55 | SQM | 65.55 | 0 | 100%
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 254.03 | 91.03 | SQM | 91.03 | 0 | 100%
SHOKAT | BORE PACKING ALL FLOOR | 180 | 295 | 8 | NOS | 8 | 0 | 100%
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 19.974 | SQM | 19.97 | -0.004 | 99.98%
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 61.966 | SQM | 61.97 | 0.004 | 100%
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 164.391 | SQM | 164.39 | -0.001 | 100%
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 104.234 | SQM | 104.23 | -0.004 | 100%
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 76.8785 | SQM | 76.88 | 0.0014697 | 100%
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100%
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 145.1194 | SQM | 145.12 | 0.0005574 | 100%
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 196 | 44.564 | 145.119 | SQM | 145.12 | 0.001 | 100%
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 59.84 | SQM | 59.84 | 0 | 100%
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 200 | 44.564 | 59.84 | SQM | 59.84 | 0 | 100%
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 218.6243 | SQM | 218.62 | -0.0043032 | 100%
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 203 | 44.564 | 218.624 | SQM | 218.62 | -0.004 | 100%
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 81.65 | SQM | 81.65 | 0 | 100%
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 207 | 44.564 | 81.65 | SQM | 81.65 | 0 | 100%
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 26.2549 | SQM | 26.25 | -0.0048607 | 99.98%
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 210 | 44.564 | 26.254 | SQM | 26.25 | -0.004 | 99.98%
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 9.76 | SQM | 9.76 | 0 | 100%
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 214 | 44.564 | 9.76 | SQM | 9.76 | 0 | 100%
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100%
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100%
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 10 | -6 | 62.5%
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.16 | RMT | 41.16 | 0 | 100%
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 98.781 | RMT | 98.78 | -0.001 | 100%
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 26.83 | RMT | 26.83 | 0 | 100%
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 3 | NOS | 3 | 0 | 100%
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 51.41 | SQM | 51.41 | 0 | 100%
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 62.858 | RMT | 62.86 | 0.002 | 100%
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 46.723 | SQM | 46.72 | -0.003 | 99.99%
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 56.845 | RMT | 56.85 | 0.005 | 100%
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 2.67 | SQM | 2.67 | 0 | 100%
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 4.67 | 0 | 100%
ANSAR HOSSAIAN SK | UTILITY FLOOR TILING | 230 | 183 | 8.92 | SQM | 8.92 | 0 | 100%
ANSAR HOSSAIAN SK | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 19.18 | 0 | 100%
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 5.559 | SQM | 5.56 | 0.001 | 100%
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | -0.004 | 99.96%
ANSAR HOSSAIAN SK | CAR PARKING AREA TILING | 234 | 183 | 15.42 | SQM | 15.42 | 0 | 100%
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100%
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.8 | SQM | 3.8 | 0 | 100%
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.505 | SQM | 17.51 | 0.005 | 100%
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.495 | SQM | 7.5 | 0.005 | 100.1%
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.082 | SQM | 35.08 | -0.002 | 99.99%
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 126.577 | SQM | 126.58 | 0.003 | 100%
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 1 | 0 | 100%
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100%
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 0.5 | LUMP SUM | 0.5 | 0 | 100%
BICHITRA CHOUDHURI | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 0.5 | LUMP SUM | 0.5 | 0 | 100%
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100%
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100%
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100%
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100%
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | -1 | 0%
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100%
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 21.44 | RMT | 21.44 | 0 | 100%
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 3 | NOS | 3 | 0 | 100%
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100%
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100%
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100%
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100%
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0.001 | 100%
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | -0.0026 | 99.99%
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100%
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0.0045 | 100%
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | -1 | 0%
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100%
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100%
RUPAK NAYAK | ALL FLOOR INTERNAL WALL & CEILING ONE COAT EMULSION PAINT REWORK | 384 | 15000 | 1 | LUMP SUM | 1 | 0 | 100%
ANSAR HOSSAIAN SK | TOILET RELOCATION REWORK TILING REPAIR WORK | 392 | 7000 | 1 | LUMP SUM | 1 | 0 | 100%
PRAKASH H N | TOILET CUSTOMISATION ELECTRICAL WORK REWORK | 393 | 3090 | 1 | LUMP SUM | 1 | 0 | 100%
KRIUTTIBAS DAS | TOILET PLUMBING CUSTOMISATION WORK REWORK | 394 | 3000 | 1 | LUMP SUM | 1 | 0 | 100%
SANTOSH KUMAR | GROUND FLOOR & FIRST FLOOR TILE DAMAGE TOTAL REWORK | 395 | 40000 | 1 | LUMP SUM | 1 | 0 | 100%
ANSAR HOSSAIAN SK | CUSTOMISATION LEDGE WALL GRANITE | 535 | 450 | 1 | NOS | 1 | 0 | 100%
ANSAR HOSSAIAN SK | CUSTOMISATION DOOR OPENING GRANITE | 536 | 350 | 5 | NOS | 5 | 0 | 100%
ANSAR HOSSAIAN SK | CUSTOMISATION FIRST FLOOR TOILET FLOOR TILE | 537 | 183 | 3.6 | SQM | 3.6 | 0 | 100%
ANSAR HOSSAIAN SK | CUSTOMISATION FIRST FLOOR TOILET WALL TILE | 538 | 183 | 17.145 | SQM | 17.15 | 0.005 | 100%

## V174
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100 | 21942.7488 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 87.161 | CUM | 87.16 | 0 | 100 | 12300.0192 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100 | 1510.74 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 68.67 | 0 | 100 | 2952.81 | 0 | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 0 | 7.95 | 0 | 0 | 0 | 0
V VENKATANARAYANA | SETBACK AREA CLEANING | 17 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.27 | MT | 0.27 | 0 | 100 | 1890 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.42 | MT | 0.42 | 0 | 100 | 2940 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.53 | MT | 0.53 | 0 | 100 | 3710 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0.49 | 0 | 100 | 3430 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.2 | MT | 1.2 | 0 | 100 | 8400 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.13 | MT | 0.13 | 0 | 100 | 910 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100 | 8270.1965 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100 | 7766.8718 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 57.78 | 0 | 100 | 17414.4298 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100 | 13653.0576 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100 | 38912.7211 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 15.17 | 0 | 100 | 4572.1166 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100 | 6520 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100 | 3449.25 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100 | 1440 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.47 | MT | 0.47 | 0 | 100 | 3290 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 0.88 | MT | 0.88 | 0 | 100 | 6160 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100 | 11826.6221 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 129.97 | SQM | 129.97 | 0 | 100 | 39171.9182 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100 | 3698.0798 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.19 | SQM | 16.19 | 0 | 100 | 4879.5365 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100 | 4420 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100 | 2729.25 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100 | 3140 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100 | 1305 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.13 | MT | 0.13 | 0 | 100 | 910 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.19 | MT | 0.19 | 0 | 100 | 1330 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0.03 | 0 | 100 | 210 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100 | 7275.6029 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.5 | SQM | 3.5 | 0 | 100 | 1054.872 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100 | 1220 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100 | 533.25 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100 | 570 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100 | 2200 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 108.15 | 0 | 100 | 20954.2788 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 133.76 | 0 | 100 | 25916.2675 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 62.97 | 0 | 100 | 12200.5634 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 20.1 | 10 | 66.771 | 1318.56 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 66.89 | 0 | 100 | 4387.984 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0.5 | 0 | 100 | 80.73 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100 | 2119.72 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100 | 8373.5309 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100 | 24731.5817 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 177.87 | 0 | 100 | 34462.6682 | 0 | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100 | 12000 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100 | 11425.4478 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 258.15 | 0 | 100 | 36123.4458 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 126.32 | 0 | 100 | 24474.7526 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100 | 1365.7363 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100 | 4780.0771 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 117.1 | 0 | 100 | 22688.3592 | 0 | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 31.122 | SQM | 31.12 | 0 | 100 | 13399.0272 | 0 | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 83.426 | SQM | 83.43 | 0 | 100 | 35921.6208 | 0 | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 7.897 | SQM | 7.9 | 0 | 100 | 1700.712 | 0 | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 14.96 | SQM | 14.96 | 0 | 100 | 3220.5888 | 0 | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 19 | NOS | 19 | 0 | 100 | 3800 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 181 | 215.28 | 19.974 | SQM | 19.97 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 184 | 96.876 | 61.966 | SQM | 61.97 | 0 | 100
RUPAK NAYAK | GROUND FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 187 | 48.438 | 164.391 | SQM | 164.39 | 0 | 100
RUPAK NAYAK | FIRST FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 188 | 48.438 | 104.234 | SQM | 104.23 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR ONE COAT PRIMER, TWO COATS EXTERIOR PAINT | 189 | 48.438 | 76.8785 | SQM | 76.88 | 0 | 100
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 58.07 | 0 | 100
RUPAK NAYAK | GROUND FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 195 | 91.494 | 145.1194 | SQM | 145.12 | 0 | 100
RUPAK NAYAK | GROUND FLOOR CEILING TWO COATS EMULSION PAINT | 199 | 91.494 | 59.84 | SQM | 59.84 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS & STAIRCASE TWO COATS EMULSION PAINT | 202 | 91.494 | 218.6243 | SQM | 218.62 | 0 | 100
RUPAK NAYAK | FIRST FLOOR CEILING TWO COATS EMULSION PAINT | 206 | 91.494 | 81.65 | SQM | 81.65 | 0 | 100
RUPAK NAYAK | FIRST FLOOR INTERNAL WALLS TWO COATS EMULSION PAINT | 209 | 91.494 | 26.2549 | SQM | 26.25 | 0 | 100
RUPAK NAYAK | TERRACE FLOOR CEILING TWO COATS EMULSION PAINT | 212 | 91.494 | 9.76 | SQM | 9.76 | 0 | 100
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 19.14 | SQM | 19.14 | 0 | 100
INDAL SAHNI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 2 | 0 | 100
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 16 | NOS | 16 | 0 | 100
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 40.76 | RMT | 40.76 | 0 | 100
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 122.28 | RMT | 122.28 | 0 | 100
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 29.59 | RMT | 29.59 | 0 | 100
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
INDAL SAHNI | GROUND FLOOR TILING | 224 | 172.224 | 51.018 | SQM | 51.02 | 0 | 100
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 62.858 | RMT | 62.86 | 0 | 100
INDAL SAHNI | FIRST FLOOR TILING | 226 | 172.224 | 46.723 | SQM | 46.72 | 0 | 100
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 56.845 | RMT | 56.85 | 0 | 100
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 172.224 | 2.67 | SQM | 2.67 | 0 | 100
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.67 | RMT | 4.67 | 0 | 100
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 182.988 | 8.92 | SQM | 8.92 | 0 | 100
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 19.18 | RMT | 19.18 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 172.224 | 5.559 | SQM | 5.56 | 0 | 100
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 10.684 | RMT | 10.68 | 0 | 100
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 182.988 | 13.6 | SQM | 13.6 | 0 | 100
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 1085 | SFT | 1085 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 172.224 | 3.736 | SQM | 3.74 | 0 | 100
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 193.752 | 17.505 | SQM | 17.51 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 182.988 | 7.495 | SQM | 7.5 | 0 | 100
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 182.988 | 35.082 | SQM | 35.08 | 0 | 100
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 121.492 | SQM | 121.49 | 0 | 100
PRAKASH JANA | EPOXY GROUTING & SOAP WASH | 245 | 26.91 | 189.15 | SQM | 189.15 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | BALCONY & STAIRCASE SS RAILING | 260 | 4954 | 21.44 | RMT | 21.44 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100
SHREE DM STEEL FURNITURE AND INTERIORS | ENTRANCE STEPS SS RAILING | 268 | 5535 | 1 | RMT | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | RAINWATER PIPE LAYING | 273 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 68.2 | RFT | 68.2 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 33 | RFT | 33 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 16.25 | RFT | 16.25 | 0 | 100
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
SHEKAR T | NAME BOARD CONSTRUCTION WORK | 287 | 800 | 1 | NOS | 1 | 0 | 100
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 125 | 363 | SFT | 363 | 0 | 100
PRAKASH JANA | LAYING FLOOR PROTECTOR SHEET & TILE CLEANING | 341 | 1.5 | 1055 | SFT | 1055 | 0 | 100
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100
INDAL SAHNI | CUSTOMIZATION TOILET TILE WORK | 436 | 1013.176 | 3.8 | SQM | 3.8 | 0 | 100
INDAL SAHNI | CUSTOMIZATION MAIN FLOORING WORK | 442 | 242.5 | 17.5 | SQM | 17.5 | 0 | 100
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 9750 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION FLOOR INTERNAL WALL THREE COATS PUTTY, ONE COAT PRIMER, TWO COATS INTERNAL EMULSION PAINTING WORK | 490 | 91.494 | 86.224 | SQM | 86.22 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION FLOOR EXTERNAL WALL ONE COAT PRIMER, TWO COATS EXTERNAL EMULSION PAINTING WORK | 491 | 48.438 | 10.25 | SQM | 10.25 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION TERRACE WASHING MACHINE TAP POINT WORK | 504 | 1500 | 1 | NOS | 1 | 0 | 100
SHOKAT | CUSTOMIZATION TOILET FLOOR CHIPPING AND 2 COATS OF WATERPROOFING | 515 | 430.56 | 6.596 | SQM | 6.6 | 0 | 100
SHOKAT | CUSTOMIZATION TOILET SCREED CONCRETE | 516 | 215.28 | 3.716 | SQM | 3.72 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION DISHWASHER POINT WORK | 533 | 1000 | 1 | NOS | 1 | 0 | 100
PRABHAKAR | CUSTOMIZATION UG SUMP CIVIL WORK | 539 | 35000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION OF GROUND FLOOR TOILET WORK | 540 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 541 | 1000 | 1 | NOS | 1 | 0 | 100
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION UG SUMP WATERPROOFING WORK | 542 | 375 | 11.344 | SQM | 11.34 | 0 | 100

## V175
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 6100.5723
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100% | 12441.1392 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | NAGARAJ | 27478.0701
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.16 | CUM | 30.16 | 0 | 100% | 4256.1792 |  | 0 | PRAKASH H N | 1000
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100% | 1510.74 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100% | 1121.904 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3349.0003 |  | 0 | SARAT BARMAN | 19914.8475
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2672.0015 |  | 0 | SAVITA DEVI | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6873.0013 |  | 0 | SHOKAT | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | SUBHASMITA DAS | 1228.525
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0% | 0 | 100% | 1300 | V VENKATANARAYANA | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 | YELLAPPA C | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 | RABIUL MOLLA | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0 | MORSELIM KHAN | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0 | TOTAL | 55722.0149
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.2505 | 0% | 0 | 100% | 2987.1715
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100% | 1440 |  | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.09 | 0.38 | 19.15% | 129.2553 | 80.85% | 2850
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 | 100% | 6600
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 | 100% | 1350
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0% | 0 | 100% | 1500
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100% | 34810.776 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.815 | 0% | 0 | 100% | 3169.4598
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100% | 1305 |  | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.83 | CUM | 0 | 0.83 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0% | 0 | 100% | 1425
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.029 | 0% | 0 | 100% | 203
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100% | 3487.536 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0% | 0 | 100% | 7795.2888
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0 | 0.38 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.17 | CUM | 0 | 0.17 | 0% | 0 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 50% | 1000 | 50% | 1000
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 9.54 | CUM | 9.54 | 0 | 100% | 7632 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 80.4 | 14.19 | 85% | 13240.7647 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 14.1885 | SQM | 14.19 | -0.0015 | 100% | 2749.6315 |  | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100% | 25056.0086 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 0 | 129.32 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.973 | 0% | 0 | 50% | 6100.5723
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.973 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 0 | 268.5 | 0% | 0 |  | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 0 | 268.5 | 0% | 0 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 0 | 197 | 0% | 0 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 0 | 197 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 0 | 59.84 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100% | 24731.5817 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 0 | 176.74 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 0 | 131.565 | 0% | 0 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 0 | 131.565 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 228.24 | 0 | 100% | 31938.0797 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 0 | 228.24 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.17 | SQM | 0 | 109.17 | 0% | 0 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.17 | SQM | 0 | 109.17 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 0 | 99.15 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 0 | 99.15 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 2250 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2255.8998 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | EXCAVATED SOIL REWORK IN FOOTING | 396 | 7000 | 1 | LUMP SUM | 1 | 0 | 100% | 7000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.349 | CUM | 0 | 4.349 | 0% | 0 | 100% | 978.525
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 0 | 5 | 0% | 0 | 100% | 250
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 41.887 | SQM | 0 | 41.887 | 0% | 0 | 100% | 13526.15
NAGARAJ | CUSTOMIZATION ROOM LINTEL CHAJJA SHUTTERING | 497 | 322.92 | 3.62 | SQM | 0 | 3.62 | 0% | 0 |  | 0
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 16.5 | SQM | 16.5 | 0 | 100% | 5328.18 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR INTERNAL WALL PLASTERING | 500 | 139.932 | 30.243 | SQM | 0 | 30.243 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR EXTERNAL WALL PLASTERING | 501 | 193.752 | 24.786 | SQM | 0 | 24.786 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR BLOCK WORK | 502 | 193.752 | 3.408 | SQM | 0 | 3.408 | 0% | 0 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.35613 | MT | 0 | 0.35613 | 0% | 0 | 100% | 2670.9825
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.26878 | MT | 0 | 0.26878 | 0% | 0 | 100% | 2015.865
PRAKASH H N | CUSTAMIZATION ROOF CHIPPING, ROOF CONDUITS, WIRING | 543 | 2500 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 625 |  | 0
55722.0149

## V176
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 14667.5883
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 274.18 | 1 | LUMP SUM | 1 | 0 | 100% | 274.18 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | KRIUTTIBAS DAS | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100% | 12441.1392 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 0 | 30.73 | 0% | 0 |  | 0 | NAGARAJ | 12671.3808
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | PRAKASH H N | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 0 | 7.95 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3349.0003 |  | 0 | SANTOSH KUMAR | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2672.0015 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 0 | 6.867 | 0% | 0 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.27 | MT | 0.27 | 0 | 100% | 1890 |  | 0 | SHOKAT | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.42 | MT | 0.42 | 0 | 100% | 2940 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.53 | MT | 0.53 | 0 | 100% | 3710 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.49 | MT | 0 | 0.49 | 0% | 0 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 27 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.2 | MT | 0 | 1.2 | 0% | 0 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 30 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 33 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | YELLAPPA C | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0 | RABIUL MOLLA | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 27.44 | SQM | 27.44 | 0 | 100% | 8270.1965 |  | 0 | KOUSHIK MANDAL | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | SHEKAR T | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 57.78 | SQM | 51.5 | 6.28 | 89.13% | 13834.6648 |  | 0 | MORSELIM KHAN | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0 | TOTAL | 27338.9691
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 15.17 | SQM | 0 | 15.17 | 0% | 0 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 0 | 3.26 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 57 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 0 | 15.33 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 59 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 0 | 1.57 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 62 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0 | 0.96 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.47 | MT | 0 | 0.47 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 0.88 | MT | 0 | 0.88 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0% | 0 | 100% | 12671.3808
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 129.97 | SQM | 0 | 129.97 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 16.19 | SQM | 0 | 16.19 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 0 | 2.21 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0 | 0.87 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.19 | MT | 0 | 0.19 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 3.5 | SQM | 0 | 3.5 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0 | 0.38 | 0% | 0 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 108.147 | SQM | 0 | 108.147 | 0% | 0 | 70% | 14667.5883
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 133.756 | SQM | 0 | 133.756 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.973 | 0% | 0 |  | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 0 | 197 | 0% | 0 |  | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 0 | 59.84 | 0% | 0 |  | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 0 | 176.74 | 0% | 0 |  | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 177.87 | SQM | 0 | 177.87 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 258.15 | SQM | 0 | 258.15 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 126.32 | SQM | 0 | 126.32 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 117.1 | SQM | 0 | 117.1 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2255.8998 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
27338.9691

## V177
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 | 0 | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100 | 2775 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100 | 3375 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100 | 4125 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100 | 9375 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
YELLAPPA C | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
YELLAPPA C | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
YELLAPPA C | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0 | 100 | 18068.4504 | 0 | 0
YELLAPPA C | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
YELLAPPA C | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
YELLAPPA C | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100 | 4855.4251 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100 | 915 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100 | 3750 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100 | 8250 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100 | 1050 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0.15 | 0 | 100 | 1125 | 0 | 0
YELLAPPA C | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
YELLAPPA C | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
YELLAPPA C | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 4.25 | 8.01 | 34.669 | 1280.916 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100 | 5313.541 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0 | 100 | 1260 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100 | 750 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100 | 1275 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0.02 | 0 | 100 | 150 | 0 | 0
YELLAPPA C | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
YELLAPPA C | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100 | 578.6726 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100 | 105 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 0 | 100 | 21682.7863 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100 | 2000.144 | 0 | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 46.88 | 0 | 100 | 3075.328 | 0 | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100 | 184.0644 | 0 | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 13000 | 1 | LUMP SUM | 1 | 0 | 100 | 13000 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 112.48 | 0 | 100 | 21793.225 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 118.09 | SQM | 118.09 | 0 | 100 | 25422.4152 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 28.584 | SQM | 28.58 | 0 | 100 | 6152.7024 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100 | 1533.87 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 70.64 | SQM | 70.64 | 0 | 100 | 15207.3792 | 0 | 0
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 14.246 | SQM | 14.25 | 0 | 100 | 1533.87 | 0 | 0
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100 | 3400 | 0 | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | 0 | 100 | 6441.1776 | 0 | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100 | 3330.7344 | 0 | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | 0 | 100 | 5851.468 | 0 | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 0 | 362.32 | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 0 | 508.36 | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 18.16 | SQM | 18.16 | 0 | 100
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 10 | 5 | 66.667
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 19.57 | 0 | 100
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 51.68 | SQM | 41.34 | 10.34 | 80
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 45.26 | RMT | 36.21 | 9.05 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 43.7 | SQM | 34.96 | 8.74 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 42.77 | RMT | 34.22 | 8.55 | 80
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 2.12 | SQM | 2.12 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.15 | RMT | 4.15 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 3.89 | SQM | 0 | 3.89 | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 8.42 | RMT | 0 | 8.42 | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 10.19 | SQM | 10.19 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 13.87 | RMT | 13.87 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 11.38 | SQM | 0 | 11.38 | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1068.49 | SFT | 1068.49 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.64 | SQM | 2.91 | 0.73 | 80
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.95 | SQM | 14.36 | 3.59 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.22 | SQM | 5.78 | 1.44 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.71 | SQM | 28.57 | 7.14 | 80
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 14500 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 25.11 | RMT | 25.11 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0

## V178
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 0 | 2 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.55 | CUM | 78.55 | 0 | 100 | 11084.976 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 0 | 27.51 | 0 | 0 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 0 | 59.29 | 0 | 0 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 59.29 | SQM | 0 | 59.29 | 0 | 0 | 0 | 0
PRABHAKAR | SETBACK AREA SOIL FILLING | 16 | 141.12 | 9.27 | CUM | 0 | 9.27 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 0 | 5.93 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.37 | MT | 0.37 | 0 | 100 | 2590 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0 | 0.5 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.25 | MT | 0 | 1.25 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.14 | MT | 0 | 0.14 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.14 | MT | 0 | 0.14 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 44.84 | 15.11 | 74.8 | 13514.4173 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 0 | 41.28 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 0 | 125.99 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 0 | 12.26 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 0 | 16.11 | 0 | 0 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 0 | 2.85 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 0 | 13.08 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 0 | 1.7 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0 | 0.61 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.5 | MT | 0 | 0.5 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 0 | 1.1 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.14 | MT | 0 | 0.14 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 0 | 41.58 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 0 | 125.21 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 0 | 12.26 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 0 | 17.63 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 0 | 2.32 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 0 | 13.56 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 0 | 1.41 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0 | 0.84 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0 | 0.1 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.17 | MT | 0 | 0.17 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 0 | 22.88 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 0 | 1.92 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0 | 0.41 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 0 | 1.98 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0 | 0.07 | 0 | 0 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 0 | 43 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 0 | 111.91 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 0 | 123.14 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 0 | 62.7 | 0 | 0 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 0 | 30.49 | 0 | 0 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 0 | 46.88 | 0 | 0 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 0 | 177.42 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 0 | 60.55 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0 | 0 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 0 | 165.15 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 0 | 61.66 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 0 | 175.88 | 0 | 0 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 0 | 136.67 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 0 | 8.87 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 0 | 36.94 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 0 | 112.48 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 278 | 64 | SFT | 0 | 64 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V179
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100 | 3201.66 | 0 | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100 | 21563.8416 | 0 | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100 | 1120.46 | 0 | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.5291 | CUM | 78.53 | 0 | 100 | 11082.1536 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0 | 100 | 1176.9408 | 0 | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100 | 3882.2112 | 0 | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100 | 1304.38 | 0 | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 59.29 | SQM | 59.29 | 0 | 100 | 2549.47 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100 | 5500 | 0 | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100 | 3000 | 0 | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0 | 100 | 5090 | 0 | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0 | 100 | 2780 | 0 | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | 0 | 100 | 5930 | 0 | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.37 | MT | 0.37 | 0 | 100 | 2590 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100 | 3150 | 0 | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100 | 3850 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.25 | MT | 1.25 | 0 | 100 | 8750 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.14 | MT | 0.14 | 0 | 100 | 980 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.14 | MT | 0.14 | 0 | 100 | 980 | 0 | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0 | 100 | 10223.2166 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100 | 7124.9069 | 0 | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0 | 100 | 18068.4504 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100 | 12441.4618 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100 | 37972.3781 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 16.11 | 0 | 100 | 4855.4251 | 0 | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100 | 2227.5 | 0 | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100 | 1980 | 0 | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100 | 4266 | 0 | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100 | 5700 | 0 | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0 | 100 | 2943 | 0 | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0 | 100 | 3400 | 0 | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100 | 915 | 0 | 0
SALLAUDDIN ANSARI | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.5 | MT | 0.5 | 0 | 100 | 3500 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100 | 7700 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.14 | MT | 0.14 | 0 | 100 | 980 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100 | 1050 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100 | 12531.8794 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100 | 37737.2923 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100 | 3695.0659 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 17.63 | 0 | 100 | 5313.541 | 0 | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0 | 100 | 4640 | 0 | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0 | 100 | 3051 | 0 | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | 0 | 100 | 2820 | 0 | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0 | 100 | 1260 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100 | 700 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.17 | MT | 0.17 | 0 | 100 | 1190 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0 | 0.02 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100 | 3255.0336 | 0 | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100 | 6895.849 | 0 | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 0 | 1.92 | 0 | 0 | 0 | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100 | 820 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | 0 | 100 | 445.5 | 0 | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0 | 0.07 | 0 | 0 | 0 | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100 | 2150 | 0 | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100 | 2000 | 0 | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 0 | 100 | 21682.7863 | 0 | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100 | 23858.6213 | 0 | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0 | 100 | 12148.2504 | 0 | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 0 | 30.49 | 0 | 0 | 0 | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 0 | 46.88 | 0 | 0 | 0 | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0 | 0 | 0 | 0
MD GIYAS | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 0 | 268.5 | 0 | 0 | 0 | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 0 | 177.42 | 0 | 0 | 0 | 0
MD GIYAS | RCC SURFACE HACKING | 141 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100 | 1909.0392 | 0 | 0
MD GIYAS | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100 | 8472.8826 | 0 | 0
MD GIYAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100 | 23335.0603 | 0 | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0 | 100 | 31998.1428 | 0 | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100 | 15000 | 0 | 0
MD GIYAS | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 61.662 | SQM | 61.66 | 0 | 100 | 8628.2071 | 0 | 0
MD GIYAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 175.883 | SQM | 175.88 | 0 | 100 | 24611.2402 | 0 | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100 | 26480.0858 | 0 | 0
MD GIYAS | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 8.87 | SQM | 8.87 | 0 | 100 | 1241.1968 | 0 | 0
MD GIYAS | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 36.94 | SQM | 36.94 | 0 | 100 | 5169.0881 | 0 | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 73 | 39.48 | 64.9 | 14143.896 | 0 | 0
MD GIYAS | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 39.1 | SQM | 0 | 39.1 | 0 | 0 | 0 | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 124.496 | SQM | 124.5 | 0 | 100 | 26802.36 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 34.823 | SQM | 34.82 | 0 | 100 | 7496.0496 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 18.043 | SQM | 18.04 | 0 | 100 | 1941.8256 | 0 | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 70.685 | SQM | 70.69 | 0 | 100
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 18.043 | SQM | 18.04 | 0 | 100
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 16 | NOS | 16 | 0 | 100
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 29.915 | SQM | 29.92 | 0 | 100
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 34.38 | SQM | 34.38 | 0 | 100
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 362.319 | SQM | 362.32 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 508.3612 | SQM | 508.36 | 0 | 100
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 508.3612 | SQM | 508.36 | 0 | 100
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 18.16 | SQM | 18.16 | 0 | 100
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 3 | NOS | 0 | 3 | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 14 | NOS | 14 | 0 | 100
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 41.17 | RMT | 41.17 | 0 | 100
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 19.57 | RMT | 19.57 | 0 | 100
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 51.68 | SQM | 41.34 | 10.34 | 80
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 45.26 | RMT | 36.21 | 9.05 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 43.7 | SQM | 34.96 | 8.74 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 42.77 | RMT | 34.22 | 8.55 | 80
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 2.12 | SQM | 2.12 | 0 | 100
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.15 | RMT | 4.15 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 3.89 | SQM | 3.89 | 0 | 100
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 8.42 | RMT | 8.42 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 10.19 | SQM | 10.19 | 0 | 100
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 13.87 | RMT | 13.87 | 0 | 100
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 11.38 | SQM | 11.38 | 0 | 100
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1068.49 | SFT | 1068.49 | 0 | 100
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.64 | SQM | 2.91 | 0.73 | 80
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.95 | SQM | 14.36 | 3.59 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 7.22 | SQM | 5.78 | 1.44 | 80
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 35.71 | SQM | 28.57 | 7.14 | 80
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 144.788 | SQM | 144.79 | 0 | 100
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 1 | 0 | 100
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 24.95 | RMT | 24.95 | 0 | 100
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | ELECTRICAL EARTHING CHAMBER CIVIL WORK | 274 | 225 | 1 | LUMP SUM | 1 | 0 | 100
AAIDHUL MIAH | PLUMBING CHAMBER CIVIL WORK | 275 | 225 | 1 | LUMP SUM | 0 | 1 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | 0 | 100
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 227 | 354 | SFT | 290.32 | 63.68 | 82.012
PRAKASH H N | MATERIAL FOR ELECTRICAL WORK | 350 | 1 | 3 | LUMP SUM | 0 | 3 | 0
ONLY FOR MATERIAL PURCHASE | MATERIAL FOR GRANITE WORK | 351 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | MATERIAL FOR PLUMBING WORK | 352 | 1 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 1 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 96.574 | SQM | 96.57 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 96.574 | SQM | 96.57 | 0 | 100
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 96.574 | SQM | 96.57 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 18.848 | SQM | 18.85 | 0 | 100
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 18.848 | SQM | 18.85 | 0 | 100
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET SCREED CONCRETE AND CINDER FILLING WORK | 438 | 215.28 | 3.625 | SQM | 3.63 | 0 | 100
JMJ WATERPROOING ENTERPRISES | CUSTOMIZATION TOILET WATERPROOFING WORK | 439 | 430.56 | 7.158 | SQM | 7.16 | 0 | 100

## V180
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 59.29 | 0 | 100% | 3201.66 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 101.87 | CUM | 101.87 | 0 | 100% | 21563.8416 |  | 0 | KRIUTTIBAS DAS | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100% | 1120.46 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 78.5291 | CUM | 78.53 | -0.0009 | 100% | 11082.1536 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.564 | CUM | 5.56 | 0.004 | 99.93% | 1176.9408 |  | 0 | NAGARAJ | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100% | 3882.2112 |  | 0 | PRAKASH H N | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.29 | SQM | 59.29 | 0 | 100% | 1304.38 |  | 0 | RAMAKRUSHNA PRADHAN | 0
PRABHAKAR | BASE FLOOR SOLING WORK | 15 | 43 | 59.29 | SQM | 59.29 | 0 | 100% | 2549.47 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | SANTOSH KUMAR | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.093 | CUM | 5.09 | 0.003 | 99.94% | 5090 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.782 | CUM | 2.78 | 0.002 | 99.93% | 2780 |  | 0 | SHOKAT | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 5.929 | CUM | 5.93 | -0.001 | 100% | 5930 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.37 | MT | 0.37 | 0 | 100% | 2590 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.45 | MT | 0.45 | 0 | 100% | 3150 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 0.55 | MT | 0.55 | 0 | 100% | 3850 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.5 | MT | 0.5 | 0 | 100% | 3500 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 1.25 | MT | 1.25 | 0 | 100% | 8750 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.14 | MT | 0.14 | 0 | 100% | 980 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.14 | MT | 0.14 | 0 | 100% | 980 |  | 0 | YELLAPPA C | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 33.923 | SQM | 33.92 | 0.003 | 99.99% | 10223.2166 |  | 0 | RABIUL MOLLA | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 23.64 | SQM | 23.64 | 0 | 100% | 7124.9069 |  | 0 | KOUSHIK MANDAL | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 59.9517 | SQM | 59.95 | 0.0017 | 100% | 18068.4504 |  | 0 | SHEKAR T | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 41.28 | SQM | 41.28 | 0 | 100% | 12441.4618 |  | 0 | MORSELIM KHAN | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 125.99 | SQM | 125.99 | 0 | 100% | 37972.3781 |  | 0 | TOTAL | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100% | 3695.0659 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 16.11 | SQM | 0 | 16.11 | 0% | 0 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100% | 2227.5 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100% | 1980 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 4.74 | CUM | 4.74 | 0 | 100% | 4266 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100% | 5700 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.083 | CUM | 13.08 | 0.003 | 99.98% | 2943 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.701 | CUM | 1.7 | 0.001 | 99.94% | 3400 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.61 | CUM | 0.61 | 0 | 100% | 915 |  | 0
H R ENGINEERS | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 0.5 | MT | 0.5 | 0 | 100% | 3500 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 1.1 | MT | 1.1 | 0 | 100% | 7700 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.14 | MT | 0.14 | 0 | 100% | 980 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 41.58 | SQM | 41.58 | 0 | 100% | 12531.8794 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 125.21 | SQM | 125.21 | 0 | 100% | 37737.2923 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.26 | SQM | 12.26 | 0 | 100% | 3695.0659 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 17.63 | SQM | 0 | 17.63 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.324 | CUM | 2.32 | 0.004 | 99.83% | 4640 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.561 | CUM | 13.56 | 0.001 | 99.99% | 3051 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.406 | CUM | 1.41 | -0.004 | 100.3% | 2820 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.843 | CUM | 0.84 | 0.003 | 99.64% | 1260 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.1 | MT | 0.1 | 0 | 100% | 700 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.17 | MT | 0.17 | 0 | 100% | 1190 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0.02 | 0 | 100% | 140 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 22.88 | SQM | 22.88 | 0 | 100% | 6895.849 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.92 | SQM | 1.92 | 0 | 100% | 578.6726 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 1.975 | CUM | 1.98 | -0.005 | 100.3% | 445.5 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.07 | CUM | 0.07 | 0 | 100% | 105 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 43 | 0 | 100% | 2150 |  | 0
H R ENGINEERS | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 111.912 | SQM | 111.91 | 0.002 | 100% | 21682.7863 |  | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 123.14 | SQM | 123.14 | 0 | 100% | 23858.6213 |  | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.702 | SQM | 62.7 | 0.002 | 100% | 12148.2504 |  | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 30.49 | RMT | 30.49 | 0 | 100% | 2000.144 |  | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 46.88 | RMT | 46.88 | 0 | 100% | 3075.328 |  | 0
PRABHAKAR | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 1.14 | 0 | 100% | 184.0644 |  | 0
PRABHAKAR | RCC SURFACE HACKING | 140 | 10.76 | 177.42 | SQM | 177.42 | 0 | 100% | 1909.0392 |  | 0
PRABHAKAR | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 60.55 | SQM | 60.55 | 0 | 100% | 8472.8826 |  | 0
PRABHAKAR | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 166.76 | 0 | 100% | 23335.0603 |  | 0
PRABHAKAR | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 165.151 | SQM | 165.15 | 0.001 | 100% | 31998.1428 |  | 0
H R ENGINEERS | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
PRABHAKAR | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 61.66 | 0.002 | 100% | 8628.2071 |  | 0
PRABHAKAR | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 175.883 | SQM | 175.88 | 0.003 | 100% | 24611.2402 |  | 0
PRABHAKAR | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 136.67 | SQM | 136.67 | 0 | 100% | 26480.0858 |  | 0
PRABHAKAR | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 8.87 | SQM | 0 | 8.87 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 36.94 | SQM | 0 | 36.94 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 112.48 | SQM | 112.48 | 0 | 100% | 21793.225 |  | 0
SHOKAT | TOILET BALCONY AND CARPARKING ROOF WATERPROOF COATING | 169 | 430.56 | 41.07 | SQM | 41.07 | 0 | 100% | 17683.0992 |  | 0
SHOKAT | TERRACE AND SHR WATERPROOF COATING | 172 | 430.56 | 78.967 | SQM | 78.97 | -0.003 | 100% | 34001.3232 |  | 0
SHOKAT | CINDER FILLING & WATERPROOF SCREED CONCRETE 75MM THICK | 175 | 215.28 | 12.077 | SQM | 12.08 | -0.003 | 100% | 2600.5824 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 177 | 215.28 | 23.226 | SQM | 23.23 | -0.004 | 100% | 5000.9544 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 18 | NOS | 18 | 0 | 100% | 3600 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 25.083 | SQM | 25.08 | 0.003 | 99.99% | 5399.2224 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 27.13 | SQM | 27.13 | 0 | 100% | 2628.3544 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 406.82 | SQM | 406.82 | 0 | 100% | 6570.143 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 406.82 | SQM | 406.82 | 0 | 100% | 13137.0314 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.064 | SQM | 58.06 | 0.004 | 99.99% | 937.669 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 562.244 | SQM | 562.24 | 0.004 | 100% | 27233.7811 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 574.613 | SQM | 574.61 | 0.003 | 100% | 9279.9515 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 581.011 | SQM | 581.01 | 0.001 | 100% | 15634.9791 |  | 0
KRISHNAKUMAR SAHANI | STAIRCASE GRANITE | 215 | 301.392 | 17.75 | SQM | 17.75 | 0 | 100% | 5349.708 |  | 0
KRISHNAKUMAR SAHANI | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
KRISHNAKUMAR SAHANI | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 12 | 3 | 80% | 4200 |  | 0
KRISHNAKUMAR SAHANI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.4 | RMT | 46.4 | 0 | 100% | 3804.8 |  | 0
KRISHNAKUMAR SAHANI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 103.53 | 0 | 100% | 3395.784 |  | 0
KRISHNAKUMAR SAHANI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.07 | RMT | 23.07 | 0 | 100% | 3026.784 |  | 0
KRISHNAKUMAR SAHANI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 4 | 0 | 100% | 4000 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 49.52 | 0 | 100% | 9062.16 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 48.42 | 0 | 100% | 2382.264 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 46 | 0 | 100% | 8418 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 50.44 | 0 | 100% | 2481.648 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 2.5 | 0 | 100% | 457.5 |  | 0
KRISHNAKUMAR SAHANI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 4.19 | 0 | 100% | 206.148 |  | 0
KRISHNAKUMAR SAHANI | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 4.01 | 0 | 100% | 733.83 |  | 0
KRISHNAKUMAR SAHANI | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 9.98 | 0 | 100% | 491.016 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT TILING | 232 | 183 | 10.18 | SQM | 10.18 | 0 | 100% | 1862.94 |  | 0
KRISHNAKUMAR SAHANI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 14 | RMT | 14 | 0 | 100% | 688.8 |  | 0
KRISHNAKUMAR SAHANI | CAR PARKING AREA TILING | 234 | 183 | 11.138 | SQM | 11.14 | -0.002 | 100% | 2038.62 |  | 0
KRISHNAKUMAR SAHANI | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 1055 | 0 | 100% | 2637.5 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.41 | SQM | 3.41 | 0 | 100% | 624.03 |  | 0
KRISHNAKUMAR SAHANI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 17.34 | 0 | 100% | 3173.22 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 6.62 | SQM | 6.62 | 0 | 100% | 1211.46 |  | 0
KRISHNAKUMAR SAHANI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 33.99 | SQM | 33.99 | 0 | 100% | 6220.17 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 122.24 | SQM | 122.24 | 0 | 100% | 7894.2592 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 4500 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 27.04 | RMT | 27.04 | 0 | 100% | 149666.4 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 1 | 0 | 100% | 12000 |  | 0
MD GIYAS | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 3 | NOS | 3 | 0 | 100% | 2250 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 76.53 | -0.001 | 100% | 2602.02 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 66 | 0 | 100% | 1518 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 17.38 | -0.0045 | 100% | 2624.38 |  | 0
KRISHNAKUMAR SAHANI | NAME BOARD TOP GRANITE | 282 | 350 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100% | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
PRABHAKAR | ADDITIONAL CIVIL AND STRUCTURAL WORK ON SFT BASIS | 293 | 227 | 354 | SFT | 354 | 0 | 100% | 80358 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 89.526 | SQM | 89.53 | -0.004 | 100% | 4336.6541 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 89.526 | SQM | 89.53 | -0.004 | 100% | 1445.9095 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 89.526 | SQM | 89.53 | -0.004 | 100% | 2409.2523 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 14.102 | SQM | 14.1 | 0.002 | 99.99% | 227.715 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 14.102 | SQM | 14.1 | 0.002 | 99.99% | 455.3172 |  | 0
RUPAK NAYAK | CUSTOMISATION EPOXY GROUTING & SOAP WASH | 480 | 64.58 | 22.642 | SQM | 22.64 | 0.002 | 99.99% | 1462.0912 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET INTERNAL PIPE LINE WORK | 544 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0

## V181
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
PRABHAKAR | ATT IN PLINTH | 1 | 54 | 151.12 | SQM | 151.12 | 0 | 100% | 8160.48 |  | 0 | AAIDHUL MIAH | 0
PRABHAKAR | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
PRABHAKAR | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
PRABHAKAR | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | KRIUTTIBAS DAS | 0
PRABHAKAR | FOOTING EARTH DRESSING | 5 | 22 | 82.57 | SQM | 82.57 | 0 | 100% | 1816.54 |  | 0 | LEGENDRY LANDSCAPE | 0
PRABHAKAR | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 135.32 | CUM | 135.32 | 0 | 100% | 19096.3584 |  | 0 | MANJUNATHA P | 0
PRABHAKAR | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | NAGARAJ | 0
PRABHAKAR | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 62.8 | CUM | 62.8 | 0 | 100% | 8862.336 |  | 0 | PRAKASH H N | 0
PRABHAKAR | BASE FLOOR EARTH DRESSING | 14 | 22 | 151.12 | SQM | 151.12 | 0 | 100% | 3324.64 |  | 0 | RAMAKRUSHNA PRADHAN | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 18 | 5500 | 1 | LUMP SUM | 1 | 0 | 100% | 5500 |  | 0 | RUPAK NAYAK | 0
V VENKATANARAYANA | SETBACK AREA SOIL FILLING | 19 | 3000 | 1 | LUMP SUM | 1 | 0 | 100% | 3000 |  | 0 | SANTOSH KUMAR | 0
PRABHAKAR | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | SARAT BARMAN | 0
PRABHAKAR | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | -0.002 | 100% | 4570 |  | 0 | SAVITA DEVI | 0
PRABHAKAR | BASE FLOOR PCC | 22 | 1000 | 15.112 | CUM | 15.11 | 0.002 | 99.99% | 15110 |  | 0 | SHOKAT | 0
PRABHAKAR | FOOTING REINFORCEMENT | 23 | 7000 | 0.65 | MT | 0.65 | 0 | 100% | 4550 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
PRABHAKAR | PEDESTAL COLUMN REINFORCEMENT | 24 | 7000 | 0.75 | MT | 0.75 | 0 | 100% | 5250 |  | 0 | SK ANSAR HOSSIAN | 0
PRABHAKAR | PLINTH BEAM REINFORCEMENT | 25 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
PRABHAKAR | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7000 | 0.9 | MT | 0.9 | 0 | 100% | 6300 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7000 | 2.8 | MT | 2.8 | 0 | 100% | 19600 |  | 0 | SUBHASMITA DAS | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0 | UDHABHAI R PARMAR | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7000 | 0.18 | MT | 0 | 0.18 | 0% | 0 |  | 0 | V VENKATANARAYANA | 0
PRABHAKAR | FOOTING SHUTTERING | 41 | 301.392 | 50.12 | SQM | 50.12 | 0 | 100% | 15105.767 |  | 0 | YELLAPPA C | 0
PRABHAKAR | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 31.67 | SQM | 31.67 | 0 | 100% | 9545.0846 |  | 0 | RABIUL MOLLA | 0
PRABHAKAR | PLINTH BEAM SHUTTERING | 43 | 301.392 | 105.11 | SQM | 105.11 | 0 | 100% | 31679.3131 |  | 0 | KOUSHIK MANDAL | 0
PRABHAKAR | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 59.91 | SQM | 59.91 | 0 | 100% | 18056.3947 |  | 0 | SHEKAR T | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 261.41 | SQM | 261.41 | 0 | 100% | 78786.8827 |  | 0 | MORSELIM KHAN | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0 | TOTAL | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 18.25 | SQM | 0 | 18.25 | 0% | 0 |  | 0
PRABHAKAR | FOOTING RCC | 50 | 225 | 23.29 | CUM | 23.29 | 0 | 100% | 5240.25 |  | 0
PRABHAKAR | PEDESTAL COLUMN RCC | 51 | 1500 | 2.62 | CUM | 2.62 | 0 | 100% | 3930 |  | 0
PRABHAKAR | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0
PRABHAKAR | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.51 | CUM | 3.51 | 0 | 100% | 7020 |  | 0
PRABHAKAR | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 30.016 | CUM | 30.02 | -0.004 | 100% | 6754.5 |  | 0
PRABHAKAR | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
PRABHAKAR | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.8 | CUM | 0 | 0.8 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7000 | 1 | MT | 1 | 0 | 100% | 7000 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7000 | 2.4 | MT | 2.4 | 0 | 100% | 16800 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7000 | 0.18 | MT | 0.18 | 0 | 100% | 1260 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7000 | 0.2 | MT | 0 | 0.2 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 61.4 | SQM | 61.4 | 0 | 100% | 18505.4688 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 243.08 | SQM | 243.08 | 0 | 100% | 73262.3674 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 14.58 | SQM | 14.58 | 0 | 100% | 4394.2954 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 20.55 | SQM | 0 | 20.55 | 0% | 0 |  | 0
PRABHAKAR | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 3.59 | 0.004 | 99.89% | 7180 |  | 0
PRABHAKAR | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 27.111 | CUM | 27.11 | 0.001 | 100% | 6099.75 |  | 0
PRABHAKAR | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 1.77 | 0.003 | 99.83% | 3540 |  | 0
PRABHAKAR | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 1.284 | CUM | 0 | 1.284 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7000 | 0.15 | MT | 0.15 | 0 | 100% | 1050 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7000 | 0.25 | MT | 0.25 | 0 | 100% | 1750 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.04 | MT | 0 | 0.04 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 8.1 | 0 | 100% | 2441.2752 |  | 0
PRABHAKAR | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 29.38 | SQM | 29.38 | 0 | 100% | 8854.897 |  | 0
PRABHAKAR | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 3.81 | SQM | 0 | 3.81 | 0% | 0 |  | 0
PRABHAKAR | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 2.83 | 0.002 | 99.93% | 636.75 |  | 0
PRABHAKAR | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.22 | CUM | 0 | 0.22 | 0% | 0 |  | 0
PRABHAKAR | ALL LEVEL COLUMN STARTER | 116 | 50 | 52 | NOS | 52 | 0 | 100% | 2600 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
PRABHAKAR | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 191.86 | SQM | 191.86 | 0 | 100% | 37173.2587 |  | 0
PRABHAKAR | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 203.55 | SQM | 203.55 | 0 | 100% | 39438.2196 |  | 0
PRABHAKAR | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 87.26 | SQM | 87.26 | 0 | 100% | 16906.7995 |  | 0
PRABHAKAR | ELEVATION RCC BAND | 133 | 65.6 | 47.7 | RMT | 0 | 47.7 | 0% | 0 |  | 0
PRABHAKAR | ELEVATION GROOVE | 137 | 65.6 | 0.1 | RMT | 0 | 0.1 | 0% | 0 |  | 0
MD GIYAS | RCC SURFACE HACKING | 141 | 10.76 | 368.27 | SQM | 368.27 | 0 | 100% | 3962.5852 |  | 0
MD GIYAS | GROUND FLOOR CEILING PLASTERING | 145 | 139.932 | 119.78 | SQM | 110 | 9.78 | 91.84% | 15392.52 |  | 0
MD GIYAS | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 146 | 139.932 | 267.58 | SQM | 267.58 | 0 | 100% | 37443.0046 |  | 0
MD GIYAS | GROUND FLOOR EXTERNAL WALL PLASTERING | 149 | 193.752 | 309.89 | SQM | 309.89 | 0 | 100% | 60041.8073 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 15000 | 1 | LUMP SUM | 1 | 0 | 100% | 15000 |  | 0
MD GIYAS | FIRST FLOOR CEILING PLASTERING | 154 | 139.932 | 118.32 | SQM | 118.32 | 0 | 100% | 16556.7542 |  | 0
MD GIYAS | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 155 | 139.932 | 366.35 | SQM | 366.35 | 0 | 100% | 51264.0882 |  | 0
MD GIYAS | FIRST FLOOR EXTERNAL WALL PLASTERING | 157 | 193.752 | 209.11 | SQM | 209.11 | 0 | 100% | 40515.4807 |  | 0
MD GIYAS | TERRACE FLOOR CEILING PLASTERING | 162 | 139.932 | 14.1 | SQM | 14.1 | 0 | 100% | 1973.0412 |  | 0
MD GIYAS | TERRACE FLOOR INTERNAL WALL PLASTERING | 163 | 139.932 | 37.29 | SQM | 37.29 | 0 | 100% | 5218.0643 |  | 0
MD GIYAS | TERRACE FLOOR EXTERNAL WALL PLASTERING | 166 | 193.752 | 180.56 | SQM | 180.56 | 0 | 100% | 34983.8611 |  | 0
CLENSTACK LLP | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 212.03 | SQM | 212.03 | 0 | 100% | 45645.8184 |  | 0
CLENSTACK LLP | WATERPROOF PLASTERING | 170 | 215.28 | 67.023 | SQM | 67.02 | 0.003 | 100% | 14428.0656 |  | 0
CLENSTACK LLP | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 27.453 | SQM | 27.45 | 0.003 | 99.99% | 2954.718 |  | 0
CLENSTACK LLP | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 99.373 | SQM | 99.37 | 0.003 | 100% | 21392.3736 |  | 0
CLENSTACK LLP | CINDER FILLING ALL FLOOR | 178 | 107.64 | 27.453 | SQM | 27.45 | 0.003 | 99.99% | 2954.718 |  | 0
CLENSTACK LLP | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 14 | 0 | 100% | 2800 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 27.313 | SQM | 27.31 | 0.003 | 99.99% | 5879.2968 |  | 0
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 147.16 | SQM | 147.16 | 0 | 100% | 14256.8608 |  | 0
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 531.773 | SQM | 531.77 | 0.003 | 100% | 8588.0855 |  | 0
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 531.77 | SQM | 531.77 | 0 | 100% | 17171.9168 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 609.07 | SQM | 609.07 | 0 | 100% | 29502.1327 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 609.07 | SQM | 609.07 | 0 | 100% | 9836.4805 |  | 0
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 609.07 | SQM | 609.07 | 0 | 100% | 16390.0737 |  | 0
INDAL SAHNI | STAIRCASE GRANITE | 215 | 301.392 | 20.67 | SQM | 20.67 | 0 | 100% | 6229.7726 |  | 0
INDAL SAHNI | DOOR OPENING GRANITE | 218 | 350 | 23 | NOS | 15 | 8 | 65.22% | 5250 |  | 0
INDAL SAHNI | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 12.18 | RMT | 12.18 | 0 | 100% | 998.76 |  | 0
INDAL SAHNI | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 112.3 | RMT | 112.3 | 0 | 100% | 3683.44 |  | 0
INDAL SAHNI | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 51.464 | RMT | 51.46 | 0.004 | 99.99% | 6751.552 |  | 0
INDAL SAHNI | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 |  | 0
INDAL SAHNI | GROUND FLOOR TILING | 224 | 183 | 78.221 | SQM | 62.58 | 15.641 | 80% | 11452.14 |  | 0
SANTOSH KUMAR | GROUND FLOOR TILING | 224 | 183 | 15.6442 | SQM | 15.64 | 0.0042 | 99.97% | 2862.12 |  | 0
INDAL SAHNI | GROUND FLOOR SKIRTING | 225 | 49.2 | 59.683 | RMT | 47.75 | 11.933 | 80.01% | 2349.3 |  | 0
SANTOSH KUMAR | GROUND FLOOR SKIRTING | 225 | 49.2 | 11.9366 | RMT | 11.94 | -0.0034 | 100% | 587.448 |  | 0
INDAL SAHNI | FIRST FLOOR TILING | 226 | 183 | 76.8 | SQM | 61.44 | 15.36 | 80% | 11243.52 |  | 0
SANTOSH KUMAR | FIRST FLOOR TILING | 226 | 183 | 15.36 | SQM | 15.36 | 0 | 100% | 2810.88 |  | 0
INDAL SAHNI | FIRST FLOOR SKIRTING | 227 | 49.2 | 69.125 | RMT | 55.3 | 13.825 | 80% | 2720.76 |  | 0
SANTOSH KUMAR | FIRST FLOOR SKIRTING | 227 | 49.2 | 13.825 | RMT | 13.83 | -0.005 | 100% | 680.436 |  | 0
INDAL SAHNI | TERRACE FLOOR TILING | 228 | 183 | 22.875 | SQM | 16.01 | 6.865 | 69.99% | 2929.83 |  | 0
SANTOSH KUMAR | TERRACE FLOOR TILING | 228 | 183 | 6.8625 | SQM | 6.86 | 0.0025 | 99.96% | 1255.38 |  | 0
INDAL SAHNI | TERRACE FLOOR SKIRTING | 229 | 49.2 | 22.389 | RMT | 15.67 | 6.719 | 69.99% | 770.964 |  | 0
SANTOSH KUMAR | TERRACE FLOOR SKIRTING | 229 | 49.2 | 6.7167 | RMT | 6.72 | -0.0033 | 100% | 330.624 |  | 0
INDAL SAHNI | UTILITY FLOOR TILING | 230 | 183 | 4.074 | SQM | 0 | 4.074 | 0% | 0 |  | 0
SANTOSH KUMAR | UTILITY FLOOR TILING | 230 | 183 | 4.074 | SQM | 4.07 | 0.004 | 99.9% | 744.81 |  | 0
INDAL SAHNI | UTILITY SKIRTING | 231 | 49.2 | 8.108 | RMT | 0 | 8.108 | 0% | 0 |  | 0
SANTOSH KUMAR | UTILITY SKIRTING | 231 | 49.2 | 8.108 | RMT | 8.11 | -0.002 | 100% | 399.012 |  | 0
INDAL SAHNI | BALCONY & SITOUT TILING | 232 | 183 | 17.16 | SQM | 12.01 | 5.15 | 69.99% | 2197.83 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT TILING | 232 | 183 | 5.148 | SQM | 5.15 | -0.002 | 100% | 942.45 |  | 0
INDAL SAHNI | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 28.083 | RMT | 19.66 | 8.423 | 70.01% | 967.272 |  | 0
SANTOSH KUMAR | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 8.4249 | RMT | 8.42 | 0.0049 | 99.94% | 414.264 |  | 0
INDAL SAHNI | CAR PARKING AREA TILING | 234 | 183 | 19.303 | SQM | 19.3 | 0.003 | 99.98% | 3531.9 |  | 0
INDAL SAHNI | FLOOR CHIPPING | 235 | 2.5 | 2278.15 | SFT | 2278.15 | 0 | 100% | 5695.375 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 4.087 | SQM | 0 | 4.087 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET FLOOR TILING | 237 | 172.224 | 6.27 | SQM | 6.27 | 0 | 100% | 1079.8445 |  | 0
INDAL SAHNI | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 18.177 | SQM | 0 | 18.177 | 0% | 0 |  | 0
SANTOSH KUMAR | GROUND FLOOR TOILET WALL TILING | 238 | 193.752 | 30.43 | SQM | 30.43 | 0 | 100% | 5895.8734 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 8.453 | SQM | 0 | 8.453 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET FLOOR TILING | 239 | 172.224 | 12.43 | SQM | 12.43 | 0 | 100% | 2140.7443 |  | 0
INDAL SAHNI | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 37.256 | SQM | 0 | 37.256 | 0% | 0 |  | 0
SANTOSH KUMAR | FIRST FLOOR TOILET WALL TILING | 240 | 193.752 | 59.784 | SQM | 59.78 | 0.004 | 99.99% | 11582.4946 |  | 0
RUPAK NAYAK | EPOXY GROUTING & SOAP WASH | 243 | 64.58 | 192.389 | SQM | 192.39 | -0.001 | 100% | 12424.5462 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 17500 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 8750 |  | 0
PRAKASH H N | VILLA EARTHING WORK | 247 | 600 | 1 | NOS | 1 | 0 | 100% | 600 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SHREE DM STEEL FURNITURE AND INTERIOR | BALCONY & STAIRCASE SS RAILING | 260 | 5535 | 28.23 | RMT | 28.23 | 0 | 100% | 156253.05 |  | 0
SAVITA DEVI | WASH BASIN ANGLE FIXING | 262 | 450 | 4 | NOS | 4 | 0 | 100% | 1800 |  | 0
SREE VINAYAKA ELECTRICALS | BESCOM METER BOX APPROVAL | 263 | 14832 | 1 | LUMP SUM | 1 | 0 | 100% | 14832 |  | 0
SAVITA DEVI | PLUMBING CHAMBER COVER FIXING | 264 | 1500 | 1 | LUMP SUM | 1 | 0 | 100% | 1500 |  | 0
SAVITA DEVI | MS GATE FOR UTILITY | 265 | 450 | 12.5 | SFT | 12.5 | 0 | 100% | 5625 |  | 0
SAVITA DEVI | FRP CHAMBER COVER FIXING | 270 | 250 | 1 | LUMP SUM | 1 | 0 | 100% | 250 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 18000 | 1 | LUMP SUM | 1 | 0 | 100% | 18000 |  | 0
MD GIYAS | LEDGE WALL PLASTERING & BLOCK WORK | 276 | 750 | 1 | NOS | 1 | 0 | 100% | 750 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 100 | RFT | 100 | 0 | 100% | 3400 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 27 | RFT | 27 | 0 | 100% | 2079 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 249 | SFT | 249 | 0 | 100% | 5727 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 15 | RFT | 15 | 0 | 100% | 2265 |  | 0
SANTOSH KUMAR | NAME BOARD TOP GRANITE | 282 | 300 | 1 | LUMP SUM | 1 | 0 | 100% | 300 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 1 | 0 | 100% | 400 |  | 0
SUNIL | ODD SITE STRUCTURAL DESIGN WORK | 315 | 13200 | 1 | LUMP SUM | 1 | 0 | 100% | 13200 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 2 | NOS | 2 | 0 | 100% | 2000 |  | 0
KRIUTTIBAS DAS | CUSTOMISATION JACUZZI POINT WORK | 409 | 1200 | 1 | NOS | 1 | 0 | 100% | 1200 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 89.526 | SQM | 89.53 | -0.004 | 100% | 4336.6541 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 89.526 | SQM | 89.53 | -0.004 | 100% | 1445.9095 |  | 0
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 89.526 | SQM | 89.53 | -0.004 | 100% | 2409.2523 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 14.102 | SQM | 14.1 | 0.002 | 99.99% | 227.715 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 14.102 | SQM | 14.1 | 0.002 | 99.99% | 455.3172 |  | 0
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 447 | 4600 | 1 | LUMP SUM | 1 | 0 | 100% | 4600 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION UTILITY SINK POINT WORK | 464 | 1000 | 3 | NOS | 1.5 | 1.5 | 50% | 1500 |  | 0
RUPAK NAYAK | CUSTOMISATION EPOXY GROUTING & SOAP WASH | 480 | 64.58 | 22.875 | SQM | 22.88 | -0.005 | 100% | 1477.5904 |  | 0
0

## V182
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 59.29 | SQM | 0 | 59.29 | 0% | 0 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 165.15 | CUM | 165.15 | 0 | 100% | 34958.952 |  | 0 | EBI ABRAHAM | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 50.93 | SQM | 50.93 | 0 | 100% | 1120.46 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 9.14 | CUM | 9.14 | 0 | 100% | 1934.7552 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 27.51 | CUM | 27.51 | 0 | 100% | 3882.2112 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 59.8 | SQM | 59.8 | 0 | 100% | 1315.6 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 5.677 | CUM | 5.68 | -0.003 | 100.1% | 5680 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 4.568 | CUM | 4.57 | -0.002 | 100% | 4570 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 7 | CUM | 7 | 0 | 100% | 7000 |  | 0 | RUPAK NAYAK | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.4 | MT | 0.4 | 0 | 100% | 3000 |  | 0 | SANTOSH KUMAR | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100% | 3375 |  | 0 | SARAT BARMAN | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.6 | MT | 0.6 | 0 | 100% | 4500 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0 | SHOKAT | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.45 | MT | 0 | 1.45 | 0% | 0 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.17 | MT | 0.09 | 0.08 | 52.94% | 675 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.1 | MT | 0 | 0.1 | 0% | 0 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 27.68 | SQM | 27.68 | 0 | 100% | 8342.5306 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 29.81 | SQM | 29.81 | 0 | 100% | 8984.4955 |  | 0 | SUBHASMITA DAS | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 63.5247 | SQM | 63.52 | 0.0047 | 99.99% | 19144.4198 |  | 0 | UDHABHAI R PARMAR | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 51.69 | SQM | 51.69 | 0 | 100% | 16691.7348 |  | 0 | V VENKATANARAYANA | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 153.64 | SQM | 0 | 153.64 | 0% | 0 |  | 0 | YELLAPPA C | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.33 | SQM | 0 | 12.33 | 0% | 0 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.97 | SQM | 0 | 15.97 | 0% | 0 |  | 0 | KOUSHIK MANDAL | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.9 | CUM | 9.9 | 0 | 100% | 2227.5 |  | 0 | SHEKAR T | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.32 | CUM | 1.32 | 0 | 100% | 1980 |  | 0 | MORSELIM KHAN | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 7.41 | CUM | 7.41 | 0 | 100% | 6669 |  | 0 | TOTAL | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 2.85 | CUM | 2.85 | 0 | 100% | 5700 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 13.08 | CUM | 0 | 13.08 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.773 | CUM | 0 | 1.773 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.55 | MT | 0 | 0.55 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.2 | MT | 0 | 1.2 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.17 | MT | 0 | 0.17 | 0% | 0 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 49.88 | SQM | 0 | 49.88 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 132.67 | SQM | 0 | 132.67 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.33 | SQM | 0 | 12.33 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 16.88 | SQM | 0 | 16.88 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 3.594 | CUM | 0 | 3.594 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 13.56 | CUM | 0 | 13.56 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.773 | CUM | 0 | 1.773 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.2 | MT | 0 | 0.2 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.02 | MT | 0 | 0.02 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 8.1 | SQM | 0 | 8.1 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 27.13 | SQM | 0 | 27.13 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 2.75 | SQM | 0 | 2.75 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.832 | CUM | 0 | 2.832 | 0% | 0 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 43 | NOS | 0 | 43 | 0% | 0 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SARAT BARMAN | ADDITIONAL REINFORCEMENT WORK | 310 | 7500 | 0.71 | LUMP SUM | 0 | 0.71 | 0% | 0 |  | 0
NAGARAJ | CUSTOMIZATION FLOOR SLAB AND BEAM SHUTTERING | 508 | 322.92 | 46.573 | SQM | 0 | 46.573 | 0% | 0 |  | 0
NAGARAJ | CUSTOMIZATION FLOOR COLUMN SHUTTERING | 509 | 322.92 | 20.55 | SQM | 0 | 20.55 | 0% | 0 |  | 0
0

## V183
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.16 | CUM | 30.16 | 0 | 100% | 4256.1792 |  | 0 | NAGARAJ | 16181.5212
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100% | 1510.74 |  | 0 | PRAKASH H N | 1000
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 4.81 | 2.057 | 70.05% | 4810 |  | 0 | SARAT BARMAN | 12742.5
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SHOKAT | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0 | SUBHASMITA DAS | 1753.25
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100% | 7980.8602 |  | 0 | UDHABHAI R PARMAR | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | V VENKATANARAYANA | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100% | 16492.1702 |  | 0 | YELLAPPA C | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 15.17 | SQM | 0 | 15.17 | 0% | 0 | 100% | 4898.6964 | MORSELIM KHAN | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0 | TOTAL | 31677.2712
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0 | 0.47 | 0% | 0 | 100% | 3525
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0 | 0.88 | 0% | 0 | 100% | 6600
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.14 | 0.04 | 77.78% | 1050 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 129.97 | SQM | 129.97 | 0 | 100% | 41969.9124 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 16.19 | SQM | 0 | 16.19 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0% | 0 | 100% | 975
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0% | 0 | 100% | 1425
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0 | 0.029 | 0% | 0 | 100% | 217.5
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0% | 0 | 100% | 3487.536
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0% | 0 | 100% | 7795.2888
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 3.5 | SQM | 0 | 3.5 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 | 100% | 1220
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0% | 0 | 100% | 533.25
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 1000 | 50% | 1000
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 9.54 | CUM | 9.54 | 0 | 100% | 7632 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.349 | CUM | 0 | 4.349 | 0% | 0 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 0 | 1.6 | 0% | 0 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 0 | 5 | 0% | 0 |  | 0
31677.2712

## V184
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | AAIDHUL MIAH | 163782.7055
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 12800
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 88.16 | CUM | 88.16 | 0 | 100% | 12441.1392 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | NAGARAJ | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 68.67 | SQM | 68.67 | 0 | 100% | 1510.74 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 0 | 7.95 | 0% | 0 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SAVITA DEVI | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SHOKAT | 63504.6544
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR, FIRST FLOOR & TERRACE FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 38 | 7000 | 1 | LUMP SUM | 0.4 | 0.6 | 40% | 2800 |  | 0 | YELLAPPA C | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 26.4 | SQM | 26.4 | 0 | 100% | 7956.7488 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100% | 16492.1702 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0 | MORSELIM KHAN | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100% | 38912.7211 |  | 0 | TOTAL | 240087.3599
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 9.25 | 0.0005 | 99.99% | 2987.01 |  | 0
NAGARAJ | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA SHUTTERING | 48 | 25000 | 1 | LUMP SUM | 0.4 | 0.6 | 40% | 10000 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
CHIRANJEEVI | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA RCC | 67 | 10000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 5000 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 107.86 | SQM | 107.86 | 0 | 100% | 32508.1411 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 0 | 9.815 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100% | 3487.536 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 0 | 24.14 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 0 | 1.89 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 0 | 2.37 | 0% | 0 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 14.873 | CUM | 14.87 | 0.003 | 99.98% | 11896 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 80.4 | 14.19 | 85% | 15577.6608 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 122 | 193.752 | 14.19 | SQM | 14.19 | 0 | 100% | 2749.3409 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100% | 25056.0086 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.973 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 0 | 62.973 | 0% | 0 | 100% | 12201.1447
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 | 100% | 1974.56
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 | 100% | 4387.984
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 | 100% | 80.73
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 0 | 268.5 | 0% | 0 | 100% | 9397.5
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 0 | 197 | 0% | 0 | 100% | 2119.72
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 0 | 59.84 | 0% | 0 | 90% | 7536.1778
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 0 | 176.74 | 0% | 0 | 90% | 22258.4235
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 0 | 131.565 | 0% | 0 | 90% | 22941.8837
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 0 | 81.65 | 0% | 0 | 90% | 10282.903
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 0 | 228.24 | 0% | 0 | 90% | 28744.2717
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.17 | SQM | 0 | 109.17 | 0% | 0 | 90% | 19036.7153
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 0 | 9.76 | 0% | 0 | 90% | 1229.1627
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 0 | 34.16 | 0% | 0 | 90% | 4302.0694
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 0 | 99.15 | 0% | 0 | 90% | 17289.4597
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 139.17 | SQM | 0 | 0 | 0% | 0 | 100% | 29960.5176
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 23.97 | SQM | 0 | 0 | 0% | 0 | 100% | 5160.2616
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 28.45 | SQM | 0 | 0 | 0% | 0 | 100% | 3062.358
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 90.39 | SQM | 0 | 0 | 0% | 0 | 100% | 19459.1592
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 28.45 | SQM | 0 | 0 | 0% | 0 | 100% | 3062.358
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 14 | NOS | 0 | 0 | 0% | 0 | 100% | 2800
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 4500 | 50% | 4500
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 6000
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 500
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1800
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.349 | CUM | 0 | 4.349 | 0% | 0 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 0 | 1.6 | 0% | 0 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 0 | 5 | 0% | 0 |  | 0
240087.3599

## V185
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 122489.1988
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | KRIUTTIBAS DAS | 8300
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100% | 9878.4 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | RUPAK NAYAK | 0
MANJUNATHA P | BASE FLOOR EARTH DRESSING | 14 | 22 | 40 | SQM | 40 | 0 | 100% | 880 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | SARAT BARMAN | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 7.95 | CUM | 7.95 | 0 | 100% | 1121.904 |  | 0 | SAVITA DEVI | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SHOKAT | 63146.8688
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | YELLAPPA C | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0 | RABIUL MOLLA | 0
SARAT BARMAN | GROUND FLOOR, FIRST FLOOR & TERRACE FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 38 | 7000 | 1 | LUMP SUM | 0.28 | 0.72 | 28% | 1960 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100% | 7980.8602 |  | 0 | SHEKAR T | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | MORSELIM KHAN | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100% | 16492.1702 |  | 0 | TOTAL | 193936.0676
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100% | 38912.7211 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
NAGARAJ | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA SHUTTERING | 48 | 25000 | 1 | LUMP SUM | 0.85 | 0.15 | 85% | 21250 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100% | 1440 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 107.86 | SQM | 107.86 | 0 | 100% | 32508.1411 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
AAIDHUL MIAH | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 1500 | 0.87 | CUM | 0.87 | 0 | 100% | 1305 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100% | 7275.6029 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
AAIDHUL MIAH | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 1500 | 0.38 | CUM | 0.38 | 0 | 100% | 570 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
MD GIYAS | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 85 | 9.59 | 89.86% | 16468.92 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 121 | 193.75 | 9.59 | SQM | 9.59 | 0 | 100% | 1858.0625 |  | 0
MD GIYAS | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100% | 25056.0086 |  | 0
MD GIYAS | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 31.49 | 31.483 | 50.01% | 6101.2505 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 31.4865 | SQM | 31.49 | -0.0035 | 100% | 6101.2505 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 | 100% | 1974.56
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 | 100% | 4387.984
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 | 100% | 80.73
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 0 | 268.5 | 0% | 0 | 100% | 9397.5
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 0 | 197 | 0% | 0 | 100% | 2119.72
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 35.9 | 23.94 | 59.99% | 5023.5588 | 30% | 2512.0593
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 106.04 | 70.7 | 60% | 14838.3893 | 30% | 7419.4745
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 0 | 131.565 | 0% | 0 | 90% | 22941.8837
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 48.99 | 32.66 | 60% | 6855.2687 | 30% | 3427.6343
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 136.94 | 91.3 | 60% | 19162.2881 | 30% | 9581.4239
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.17 | SQM | 0 | 109.17 | 0% | 0 | 90% | 19036.7153
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 5.86 | 3.9 | 60.04% | 820.0015 | 30% | 409.7209
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 20.5 | 13.66 | 60.01% | 2868.606 | 30% | 1434.0231
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 0 | 99.15 | 0% | 0 | 90% | 17289.4597
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 137.47 | SQM | 0 | 0 | 0% | 0 | 100% | 29594.5416
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 26.4 | SQM | 0 | 0 | 0% | 0 | 100% | 5683.392
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 33.78 | SQM | 0 | 0 | 0% | 0 | 100% | 3636.0792
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 80.81 | SQM | 0 | 0 | 0% | 0 | 100% | 17396.7768
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 33.78 | SQM | 0 | 0 | 0% | 0 | 100% | 3636.0792
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 16 | NOS | 0 | 0 | 0% | 0 | 100% | 3200
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 4500 | 50% | 4500
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 500
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1800
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 1500 | 50% | 1500
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 6489.53 | 1 | LUMP SUM | 1 | 0 | 100% | 6489.53 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 2 | NOS | 2 | 0 | 100% | 2000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.349 | CUM | 4.35 | -0.001 | 100% | 978.75 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100% | 250 |  | 0
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 41.887 | SQM | 41.89 | -0.003 | 100% | 13527.1188 |  | 0
NAGARAJ | CUSTOMIZATION ROOM LINTEL CHAJJA SHUTTERING | 497 | 322.92 | 3.62 | SQM | 3.62 | 0 | 100% | 1168.9704 |  | 0
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 16.5 | SQM | 16.5 | 0 | 100% | 5328.18 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR CEILING PLASTERING | 499 | 139.932 | 21.306 | SQM | 12.78 | 8.526 | 59.98% | 1788.331 | 30% | 894.4174
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR INTERNAL WALL PLASTERING | 500 | 139.932 | 64.585 | SQM | 38.75 | 25.835 | 60% | 5422.365 | 30% | 2711.2525
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR EXTERNAL WALL PLASTERING | 501 | 193.752 | 64.438 | SQM | 0 | 64.438 | 0% | 0 | 90% | 11236.4922
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.35613 | MT | 0.36 | -0.003869 | 101.1% | 2700 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.26878 | MT | 0.27 | -0.001218 | 100.5% | 2025 |  | 0
MD GIYAS | CUSTOMIZATION FLOOR BLOCK WORK | 545 | 193.752 | 52.216 | SQM | 26.11 | 26.106 | 50% | 5058.8647 |  | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR BLOCK WORK | 545 | 193.752 | 26.108 | SQM | 0 | 26.108 | 0% | 0 | 100% | 5058.4772
AAIDHUL MIAH | CUSTOMISATION TERRACE RCC SURFACE HACKING | 546 | 10.76 | 53.501 | SQM | 0 | 53.501 | 0% | 0 | 100% | 575.6708
193936.0676

## V186
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 35495.1772
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 103.66 | CUM | 103.66 | 0 | 100% | 21942.7488 |  | 0 | EBI ABRAHAM | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | JMJ WATERPROOING ENTERPRISES | 29408.2595
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | KRIUTTIBAS DAS | 17800
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 70 | CUM | 70 | 0 | 100% | 9878.4 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | RUPAK NAYAK | 56881.8521
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 5.49 | 1.377 | 79.95% | 5490 |  | 0 | SARAT BARMAN | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SHOKAT | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR, FIRST FLOOR & TERRACE FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 38 | 7000 | 1 | LUMP SUM | 0.36 | 0.64 | 36% | 2520 |  | 0 | UDHABHAI R PARMAR | 0
NAGARAJ | FOOTING SHUTTERING | 41 | 301.392 | 26.48 | SQM | 26.48 | 0 | 100% | 7980.8602 |  | 0 | V VENKATANARAYANA | 0
NAGARAJ | PEDESTAL COLUMN SHUTTERING | 42 | 301.392 | 25.77 | SQM | 25.77 | 0 | 100% | 7766.8718 |  | 0 | YELLAPPA C | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 301.392 | 54.72 | SQM | 54.72 | 0 | 100% | 16492.1702 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 301.392 | 45.3 | SQM | 45.3 | 0 | 100% | 13653.0576 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 301.392 | 129.11 | SQM | 129.11 | 0 | 100% | 38912.7211 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0 | MORSELIM KHAN | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 0 | 9.2505 | 0% | 0 |  | 0 | TOTAL | 139585.2888
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 15.17 | SQM | 15.17 | 0 | 100% | 4572.1166 |  | 0
NAGARAJ | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA SHUTTERING | 48 | 23831.03 | 1 | LUMP SUM | 0.38 | 0.62 | 38% | 9055.7914 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.26 | CUM | 3.26 | 0 | 100% | 6520 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.33 | CUM | 15.33 | 0 | 100% | 3449.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
MD GIYAS | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 1500 | 0.96 | CUM | 0.96 | 0 | 100% | 1440 |  | 0
AAIDHUL MIAH | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA RCC | 67 | 10000 | 1 | LUMP SUM | 0.32 | 0.68 | 32% | 3200 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 7500 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 301.392 | 39.24 | SQM | 39.24 | 0 | 100% | 11826.6221 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 301.392 | 107.8 | SQM | 107.8 | 0 | 100% | 32490.0576 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 301.392 | 12.27 | SQM | 12.27 | 0 | 100% | 3698.0798 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 301.392 | 9.815 | SQM | 0 | 9.815 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
MD GIYAS | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.83 | CUM | 0 | 0.83 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7500 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 301.392 | 10.8 | SQM | 10.8 | 0 | 100% | 3255.0336 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 301.392 | 24.14 | SQM | 24.14 | 0 | 100% | 7275.6029 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 301.392 | 1.89 | SQM | 0 | 1.89 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.61 | CUM | 0.61 | 0 | 100% | 1220 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
MD GIYAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.17 | CUM | 0 | 0.17 | 0% | 0 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
MD GIYAS | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 80.4 | 14.19 | 85% | 15577.6608 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 14.1885 | SQM | 0 | 14.1885 | 0% | 0 | 100% | 2749.0503
MD GIYAS | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 129.32 | 0 | 100% | 25056.0086 |  | 0
MD GIYAS | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 62.973 | SQM | 31.49 | 31.483 | 50.01% | 6101.2505 |  | 0
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 131 | 193.75 | 31.49 | SQM | 31.49 | 0 | 100% | 6101.1875 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 30.1 | RMT | 0 | 30.1 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 66.89 | RMT | 0 | 66.89 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 0.5 | SQM | 0 | 0.5 | 0% | 0 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 268.5 | 0 | 100% | 9397.5 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 197 | SQM | 197 | 0 | 100% | 2119.72 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 59.84 | SQM | 59.84 | 0 | 100% | 8373.5309 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 176.74 | SQM | 176.74 | 0 | 100% | 24731.5817 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 131.565 | SQM | 105.25 | 26.315 | 80% | 20392.398 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 81.65 | SQM | 81.65 | 0 | 100% | 11425.4478 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 228.24 | SQM | 228.24 | 0 | 100% | 31938.0797 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 109.17 | SQM | 109.17 | 0 | 100% | 21151.9058 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 9.76 | SQM | 9.76 | 0 | 100% | 1365.7363 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 34.16 | SQM | 34.16 | 0 | 100% | 4780.0771 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 99.15 | SQM | 99.15 | 0 | 100% | 19210.5108 |  | 0
JMJ WATERPROOING ENTERPRISES | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 175.59 | SQM | 175.59 | 0 | 100% | 37801.0152 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF PLASTERING | 170 | 215.28 | 136.43 | SQM | 136.43 | 0 | 100% | 29370.6504 |  | 0
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 34.58 | SQM | 0 | 34.58 | 0% | 0 | 100% | 3722.1912
JMJ WATERPROOING ENTERPRISES | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 88.83 | SQM | 0 | 88.83 | 0% | 0 | 100% | 19123.3224
JMJ WATERPROOING ENTERPRISES | CINDER FILLING ALL FLOOR | 178 | 107.64 | 34.58 | SQM | 5.1974 | 29.3826 | 15.03% | 559.4453 | 84.97% | 3162.7459
JMJ WATERPROOING ENTERPRISES | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 0 | 17 | 0% | 0 | 100% | 3400
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 0 | 19.974 | 0% | 0 | 100% | 4300.0027
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 0 | 61.966 | 0% | 0 | 100% | 6003.2661
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 0 | 345.504 | 0% | 0 | 100% | 5579.8896
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 0 | 345.504 | 0% | 0 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 0 | 58.07 | 0% | 0 | 100% | 937.8305
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 0 | 524.433 | 0% | 0 | 100% | 25402.4857
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 0 | 535.5 | 0% | 0 | 100% | 8648.325
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 0 | 541.249 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 4500 | 50% | 4500
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 6000
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 500
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1800
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 3000
PRAKASH H N | CUSTOMIZATION ELECTRICAL WORK/BASED ON 15% OF TOTAL CUSTOMISATION VALUE | 406 | 3745.5 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 1872.75 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 2 | NOS | 2 | 0 | 100% | 2000 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 89.526 | SQM | 0 | 89.526 | 0% | 0 | 100% | 4336.4604
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 89.526 | SQM | 0 | 89.526 | 0% | 0 | 100% | 1445.8449
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 89.526 | SQM | 0 | 89.526 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 14.102 | SQM | 0 | 14.102 | 0% | 0 | 100% | 227.7473
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 14.102 | SQM | 0 | 14.102 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION BATHTUB WORK | 425 | 3000 | 1 | NOS | 1 | 0 | 100% | 3000 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.349 | CUM | 4.35 | -0.001 | 100% | 978.75 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100% | 250 |  | 0
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 41.887 | SQM | 41.89 | -0.003 | 100% | 13527.1188 |  | 0
NAGARAJ | CUSTOMIZATION ROOM LINTEL CHAJJA SHUTTERING | 497 | 322.92 | 3.62 | SQM | 3.62 | 0 | 100% | 1168.9704 |  | 0
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 16.5 | SQM | 16.5 | 0 | 100% | 5328.18 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR CEILING PLASTERING | 499 | 139.932 | 21.306 | SQM | 0 | 21.306 | 0% | 0 | 90% | 2683.2521
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR INTERNAL WALL PLASTERING | 500 | 139.932 | 64.585 | SQM | 0 | 64.585 | 0% | 0 | 90% | 8133.7574
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR EXTERNAL WALL PLASTERING | 501 | 193.752 | 64.438 | SQM | 0 | 64.438 | 0% | 0 | 90% | 11236.4922
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.35613 | MT | 0.36 | -0.003869 | 101.1% | 2700 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.26878 | MT | 0.27 | -0.001218 | 100.5% | 2025 |  | 0
AAIDHUL MIAH | CUSTOMIZATION FLOOR BLOCK WORK | 545 | 193.752 | 52.216 | SQM | 0 | 52.216 | 0% | 0 | 100% | 10116.9544
AAIDHUL MIAH | CUSTOMISATION TERRACE RCC SURFACE HACKING | 546 | 10.76 | 53.501 | SQM | 0 | 53.501 | 0% | 0 | 100% | 575.6708
139585.2888

## V187
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment |  | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 |  | AAIDHUL MIAH | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 |  | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 |  | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 |  | KRIUTTIBAS DAS | 13800
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 |  | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 |  | MANJUNATHA P | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 75.32 | CUM | 75.32 | 0 | 100% | 10629.1584 |  | 0 |  | NAGARAJ | 3779.7786
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 |  | PRAKASH H N | 19000
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 |  | RAMAKRUSHNA PRADHAN | 0
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 4.17 | CUM | 4.17 | 0 | 100% | 588.4704 |  | 0 |  | RUPAK NAYAK | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 |  | SANTOSH KUMAR | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 |  | SARAT BARMAN | 3040
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 10.81 | 0 | 100% | 1525.5072 |  | 0 |  | SAVITA DEVI | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 |  | SHOKAT | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 |  | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 |  | SK ANSAR HOSSIAN | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100% | 2775 |  | 0 |  | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100% | 3375 |  | 0 |  | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0 |  | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0 |  | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100% | 9375 |  | 0 |  | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0 |  | YELLAPPA C | 52854.7993
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.14 | MT | 0 | 0.14 | 0% | 0 | 100% | 1400 |  | RABIUL MOLLA | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 |  | KOUSHIK MANDAL | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 |  | SHEKAR T | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 |  | MORSELIM KHAN | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0 |  | TOTAL | 92474.5779
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.2505 | 0% | 0 |  | 0
NAGARAJ | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA SHUTTERING | 48 | 25000 | 1 | LUMP SUM | 0.4 | 0.6 | 40% | 10000 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
YELLAPPA C | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA RCC |  | 10000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 10000
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 65 | 3000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100% | 8250 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0% | 0 | 100% | 1500
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100% | 34810.776 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 9.82 | -0.005 | 100.1% | 3171.0744 | 100% | 3169.4598
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.79 | CUM | 1.79 | 0 | 100% | 3580 |  | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 95 | 3000 | 0.843 | CUM | 0 | 0.843 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100% | 750 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.02 | MT | 0 | 0.02 | 0% | 0 | 100% | 140
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100% | 3487.536 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 24.14 | 0 | 100% | 7795.2888 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0% | 0 | 100% | 610.3188
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
CHIRANJEEVI | TERRACE FLOOR LINTEL BEAM & CHEJJA RCC | 115 | 3000 | 0.07 | CUM | 0 | 0.07 | 0% | 0 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 106.054 | SQM | 90.15 | 15.904 | 85% | 17466.7428 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 113.2014 | SQM | 0 | 113.2014 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 69.96 | SQM | 0 | 69.96 | 0% | 0 |  | 0
YELLAPPA C | GROUND FLOOR BLOCK WORK | 120 | 215.28 | 106.054 | SQM | 90.15 | 15.904 | 85% | 19407.492 | 15% | 3423.8131 | 215.28
YELLAPPA C | FIRST FLOOR BLOCK WORK | 124 | 215.28 | 113.2014 | SQM | 0 | 113.2014 | 0% | 0 | 100% | 24369.9974
YELLAPPA C | TERRACE FLOOR BLOCK WORK | 129 | 215.28 | 69.96 | SQM | 0 | 69.96 | 0% | 0 | 100% | 15060.9888
CHIRANJEEVI | ELEVATION RCC BAND | 133 | 65.6 | 27.15 | RMT | 0 | 27.15 | 0% | 0 |  | 0
CHIRANJEEVI | ELEVATION GROOVE | 137 | 65.6 | 43.88 | RMT | 0 | 43.88 | 0% | 0 |  | 0
CHIRANJEEVI | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0% | 0 |  | 0
CHIRANJEEVI | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 0 | 268.5 | 0% | 0 |  | 0
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 268.5 | SQM | 0 | 268.5 | 0% | 0 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 8.07 | 348.385 | SQM | 0 | 348.385 | 0% | 0 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 8.07 | 348.385 | SQM | 0 | 348.385 | 0% | 0 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 65.55 | SQM | 0 | 65.55 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 65.55 | SQM | 0 | 65.55 | 0% | 0 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0% | 0 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 173.109 | SQM | 0 | 173.109 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 173.109 | SQM | 0 | 173.109 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 16500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 16500
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 0 | 61.662 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 0 | 61.662 | 0% | 0 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 185.883 | SQM | 0 | 185.883 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 185.883 | SQM | 0 | 185.883 | 0% | 0 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 150.161 | SQM | 0 | 150.161 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 150.161 | SQM | 0 | 150.161 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 10.287 | SQM | 0 | 10.287 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 10.287 | SQM | 0 | 10.287 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 66.94 | SQM | 0 | 66.94 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 66.94 | SQM | 0 | 66.94 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 87.48 | SQM | 0 | 87.48 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 87.48 | SQM | 0 | 87.48 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 18500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 9000
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1800
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUNIL | CUSTOMIZATION STRUCTURAL DESIGN WORK | 299 | 9900 | 1 | LUMP SUM | 1 | 0 | 100% | 9900 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0
OTIS ELEVATOR COMPANY | SUPPLY & INSTALLATION OF LIFT | 344 | 805576.27 | 1 | UNIT | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC REWORK | 397 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING REWORK | 398 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING REWORK | 399 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 3000
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2500
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 37.921 | SQM | 37.92 | 0.001 | 100% | 12245.1264 |  | 0
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 14.003 | SQM | 14 | 0.003 | 99.98% | 4520.88 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.34416 | MT | 0.34 | 0.004161 | 98.79% | 2550 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.23678 | MT | 0.24 | -0.003217 | 101.4% | 1800 |  | 0
92474.5779

## V188
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | AAIDHUL MIAH | 62314.2626
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | RAMAKRUSHNA PRADHAN | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | RUPAK NAYAK | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 4.81 | 2.057 | 70.05% | 4810 |  | 0 | SAVITA DEVI | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SHOKAT | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SK ANSAR HOSSIAN | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | SUBHASMITA DAS | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR, FIRST FLOOR & TERRACE FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 38 | 7000 | 1 | LUMP SUM | 0.4 | 0.6 | 40% | 2800 |  | 0 | V VENKATANARAYANA | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 | YELLAPPA C | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 | RABIUL MOLLA | 0
NAGARAJ | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | KOUSHIK MANDAL | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0 | MORSELIM KHAN | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0 | TOTAL | 62314.2626
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.2505 | 0% | 0 |  | 0
NAGARAJ | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA SHUTTERING | 48 | 25000 | 1 | LUMP SUM | 0.4 | 0.6 | 40% | 10000 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.53 | CUM | 15.53 | 0 | 100% | 3494.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.14 | 0.04 | 77.78% | 1050 |  | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0% | 0 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100% | 34810.776 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.815 | 0% | 0 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
CHIRANJEEVI | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 93 | 3000 | 0.843 | CUM | 0 | 0.843 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0% | 0 |  | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.029 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0% | 0 |  | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0 | 0.41 | 0% | 0 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 0 | 2.412 | 0% | 0 |  | 0
CHIRANJEEVI | TERRACE FLOOR ROOF BEAM & SLAB RCC | 113 | 3000 | 0.07 | CUM | 0 | 0.07 | 0% | 0 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0% | 0 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 94.59 | SQM | 0 | 94.59 | 0% | 0 | 100% | 18327.0017
AAIDHUL MIAH | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 129.32 | SQM | 0 | 129.32 | 0% | 0 | 80% | 20044.8069
AAIDHUL MIAH | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 69.96 | SQM | 0 | 69.96 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 27.15 | RMT | 0 | 27.15 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 43.88 | RMT | 0 | 43.88 | 0% | 0 |  | 0
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0% | 0 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 8.073 | 348.385 | SQM | 0 | 348.385 | 0% | 0 | 100% | 2812.5121
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 65.55 | SQM | 0 | 65.55 | 0% | 0 | 65% | 5962.1527
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0% | 0 | 65% | 15167.7892
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 173.109 | SQM | 0 | 173.109 | 0% | 0 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 7250 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 0 | 61.662 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 185.883 | SQM | 0 | 185.883 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 150.161 | SQM | 0 | 150.161 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 10.287 | SQM | 0 | 10.287 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 66.94 | SQM | 0 | 66.94 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 87.48 | SQM | 0 | 87.48 | 0% | 0 |  | 0
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 |  | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC REWORK | 397 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.624 | CUM | 0 | 4.624 | 0% | 0 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 0 | 1.6 | 0% | 0 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 0 | 5 | 0% | 0 |  | 0
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 45.091 | SQM | 0 | 45.091 | 0% | 0 |  | 0
NAGARAJ | CUSTOMIZATION ROOM LINTEL CHAJJA SHUTTERING | 497 | 322.92 | 3.178 | SQM | 0 | 3.178 | 0% | 0 |  | 0
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 16.5 | SQM | 0 | 16.5 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR CEILING PLASTERING | 499 | 139.932 | 22.638 | SQM | 0 | 22.638 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR INTERNAL WALL PLASTERING | 500 | 139.932 | 65.546 | SQM | 0 | 65.546 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR EXTERNAL WALL PLASTERING | 501 | 193.752 | 69.843 | SQM | 0 | 69.843 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR BLOCK WORK | 502 | 193.752 | 31.944 | SQM | 0 | 31.944 | 0% | 0 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.36531 | MT | 0 | 0.36531 | 0% | 0 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.25218 | MT | 0 | 0.25218 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE RCC SURFACE HACKING | 546 | 10.76 | 53.899 | SQM | 0 | 53.899 | 0% | 0 |  | 0
62314.2626

## V189
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | AAIDHUL MIAH | 4388.3684
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 5000
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 53.78 | SQM | 53.78 | 0 | 100% | 1183.16 |  | 0 | LEGENDRY LANDSCAPE | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | MANJUNATHA P | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 75.32 | CUM | 75.32 | 0 | 100% | 10629.1584 |  | 0 | NAGARAJ | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | PRAKASH H N | 0
MANJUNATHA P | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 0.412 | CUM | 0.41 | 0.002 | 99.51% | 86.7888 |  | 0 | RAMAKRUSHNA PRADHAN | 6743.6865
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | RUPAK NAYAK | 56881.8521
MANJUNATHA P | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 4.17 | CUM | 4.17 | 0 | 100% | 588.4704 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | SARAT BARMAN | 0
MANJUNATHA P | BASE FLOOR EARTH DRESSING | 14 | 22 | 63.19 | SQM | 63.19 | 0 | 100% | 1390.18 |  | 0 | SAVITA DEVI | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | SHOKAT | 364.469
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 10.81 | 0 | 100% | 1525.5072 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0.001 | 99.97% | 3350 |  | 0 | SK ANSAR HOSSIAN | 64283.3616
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.37 | MT | 0.37 | 0 | 100% | 2775 |  | 0 | SUBHASMITA DAS | 12000
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.45 | MT | 0.45 | 0 | 100% | 3375 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.55 | MT | 0.55 | 0 | 100% | 4125 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0 | YELLAPPA C | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.25 | MT | 1.25 | 0 | 100% | 9375 |  | 0 | RABIUL MOLLA | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0 | KOUSHIK MANDAL | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.14 | MT | 0.14 | 0 | 100% | 1400 |  | 0 | SHEKAR T | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 | MORSELIM KHAN | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 | TOTAL | 149661.7376
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 301.392 | 9.2505 | SQM | 9.25 | 0.0005 | 99.99% | 2787.876 |  | 0
NAGARAJ | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA SHUTTERING | 48 | 25000 | 1 | LUMP SUM | 0.6 | 0.4 | 60% | 15000 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 16.867 | CUM | 16.87 | -0.003 | 100% | 3795.75 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.77 | CUM | 1.77 | 0 | 100% | 3540 |  | 0
CHIRANJEEVI | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA RCC | 63 | 3000 | 0.61 | CUM | 0 | 0.61 | 0% | 0 |  | 0
CHIRANJEEVI | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA RCC | 67 | 10000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.5 | MT | 0.5 | 0 | 100% | 3750 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 1.1 | MT | 1.1 | 0 | 100% | 8250 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.14 | MT | 0.14 | 0 | 100% | 1050 |  | 0
SARAT BARMAN | FIRST & TERRACE FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 81 | 4200 | 1 | LUMP SUM | 1 | 0 | 100% | 4200 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100% | 34810.776 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.1 | MT | 0.1 | 0 | 100% | 750 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.17 | MT | 0.17 | 0 | 100% | 1275 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100% | 3487.536 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 24.14 | 0 | 100% | 7795.2888 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 2.41 | 0.002 | 99.92% | 542.25 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 106.054 | SQM | 90.15 | 15.904 | 85% | 17466.7428 |  | 0
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 113.204 | SQM | 113.2 | 0.004 | 100% | 21932.7264 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0% | 0 | 100% | 2101.824
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0% | 0 | 100% | 2102.48
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0% | 0 | 100% | 184.0644
AAIDHUL MIAH | SCAFFOLDING FOR EXTERNAL PLASTERING | 139 | 35 | 71.68 | SQM | 71.68 | 0 | 100% | 2508.8 |  | 0
CHIRANJEEVI | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 0 | 206.732 | 0% | 0 |  | 0
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 161.909 | SQM | 161.91 | -0.001 | 100% | 1742.1516 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 65.55 | SQM | 0 | 65.55 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100% | 27220.972 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 0 | 208.32 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 70.31 | SQM | 70.31 | 0 | 100% | 13622.7031 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 0 | 61.662 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0.002 | 100% | 10409.5415 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 185.883 | SQM | 0 | 185.883 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | -0.003 | 100% | 30850.808 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 0 | 142.16 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 56.143 | SQM | 56.14 | 0.003 | 99.99% | 10877.2373 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 10.27 | SQM | 0 | 10.27 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 0 | 33.43 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100% | 4677.9268 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 87.48 | SQM | 0 | 87.48 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 38.8104 | SQM | 38.81 | 0.0004 | 100% | 7519.5151 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 117.687 | SQM | 117.69 | -0.003 | 100% | 25336.3032 |  | 0
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 21.029 | SQM | 21.03 | -0.001 | 100% | 4527.3384 |  | 0
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 22.036 | SQM | 18.65 | 3.386 | 84.63% | 2007.486 | 15.37% | 364.469
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 78.011 | SQM | 78.01 | 0.001 | 100% | 16793.9928 |  | 0
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 18.646 | SQM | 18.65 | -0.004 | 100% | 2007.486 |  | 0
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 17 | NOS | 17 | 0 | 100% | 3400 |  | 0
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 0 | 19.974 | 0% | 0 | 100% | 4300.0027
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 0 | 61.966 | 0% | 0 | 100% | 6003.2661
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 0 | 345.504 | 0% | 0 | 100% | 5579.8896
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 0 | 345.504 | 0% | 0 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 0 | 58.07 | 0% | 0 | 100% | 937.8305
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 0 | 524.433 | 0% | 0 | 100% | 25402.4857
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 0 | 535.5 | 0% | 0 | 100% | 8648.325
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 0 | 541.249 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | STAIRCASE GRANITE | 215 | 301.392 | 17.75 | SQM | 0 | 17.75 | 0% | 0 | 95% | 5082.2226
SK ANSAR HOSSIAN | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 0 | 15 | 0% | 0 | 85% | 4462.5
SK ANSAR HOSSIAN | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.4 | RMT | 0 | 46.4 | 0% | 0 | 95% | 3614.56
SK ANSAR HOSSIAN | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 0 | 103.53 | 0% | 0 | 95% | 3225.9948
SK ANSAR HOSSIAN | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.07 | RMT | 0 | 23.07 | 0% | 0 | 95% | 2875.4448
SK ANSAR HOSSIAN | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 0 | 49.52 | 0% | 0 | 95% | 8609.052
SK ANSAR HOSSIAN | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 0 | 48.42 | 0% | 0 | 95% | 2263.1508
SK ANSAR HOSSIAN | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 0 | 46 | 0% | 0 | 95% | 7997.1
SK ANSAR HOSSIAN | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 0 | 50.44 | 0% | 0 | 95% | 2357.5656
SK ANSAR HOSSIAN | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 0 | 2.5 | 0% | 0 | 95% | 434.625
SK ANSAR HOSSIAN | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 0 | 4.19 | 0% | 0 | 95% | 195.8406
SK ANSAR HOSSIAN | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 0 | 4.01 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 0 | 9.98 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | BALCONY & SITOUT TILING | 232 | 183 | 10.18 | SQM | 0 | 10.18 | 0% | 0 | 95% | 1769.793
SK ANSAR HOSSIAN | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 14 | RMT | 0 | 14 | 0% | 0 | 95% | 654.36
SK ANSAR HOSSIAN | CAR PARKING AREA TILING | 234 | 183 | 11.138 | SQM | 0 | 11.138 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 0 | 1055 | 0% | 0 | 100% | 2637.5
SK ANSAR HOSSIAN | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.41 | SQM | 0 | 3.41 | 0% | 0 | 90% | 561.627
SK ANSAR HOSSIAN | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 0 | 17.34 | 0% | 0 | 90% | 2855.898
SK ANSAR HOSSIAN | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 6.62 | SQM | 0 | 6.62 | 0% | 0 | 90% | 1090.314
SK ANSAR HOSSIAN | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 33.99 | SQM | 0 | 33.99 | 0% | 0 | 90% | 5598.153
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 1 | 0 | 100% | 9000 |  | 0
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 1 | 0 | 100% | 6000 |  | 0
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 1 | 0 | 100% | 500 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 4000
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 1 | 0 | 100% | 1800 |  | 0
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 12000
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 | 100% | 2601.986
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 | 100% | 1518
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 | 100% | 2623.7005
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1000
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0.3 | 0.7 | 30% | 900 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHBASIN TAP POINT WORK | 408 | 1000 | 1 | NOS | 1 | 0 | 100% | 1000 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 89.526 | SQM | 0 | 89.526 | 0% | 0 | 100% | 4336.4604
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 89.526 | SQM | 0 | 89.526 | 0% | 0 | 100% | 1445.8449
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 89.526 | SQM | 0 | 89.526 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 14.102 | SQM | 0 | 14.102 | 0% | 0 | 100% | 227.7473
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 14.102 | SQM | 0 | 14.102 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION WASHING MACHINE POINT WORK | 421 | 1500 | 1 | NOS | 1 | 0 | 100% | 1500 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.624 | CUM | 4.62 | 0.004 | 99.91% | 1039.5 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100% | 250 |  | 0
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 45.091 | SQM | 45.09 | 0.001 | 100% | 14560.4628 |  | 0
NAGARAJ | CUSTOMIZATION ROOM LINTEL CHAJJA SHUTTERING | 497 | 322.92 | 3.178 | SQM | 3.18 | -0.002 | 100.1% | 1026.8856 |  | 0
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 16.5 | SQM | 16.5 | 0 | 100% | 5328.18 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR CEILING PLASTERING | 499 | 139.932 | 22.638 | SQM | 22.64 | -0.002 | 100% | 3168.0605 |  | 0
CHIRANJEEVI | CUSTOMISATION TERRACE FLOOR INTERNAL WALL PLASTERING | 500 | 139.932 | 65.546 | SQM | 0 | 65.546 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR INTERNAL WALL PLASTERING | 500 | 139.932 | 65.546 | SQM | 65.55 | -0.004 | 100% | 9172.5426 |  | 0
CHIRANJEEVI | CUSTOMISATION TERRACE FLOOR EXTERNAL WALL PLASTERING | 501 | 193.752 | 58.86 | SQM | 0 | 58.86 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR EXTERNAL WALL PLASTERING | 501 | 193.752 | 69.843 | SQM | 69.84 | 0.003 | 100% | 13531.6397 |  | 0
CHIRANJEEVI | CUSTOMISATION TERRACE FLOOR BLOCK WORK | 502 | 193.752 | 31.944 | SQM | 31.94 | 0.004 | 99.99% | 6188.4389 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.36531 | MT | 0.37 | -0.004687 | 101.3% | 2775 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.25218 | MT | 0.25 | 0.002183 | 99.13% | 1875 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE RCC SURFACE HACKING | 546 | 10.76 | 53.899 | SQM | 53.9 | -0.001 | 100% | 579.964 |  | 0
SK ANSAR HOSSIAN | CUSTOMIZATION MAIN FLOORING WORK | 442 | 232.339 | 19.038 | SQM | 0 | 19.038 | 0% | 0 | 95% | 4202.1064
SK ANSAR HOSSIAN | CUSTOMIZATION TOILET TILE WORK | 436 | 1134.593 | 3.717 | SQM | 0 | 3.717 | 0% | 0 | 90% | 3795.554
149661.7376

## V190
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment | Contractor | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100% | 3708.18 |  | 0 | AAIDHUL MIAH | 7469.8002
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100% | 4000 |  | 0 | EBI ABRAHAM | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100% | 1000 |  | 0 | JMJ WATERPROOING ENTERPRISES | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100% | 22766.184 |  | 0 | KRIUTTIBAS DAS | 20800
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100% | 1140.26 |  | 0 | LEGENDRY LANDSCAPE | 0
MANJUNATHA P | FOOTING EARTH DRESSING | 5 | 22 | 1.95 | SQM | 1.95 | 0 | 100% | 42.9 |  | 0 | MANJUNATHA P | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100% | 2562.7392 |  | 0 | NAGARAJ | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 75.32 | CUM | 75.32 | 0 | 100% | 10629.1584 |  | 0 | PRAKASH H N | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100% | 1134.6048 |  | 0 | RAMAKRUSHNA PRADHAN | 6743.6865
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100% | 4336.6176 |  | 0 | RUPAK NAYAK | 56881.8521
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100% | 630.74 |  | 0 | SANTOSH KUMAR | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0% | 0 |  | 0 | SARAT BARMAN | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.35 | CUM | 3.35 | 0 | 100% | 3350 |  | 0 | SAVITA DEVI | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | -0.002 | 100.1% | 2670 |  | 0 | SHOKAT | 56096.25
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | -0.003 | 100% | 6870 |  | 0 | SHREE DM STEEL FURNITURE AND INTERIOR | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100% | 2025 |  | 0 | SK ANSAR HOSSIAN | 63233.3616
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100% | 3150 |  | 0 | SREE VINAYAKA ELECTRICALS | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100% | 3975 |  | 0 | SRI CHOWDESHWARI WATER SUPPLY | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100% | 3675 |  | 0 | SUBHASMITA DAS | 12000
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 1.2 | 0 | 100% | 9000 |  | 0 | UDHABHAI R PARMAR | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0 | V VENKATANARAYANA | 0
SARAT BARMAN | GROUND FLOOR, FIRST FLOOR & TERRACE FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 38 | 7000 | 1 | LUMP SUM | 0.6 | 0.4 | 60% | 4200 |  | 0 | YELLAPPA C | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100% | 8550.9216 |  | 0 | RABIUL MOLLA | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100% | 8321.6484 |  | 0 | KOUSHIK MANDAL | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100% | 17670.1824 |  | 0 | SHEKAR T | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 45.3 | 0 | 100% | 14628.276 |  | 0 | MORSELIM KHAN | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 129.11 | 0 | 100% | 41692.2012 |  | 0 | TOTAL | 223224.9504
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
NAGARAJ | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA SHUTTERING | 48 | 25000 | 1 | LUMP SUM | 0.6 | 0.4 | 60% | 15000 |  | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100% | 2043 |  | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100% | 2550 |  | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100% | 3600 |  | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 3.04 | 0.001 | 99.97% | 6080 |  | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.53 | CUM | 15.53 | 0 | 100% | 3494.25 |  | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
CHIRANJEEVI | ALL FLOOR SILL, THROUGH LINTEL BEAM & CHEJJA RCC | 67 | 10000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | GROUND FLOOR ROOF CONDUIT | 68 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0.47 | 0 | 100% | 3525 |  | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0.88 | 0 | 100% | 6600 |  | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0.18 | 0 | 100% | 1350 |  | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 39.24 | 0 | 100% | 12671.3808 |  | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 107.8 | 0 | 100% | 34810.776 |  | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 12.27 | 0 | 100% | 3962.2284 |  | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 2.21 | 0 | 100% | 4420 |  | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 12.13 | 0 | 100% | 2729.25 |  | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 1.57 | 0 | 100% | 3140 |  | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0.13 | 0 | 100% | 975 |  | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0.19 | 0 | 100% | 1425 |  | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 10.8 | 0 | 100% | 3487.536 |  | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 24.14 | 0 | 100% | 7795.2888 |  | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0.41 | 0 | 100% | 820 |  | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.37 | CUM | 2.37 | 0 | 100% | 533.25 |  | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 44 | 0 | 100% | 2200 |  | 0
PRAKASH H N | FIRST & TERRACE FLOOR ROOF CONDUIT WORK | 118 | 2000 | 1 | LUMP SUM | 1 | 0 | 100% | 2000 |  | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0.003 | 99.96% | 5864 |  | 0
CHIRANJEEVI | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 106.054 | SQM | 90.15 | 15.904 | 85% | 17466.7428 |  | 0
AAIDHUL MIAH | GROUND FLOOR BLOCK WORK | 120 | 193.752 | 106.054 | SQM | 90.15 | 15.904 | 85% | 17466.7428 | 15% | 3081.4318
CHIRANJEEVI | FIRST FLOOR BLOCK WORK | 124 | 193.752 | 113.204 | SQM | 113.2 | 0.004 | 100% | 21932.7264 |  | 0
CHIRANJEEVI | TERRACE FLOOR BLOCK WORK | 129 | 193.752 | 67.31 | SQM | 67.31 | 0 | 100% | 13041.4471 |  | 0
AAIDHUL MIAH | ELEVATION RCC BAND | 133 | 65.6 | 32.04 | RMT | 0 | 32.04 | 0% | 0 | 100% | 2101.824
AAIDHUL MIAH | ELEVATION GROOVE | 137 | 65.6 | 32.05 | RMT | 0 | 32.05 | 0% | 0 | 100% | 2102.48
AAIDHUL MIAH | ELEAVTION BLOCK WORK | 138 | 161.46 | 1.14 | SQM | 0 | 1.14 | 0% | 0 | 100% | 184.0644
AAIDHUL MIAH | RCC SURFACE HACKING | 140 | 10.76 | 206.732 | SQM | 206.73 | 0.002 | 100% | 2224.4148 |  | 0
CHIRANJEEVI | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 65.55 | SQM | 0 | 65.55 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR CEILING PLASTERING | 142 | 139.932 | 71.63 | SQM | 71.63 | 0 | 100% | 10023.3292 |  | 0
CHIRANJEEVI | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 166.76 | SQM | 0 | 166.76 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 143 | 139.932 | 194.53 | SQM | 194.53 | 0 | 100% | 27220.972 |  | 0
CHIRANJEEVI | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 0 | 208.32 | 0% | 0 |  | 0
AAIDHUL MIAH | GROUND FLOOR EXTERNAL WALL PLASTERING | 147 | 193.752 | 208.32 | SQM | 208.32 | 0 | 100% | 40362.4166 |  | 0
PRAKASH H N | WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING | 150 | 14500 | 1 | LUMP SUM | 1 | 0 | 100% | 14500 |  | 0
CHIRANJEEVI | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 61.662 | SQM | 0 | 61.662 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR CEILING PLASTERING | 151 | 139.932 | 74.392 | SQM | 74.39 | 0.002 | 100% | 10409.5415 |  | 0
CHIRANJEEVI | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 185.883 | SQM | 0 | 185.883 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR INTERNAL WALL & STAIRCASE PLASTERING | 152 | 139.932 | 220.467 | SQM | 220.47 | -0.003 | 100% | 30850.808 |  | 0
CHIRANJEEVI | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 0 | 142.16 | 0% | 0 |  | 0
AAIDHUL MIAH | FIRST FLOOR EXTERNAL WALL PLASTERING | 156 | 193.752 | 142.16 | SQM | 142.16 | 0 | 100% | 27543.7843 |  | 0
CHIRANJEEVI | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 10.287 | SQM | 0 | 10.287 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR CEILING PLASTERING | 160 | 139.932 | 11.61 | SQM | 11.61 | 0 | 100% | 1624.6105 |  | 0
CHIRANJEEVI | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 0 | 33.43 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR INTERNAL WALL PLASTERING | 161 | 139.932 | 33.43 | SQM | 33.43 | 0 | 100% | 4677.9268 |  | 0
CHIRANJEEVI | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 87.48 | SQM | 0 | 87.48 | 0% | 0 |  | 0
AAIDHUL MIAH | TERRACE FLOOR EXTERNAL WALL PLASTERING | 165 | 193.752 | 153.39 | SQM | 153.39 | 0 | 100% | 29719.6193 |  | 0
SHOKAT | TOILET, BALCONY, TERRACE & SHR WATERPROOF COATING | 168 | 215.28 | 120.9949 | SQM | 0 | 120.9949 | 0% | 0 | 100% | 26047.7778
SHOKAT | WATERPROOF PLASTERING | 170 | 215.28 | 17.8759 | SQM | 0 | 17.8759 | 0% | 0 | 100% | 3848.3333
SHOKAT | WATERPROOF SCREED CONCRETE 50MM THICK | 173 | 107.64 | 23.6836 | SQM | 0 | 23.6836 | 0% | 0 | 100% | 2549.3056
SHOKAT | WATERPROOF SCREED CONCRETE 75MM THICK | 174 | 215.28 | 81.2966 | SQM | 0 | 81.2966 | 0% | 0 | 100% | 17501.5278
SHOKAT | CINDER FILLING ALL FLOOR | 178 | 107.64 | 23.6836 | SQM | 0 | 23.6836 | 0% | 0 | 100% | 2549.3056
SHOKAT | BORE PACKING ALL FLOOR | 180 | 200 | 18 | NOS | 0 | 18 | 0% | 0 | 100% | 3600
RUPAK NAYAK | BUBBLE SPRAY WORK | 183 | 215.28 | 19.974 | SQM | 0 | 19.974 | 0% | 0 | 100% | 4300.0027
RUPAK NAYAK | STUCCO PAINTING | 185 | 96.88 | 61.966 | SQM | 0 | 61.966 | 0% | 0 | 100% | 6003.2661
RUPAK NAYAK | ONE COAT EXTERNAL PRIMER | 186 | 16.15 | 345.504 | SQM | 0 | 345.504 | 0% | 0 | 100% | 5579.8896
RUPAK NAYAK | ALL FLOOR TWO COATS EXTERIOR PAINT | 190 | 32.292 | 345.504 | SQM | 0 | 345.504 | 0% | 0 |  | 0
RUPAK NAYAK | SCAFFOLDING FOR BUBBLE SPRAY & STUCCO PAINTING | 191 | 16.15 | 58.07 | SQM | 0 | 58.07 | 0% | 0 | 100% | 937.8305
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING THREE COATS PUTTY | 192 | 48.438 | 524.433 | SQM | 0 | 524.433 | 0% | 0 | 100% | 25402.4857
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING ONE COAT PRIMER | 193 | 16.15 | 535.5 | SQM | 0 | 535.5 | 0% | 0 | 100% | 8648.325
RUPAK NAYAK | ALL FLOOR INERNAL WALLS & CEILING TWO COATS EMULSION PAINT | 194 | 26.91 | 541.249 | SQM | 0 | 541.249 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | STAIRCASE GRANITE | 215 | 301.392 | 17.75 | SQM | 0 | 17.75 | 0% | 0 | 95% | 5082.2226
SK ANSAR HOSSIAN | LEDGE WALL GRANITE | 217 | 450 | 2 | NOS | 0 | 2 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | DOOR OPENING GRANITE | 218 | 350 | 15 | NOS | 0 | 15 | 0% | 0 | 65% | 3412.5
SK ANSAR HOSSIAN | HALF ROUND NOSING IN THREADS GRANITE | 219 | 82 | 46.4 | RMT | 0 | 46.4 | 0% | 0 | 95% | 3614.56
SK ANSAR HOSSIAN | NON SLIP GROOVED IN THREADS GRANITE | 220 | 32.8 | 103.53 | RMT | 0 | 103.53 | 0% | 0 | 95% | 3225.9948
SK ANSAR HOSSIAN | SKIRITING WITH HALF NOSING GRANITE | 221 | 131.2 | 23.07 | RMT | 0 | 23.07 | 0% | 0 | 95% | 2875.4448
SK ANSAR HOSSIAN | WASH BASIN GRANITE FIXING | 222 | 1000 | 4 | NOS | 0 | 4 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | GROUND FLOOR TILING | 224 | 183 | 49.52 | SQM | 0 | 49.52 | 0% | 0 | 95% | 8609.052
SK ANSAR HOSSIAN | GROUND FLOOR SKIRTING | 225 | 49.2 | 48.42 | RMT | 0 | 48.42 | 0% | 0 | 95% | 2263.1508
SK ANSAR HOSSIAN | FIRST FLOOR TILING | 226 | 183 | 46 | SQM | 0 | 46 | 0% | 0 | 95% | 7997.1
SK ANSAR HOSSIAN | FIRST FLOOR SKIRTING | 227 | 49.2 | 50.44 | RMT | 0 | 50.44 | 0% | 0 | 95% | 2357.5656
SK ANSAR HOSSIAN | TERRACE FLOOR TILING | 228 | 183 | 2.5 | SQM | 0 | 2.5 | 0% | 0 | 95% | 434.625
SK ANSAR HOSSIAN | TERRACE FLOOR SKIRTING | 229 | 49.2 | 4.19 | RMT | 0 | 4.19 | 0% | 0 | 95% | 195.8406
SK ANSAR HOSSIAN | UTILITY FLOOR TILING | 230 | 183 | 4.01 | SQM | 0 | 4.01 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | UTILITY SKIRTING | 231 | 49.2 | 9.98 | RMT | 0 | 9.98 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | BALCONY & SITOUT TILING | 232 | 183 | 10.18 | SQM | 0 | 10.18 | 0% | 0 | 95% | 1769.793
SK ANSAR HOSSIAN | BALCONY & SITOUT SKIRTING | 233 | 49.2 | 14 | RMT | 0 | 14 | 0% | 0 | 95% | 654.36
SK ANSAR HOSSIAN | CAR PARKING AREA TILING | 234 | 183 | 11.138 | SQM | 0 | 11.138 | 0% | 0 |  | 0
SK ANSAR HOSSIAN | FLOOR CHIPPING | 235 | 2.5 | 1055 | SFT | 0 | 1055 | 0% | 0 | 100% | 2637.5
SK ANSAR HOSSIAN | GROUND FLOOR TOILET FLOOR TILING | 237 | 183 | 3.41 | SQM | 0 | 3.41 | 0% | 0 | 90% | 561.627
SK ANSAR HOSSIAN | GROUND FLOOR TOILET WALL TILING | 238 | 183 | 17.34 | SQM | 0 | 17.34 | 0% | 0 | 90% | 2855.898
SK ANSAR HOSSIAN | FIRST FLOOR TOILET FLOOR TILING | 239 | 183 | 6.62 | SQM | 0 | 6.62 | 0% | 0 | 90% | 1090.314
SK ANSAR HOSSIAN | FIRST FLOOR TOILET WALL TILING | 240 | 183 | 33.99 | SQM | 0 | 33.99 | 0% | 0 | 90% | 5598.153
PRAKASH H N | WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 246 | 15500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | ELECTRICAL TESTING & COMMISIONING | 248 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | TOILETS, KITCHEN & UTILITY INTERNAL WATER SUPPLY PIPING WORK WITH WALL CUTTING,CHIPPING & PRESSURE TESTING, SEWER & WASTE WATER PIPING | 250 | 9000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 4500 | 50% | 4500
KRIUTTIBAS DAS | TOILETS,BALCONY, TERRACE VERTICAL LINE (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES)WITH SUPPORTING CHANNELS UPTO INSPECTION CHAMBER | 251 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 6000
KRIUTTIBAS DAS | GROUND FLOOR TOILET CHIPPING & EXCAVATION | 253 | 500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | EXTERNAL PIPE LINE WORKS WITH PROPER SLOPES (WATER SUPPLY,SEWER,WASTE,RAIN WATER LINES) INSPECTION CHAMBER TO MAIN CHAMBER CONNECTION | 254 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 4000
KRIUTTIBAS DAS | COLLECTING FIXING,TESTING,COMMISSIONING OF ALL THE CP & SANITARY FIXTURES | 255 | 6000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CARPARKING AREA PCC CUTTING,EXCAVATION,PIPE LAYING WORK | 256 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CORE CUTTING | 257 | 1800 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1800
KRIUTTIBAS DAS | PLUMBING TESTING & HANDOVER | 258 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
SUBHASMITA DAS | PLUMBING CHAMBER MAKING AND SET BACK SOIL FILLING | 272 | 12000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 12000
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.529 | 0% | 0 | 100% | 2601.986
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0.0026 | 99.99% | 2256.1 |  | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0% | 0 | 100% | 1518
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.3755 | 0% | 0 | 100% | 2623.7005
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
EBI ABRAHAM | SANCTION PLANS OF VILLAS FOR PANCHAYATH APPROVAL | 316 | 4000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTAMIZATION TOILET EXTERNAL PIPE LINE WORK | 401 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 1000
KRIUTTIBAS DAS | CUSTAMIZATION TOILET VERTICAL PIPE LINE WORK | 402 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 | 100% | 2000
KRIUTTIBAS DAS | CUSTAMIZATION TOILET CP AND SANITARY WORK | 403 | 2000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | CUSTOMIZATION PLUMBING TESTING AND COMMISSIONING WORK | 404 | 1000 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
KRIUTTIBAS DAS | LABOR FOR CUSTOMIZATION TOILET INTERNAL PIPE LINE WORK | 405 | 3000 | 1 | LUMP SUM | 0.5 | 0.5 | 50% | 1500 | 50% | 1500
PRAKASH H N | CUSTAMIZATION ROOM WIRING,SWITCH FIXING, DB TERMINATION & METER BOARD TERMINATION WITH BESCOM METER, EARTHING WORK | 413 | 2500 | 1 | LUMP SUM | 0 | 1 | 0% | 0 |  | 0
PRAKASH H N | CUSTAMIZATION ROOM WALL CUTTING,CHIPPING, WALL CONDUITS, METAL BOX, DB, METER BOARD FIXING) | 414 | 2500 | 1 | LUMP SUM | 1 | 0 | 100% | 2500 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING THREE COATS OF PUTTY | 415 | 48.438 | 89.526 | SQM | 0 | 89.526 | 0% | 0 | 100% | 4336.4604
RUPAK NAYAK | CUSTOMIZATION ROOM INTERNAL WALL AND CEILING ONE COAT PRIMER | 416 | 16.15 | 89.526 | SQM | 0 | 89.526 | 0% | 0 | 100% | 1445.8449
RUPAK NAYAK | CUSOMIZATION ROOM INTERNAL WALL AND CEILING TWO COATS OF INTERNAL EMULSION PAINT | 417 | 26.91 | 89.526 | SQM | 0 | 89.526 | 0% | 0 |  | 0
RUPAK NAYAK | CUSTOMIZATION ROOM ONE COAT OF EXTERNAL PRIMER | 418 | 16.15 | 14.102 | SQM | 0 | 14.102 | 0% | 0 | 100% | 227.7473
RUPAK NAYAK | CUSTOMIZATION ROOM TWO COAT OF EXTERNAL PAINT | 419 | 32.292 | 14.102 | SQM | 0 | 14.102 | 0% | 0 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM SLAB AND BEAM RCC | 493 | 225 | 4.624 | CUM | 4.62 | 0.004 | 99.91% | 1039.5 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN AND LINTEL CHAJJA RCC | 494 | 2000 | 1.6 | CUM | 1.6 | 0 | 100% | 3200 |  | 0
SUBHASMITA DAS | CUSTOMIZATION ROOM COLUMN STARTER | 495 | 50 | 5 | NOS | 5 | 0 | 100% | 250 |  | 0
NAGARAJ | CUSTOMIZATION ROOM SLAB AND BEAM SHUTTERING | 496 | 322.92 | 45.091 | SQM | 45.09 | 0.001 | 100% | 14560.4628 |  | 0
NAGARAJ | CUSTOMIZATION ROOM LINTEL CHAJJA SHUTTERING | 497 | 322.92 | 3.178 | SQM | 3.18 | -0.002 | 100.1% | 1026.8856 |  | 0
NAGARAJ | CUSTOMIZATION ROOM COLUMN SHUTTERING | 498 | 322.92 | 16.5 | SQM | 16.5 | 0 | 100% | 5328.18 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR CEILING PLASTERING | 499 | 139.932 | 22.638 | SQM | 22.64 | -0.002 | 100% | 3168.0605 |  | 0
CHIRANJEEVI | CUSTOMISATION TERRACE FLOOR INTERNAL WALL PLASTERING | 500 | 139.932 | 65.546 | SQM | 0 | 65.546 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR INTERNAL WALL PLASTERING | 500 | 139.932 | 65.546 | SQM | 65.55 | -0.004 | 100% | 9172.5426 |  | 0
CHIRANJEEVI | CUSTOMISATION TERRACE FLOOR EXTERNAL WALL PLASTERING | 501 | 193.752 | 58.86 | SQM | 0 | 58.86 | 0% | 0 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE FLOOR EXTERNAL WALL PLASTERING | 501 | 193.752 | 69.843 | SQM | 69.84 | 0.003 | 100% | 13531.6397 |  | 0
CHIRANJEEVI | CUSTOMISATION TERRACE FLOOR BLOCK WORK | 502 | 193.752 | 31.944 | SQM | 31.94 | 0.004 | 99.99% | 6188.4389 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM SLAB AND BEAM REINFORCEMENT | 510 | 7500 | 0.36531 | MT | 0.37 | -0.004687 | 101.3% | 2775 |  | 0
SARAT BARMAN | CUSTOMIZATION ROOM COLUMN LINTEL AND CHEJJA REINFORCEMENT | 511 | 7500 | 0.25218 | MT | 0.25 | 0.002183 | 99.13% | 1875 |  | 0
AAIDHUL MIAH | CUSTOMISATION TERRACE RCC SURFACE HACKING | 546 | 10.76 | 53.899 | SQM | 53.9 | -0.001 | 100% | 579.964 |  | 0
SK ANSAR HOSSIAN | CUSTOMIZATION MAIN FLOORING WORK | 442 | 232.339 | 19.038 | SQM | 0 | 19.038 | 0% | 0 | 95% | 4202.1064
SK ANSAR HOSSIAN | CUSTOMIZATION TOILET TILE WORK | 436 | 1134.593 | 3.717 | SQM | 0 | 3.717 | 0% | 0 | 90% | 3795.554
223224.9504

## V191
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
SUBHASMITA DAS | ATT IN PLINTH | 1 | 54 | 68.67 | SQM | 68.67 | 0 | 100 | 3708.18 | 0 | 0
MANJUNATHA P | SITE CLEANING & GRUBBING | 2 | 4000 | 1 | LUMP SUM | 1 | 0 | 100 | 4000 | 0 | 0
MANJUNATHA P | TREE CUTTING | 3 | 500 | 2 | NOS | 2 | 0 | 100 | 1000 | 0 | 0
MANJUNATHA P | FOOTING EXCAVATION | 4 | 211.68 | 107.55 | CUM | 107.55 | 0 | 100 | 22766.184 | 0 | 0
SUBHASMITA DAS | FOOTING EARTH DRESSING | 5 | 22 | 51.83 | SQM | 51.83 | 0 | 100 | 1140.26 | 0 | 0
MANJUNATHA P | FOOTING EARTH DRESSING | 5 | 22 | 1.95 | SQM | 1.95 | 0 | 100 | 42.9 | 0 | 0
SUBHASMITA DAS | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 18.16 | CUM | 18.16 | 0 | 100 | 2562.7392 | 0 | 0
MANJUNATHA P | EARTH REFILLING FOR FOOTINGS | 8 | 141.12 | 75.32 | CUM | 75.32 | 0 | 100 | 10629.1584 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM EXCAVATION | 11 | 211.68 | 5.36 | CUM | 5.36 | 0 | 100 | 1134.6048 | 0 | 0
SUBHASMITA DAS | EARTH BACKFILLING OF BASE FLOOR | 13 | 141.12 | 30.73 | CUM | 30.73 | 0 | 100 | 4336.6176 | 0 | 0
SUBHASMITA DAS | BASE FLOOR EARTH DRESSING | 14 | 22 | 28.67 | SQM | 28.67 | 0 | 100 | 630.74 | 0 | 0
SUBHASMITA DAS | BASE FLOOR SOLING WORK | 15 | 43 | 68.67 | SQM | 0 | 68.67 | 0 | 0 | 0 | 0
MANJUNATHA P | SETBACK AREA SOIL FILLING | 16 | 141.12 | 10.81 | CUM | 10.81 | 0 | 100 | 1525.5072 | 0 | 0
SUBHASMITA DAS | FOOTING PCC WORK | 20 | 1000 | 3.351 | CUM | 3.35 | 0 | 100 | 3350 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM BOTTOM PCC WORK | 21 | 1000 | 2.668 | CUM | 2.67 | 0 | 100 | 2670 | 0 | 0
SUBHASMITA DAS | BASE FLOOR PCC | 22 | 1000 | 6.867 | CUM | 6.87 | 0 | 100 | 6870 | 0 | 0
SARAT BARMAN | FOOTING REINFORCEMENT | 23 | 7500 | 0.27 | MT | 0.27 | 0 | 100 | 2025 | 0 | 0
SARAT BARMAN | PEDESTAL COLUMN REINFORCEMENT | 24 | 7500 | 0.42 | MT | 0.42 | 0 | 100 | 3150 | 0 | 0
SARAT BARMAN | PLINTH BEAM REINFORCEMENT | 25 | 7500 | 0.53 | MT | 0.53 | 0 | 100 | 3975 | 0 | 0
SARAT BARMAN | GROUND FLOOR COLUMN REINFORCEMENT | 26 | 7500 | 0.49 | MT | 0.49 | 0 | 100 | 3675 | 0 | 0
SARAT BARMAN | GROUND FLOOR ROOF BEAM & SLAB REINFORCEMENT | 29 | 7500 | 1.2 | MT | 0 | 1.2 | 0 | 0 | 0 | 0
SARAT BARMAN | GROUND FLOOR STAIRCASE SLAB REINFORCEMENT | 32 | 7500 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
SARAT BARMAN | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 35 | 10000 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
MANJUNATHA R | FOOTING SHUTTERING | 41 | 322.92 | 26.48 | SQM | 26.48 | 0 | 100 | 8550.9216 | 0 | 0
MANJUNATHA R | PEDESTAL COLUMN SHUTTERING | 42 | 322.92 | 25.77 | SQM | 25.77 | 0 | 100 | 8321.6484 | 0 | 0
MANJUNATHA R | PLINTH BEAM SHUTTERING | 43 | 322.92 | 54.72 | SQM | 54.72 | 0 | 100 | 17670.1824 | 0 | 0
NAGARAJ | GROUND FLOOR COLUMN SHUTTERING | 44 | 322.92 | 45.3 | SQM | 0 | 45.3 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR ROOF BEAM & SLAB SHUTTERING | 45 | 322.92 | 129.11 | SQM | 0 | 129.11 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR STAIRCASE SLAB SHUTTERING | 46 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | GROUND FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 47 | 322.92 | 9.2505 | SQM | 0 | 9.25 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FOOTING RCC | 50 | 225 | 9.08 | CUM | 9.08 | 0 | 100 | 2043 | 0 | 0
SUBHASMITA DAS | PEDESTAL COLUMN RCC | 51 | 1500 | 1.7 | CUM | 1.7 | 0 | 100 | 2550 | 0 | 0
SUBHASMITA DAS | PLINTH BEAM RCC | 53 | 900 | 4 | CUM | 4 | 0 | 100 | 3600 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR COLUMN RCC | 55 | 2000 | 3.041 | CUM | 0 | 3.04 | 0 | 0 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR ROOF BEAM & SLAB RCC | 58 | 225 | 15.53 | CUM | 0 | 15.53 | 0 | 0 | 0 | 0
SUBHASMITA DAS | GROUND FLOOR STAIRCASE SLAB RCC | 61 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR COLUMN REINFORCEMENT | 69 | 7500 | 0.47 | MT | 0 | 0.47 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR ROOF BEAM & SLAB REINFORCEMENT | 73 | 7500 | 0.88 | MT | 0 | 0.88 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR STAIRCASE SLAB REINFORCEMENT | 77 | 7500 | 0.18 | MT | 0 | 0.18 | 0 | 0 | 0 | 0
SARAT BARMAN | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA REINFORCEMENT | 80 | 10000 | 0.15 | MT | 0 | 0.15 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR COLUMN SHUTTERING | 84 | 322.92 | 39.24 | SQM | 0 | 39.24 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR ROOF BEAM & SLAB SHUTTERING | 85 | 322.92 | 107.8 | SQM | 0 | 107.8 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR STAIRCASE SLAB SHUTTERING | 86 | 322.92 | 12.27 | SQM | 0 | 12.27 | 0 | 0 | 0 | 0
NAGARAJ | FIRST FLOOR SILL, LINTEL BEAM & CHEJJA SHUTTERING | 87 | 322.92 | 9.815 | SQM | 0 | 9.82 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR COLUMN RCC | 88 | 2000 | 2.21 | CUM | 0 | 2.21 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR ROOF BEAM & SLAB RCC | 91 | 225 | 12.13 | CUM | 0 | 12.13 | 0 | 0 | 0 | 0
SUBHASMITA DAS | FIRST FLOOR STAIRCASE SLAB RCC | 92 | 2000 | 1.57 | CUM | 0 | 1.57 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR COLUMN REINFORCEMENT | 97 | 7500 | 0.13 | MT | 0 | 0.13 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR ROOF BEAM & SLAB REINFORCEMENT | 100 | 7500 | 0.19 | MT | 0 | 0.19 | 0 | 0 | 0 | 0
SARAT BARMAN | TERRACE FLOOR LINTEL BEAM & CHEJJA REINFORCEMENT | 103 | 7000 | 0.029 | MT | 0 | 0.03 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR COLUMN SHUTTERING | 106 | 322.92 | 10.8 | SQM | 0 | 10.8 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR BEAM & SLAB SHUTTERING | 107 | 322.92 | 24.14 | SQM | 0 | 24.14 | 0 | 0 | 0 | 0
NAGARAJ | TERRACE FLOOR LINTEL BEAM & CHEJJA SHUTTERING | 108 | 322.92 | 1.89 | SQM | 0 | 1.89 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR COLUMN RCC | 109 | 2000 | 0.41 | CUM | 0 | 0.41 | 0 | 0 | 0 | 0
SUBHASMITA DAS | TERRACE FLOOR ROOF BEAM & SLAB RCC | 112 | 225 | 2.412 | CUM | 0 | 2.41 | 0 | 0 | 0 | 0
SUBHASMITA DAS | ALL LEVEL COLUMN STARTER | 116 | 50 | 44 | NOS | 0 | 44 | 0 | 0 | 0 | 0
SUBHASMITA DAS | BELOW PLINTH BLOCK WORK | 119 | 800 | 7.333 | CUM | 7.33 | 0 | 100 | 5864 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0

## V192
Contractors/Vendors | Description | Code | BOQ Item Rate * | WO Qty. (Estimated) | UOM | Executed / Consumed Qty | Balance Qty | % Completion (Consumption) | To Date | Release % | Current Payment
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA BLOCK WORK | 277 | 34 | 76.529 | RFT | 0 | 76.53 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA KERB STONE REWORK | 278 | 77 | 29.3026 | RFT | 29.3 | 0 | 100 | 2256.1 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA PAVER BLOCK REWORK | 279 | 23 | 66 | SFT | 0 | 66 | 0 | 0 | 0 | 0
RAMAKRUSHNA PRADHAN | FRONT OF HOUSE FOOTPATH AREA RAMP REWORK | 280 | 151 | 17.3755 | RFT | 0 | 17.38 | 0 | 0 | 0 | 0
RUPAK NAYAK | NAME BOARD PAINTING WORK WITH BUBBLE SPRAY FINSIH | 283 | 400 | 1 | LUMP SUM | 0 | 1 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0
[9 empty] | 0 | 0 | 0